## Master
A | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
3524 | 3524 | 2654 | 3481 | 3513 | 1071 | 3481 | 3481 | 3480 | 3277 | 999 | 759 | 1092 | 1085 | 1602 | 1429 | 1427 | 1612 | 330 | 1226 | 3705 | 1407 | 734 | 756 | 3524 | 0 | 0 | 406 | 1414 | 945 | 244 | 249 | 6 | 7 | 1155 | 354 | 957 | 1155 | 188 | 934 | 1154 | 597 | 948 | 1154 | 576 | 1577 | 3520 | 1586 | 293 | 1587 | 1334 | 1585 | 1629 | 1358 | 1594 | 1141 | 112 | 1102 | 743 | 10 | 647 | 140 | 248
Site ID | Final Site Name | Site Owner | Site Code | Site Type | Key Number | long | lat | Governorate | Structure | Owner Name | Owner contact number | Structure Type | Hieght (m) | Part of | Phase Name | Priority | Cluster | Area | Weekly Plan | TSS SMP | TSSR Subcon | NEW Allocation | TSSR PO# | TS Survey (Ac) | abcd | ab | 5G sectors Names | 5G solution | Site Sectors # | IBS Sector | TDD Site | NoKia NPO status | Nokia NPO Comment | TI Status | TI Comment | Cluster Owner (TI) | RF Plan. Status | RF Plan Comment | Cluster Owner (Planing) | RF Optim Status | RF Opt. comment | Cluster Owner (Optimization) | Civil Status | Civil Comment | Cluster Owner (Civil) | MW Status | Cluster Owner (MW) | REC. Cab. Swap | SPOC Readiness | Version | SPOC Status | TSSR Overall Status | TSSR status Date | SPOC Reviewed | Week number | TSSR Remark | Action Age | RFI Status | Gap Analysis | Approved | Nokia Site Owner | TSSR Ready | Dismantle Status | Dismantle Date | Validate | Red Zone Sites | Sequence
495 | Ramtha_Thnebeh_South_TASC_O | TASC | IRB-705-R | Outdoor |  | 35.9056 | 32.6892 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 1 | Cluster-4 |  |  | SMP-WO-1737458 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-16 | [7 empty] | Laith | TSSR Ready
497 | Alaal_Big_Mosque_TASC_O | TASC | IRB-714-R | Outdoor |  | 35.9077 | 32.6376 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 2 | Cluster-4 |  |  | SMP-WO-1737464 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-16 | [8 empty] | TSSR Ready
6370 | Kharja_South_TASC_O | TASC | IRB-749-R | Outdoor |  | 35.8867 | 32.6499 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 3 | Cluster-63 |  |  | SMP-WO-1737468 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [7 empty] | Mofeed | TSSR Ready
498 | Irbid_Qasfa_TASC_O | TASC | IRB-734-R | Outdoor |  | 35.8629 | 32.6321 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 4 | Cluster-4 |  |  | SMP-WO-1737472 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-16 | [8 empty] | TSSR Ready
491 | Harema_Center_TASC_O | TASC | IRB-679-R | Outdoor |  | 35.8751 | 32.6269 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 5 | Cluster-4 |  |  | SMP-WO-1737474 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [8 empty] | TSSR Ready
447 | 447-Khayria_BeitRas_CTR_PD_Fiber_TASC_O | TASC | IRB-420-R | Irbid |  | 32.6172 | 35.8633 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 6 | Cluster-4 |  |  | SMP-WO-1737476 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [7 empty] | Mofeed | TSSR Ready
463 | 463-Khayria_BeitRas_South_PF_EBand_TASC_O | TASC | IRB-554-R | Outdoor |  | 32.6095 | 35.8673 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 7 | Cluster-4 |  |  | SMP-WO-1521180 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 |  |  |  |  | Released |  | Obieda | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 4 | A |  | TSSR Under ROM Review | 2025-12-29 | [7 empty] | Mofeed | TSSR Ready |  |  | Downloaded
406 | 406-Khayria_BeitRas_PC_Fiber_O | TASC | IRB-6-R | Outdoor |  | 32.6067 | 35.8603 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 8 | Cluster-4 |  |  | SMP-WO-1521181 | Al Lewan |  |  | Done |  |  | 5G | 5G | 3 |  |  |  |  | Released |  | Obieda | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 4 | A |  | TSSR Under ROM Review | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
494 | Kufor_Jayez_Mahaftha_Mosque_TASC_O | TASC | IRB-698-R | Outdoor |  | 35.8535 | 32.6175 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 9 | Cluster-4 |  |  | SMP-WO-1737480 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-16 | [8 empty] | TSSR Ready
417 | 417-Zoubi_Gas_Station_PC_Fiber_TASC | TASC | IRB-16-R | Indoor | 716 | 32.6241 | 35.8462 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 10 | Cluster-4 |  |  | SMP-WO-1737481 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 4 | A |  | TSSR Under Zain validation | 2025-12-29 | [7 empty] | Mofeed | TSSR Ready
487 | Sama_Rousan_Gov_Complex_Tasc_O | TASC | IRB-663-R | Outdoor |  | 35.8403 | 32.6334 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 11 | Cluster-4 |  |  | SMP-WO-1737482 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Moath | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 4 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready
475 | 475-Yarmouk_Hospital_Ent_PE_Fiber_TASC_O | TASC | IRB-483-R | Outdoor |  | 32.6395 | 35.8389 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 12 | Cluster-4 |  |  | SMP-WO-1737483 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Moath | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  |  | Released |  |  | 4 | A |  | TSSR Under Zain validation | 2025-12-29 | [7 empty] | Mofeed | TSSR Ready
422 | 422-Izreet_Irbid_O | TASC | IRB-566-R | Outdoor |  | 32.6477 | 35.8477 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 13 | Cluster-4 |  |  | SMP-WO-1737484 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Moath | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [7 empty] | Mofeed | TSSR Ready
441 | 441-Sama_Rousan_PE_EBand_TASC | TASC | IRB-21-G | Indoor | 750 | 32.6384 | 35.8267 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 14 | Cluster-4 |  |  | SMP-WO-1737485 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Moath | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [8 empty] | TSSR Ready
489 | Kufer_Jayez_East _TASC_O | TASC | IRB-667-R | Outdoor |  | 35.8334 | 32.6238 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 15 | Cluster-4 |  |  | SMP-WO-1737486 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Moath | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [7 empty] | Mofeed | TSSR Ready
456 | 456-Kufer_Jayez_PE_TASC | TASC | IRB-240-R | Indoor | 2127 | 32.6195 | 35.8255 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 16 | Cluster-4 |  |  | SMP-WO-1737487 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under ROM Review | 2025-12-22 | [8 empty] | TSSR Ready
483 | 483-Um_Jadayel_North_O | TASC | IRB-637-R | Outdoor |  | 32.5953 | 35.8406 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 17 | Cluster-4 |  |  | SMP-WO-1737488 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Moath | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-22 | [8 empty] | TSSR Ready
449 | 449-BeitRas_West_PD_Fiber_TASC_O | TASC | IRB-429-R | Outdoor |  | 32.5934 | 35.8496 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 18 | Cluster-4 |  |  | SMP-WO-1521184 | Al Tawseea |  |  | Done |  |  | 5G | 5G | 5 |  |  |  |  | Released |  | Moath | Released |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-22 | [8 empty] | TSSR Ready
451 | 451-BeitRas_CTR_PD_Fiber_TASC_O | TASC | IRB-430-R | Outdoor |  | 32.598 | 35.8543 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 19 | Cluster-4 |  |  | SMP-WO-1521182 | Al Tawseea |  |  | Done |  |  | 5G | 5G | 3 |  |  |  |  | Released |  | Moath | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [7 empty] | Mofeed | TSSR Ready
402 | 402-BSC_BeitRas_PA_Fiber | TASC | IRB-2-G | Indoor | 629 | 32.5911 | 35.8581 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 20 | Cluster-4 |  |  | SMP-WO-1521185 | Al Tawseea |  |  | Done |  |  | 5G | 5G | 4 |  | ABC |  |  | Released |  | Moath | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 3 | A |  | TSSR Under Zain validation | 2025-12-29 |  |  | Need Fence key | [5 empty] | TSSR Ready |  |  | Downloaded
428 | 428-BeitRas_2_PD_Fiber_TASC_O | TASC | IRB-273-R | Outdoor |  | 32.5954 | 35.8623 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 21 | Cluster-4 |  |  | SMP-WO-1521183 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Waed |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Subcon validation | 2025-12-15 | [8 empty] | TSSR Ready |  |  | Downloaded
490 | 490-Hakama_Beit_Ras_TASC_O | TASC | IRB-654-R | Outdoor |  | 35.8743 | 32.5978 | Irbid | RT |  |  |  |  | Swap For Exsting Thin layer | RO4 | 22 | Cluster-4 |  |  | SMP-WO-1527889 | Al Tawseea |  |  | Done |  |  | 5G | 5G | 4 |  |  |  |  | Released |  | Waed | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-22 | [7 empty] | Mofeed | TSSR Ready
450 | 450-Hakama_North_PD_Fiber_TASC_O | TASC | IRB-350-R | Outdoor |  | 32.5969 | 35.8816 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 23 | Cluster-4 |  |  | SMP-WO-1521274 | Al Tawseea |  |  | Done |  |  | 5G | 5G | 4 |  |  |  |  | Released |  | Waed | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 4 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready
6371 | Maru_Irbid_South_TASC_O | TASC | IRB-729-R | Outdoor |  | 35.9869 | 32.5924 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 24 | Cluster-63 |  |  | SMP-WO-1737498 | Al Tawseea |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Waed | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-16 | [8 empty] | TSSR Ready
424 | 424-Hakama_2_PC_Fiber_TASC | TASC | IRB-225-R | Indoor | 2128 | 32.5912 | 35.8906 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 25 | Cluster-4 |  |  | SMP-WO-1521275 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Waed |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb | Yes | 0 |  |  | TSSR Under ROM Review | 2025-12-22 | [8 empty] | TSSR Ready |  |  | Downloaded
421 | 421-Hakama_1_PD_Fiber_TASC | TASC | IRB-226-R | Indoor | 2101 | 32.5893 | 35.8805 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 26 | Cluster-4 |  |  | SMP-WO-1521276 | Al Lewan |  |  | Done |  |  | 5G | 5G | 2 |  |  |  |  | Released |  | Waed | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-17 | [8 empty] | TSSR Ready
493 | Beit_Ras_South_Hakama_Entrance_TASC_O | TASC | IRB-697-R | Outdoor |  | 35.8725 | 32.5875 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 27 | Cluster-4 |  |  | SMP-WO-1737501 | Al Tawseea |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Waed | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-22 | [7 empty] | Mofeed | TSSR Ready
446 | 446-BeitRas_Str_CTR_PF_EBand_TASC_O | TASC | IRB-545-R | Outdoor |  | 32.5882 | 35.8647 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 28 | Cluster-4 |  |  | SMP-WO-1521189 | Al Tawseea |  |  | Done |  |  | 5G | 5G | 4 |  |  |  |  | Pending |  | Waed | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 3 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
448 | 448-BeitRas_Tatweer_PD_Fiber_TASC_O | TASC | IRB-428-R | Outdoor |  | 32.5884 | 35.8534 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 29 | Cluster-4 |  |  | SMP-WO-1521188 | Al Tawseea |  |  | Done |  |  | 5G | 5G | 4 |  | ABC |  |  | Pending |  | Waed | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 3 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
496 | Beit_Ras_Tatweer_HSG_East_TASC_O | TASC | IRB-699-R | Outdoor |  | 35.8499 | 32.589 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 30 | Cluster-4 |  |  | SMP-WO-1737504 | Al Tawseea |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Waed | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 3 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready
4483 | 4483-Dabulia_Um_Jadayel_O | TASC | IRB-608-R | Outdoor |  | 32.5857 | 35.8416 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 31 | Cluster-44 |  |  | SMP-WO-1521187 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
4466 | 4466-Barha_Foara_St_PE_TASC_O | TASC | IRB-447-R | Outdoor |  | 32.5842 | 35.8323 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 32 | Cluster-44 |  |  | SMP-WO-1737506 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Zaid | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 3 | A |  | TSSR Under Nokia GSD Validation | 2025-12-29 | [8 empty] | TSSR Ready
4465 | 4465-Barha_Aban_PD_TASC_O | TASC | IRB-446-R | Outdoor |  | 32.5769 | 35.8245 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 33 | Cluster-44 |  |  | SMP-WO-1521472 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
4407 | 4407-Barha_3_PC_EBand_TASC | TASC | IRB-204-R | Indoor | 791 | 32.5736 | 35.829 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 34 | Cluster-44 |  |  | SMP-WO-1521473 | Al Lewan | [5 empty] | 5G | 5G | 5 |  | ABC |  |  |  |  | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb | Yes | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
4437 | 4437-Barha_Almarj_Ave_PF_EBand_TASC_O | TASC | IRB-405-R | Outdoor |  | 32.5709 | 35.837 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 35 | Cluster-44 |  |  | SMP-WO-1521453 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 |  |  |  |  | Released |  | Zaid | Released |  | Omar Sami | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 3 | A |  | TSSR Under Nokia GSD Validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
4470 | 4470-Irbid_Mahajer_CRL_PF_TASC_O | TASC | IRB-471-R | Outdoor |  | 32.5741 | 35.8405 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 36 | Cluster-44 |  |  | SMP-WO-1521452 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Subcon validation | 2025-12-15 | [7 empty] | Mofeed | TSSR Ready |  |  | Downloaded
4431 | 4431-Hay_Matareq_Irbid_PD_Fiber_O | TASC | IRB-298-R | Outdoor |  | 32.5768 | 35.8477 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 37 | Cluster-44 |  |  | SMP-WO-1737511 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation | 2025-12-15 | [8 empty] | TSSR Ready
4434 | 4434-Hay_Matareq_North_Irbid_PE_Fiber_TASC_O | TASC | IRB-497-R | Irbid |  | 32.5808 | 35.852 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 38 | Cluster-44 |  |  | SMP-WO-1737512 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Zaid | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 3 | A |  | TSSR Under Zain validation | 2025-12-29 |  |  | Lock key | [5 empty] | TSSR Ready
4488 | Hneina_North_TASC_O | TASC | IRB-675-R | Outdoor |  | 35.8578 | 32.5815 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 39 | Cluster-44 |  |  | SMP-WO-1737513 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Zaid | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 3 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready
443 | 443-BeitRas_South_PE_Fiber_Manage_O | ZAIN/M | IRB-411-R | Outdoor |  | 32.5835 | 35.862 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 40 | Cluster-4 |  |  | SMP-WO-1521190 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 |  |  |  |  | Released |  | Zaid | Released |  | Baher Obaidat | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 3 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
444 | 444-Zubeir_St_Hanenah_PB_Fiber_TASC | TASC | IRB-156-R | Indoor | 757 | 32.5786 | 35.8578 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 41 | Cluster-4 |  |  | SMP-WO-1521514 | Al Lewan |  |  | Done |  |  | 5G | 5G | 3 |  |  |  |  | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
480 | 480-Irbid_AlKarama_Top_O | TASC | IRB-606-R | Outdoor |  | 32.578 | 35.8606 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 42 | Cluster-4 |  |  | SMP-WO-1521511 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 |  |  |  |  | Released |  | Obieda | Released |  | Baher Obaidat | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 5 | A |  | Approved | 2025-12-22 | [8 empty] | TSSR Ready |  |  | Downloaded
4414 | 4414-Hakama_CRL_PC_Fiber_TASC | TASC | IRB-13-R | Indoor | 643 | 32.5787 | 35.8668 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 43 | Cluster-44 |  |  | SMP-WO-1737518 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [8 empty] | TSSR Ready
4478 | 4478-Hay_Matareq_East_PE_Fiber_TASC_O | TASC | IRB-474-R | Outdoor |  | 32.5769 | 35.8536 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 44 | Cluster-44 |  |  | SMP-WO-1521515 | Al Lewan |  |  | Done |  |  | 5G | 5G | 3 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Subcon validation | 2025-12-15 | [8 empty] | TSSR Ready |  |  | Downloaded
4424 | 4424-Hanenah_Irbid_2_PE_Fiber_TASC_O | TASC | IRB-279-R | Irbid |  | 32.574 | 35.8578 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 45 | Cluster-44 |  |  | SMP-WO-1737520 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Pending |  | Obieda | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 2 | A |  | TSSR Under Nokia GSD Validation | 2025-12-29 | [8 empty] | TSSR Ready
4404 | 4404-Hanenah_Irbid_PE_Fiber_TASC | TASC | IRB-15-R | Indoor | 645 | 32.5724 | 35.8548 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 46 | Cluster-44 |  |  | SMP-WO-1737521 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia GSD Validation | 2025-12-22 | [8 empty] | TSSR Ready
4452 | 4452-Irbid_Ind_CRL_PE_Fiber_TASC_O | TASC | IRB-414-R | Irbid |  | 32.5719 | 35.8622 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 47 | Cluster-44 |  |  | SMP-WO-1737522 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb |  | 4 | A |  | TSSR Under Zain validation | 2025-12-29 | [8 empty] | TSSR Ready
4423 | 4423-Irbid_Ind_3_PE_Fiber_TASC_O | TASC | IRB-271-R | Irbid |  | 32.572 | 35.8684 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 48 | Cluster-44 |  |  | SMP-WO-1737523 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Obieda | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 3 | A |  | TSSR Under Nokia GSD Validation | 2025-12-29 | [8 empty] | TSSR Ready
4401 | 4401-Irbid_Ind_PB_Fiber_TASC | TASC | IRB-1-R | Irbid | 616 | 32.5683 | 35.8708 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 49 | Cluster-44 |  |  | SMP-WO-1737524 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under ROM Review | 2025-12-29 | [8 empty] | TSSR Ready
4451 | 4451-Hakama_St_PD_Fiber_TASC | TASC | IRB-25-R | Indoor | 614 | 32.57 | 35.8601 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 50 | Cluster-44 |  |  | SMP-WO-1737525 | Al Lewan | [5 empty] | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Need Access |  |  |  | Locker / no contact | [5 empty] | TSSR Ready
4450 | 4450-Irbid_North_CPLX_PE_Fiber_TASC_O | TASC | IRB-345-R | Irbid |  | 32.5683 | 35.8566 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 51 | Cluster-44 |  |  | SMP-WO-1737526 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Released |  | Moath | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 3 | A |  | TSSR Under Nokia GSD Validation | 2025-12-29 | [8 empty] | TSSR Ready
4454 | 4454-Hay_Jawhara_East_PE_Fiber_TASC_O | TASC | IRB-423-R | Outdoor |  | 32.5698 | 35.8494 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 52 | Cluster-44 |  |  | SMP-WO-1521434 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [7 empty] | Najjar | TSSR Ready |  |  | Downloaded
4422 | 4422-Irbid_Hay_Nasser_East_PD_Fiber_TASC_O | TASC | IRB-377-R | Irbid |  | 32.5734 | 35.8498 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 53 | Cluster-44 |  |  | SMP-WO-1737528 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation | [9 empty] | TSSR Ready
4464 | 4464-Hay_Nasser_West_PE_Fiber_TASC_O | TASC | IRB-439-R | Outdoor |  | 32.5721 | 35.8459 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 54 | Cluster-44 |  |  | SMP-WO-1521433 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb | Yes | 0 |  |  | TSSR Under Nokia GSD Validation | [9 empty] | TSSR Ready |  |  | Downloaded
4421 | 4421-Quds_St_Irbid_PC_EBand_O | TASC | IRB-18-R | Outdoor | 613 | 32.569 | 35.8415 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 55 | Cluster-44 |  |  | SMP-WO-1521454 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 |  | ABC |  |  |  |  | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb | Yes | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [8 empty] | TSSR Ready |  |  | Downloaded
4468 | 4468-Fuara_UNRWA_Sch_Irbid_O | TASC | IRB-582-R | Irbid |  | 32.5682 | 35.846 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 56 | Cluster-44 |  |  | SMP-WO-1737531 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia GSD Validation | [9 empty] | TSSR Ready
4495 | Irbid_AlNaser_UNRWA_Schools_TASC_O | TASC | IRB-704-R | Outdoor |  | 35.8497 | 32.5673 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 57 | Cluster-44 |  |  | SMP-WO-1737532 | Al Lewan |  |  | Done |  |  | No 5G | [6 empty] | Pending |  | Moath | Released |  |  | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  |  | Released |  |  | 2 | A |  | TSSR Under Nokia GSD Validation | 2025-12-29 | [8 empty] | TSSR Ready
4480 | 4480-AlOdeh_Irbid_Camp_End_O | TASC | IRB-584-R | Outdoor |  | 32.5664 | 35.8541 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 58 | Cluster-44 |  |  | SMP-WO-1521487 | Al Lewan | [5 empty] | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Need Access | [9 empty] | TSSR Ready |  |  | Downloaded
4447 | 4447-Irbid_Hay_Shamali_PE_EBand_TASC | TASC | IRB-26-R | Indoor | 607 | 32.5655 | 35.8572 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 59 | Cluster-44 |  |  | SMP-WO-1737534 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4479 | 4479-North_Ave_East_PE_TASC_O | TASC | IRB-492-R | Irbid |  | 32.5655 | 35.8601 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 60 | Cluster-44 |  |  | SMP-WO-1737535 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4402 | 4402-Irbid_30th_St_PE_TASC | TASC | IRB-218-R | Indoor | 680 | 32.5639 | 35.8637 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 61 | Cluster-44 |  |  | SMP-WO-1737537 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4456 | 4456-Shamleh_Sch_Back_PE_Fiber_TASC_O | TASC | IRB-426-R | Irbid |  | 32.5641 | 35.8707 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 62 | Cluster-44 |  |  | SMP-WO-1737538 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4462 | 4462-30th_St_Back_PE_Fiber_TASC_O | TASC | IRB-437-R | Irbid |  | 32.561 | 35.8666 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 63 | Cluster-44 |  |  | SMP-WO-1737539 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4472 | 4472-Sal_CRL_East_PE_TASC_O | TASC | IRB-463-R | Irbid |  | 32.5604 | 35.8607 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 64 | Cluster-44 |  |  | SMP-WO-1737540 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4425 | 4425-Hashmia_Irbid_PE_EBand_TASC_O | TASC | IRB-286-R | Irbid |  | 32.5627 | 35.8588 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 65 | Cluster-44 |  |  | SMP-WO-1737541 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4416 | 4416-Sal_CRL_Irbid_PE_EBand_TASC | TASC | IRB-130-R | Indoor | 753 | 32.5608 | 35.8567 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 66 | Cluster-44 |  |  | SMP-WO-1737543 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4441 | 4441-Irbid_Electricity_CRL_PD_TASC_O | TASC | IRB-321-R | Irbid |  | 32.5622 | 35.8543 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 67 | Cluster-44 |  |  | SMP-WO-1737544 | Al Lewan | [5 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Need Access
4482 | 4482-AlOdeh_Irbid_Camp_Mid_O | TASC | IRB-583-R | Outdoor |  | 32.5625 | 35.8517 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 68 | Cluster-44 |  |  | SMP-WO-1521485 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Waed |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [11 empty] | Downloaded
4415 | 4415-Irbid_Camp_PC_Fiber_TASC | TASC | IRB-14-R | Indoor | 727 | 32.5651 | 35.8513 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 69 | Cluster-44 |  |  | SMP-WO-1737546 | Al Lewan | [5 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29
4428 | 4428-Irbid_Camp_Quran_CTR_PF_Fiber_TASC_O | TASC | IRB-522-R | Irbid |  | 32.5644 | 35.8486 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 70 | Cluster-44 |  |  | SMP-WO-1737547 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4442 | 4442-Irbid_Camp_North_PD_Fiber_TASC_O | TASC | IRB-326-R | Outdoor |  | 32.5656 | 35.8465 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 71 | Cluster-44 |  |  | SMP-WO-1521484 | Al Tawseea | [5 empty] | 5G | 5G | 4 |  |  |  |  | Pending |  | Zaid | Released |  | Omar Sami | Pending |  | Thabet Jaradat & Ahmad Hajdawood | Pending |  | Omar Qaqish & Yousef Al-Natour | Released | Akram Elturk / Ahmad Al-khateeb | Yes | 2 | A |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [11 empty] | Downloaded
4426 | 4426-Irbid_Camp_West_PF_TASC_O | TASC | IRB-521-R | Outdoor |  | 32.5628 | 35.8465 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 72 | Cluster-44 |  |  | SMP-WO-1521488 | Al Tawseea | [5 empty] | 5G | 5G | 4 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [7 empty] | Mofeed |  |  |  | Downloaded
4446 | 4446-Irbid_Camp_UNESCO_PF_O | TASC | IRB-362-R | Irbid |  | 32.5617 | 35.8489 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 73 | Cluster-44 |  |  | SMP-WO-1737550 | Al Tawseea | [5 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29
4406 | 4406-Tal_Irbid_PSD_PF_TASC_O | TASC | IRB-356-R | Irbid |  | 32.5587 | 35.8474 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 74 | Cluster-44 |  |  | SMP-WO-1737551 | Al Tawseea | [5 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Need Access
4481 | 4481-Hakama_St_Market_PF_TASC_O | TASC | IRB-435-R | Outdoor |  | 32.5589 | 35.8507 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 75 | Cluster-44 |  |  | SMP-WO-1521486 | Al Tawseea | [5 empty] | 5G | 5G | 3 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [11 empty] | Downloaded
4405 | 4405-Lebanon_CTR_PB_TASC | TASC | IRB-150-R | Indoor | 743 | 32.5567 | 35.8535 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 76 | Cluster-44 |  |  | SMP-WO-1521521 | Al Tawseea | [5 empty] | 5G | 5G | 4 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Subcon validation | [12 empty] | Downloaded
4459 | 4459-Hashmi_St_End_Irbid_PF_TASC_O | TASC | IRB-427-R | Irbid |  | 32.5566 | 35.85 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 77 | Cluster-44 |  |  | SMP-WO-1737554 | Al Lewan | [5 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29
4403 | 4403-Irbid_PA_Fiber_TASC | TASC | IRB-53-R | Indoor | 602 | 32.557 | 35.8464 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 78 | Cluster-44 |  |  | SMP-WO-1521557 | Al Lewan | [5 empty] | 5G | 5G | 4 |  | ABC |  |  |  |  | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Subcon validation | [8 empty] | Mofeed |  |  |  | Downloaded
4440 | 4440-Huson_St_PD_Fiber_TASC | TASC | IRB-89-R | Indoor | 671 | 32.5544 | 35.8507 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 79 | Cluster-44 |  |  | SMP-WO-1521508 | Al Lewan | [5 empty] | 5G | 5G | 3 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Subcon validation | [12 empty] | Downloaded
4467 | 4467-Irbid_Wasfi_Tal_CRL_West_PE_TASC_O | TASC | IRB-500-R | Outdoor | 2162 | 32.5543 | 35.8468 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 80 | Cluster-44 |  |  | SMP-WO-1737557 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29
4417 | 4417-Old_Aghwar_Bus_CPLX_PF_TASC | TASC | IRB-247-R | Indoor | 2135 | 32.5545 | 35.8437 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 81 | Cluster-44 |  |  | SMP-WO-1737558 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4436 | 4436-Barha_2_PC_Fiber_TASC | TASC | IRB-85-R | Indoor | 626 | 32.556 | 35.8401 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 82 | Cluster-44 |  |  | SMP-WO-1521438 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 |  | ABC |  |  |  |  | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Subcon validation | [12 empty] | Downloaded
4491 | Irbid_AlNadeef_Av_TASC_O | TASC | IRB-702-R | Outdoor |  | 35.8363 | 32.5562 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 83 | Cluster-44 |  |  | SMP-WO-1737560 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Subcon validation
4449 | 4449-Barha_Rahbat_Sch_PF_TASC_O | TASC | IRB-523-R | Outdoor |  | 32.5595 | 35.8406 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 84 | Cluster-44 |  |  | SMP-WO-1521423 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4419 | 4419-Hay_Matlaa_1_PE_TASC_O | TASC | IRB-269-R | Irbid |  | 32.5622 | 35.8408 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 85 | Cluster-44 |  |  | SMP-WO-1737562 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4418 | 4418-Hay_Matlaa_2_PE_TASC_O | TASC | IRB-266-R | Outdoor |  | 32.5648 | 35.8394 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 86 | Cluster-44 |  |  | SMP-WO-1521440 | Al Lewan |  |  | Done |  |  | 5G | 5G | 3 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4409 | 4409-Barha_CTR_PF_EBand_TASC | TASC | IRB-214-R | Indoor | 2107 | 32.5611 | 35.8379 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 87 | Cluster-44 |  |  | SMP-WO-1737565 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4448 | 4448-Quds_St_End_PE_TASC_O | TASC | IRB-402-R | Outdoor |  | 32.5659 | 35.8326 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 88 | Cluster-44 |  |  | SMP-WO-1521460 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [8 empty] | Laith |  |  |  | Downloaded
4435 | 4435-Barha_South_PF_TASC_O | TASC | IRB-404-R | Irbid |  | 32.568 | 35.83 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 89 | Cluster-44 |  |  | SMP-WO-1737567 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4484 | Barha_Palestine_Street_TASC_O | TASC | IRB-577-R | Outdoor |  | 35.8264 | 32.5631 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 90 | Cluster-44 |  |  | SMP-WO-1737568 | R&D |  |  | Done |  |  | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29
4427 | 4427-Barha_4_PE_TASC_O | TASC | IRB-287-R | Outdoor |  | 32.5661 | 35.8222 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 91 | Cluster-44 |  |  | SMP-WO-1521476 | R&D |  |  | Done |  |  | 5G | 5G | 3 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | TSSR Under Nokia NPO Validation | 2025-12-29 | [11 empty] | Downloaded
4486 | Irbid_Aban_Mosque_Barha_TASC_O | TASC | IRB-661-R | Outdoor |  | 35.8192 | 32.5685 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 92 | Cluster-44 |  |  | SMP-WO-1737570 | PIS |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4494 | Barha_Basateen_Av_TASC_O | TASC | IRB-706-R | Outdoor |  | 35.819 | 32.5641 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 93 | Cluster-44 |  |  | SMP-WO-1737571 | PIS |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4413 | 4413-Hay_Torkman_Irbid_PE_EBand_TASC | TASC | IRB-249-R | Indoor | 2141 | 32.5594 | 35.8252 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 94 | Cluster-44 |  |  | SMP-WO-1521450 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [8 empty] | Mofeed |  |  |  | Downloaded
4475 | 4475-Turkman_Ave_West_PE_TASC_O | TASC | IRB-482-R | Outdoor |  | 32.5561 | 35.8259 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 95 | Cluster-44 |  |  | SMP-WO-1521414 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4443 | 4443-Palestine_St_PD_EBand_TASC | TASC | IRB-131-R | Indoor | 752 | 32.5609 | 35.8298 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 96 | Cluster-44 |  |  | SMP-WO-1521424 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4458 | 4458-Palestine_St_Mid_PE_Fiber_TASC_O | TASC | IRB-432-R | Irbid |  | 32.5591 | 35.8339 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 97 | Cluster-44 |  |  | SMP-WO-1737575 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4457 | 4457-Barha_PA_Fiber_TASC | TASC | IRB-30-R | Indoor | 604 | 32.5559 | 35.8318 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 98 | Cluster-44 |  |  | SMP-WO-1521415 | Al Lewan |  |  | Done |  |  | 5G | 5G | 3 |  | ABC |  |  |  |  | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb | Yes | 0 |  |  | Site not Surveyed |  |  |  | Tower ladder is missing | [8 empty] | Downloaded
4489 | Barha_End_Tasc_O | TASC | IRB-659-R | Outdoor |  | 35.8334 | 32.5536 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 99 | Cluster-44 |  |  | SMP-WO-1737577 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4445 | 4445-Irbid_Zabda_CRL_PE_EBand_TASC_O | TASC | IRB-320-R | Outdoor |  | 32.5523 | 35.8423 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 100 | Cluster-44 |  |  | SMP-WO-1521501 | Al Lewan |  |  | Done |  |  | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb | Yes | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4411 | 4411-Rasheed_St_Irbid_PD_EBand_TASC | TASC | IRB-61-R | Indoor | 612 | 32.551 | 35.845 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 101 | Cluster-44 |  |  | SMP-WO-1521502 | [6 empty] | 5G | 5G | 3 | [6 empty] | Waed |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4490 | Ibn_Katheir_Irbid_Mosque_Tasc_O | TASC | IRB-676-R | Outdoor |  | 35.8441 | 32.5451 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 102 | Cluster-44 |  |  | SMP-WO-1737580 | [6 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4469 | 4469-Irbid_Manara_District_O | TASC | IRB-573-R | Outdoor |  | 32.5484 | 35.8473 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 103 | Cluster-44 |  |  | SMP-WO-1521503 | [6 empty] | 5G | 5G | 3 | [6 empty] | Waed |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4476 | 4476-Irbid_Civil_Affairs_Dep_PE_TASC_O | TASC | IRB-464-R | Irbid |  | 32.5553 | 35.8561 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 104 | Cluster-44 |  |  | SMP-WO-1737582 | [6 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4455 | 4455-Irbid_Hashmi_St_PE_EBand_TASC_O | TASC | IRB-312-R | Outdoor | 2202 | 32.5572 | 35.8577 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 105 | Cluster-44 |  |  | SMP-WO-1737583 | [6 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4439 | 4439-Queen_Nour_CRL_PA_Fiber_TASC | TASC | IRB-88-R | Indoor | 652 | 32.5569 | 35.863 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 106 | Cluster-44 |  |  | SMP-WO-1521523 | [6 empty] | 5G | 5G | 4 |  | ABC |  |  |  |  | Waed |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb | Yes | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4477 | 4477-New_Generation_Sch_PE_TASC_O | TASC | IRB-490-R | Irbid |  | 32.5542 | 35.8666 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 107 | Cluster-44 |  |  | SMP-WO-1737585 | [6 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4430 | 4430-Hay_Andalous_Irbid_PD_EBand_TASC_Relo_O | TASC | IRB-508-R | Irbid |  | 32.555 | 35.8725 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 108 | Cluster-44 |  |  | SMP-WO-1737586 | [6 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4461 | 4461-Hay_Tlool_East_Irbid_PE_O | TASC | IRB-563-R | Irbid |  | 32.5493 | 35.873 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 109 | Cluster-44 |  |  | SMP-WO-1737587 | [6 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4429 | 4429-Zahra_Irbid_PE_TASC | TASC | IRB-198-R | Indoor | 784 | 32.5515 | 35.8779 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 110 | Cluster-44 |  |  | SMP-WO-1737588 | [6 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4438 | 4438-Zahra_Garden_Irbid_PE_EBand_TASC_O | TASC | IRB-355-R | Irbid |  | 32.5468 | 35.8779 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 111 | Cluster-44 |  |  | SMP-WO-1737589 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4485 | 4485-Boshra_Circle_Mid_TASC_O | TASC | IRB-605-R | Outdoor |  | 32.5465 | 35.884 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 112 | Cluster-44 |  |  | SMP-WO-1521211 | [6 empty] | 5G | 5G | 4 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4460 | 4460-Bushra_South_Ave_PF_TASC_O | TASC | IRB-527-R | Outdoor |  | 32.5506 | 35.8879 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 113 | Cluster-44 |  |  | SMP-WO-1521217 | [6 empty] | 5G | 5G | 4 | [6 empty] | Zaid |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4487 | Irbid_Al_Andalos_East_TASC_O | TASC | IRB-681-R | Outdoor |  | 35.8811 | 32.5544 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 114 | Cluster-44 |  |  | SMP-WO-1737592 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4433 | 4433-Hay_Rawda_Irbid_PE_EBand_TASC_O | TASC | IRB-306-R | Irbid |  | 32.5558 | 35.8771 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 115 | Cluster-44 |  |  | SMP-WO-1737593 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4420 | 4420-Rawabi_Irbid_PE_Relo | TASC | IRB-580-R | Irbid |  | 32.5596 | 35.88 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 116 | Cluster-44 |  |  | SMP-WO-1737594 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4432 | 4432-Tunis_Garden_Irbid_PF_O | TASC | IRB-307-R | Irbid |  | 32.563 | 35.8772 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 117 | Cluster-44 |  |  | SMP-WO-1737595 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4473 | 4473-Irbid_Badiaa_Ave_North_PE_TASC_O | TASC | IRB-480-R | Irbid |  | 32.5746 | 35.877 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 118 | Cluster-44 |  |  | SMP-WO-1737596 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4412 | 4412-Irbid_Ind_2_PE_EBand_TASC | TASC | IRB-239-R | Indoor | 2126 | 32.5713 | 35.8792 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 119 | Cluster-44 |  |  | SMP-WO-1737598 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4444 | 4444-Mansour_Gardens_PE_TASC_O | TASC | IRB-315-R | Irbid |  | 32.567 | 35.8778 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 120 | Cluster-44 |  |  | SMP-WO-1737599 | [6 empty] | No 5G | [8 empty] | Zaid | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4453 | 4453-Irbid_Mallah_Msq_PD_TASC_O | TASC | IRB-418-R | Irbid |  | 32.5658 | 35.8822 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 121 | Cluster-44 |  |  | SMP-WO-1737601 | [6 empty] | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4493 | Boshra_Al_Bushra_Msq_Bk_TASC_O | TASC | IRB-721-R | Outdoor |  | 35.8867 | 32.5586 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 122 | Cluster-44 |  |  | SMP-WO-1737602 | [6 empty] | No 5G | [8 empty] | Obieda | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4410 | 4410-Bushra_PC_EBand_TASC | TASC | IRB-9-R | Indoor | 625 | 32.5596 | 35.8921 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 123 | Cluster-44 |  |  | SMP-WO-1521215 | [6 empty] | 5G | 5G | 3 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed
4471 | 4471-Bushra_Old_Cemetary_PE_EBand_TASC_O | TASC | IRB-476-R | Outdoor |  | 32.5566 | 35.8966 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 124 | Cluster-44 |  |  | SMP-WO-1521216 | [6 empty] | 5G | 5G | 4 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4463 | 4463-Bushra_North_PF_TASC_O | TASC | IRB-440-R | Outdoor |  | 32.5635 | 35.8954 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 125 | Cluster-44 |  |  | SMP-WO-1521214 | [6 empty] | 5G | 5G | 4 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
4474 | 4474-Bushra_Busia_PF_TASC_O | TASC | IRB-441-R | Outdoor |  | 32.5677 | 35.9031 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 126 | Cluster-44 |  |  | SMP-WO-1521212 | [6 empty] | 5G | 5G | 4 | [6 empty] | Obieda |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
426 | 426-Saal_CTR_PE_TASC | TASC | IRB-253-R | Indoor | 2144 | 32.5681 | 35.9119 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 127 | Cluster-4 |  |  | SMP-WO-1521327 | [6 empty] | 5G | 5G | 3 | [6 empty] | Obieda |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
452 | 452-Saal_PF_O | TASC | IRB-27-R | Outdoor |  | 32.5715 | 35.9228 | Irbid | Pole |  |  |  |  | Swap For Exsting Thin layer | RO4 | 128 | Cluster-4 |  |  | SMP-WO-1521326 | [6 empty] | 5G | 5G | 3 | [6 empty] | Obieda |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed |  |  | Dismantle 2nd L1800 RRU | Need Conatct Person to arrange //L1800+ RRU | [8 empty] | Downloaded
439 | 439-Sal_Alia_Ave_PF_TASC_O | TASC | IRB-525-R | Outdoor |  | 32.5797 | 35.9084 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 129 | Cluster-4 |  |  | SMP-WO-1521325 | [6 empty] | 5G | 5G | 4 | [6 empty] | Obieda |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
432 | 432-Mzaireeb_Irbid_PF_O | TASC | IRB-380-R | Irbid |  | 32.6559 | 35.8201 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 130 | Cluster-4 |  |  | SMP-WO-1737610 | [6 empty] | No 5G | [8 empty] | Obieda |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
425 | 425-Samar_Irbid_PC_Fiber_TASC | TASC | IRB-241-R | Indoor | 2131 | 32.6773 | 35.7876 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 131 | Cluster-4 |  |  | SMP-WO-1737611 | [6 empty] | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
473 | 473-Ibdar_CTR_PF_TASC_O | TASC | IRB-479-R | Irbid |  | 32.6628 | 35.7846 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 132 | Cluster-4 |  |  | SMP-WO-1737612 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under ROM Review | 2025-12-22
467 | 467-Ibdar_Mzaireeb_Rd_PE_Fiber_TASC_O | TASC | IRB-451-R | Irbid |  | 32.6539 | 35.8025 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 133 | Cluster-4 |  |  | SMP-WO-1737613 | Al Lewan |  |  | Done |  |  | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | TSSR Under ROM Review | 2025-12-29
409 | 409-Um_Jadayel_PD_TASC | TASC | IRB-8-G | Indoor | 722 | 32.6019 | 35.8039 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 134 | Cluster-4 |  |  | SMP-WO-1737614 | [6 empty] | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
482 | 482-Um_Jadayel_West_O | TASC | IRB-634-R | Irbid |  | 32.6048 | 35.7939 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 135 | Cluster-4 |  |  | SMP-WO-1737615 | [6 empty] | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
458 | 458-Hawar_Irbid_PF_Org_Manage_O | ZAIN/M | IRB-506-G | Irbid |  | 32.6021 | 35.7685 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 136 | Cluster-4 |  |  | SMP-WO-1737616 | [6 empty] | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
472 | 472-Soum_North_PF_TASC_O | TASC | IRB-448-R | Irbid |  | 32.5875 | 35.7947 | Irbid | Pole |  |  |  |  | Full Swap | RO4 | 137 | Cluster-4 |  |  | SMP-WO-1737617 | [6 empty] | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4408 | 4408-Barha_Irbid_Ring_Rd_PF_O | TASC | IRB-564-R | Outdoor |  | 32.5835 | 35.8162 | Irbid | Tower |  |  |  |  | Swap For Exsting Thin layer | RO4 | 138 | Cluster-44 |  |  | SMP-WO-1521471 | [6 empty] | 5G | 5G | 4 | [6 empty] | Moath |  |  | Omar Sami |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  | 0 |  |  | Site not Surveyed | [12 empty] | Downloaded
404 | 404-Soum_Irbid_PE_TASC | TASC | IRB-209-R | Indoor | 796 | 32.5744 | 35.8008 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 139 | Cluster-4 |  |  | SMP-WO-1737619 | [6 empty] | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
454 | 454-Soum_Ent_PF_TASC_O | TASC | IRB-549-R | Irbid |  | 32.5654 | 35.7942 | Irbid | Tower |  |  |  |  | Full Swap | RO4 | 140 | Cluster-4 |  |  | SMP-WO-1737620 | [6 empty] | No 5G | [8 empty] | Moath |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
499 | Zahar_Secondary_Scl_Bk_TASC_O | TASC | IRB-738-R | Outdoor |  | 35.778 | 32.5666 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 141 | Cluster-4 |  |  | SMP-WO-1737621 | [6 empty] | No 5G | [8 empty] | Waed |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
44XX | Alsonbolah_Irbid | TASC | #N/A | Outdoor |  | 35.8839 | 32.5746 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 142 | Cluster-44 | [9 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4XX | Mughayar_irbid_South | TASC | #N/A | Outdoor |  | 35.8583 | 32.5409 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 143 | Cluster-4 | [9 empty] | No 5G | [8 empty] | Waed |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
24XX | Irbid_MOH_O | TASC | #N/A | Outdoor |  | 35.9265 | 32.588 | Irbid | RT |  |  |  |  | Full Swap | RO4 | 144 | Cluster-24 | [9 empty] | No 5G | [8 empty] | Waed | [5 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
707 | 707-Petra_PB_Fiber_TASC | TASC | MAN-7-G | Indoor | 808 | 30.336 | 35.5159 | Ma'an | Tower |  |  |  |  | ThinLayer | RO4 | 145 | Cluster-7 |  |  | SMP-WO-1737622 | [6 empty] | ABC | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
774 | 774-Petra_2_PE_EBand_TASC | TASC | MAN-63-G | Indoor | 920 | 30.329 | 35.4922 | Ma'an | Tower |  |  |  |  | ThinLayer | RO4 | 146 | Cluster-7 |  |  | SMP-WO-1737623 | [6 empty] | BCD | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
779 | 779-Wadi_Moussa_Nawafleh_PE_Fiber_TASC_O | TASC | MAN-126-R | Ma'an |  | 30.324 | 35.4804 | Ma'an | Pole |  |  |  |  | ThinLayer | RO4 | 147 | Cluster-7 |  |  | SMP-WO-1737626 | [6 empty] | ACD | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
702 | 702-Petra_Mountain_PSD_PB_Fiber_TASC | TASC | MAN-62-G | Indoor | 940 | 30.315 | 35.4683 | Ma'an | Tower |  |  |  |  | ThinLayer | RO4 | 148 | Cluster-7 |  |  | SMP-WO-1737627 | [6 empty] | ABC | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
750 | 750-Wadi_Moussa_Zrezrea_PE_EBand_TASC_O | TASC | MAN-180-R | Ma'an |  | 30.3151 | 35.4866 | Ma'an | Tower |  |  |  |  | ThinLayer | RO4 | 149 | Cluster-7 |  |  | SMP-WO-1737628 | [6 empty] | BCD | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
764 | 764-Maan_Governorate_PE_O | TASC | MAN-124-R | Ma'an |  | 30.2142 | 35.7364 | Ma'an | Pole |  |  |  |  | ThinLayer | RO4 | 150 | Cluster-7 |  |  | SMP-WO-1737629 | [6 empty] | ABC | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
798 | 798-Maan_Esteraha_Ave_PF_TASC_O | TASC | MAN-138-R | Ma'an |  | 30.207 | 35.7319 | Ma'an | Pole |  |  |  |  | ThinLayer | RO4 | 151 | Cluster-7 |  |  | SMP-WO-1737630 | [6 empty] | ABD | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
6286 | Othruh_Rd | TASC | MAN-240-R | Outdoor |  | 35.7236 | 30.2104 | Ma'an | RT |  |  |  |  | ThinLayer | RO4 | 152 | Cluster-62 |  |  | SMP-WO-1737631 | [6 empty] | ABC | [21 empty] | 0 |  |  | Site not Surveyed
763 | 763-Maan_Faisal_Mall_PE_O | TASC | MAN-122-R | Ma'an |  | 30.2171 | 35.7181 | Ma'an | Pole |  |  |  |  | ThinLayer | RO4 | 153 | Cluster-7 |  |  | SMP-WO-1737632 | [6 empty] | ABC | [11 empty] | Laith | [9 empty] | 0 |  |  | Site not Surveyed
6283 | Sateh_Maan_West | TASC | MAN-239-R | Outdoor |  | 35.7272 | 30.2222 | Ma'an | RT |  |  |  |  | ThinLayer | RO4 | 154 | Cluster-62 |  |  | SMP-WO-1737633 | [6 empty] | ABC | [21 empty] | 0 |  |  | Site not Surveyed
5833 | 5833-Hasa_City_PE_TASC | TASC | KRK-33-G | Indoor | 936 | 30.848 | 35.9782 | Tafila | Tower |  |  |  |  | ThinLayer | RO4 | 155 | Cluster-58 |  |  | SMP-WO-1737634 | [6 empty] | ABC | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
6207 | Hassa_Housing | TASC | TAF-61-R | Outdoor |  | 35.9787 | 30.8255 | Tafila | RT |  |  |  |  | ThinLayer | RO4 | 156 | Cluster-62 |  |  | SMP-WO-1737635 | [6 empty] | ABC | [21 empty] | 0 |  |  | Site not Surveyed
5855 | 5855-Hasa_West_PF_O | TASC | KRK-197-R | Tafila |  | 30.8175 | 35.9697 | Tafila | Tower |  |  |  |  | ThinLayer | RO4 | 157 | Cluster-58 |  |  | SMP-WO-1737636 | [6 empty] | ABC | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5853 | 5853-AlEyis_Tafilah_PE_EBand_TASC_O | TASC | TAF-34-R | Tafila |  | 30.8294 | 35.6428 | Tafila | Tower |  |  |  |  | ThinLayer | RO4 | 158 | Cluster-58 |  |  | SMP-WO-1737637 | [6 empty] | ABD | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5873 | 5873-Tafilah_College_PC_Fiber_TASC | TASC | TAF-16-R | Indoor | 921 | 30.8383 | 35.6414 | Tafila | Pole |  |  |  |  | ThinLayer | RO4 | 159 | Cluster-58 |  |  | SMP-WO-1737638 | [6 empty] | ABC | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5881 | 5881-Tafilah_College_2_PE_TASC_O | TASC | TAF-27-R | Tafila |  | 30.8485 | 35.6453 | Tafila | Pole |  |  |  |  | ThinLayer | RO4 | 160 | Cluster-58 |  |  | SMP-WO-1737640 | [6 empty] | ACD | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5821 | 5821-Tafilah_Zreqeat_PD_Fiber_TASC_O | TASC | TAF-32-R | Tafila |  | 30.8475 | 35.6328 | Tafila | Tower |  |  |  |  | ThinLayer | RO4 | 161 | Cluster-58 |  |  | SMP-WO-1737641 | [6 empty] | ACD | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5872 | 5872-Bsaira_Tafilah_PD_Fiber_TASC | TASC | TAF-24-R | Indoor | 980 | 30.7338 | 35.6112 | Tafila | Pole |  |  |  |  | ThinLayer | RO4 | 162 | Cluster-58 |  |  | SMP-WO-1737642 | [6 empty] | ABC | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5847 | 5847-Bsaira_Market_PE_Fiber_TASC_O | TASC | TAF-46-R | Tafila |  | 30.7359 | 35.6082 | Tafila | Pole |  |  |  |  | ThinLayer | RO4 | 163 | Cluster-58 |  |  | SMP-WO-1737643 | [6 empty] | BCD | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5876 | 5876-Bsaira_Tafilah_2_PE_Fiber_TASC_O | TASC | TAF-30-R | Tafila |  | 30.726 | 35.6171 | Tafila | Pole |  |  |  |  | ThinLayer | RO4 | 164 | Cluster-58 |  |  | SMP-WO-1737644 | [6 empty] | ABD | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
5891 | 5891-Tafilah_Bsaira_Rd_PE_Fiber_TASC_O | TASC | TAF-40-R | Tafila |  | 30.7194 | 35.6227 | Tafila | Pole |  |  |  |  | ThinLayer | RO4 | 165 | Cluster-58 |  |  | SMP-WO-1737645 | [6 empty] | ABD | [11 empty] | M. Al-Amro | [9 empty] | 0 |  |  | Site not Surveyed
4682 | 4682-Rasoon_PA_EBand_TASC | TASC | AJL-12-G | Indoor | 709 | 32.4135 | 35.7531 | Ajloun | Tower |  |  |  |  | ThinLayer | RO4 | 166 | Cluster-46 |  |  | SMP-WO-1737646 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
4684 | 4684-Arjan_Ajloun_PF_TASC_O | TASC | AJL-43-R | Ajloun |  | 32.3929 | 35.7322 | Ajloun | Tower |  |  |  |  | ThinLayer | RO4 | 167 | Cluster-46 |  |  | SMP-WO-1737647 | [6 empty] | ACD | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1468 | 1468-Ibeen_2_PE_TASC_O | TASC | Ajl-31-R | Ajloun |  | 32.3624 | 35.7982 | Ajloun | Tower |  |  |  |  | ThinLayer | RO4 | 168 | Cluster-14 |  |  | SMP-WO-1737648 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1418 | 1418-Souf_West_PD_EBand_TASC | TASC | JRS-39-R | Indoor | 2149 | 32.3129 | 35.8355 | Jarash | Tower |  |  |  |  | ThinLayer | RO4 | 169 | Cluster-14 |  |  | SMP-WO-1737649 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1467 | 1467-Anjarah_Ent_PE_Fiber_TASC | TASC | AJL-29-R | Indoor | 2148 | 32.3086 | 35.766 | Ajloun | Pole |  |  |  |  | ThinLayer | RO4 | 170 | Cluster-14 |  |  | SMP-WO-1737650 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1436 | 1436-Anjarah_North_PD_Fiber_TASC_O | TASC | AJL-45-R | Ajloun |  | 32.3096 | 35.7578 | Ajloun | Pole |  |  |  |  | ThinLayer | RO4 | 171 | Cluster-14 |  |  | SMP-WO-1737651 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
6382 | Anjarah_King_Abdullah_School | TASC | AJL-78-R | Outdoor |  | 35.7407 | 32.3025 | Ajloun | RT |  |  |  |  | ThinLayer | RO4 | 172 | Cluster-63 |  |  | SMP-WO-1737652 | [6 empty] | ABC | [14 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1485 | 1485-Ain_Bustan_Anjarah_PE_Fiber_TASC_O | TASC | AJL-36-R | Ajloun |  | 32.3036 | 35.7246 | Ajloun | Tower |  |  |  |  | ThinLayer | RO4 | 173 | Cluster-14 |  |  | SMP-WO-1737653 | [6 empty] | BCD | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1404 | 1404-Amreyyeh_Ajloun_PF_TASC_O | TASC | AJL-39-R | Ajloun |  | 32.2914 | 35.7116 | Ajloun | Pole |  |  |  |  | ThinLayer | RO4 | 174 | Cluster-14 |  |  | SMP-WO-1737654 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1422 | 1422-Kufranjeh_CTR_PC_Fiber_TASC | TASC | AJL-7-G | Indoor | 696 | 32.3028 | 35.7118 | Ajloun | Tower |  |  |  |  | ThinLayer | RO4 | 175 | Cluster-14 |  |  | SMP-WO-1737655 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1476 | 1476-Kufranjeh_West_PD_Fiber_TASC_O | TASC | AJL-32-R | Ajloun |  | 32.2986 | 35.6981 | Ajloun | Pole |  |  |  |  | ThinLayer | RO4 | 176 | Cluster-14 |  |  | SMP-WO-1737656 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
6006 | 6006-Souf_Manara_Mountain_O | TASC | JRS-110-R | Jarash |  | 32.309 | 35.8343 | Jarash | Tower |  |  |  |  | ThinLayer | RO4 | 177 | Cluster-60 |  |  | SMP-WO-1737657 | [6 empty] | ABC | [14 empty] | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1437 | 1437-Souf_PC_TASC | TASC | JRS-11-R | Indoor | 670 | 32.3189 | 35.8506 | Jarash | Tower |  |  |  |  | ThinLayer | RO4 | 178 | Cluster-14 |  |  | SMP-WO-1737658 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
1588 | 1588-Jawasreh_North_PE_Fiber_TASC_O | TASC | MAD-271-R | Balqa |  | 31.874 | 35.6272 | Balqa | Pole |  |  |  |  | ThinLayer | RO4 | 179 | Cluster-15 |  |  | SMP-WO-1737659 | [6 empty] | ABC | [11 empty] | M. Al-Amro |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
3144 | 3144-Hitteen_Camp_Qwasmi_Msq_PF_TASC_O | TASC | ZRQ-344-R | Zarqa |  | 32.0023 | 36.02 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 180 | Cluster-31 |  |  | SMP-WO-1737660 | [6 empty] | ACD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
3153 | Hitteen_Camp_West_Tasc_O | TASC | ZRQ-491-R | Outdoor |  | 36.0094 | 32.0097 | Zarqa | RT |  |  |  |  | ThinLayer | RO4 | 181 | Cluster-31 |  |  | SMP-WO-1737661 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
3121 | 3121-Hay_Rasheed_PC_EBand_TASC | TASC | ZRQ-130-R | Indoor | 555 | 32.0218 | 36.0199 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 182 | Cluster-31 |  |  | SMP-WO-1737662 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
3150 | 3150-Rusaifeh_Court_Back_O | TASC | ZRQ-460-R | Zarqa |  | 32.0258 | 36.0188 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 183 | Cluster-31 |  |  | SMP-WO-1737663 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
3125 | 3125-Jreiba_2_PD_TASC | TASC | ZRQ-192-R | Indoor | 597 | 32.0322 | 36.0187 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 184 | Cluster-31 |  |  | SMP-WO-1737667 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
3151 | 3151-Jabal_Shamali_4_O | TASC | ZRQ-461-R | Zarqa |  | 32.0307 | 36.0272 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 185 | Cluster-31 |  |  | SMP-WO-1737668 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
3110 | 3110-Jabal_Shamali_3_PD_TASC | TASC | ZRQ-103-R | Indoor | 509 | 32.0263 | 36.0258 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 186 | Cluster-31 |  |  | SMP-WO-1737669 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4347 | 4347-Jabal_Shamali_2_PB_Fiber_TASC | TASC | ZRQ-116-R | Indoor | 562 | 32.0318 | 36.0372 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 187 | Cluster-43 |  |  | SMP-WO-1737670 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4333 | 4333-Zarqa_Qadesieh_Back_PF_TASC_O | TASC | ZRQ-424-R | Zarqa |  | 32.0409 | 36.0313 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 188 | Cluster-43 |  |  | SMP-WO-1737671 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4340 | 4340-Jabal_Shamali_End_PF_EBand_TASC_O | TASC | ZRQ-254-R | Zarqa |  | 32.0362 | 36.037 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 189 | Cluster-43 |  |  | SMP-WO-1737672 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4302 | 4302-Prince_Faisal_Hospital_PD_TASC_O | TASC | ZRQ-256-R | Zarqa |  | 32.0346 | 36.0452 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 190 | Cluster-43 |  |  | SMP-WO-1737673 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4315 | 4315-Iskan_Talal_PE_EBand_TASC | TASC | ZRQ-24-R | Indoor | 560 | 32.0365 | 36.0548 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 191 | Cluster-43 |  |  | SMP-WO-1737674 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4308 | 4308-Razi_Hospital_PC_Fiber_TASC | TASC | ZRQ-8-R | Indoor | 544 | 32.0299 | 36.0622 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 192 | Cluster-43 |  |  | SMP-WO-1737675 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4321 | 4321-Awajan_2_PB_Fiber_TASC | TASC | ZRQ-158-R | Indoor | 571 | 32.0252 | 36.0589 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 193 | Cluster-43 |  |  | SMP-WO-1737676 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4335 | 4335-Jabal_Shamali_Back_PE_Fiber_O | TASC | ZRQ-291-R | Zarqa |  | 32.0268 | 36.0417 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 194 | Cluster-43 |  |  | SMP-WO-1737679 | [6 empty] | BCD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4325 | 4325-Jabal_Shamali_Market_PF_TASC | TASC | ZRQ-159-R | Indoor | 583 | 32.0225 | 36.0442 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 195 | Cluster-43 |  |  | SMP-WO-1737680 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4362 | 4362-Russayfah_West_PE_TASC_O | TASC | ZRQ-265-R | Zarqa |  | 32.0162 | 36.0409 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 196 | Cluster-43 |  |  | SMP-WO-1737681 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4314 | 4314-Russayfah_PE_EBand_TASC | TASC | ZRQ-107-R | Indoor | 519 | 32.0173 | 36.0592 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 197 | Cluster-43 |  |  | SMP-WO-1737682 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4332 | 4332-Zarqa_Kng_Talal_Ave_PF_TASC_O | TASC | ZRQ-418-R | Zarqa |  | 32.0315 | 36.0703 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 198 | Cluster-43 |  |  | SMP-WO-1737683 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1001 | 1001-BSC_Dwaik_PA_Fiber_TASC_O | TASC | ZRQ-1-G | Outdoor | 518 | 32.04 | 36.0665 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 199 | Cluster-10 |  |  | SMP-WO-1737684 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1021 | 1021-Jabal_Hassan_North_PF_TASC_O | TASC | ZRQ-372-R | Zarqa |  | 32.0363 | 36.0741 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 200 | Cluster-10 |  |  | SMP-WO-1737685 | [6 empty] | BCD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1027 | 1027-Jabal_Amir_Hassan_East_PF_TASC_O | TASC | ZRQ-394-R | Zarqa |  | 32.036 | 36.0799 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 201 | Cluster-10 |  |  | SMP-WO-1737686 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1031 | 1031-Jabal_Rahmeh_PC_EBand_TASC | TASC | ZRQ-196-R | Indoor | 598 | 32.0412 | 36.0805 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 202 | Cluster-10 |  |  | SMP-WO-1737687 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1017 | 1017-Zarqa_Quds_CRL_West_PF_TASC_O | TASC | ZRQ-426-R | Zarqa |  | 32.0456 | 36.0755 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 203 | Cluster-10 |  |  | SMP-WO-1737688 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1055 | 1055-Quds_CRL_Zarqa_PF_TASC_O | TASC | ZRQ-366-R | Zarqa |  | 32.0472 | 36.0795 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 204 | Cluster-10 |  |  | SMP-WO-1737689 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1030 | 1030-Jabal_Abiyad_CTR_PF_TASC_O | TASC | ZRQ-395-R | Zarqa |  | 32.0566 | 36.0775 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 205 | Cluster-10 |  |  | SMP-WO-1737690 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1002 | 1002-Zawahrah_PB_Fiber_TASC | TASC | ZRQ-2-R | Indoor | 526 | 32.0626 | 36.0714 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 206 | Cluster-10 |  |  | SMP-WO-1737691 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4234 | 4234-Zarqa_Girls_Secondary_Sch_PF_TASC_O | TASC | ZRQ-404-R | Zarqa |  | 32.0612 | 36.0829 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 207 | Cluster-42 |  |  | SMP-WO-1737692 | [6 empty] | ACD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1932 | 1932-Masoum_Ave_2_PE | TASC | ZRQ-219-R | Indoor | 1812 | 32.0854 | 36.0777 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 208 | Cluster-19 |  |  | SMP-WO-1737693 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1926 | 1926-Masoum_Ave_PE_EBand_TASC | TASC | ZRQ-77-R | Indoor | 516 | 32.0811 | 36.073 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 209 | Cluster-19 |  |  | SMP-WO-1737694 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1930 | 1930-Masoum_CRL_PD_Fiber_TASC | TASC | ZRQ-125-R | Indoor | 563 | 32.0781 | 36.0754 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 210 | Cluster-19 |  |  | SMP-WO-1737695 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4212 | 4212-Zarqa_Hay_Hussein_End_PF_TASC_O | TASC | ZRQ-333-R | Zarqa |  | 32.0741 | 36.0755 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 211 | Cluster-42 |  |  | SMP-WO-1737696 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4226 | 4226-Hay_Shaker_PF_EBand_TASC_O | TASC | ZRQ-410-R | Zarqa |  | 32.0713 | 36.0785 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 212 | Cluster-42 |  |  | SMP-WO-1737697 | [6 empty] | ACD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4232 | 4232-Hay_Hussein_West_PE_EBand_TASC_O | TASC | ZRQ-412-R | Zarqa |  | 32.0684 | 36.0778 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 213 | Cluster-42 |  |  | SMP-WO-1737698 | [6 empty] | ACD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4224 | 4224-Hay_Hussein_2_PB_Fiber_TASC | TASC | ZRQ-149-R | Indoor | 577 | 32.0675 | 36.0806 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 214 | Cluster-42 |  |  | SMP-WO-1737699 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4248 | 4248-Hay_Hussein_CTR_PE_Fiber_TASC_O | TASC | ZRQ-367-R | Zarqa |  | 32.0668 | 36.0845 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 215 | Cluster-42 |  |  | SMP-WO-1737700 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4211 | 4211-Hay_Hussein_PC_Fiber_TASC | TASC | ZRQ-41-R | Indoor | 556 | 32.0713 | 36.0833 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 216 | Cluster-42 |  |  | SMP-WO-1737702 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4236 | New_Zarqa_Ramzi_Av_Tasc_O | TASC | ZRQ-506-R | Outdoor |  | 36.0861 | 32.0729 | Zarqa | RT |  |  |  |  | ThinLayer | RO4 | 217 | Cluster-42 |  |  | SMP-WO-1737703 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4239 | 4239-Ghwereieh_PC_Fiber_TASC | TASC | ZRQ-58-R | Indoor | 536 | 32.0724 | 36.0943 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 218 | Cluster-42 |  |  | SMP-WO-1737704 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1913 | 1913-Ghwereieh_2_PE_EBand_TASC | TASC | ZRQ-143-R | Indoor | 575 | 32.0778 | 36.0953 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 219 | Cluster-19 |  |  | SMP-WO-1737705 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1910 | 1910-Hay_Amir_Abdullah_PF_EBand_TASC | TASC | ZRQ-40-R | Indoor | 550 | 32.0806 | 36.0961 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 220 | Cluster-19 |  |  | SMP-WO-1737706 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1940 | 1940-Ghwereieh_Hay_Baraakh_PF_EBand_TASC_O | TASC | ZRQ-263-R | Zarqa |  | 32.0797 | 36.093 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 221 | Cluster-19 |  |  | SMP-WO-1737707 | [6 empty] | BCD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1922 | 1922-Zarqa_Jadedah_2_PE_EBand_TASC | TASC | ZRQ-82-R | Indoor | 524 | 32.0857 | 36.0905 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 222 | Cluster-19 |  |  | SMP-WO-1737710 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1943 | 1943-AbuAlfool_Palace_PE_EBand_TASC | TASC | ZRQ-227-R | Indoor | 1818 | 32.092 | 36.107 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 223 | Cluster-19 |  |  | SMP-WO-1737711 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1902 | 1902-Falater_Batrawi_PB_Fiber_TASC | TASC | ZRQ-200-R | Indoor | 500 | 32.0975 | 36.1016 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 224 | Cluster-19 |  |  | SMP-WO-1737712 | [6 empty] | ABD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1919 | 1919-Zarqa_Jadedah_Middle_PE_TASC_O | TASC | ZRQ-427-R | Zarqa |  | 32.0945 | 36.097 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 225 | Cluster-19 |  |  | SMP-WO-1737713 | [6 empty] | ACD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1903 | 1903-Zarqa_Jadedah_26_St_PE_Fiber_TASC | TASC | ZRQ-226-R | Indoor | 1816 | 32.0919 | 36.0923 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 226 | Cluster-19 |  |  | SMP-WO-1737714 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1935 | 1935-Zarqa_Jadedah_Mid_PE_GPON_TASC_O | TASC | ZRQ-438-R | Zarqa |  | 32.0896 | 36.0919 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 227 | Cluster-19 |  |  | SMP-WO-1737715 | [6 empty] | BCD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1960 | 1960-Zarqa_16_St_PE_TASC_O | TASC | ZRQ-342-R | Zarqa |  | 32.0892 | 36.0998 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 228 | Cluster-19 |  |  | SMP-WO-1737716 | [6 empty] | BCD | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1923 | 1923-Zarqa_Jadedah_1_PB_Fiber_TASC | TASC | ZRQ-76-R | Indoor | 523 | 32.0913 | 36.1018 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 229 | Cluster-19 |  |  | SMP-WO-1737717 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1944 | 1944-AbuAlfool_North_PE_TASC | TASC | ZRQ-156-R | Indoor | 585 | 32.0845 | 36.1016 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 230 | Cluster-19 |  |  | SMP-WO-1737718 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1937 | 1937-Abu_AlFool_Salah_Din_Msq_O | TASC | ZRQ-458-R | Zarqa |  | 32.0818 | 36.103 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 231 | Cluster-19 |  |  | SMP-WO-1737719 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1927 | 1927-AbuAlfool_PA_Fiber_TASC | TASC | ZRQ-81-R | Indoor | 501 | 32.0795 | 36.1006 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 232 | Cluster-19 |  |  | SMP-WO-1737721 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4250 | 4250-Ghwereieh_CTR_PE_EBand_TASC_O | TASC | ZRQ-261-R | Zarqa |  | 32.0743 | 36.0973 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 233 | Cluster-42 |  |  | SMP-WO-1737722 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4216 | 4216-Jaish_St_PE_TASC | TASC | ZRQ-46-R | Indoor | 531 | 32.0696 | 36.0974 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 234 | Cluster-42 |  |  | SMP-WO-1737723 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4251 | 4251-Ghwereieh_Ent_PE_Fiber_TASC_O | TASC | ZRQ-262-R | Zarqa |  | 32.0679 | 36.0939 | Zarqa | Pole |  |  |  |  | ThinLayer | RO4 | 235 | Cluster-42 |  |  | SMP-WO-1737724 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
4223 | 4223-Hawouz_Hospital_East_PE_Fiber_TASC_O | TASC | ZRQ-391-R | Zarqa |  | 32.0708 | 36.0904 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 236 | Cluster-42 |  |  | SMP-WO-1737725 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1901 | 1901-BSC_Zarqa_WaterTank_PA_Fiber_TASC | TASC | ZRQ-31-G | Indoor | 512 | 32.0764 | 36.0897 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 237 | Cluster-19 |  |  | SMP-WO-1737726 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1904 | 1904-Zarqa_Safeway_Back_PF | TASC | ZRQ-228-R | Indoor | 1819 | 32.0814 | 36.085 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 238 | Cluster-19 |  |  | SMP-WO-1737727 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
1912 | 1912-Hay_Ramzi_PD_Fiber_TASC | TASC | ZRQ-42-R | Indoor | 515 | 32.0788 | 36.0806 | Zarqa | Tower |  |  |  |  | ThinLayer | RO4 | 239 | Cluster-19 |  |  | SMP-WO-1737728 | [6 empty] | ABC | [11 empty] | Baher Obaidat |  |  | Karam Jaber & Akram Abdelrahim | [6 empty] | 0 |  |  | Site not Surveyed
2997 | 2997-Ramtha_Hawooz_West | TASC | IRB-651-R | Irbid |  | 32.5655 | 35.9889 | Irbid | Tower |  |  |  |  | ThinLayer | RO4 | 240 | Cluster-29 |  |  | SMP-WO-1737729 | [18 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
2904 | 2904-Ramtha_East_Ent_PF_TASC_O | TASC | IRB-542-R | Irbid |  | 32.56 | 35.984 | Irbid | Tower |  |  |  |  | ThinLayer | RO4 | 241 | Cluster-29 |  |  | SMP-WO-1737730 | [18 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
2959 | 2959-Ramtha_AbuBasal_West_PF_EBand_TASC_O | TASC | IRB-453-R | Irbid |  | 32.5553 | 35.9942 | Irbid | Pole |  |  |  |  | ThinLayer | RO4 | 242 | Cluster-29 |  |  | SMP-WO-1737731 | [18 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
2964 | 2964-Ramtha_East_2_PF_TASC_O | TASC | IRB-469-R | Irbid |  | 32.5596 | 36.022 | Irbid | Pole |  |  |  |  | ThinLayer | RO4 | 243 | Cluster-29 |  |  | SMP-WO-1737732 | [18 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
2993 | 2993-Ramtha_East_4_O | TASC | IRB-616-R | Irbid |  | 32.5657 | 36.029 | Irbid | Tower |  |  |  |  | ThinLayer | RO4 | 244 | Cluster-29 |  |  | SMP-WO-1737733 | [18 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
2925 | 2925-Ramtha_Hay_Bashabsheh_PF_TASC | TASC | IRB-263-R | Indoor | 2153 | 32.5717 | 36.0216 | Irbid | Pole |  |  |  |  | ThinLayer | RO4 | 245 | Cluster-29 |  |  | SMP-WO-1737734 | [18 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood | [6 empty] | 0 |  |  | Site not Surveyed
463 | 463-Khayria_BeitRas_South_PF_EBand_TASC_O | TASC | IRB-554-R | Outdoor |  | 32.6095 | 35.8673 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 1 | Cluster-4 |  | W07 | SMP-WO-1521180 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-26 | Yes | [10 empty] | Downloaded
406 | 406-Khayria_BeitRas_PC_Fiber_O | TASC | IRB-6-R | Outdoor |  | 32.6067 | 35.8603 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 2 | Cluster-4 |  | W07 | SMP-WO-1521181 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | wrong data | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes | [10 empty] | Downloaded
490 | 490-Hakama_Beit_Ras_TASC_O | TASC | IRB-654-R | Outdoor |  | 35.8743 | 32.5978 | Irbid | RT |  |  |  |  | ThinLayer | RO3 | 3 | Cluster-4 |  |  |  | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  |  |  | A/C/D | 5G | 4 | [6 empty] | Obieda |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb
451 | 451-BeitRas_CTR_PD_Fiber_TASC_O | TASC | IRB-430-R | Outdoor |  | 32.598 | 35.8543 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 4 | Cluster-4 |  |  |  | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  |  |  | B/C/D | 5G | 3 | [6 empty] | Obieda |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb
428 | 428-BeitRas_2_PD_Fiber_TASC_O | TASC | IRB-273-R | Outdoor |  | 32.5954 | 35.8623 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 5 | Cluster-4 |  | W07 | SMP-WO-1521183 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | Incorrect power solution: Need photo for door of the APM cabinet./solved Incorrect antenna solution: Adding a 5G antenna directly on the mast for Sector C. Clearer photos are needed for Sector D./solved Incorrect antenna solution: Plan to install the 5G antenna under the TDD antenna for sector D—need to replace the DP with another 3m DP./solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-04 | Yes | [10 empty] | Downloaded
449 | 449-BeitRas_West_PD_Fiber_TASC_O | TASC | IRB-429-R | Outdoor |  | 32.5934 | 35.8496 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 6 | Cluster-4 |  |  |  | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  |  |  | A/C/D | 5G | 5 | [6 empty] | Obieda |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb |  |  | A
402 | 402-BSC_BeitRas_PA_Fiber | TASC | IRB-2-G | Indoor | 629 | 32.5911 | 35.8581 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 7 | Cluster-4 |  | W08 | SMP-WO-1521185 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved | More power information is needed – the plastic cover of each rectifier must be removed to inspect the copper plate connections./solved | Obieda | Approved | set all new 5G antennas at the same 4G antennas heights | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-23 | Yes |  | Need Fence key | [8 empty] | Downloaded
4483 | 4483-Dabulia_Um_Jadayel_O | TASC | IRB-608-R | Outdoor |  | 32.5857 | 35.8416 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 8 | Cluster-44 |  | W08 | SMP-WO-1521187 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  | Rejected, Update Coordinate (32.585092 35.841635), Azimuth SEC-B(160) | Approved |  | Obieda | Approved |  | Omar Sami | Approved | 1. Sec.A compass is incorrect Sec.B angle view isn't clear and compass showing different angle Sec.C compass and angle view aren't 260 Sec.D compass isn't correct Sec.A & B M.tilt values don't match snapshots, | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-03 | Yes | [10 empty] | Downloaded
448 | 448-BeitRas_Tatweer_PD_Fiber_TASC_O | TASC | IRB-428-R | Outdoor |  | 32.5884 | 35.8534 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 9 | Cluster-4 |  | W08 | SMP-WO-1521188 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  | ABC |  |  | Approved | Incorrect ACOC Location/solved Need New Mast! /solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in the civil sheet and pictures are not cleared | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-05 | Yes | [10 empty] | Downloaded
446 | 446-BeitRas_Str_CTR_PF_EBand_TASC_O | TASC | IRB-545-R | Outdoor |  | 32.5882 | 35.8647 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 10 | Cluster-4 |  | W08 | SMP-WO-1521189 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-24 | Yes | [10 empty] | Downloaded
443 | 443-BeitRas_South_PE_Fiber_Manage_O | ZAIN/M | IRB-411-R | Outdoor |  | 32.5835 | 35.862 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 11 | Cluster-4 |  | W08 | SMP-WO-1521190 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-26 | Yes | [10 empty] | Downloaded
4782 | 4782-Mafraq_Market_CTR_PE_Fiber_TASC_O | TASC | MFQ-225-R | Outdoor |  | 32.3434 | 36.2101 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 12 | Cluster-47 |  | W08 | SMP-WO-1521191 | SMART | SMART |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-05 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4791 | 4791-Mafraq_Jerash_St_PD_Fiber_O | TASC | MFQ-108-R | Outdoor |  | 32.3417 | 36.2039 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 13 | Cluster-47 |  | W08 | SMP-WO-1521192 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  | AC |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved | Existing TDD Antenna Azimuth for sector "A" not "B" 4G Sec A mechanical should be Down 3 not 0 Be careful of 5G Antenna location, why its not aligned with 4G height ? | Karam Jaber & Akram Abdelrahim | Approved | Wrong data and civil requirmnet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
4729 | 4729-Mafraq_CTR_PC_Fiber_TASC | TASC | MFQ-72-R | Indoor | 783 | 32.3414 | 36.208 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 14 | Cluster-47 |  | W08 | SMP-WO-1521193 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  | A |  |  | Approved | Incorrect ACOC Location/solved incorrect antenna solution (RF sheet)/solved Not enough information for power CBs and rectifier photo/solved | Obieda | Approved |  | Omar Sami | Approved | 2G3G4G Mechanical tilting Photo naming mismatch ( Photos for sec-D it should be for sec-C) and sec-D is empty Proposed solution for 4G & 5G heights are not accepted, it should remain as existing height (A:9m, B:6m, C:6m, D:9m) | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-03 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4799 | 4799-Mafraq_Market_TL_PE_TASC_O | TASC | MFQ-185-R | Outdoor |  | 32.3395 | 36.2101 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 15 | Cluster-47 |  | W08 | SMP-WO-1521194 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4798 | 4798-Mafraq_CTR_2_PE_Fiber_TASC_O | TASC | MFQ-162-R | Outdoor |  | 32.3378 | 36.206 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 16 | Cluster-47 |  | W09 | SMP-WO-1521195 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved | Note: [3G4G Sec A] in RF table (Azimuth should be 90 not 0) | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4795 | 4795-Mafraq_2_PB_Fiber_TASC | TASC | MFQ-22-R | Indoor | 703 | 32.3367 | 36.2028 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 17 | Cluster-47 |  | W09 | SMP-WO-1521196 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  | AC |  |  | Approved | Incorrect ACOC Location/solved incorrect power solution: Need more details about 2G DCDU/solved | Obieda | Approved |  | Omar Sami | Approved | Why the height of new sec-A is 11.4 instead of 12.5 ? , is it a typo ? or what Modify Mechanical 2G sec-B (Down instead of up) Modify mechanical 3G sec-B (Down instead of up) | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-03 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4785 | 4785-Mafraq_South_Ent_PD_Fiber_TASC_O | TASC | MFQ-126-R | Outdoor |  | 32.3348 | 36.2081 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 18 | Cluster-47 |  | W09 | SMP-WO-1521198 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4307 | 4307-Zarqa_Awajan_South_PF_TASC_O | TASC | ZRQ-324-R | Outdoor |  | 32.0242 | 36.0646 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 19 | Cluster-43 |  | W09 | SMP-WO-1521199 | SMART | SMART |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | The antenna height not matched with pictures | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2954 | 2954-Naaimeh_North_PE_TASC_O | TASC | IRB-421-R | Outdoor |  | 32.4238 | 35.9175 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 20 | Cluster-29 |  | W09 | SMP-WO-1521200 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-24 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2901 | 2901-Naaimeh_Bridge_MGS_PF_TASC_O | TASC | IRB-280-R | Outdoor |  | 32.4234 | 35.9501 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 21 | Cluster-29 |  | W09 | SMP-WO-1521201 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-24 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2984 | 2984-Naaimeh_Ent_PF_TASC_O | TASC | IRB-541-R | Outdoor |  | 32.4177 | 35.9266 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 22 | Cluster-29 |  | W09 | SMP-WO-1521202 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | We have 3*CB's : 63A, 63A, and 16A. Please ensure that during the outage, the 16A CB replaced with 63A CB. | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-26 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2955 | 2955-Naaimeh_CTR_PE_TASC_O | TASC | IRB-313-R | Outdoor |  | 32.4168 | 35.913 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 23 | Cluster-29 |  | W09 | SMP-WO-1521203 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-26 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2991 | 2991-Naimeh_West_Avenue_O | TASC | IRB-588-R | Outdoor |  | 32.4159 | 35.9069 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 24 | Cluster-29 |  | W09 | SMP-WO-1521204 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-26 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2919 | 2919-Naaimeh_PC_TASC | TASC | IRB-107-G | Indoor | 705 | 32.4118 | 35.9034 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 25 | Cluster-29 |  | W09 | SMP-WO-1521205 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6548 | 6548-Naaimeh_South_End_Tasc_O | TASC | IRB-593-R | Outdoor | 0 | 35.9221 | 32.4114 | Irbid | RT |  |  |  |  | ThinLayer | RO3 | 26 | Cluster-29 |  | W09 | SMP-WO-1527890 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved | Accepted, however for Sec.A & B modify the values and make them match the compass. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-05 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2976 | 2976-Naaimeh_South_PF_TASC_O | TASC | IRB-519-R | Outdoor |  | 32.4041 | 35.8945 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 27 | Cluster-29 |  | W09 | SMP-WO-1521206 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | power sheet: all information in the sub sheet not correct/sector c will be swap not reuse | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Missing data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-05 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4752 | 4752-Hay_Hussein_End_Mafraq_PD_Fiber_TASC_O | TASC | MFQ-119-R | Outdoor |  | 32.3521 | 36.2028 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 28 | Cluster-47 |  | W09 | SMP-WO-1521208 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | FPFH2: Reuse Existing fuse 2*30A for FPFH2 (LLVD). /ACOC:We have space behind the power cabinet . | Waed | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-27 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4747 | 4747-Hay_Hussein_2_Mafraq_PE_Fiber_TASC_O | TASC | MFQ-118-R | Outdoor |  | 32.3495 | 36.2056 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 29 | Cluster-47 |  | W09 | SMP-WO-1521209 | SMART | SMART |  | Done |  |  | B/C | 5G | 3 |  |  |  |  | Approved | power sheet: modify power sheet ,The information is incomplete. | Waed | Approved |  | Omar Sami | Approved | There's no 4G service over Sec-A !! (Rearrange the table in RF tab) | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-27 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6035 | 6035-Hay_Hussein_Mafraq_CTR_O | TASC | MFQ-273-R | Outdoor |  | 32.3479 | 36.2084 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 30 | Cluster-47 |  | W09 | SMP-WO-1521210 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved | Solution Sec (A,B,C) -new Antenna location is proposed at 10m height while it should be at 12m Modify Sector (A,B,C) -new 5G Antenna location to be aligned with 4G (10 Port Antenna) at 12m height | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-05 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4485 | 4485-Boshra_Circle_Mid_TASC_O | TASC | IRB-605-R | Outdoor |  | 32.5465 | 35.884 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 31 | Cluster-44 |  | W10 | SMP-WO-1521211 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved | correct the data in the RF table for 4g azimuth, make sure it follows 3g data. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-24 | Yes | [10 empty] | Downloaded
4474 | 4474-Bushra_Busia_PF_TASC_O | TASC | IRB-441-R | Outdoor |  | 32.5677 | 35.9031 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 32 | Cluster-44 |  | W10 | SMP-WO-1521212 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-24 | Yes | [10 empty] | Downloaded
4463 | 4463-Bushra_North_PF_TASC_O | TASC | IRB-440-R | Outdoor |  | 32.5635 | 35.8954 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 33 | Cluster-44 |  | W10 | SMP-WO-1521214 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | Please specify the exact NUM OF empty CB s for LLVD &BLVD . | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong and missed data in the provided civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes | [10 empty] | Downloaded
4410 | 4410-Bushra_PC_EBand_TASC | TASC | IRB-9-R | Indoor | 625 | 32.5596 | 35.8921 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 34 | Cluster-44 |  | W10 | SMP-WO-1521215 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-24 | Yes
4471 | 4471-Bushra_Old_Cemetary_PE_EBand_TASC_O | TASC | IRB-476-R | Outdoor |  | 32.5566 | 35.8966 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 35 | Cluster-44 |  | W10 | SMP-WO-1521216 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved | Kindly follow the TSSR that has been sent previously, as the current all azimuth values are different | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-03 | Yes | [10 empty] | Downloaded
4460 | 4460-Bushra_South_Ave_PF_TASC_O | TASC | IRB-527-R | Outdoor |  | 32.5506 | 35.8879 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 36 | Cluster-44 |  | W10 | SMP-WO-1521217 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes | [10 empty] | Downloaded
2923 | 2923-Howara_Irbid_PC_EBand_TASC | TASC | IRB-119-G | Indoor | 646 | 32.5423 | 35.8881 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 37 | Cluster-29 |  | W10 | SMP-WO-1521218 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | Please to mention that we need to upgrade the C.B to 100A Update: approved. | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-19 | Yes |  | Need Fence key |  | RFI | [6 empty] | Downloaded
1228 | 1228-Khazan-Aqaba-West-PF-TASC-O | TASC | AQB-274-R | Outdoor |  | 29.5247 | 35.0132 | Aqaba | Pole |  |  |  |  | ThinLayer | RO3 | 38 | Cluster-12 |  | W10 | SMP-WO-1521219 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved | No Need for AMIA in Power Design Adding extra AHEB should be revised. Update:approved. | Zaid | Approved |  | Laith | Approved | we need explain why it will be replaced 8-port Antenna with 12-port Antenna. | Hosni Olayan & Mohammad Abujrai | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4602 | 4602-Kufer_Youba_2_PE_TASC_O | TASC | IRB-372-R | Outdoor |  | 32.5518 | 35.8028 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 39 | Cluster-46 |  | W10 | SMP-WO-1521220 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved | accepted after resubmission Sector B view and data are correct, however kindly correct sector B compass as it's showing 60 instead of 120 | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-27 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4694 | 4694-Kufer_Youba_East_PF_EBand_BTS_O | TASC | IRB-559-R | Outdoor |  | 32.5485 | 35.8091 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 40 | Cluster-46 |  | W10 | SMP-WO-1521221 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | L1800+ case Update: approved. | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-03 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | RFI | [6 empty] | Downloaded
6095 | 6095-Kufer_Youba_Girls_Sec_Sch | TASC | IRB-611-R | Outdoor |  | 32.5413 | 35.8091 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 41 | Cluster-46 |  | W10 | SMP-WO-1521222 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-27 | Yes |  |  |  | RFI
4643 | 4643-Kufer_Youba_PC_Fiber_TASC | TASC | IRB-44-G | Indoor | 707 | 32.5367 | 35.807 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 42 | Cluster-46 |  | W10 | SMP-WO-1521223 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | Please to take a pic for the right cabinet when its door opened, if its empty from radios please to propose dismantle it and relocate the DCDU to beside cabinet. We should mention on the BTS sheet that the 2G antenna will be dismantled Power Solution should be: Upgrade the 1st DCDU C.B to 100A, relocate all RRUs in DCDU 3 to be connected on the 1st one, Upgrade the 2nd DCDU to 100A and connect AMIA on it. FPFH1:63A,FPFH2:63A Update:approved. | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-03 | Yes |  | Need Mag Key |  | RFI | [6 empty] | Downloaded
4655 | 4655-Kufer_Youba_Top_PF_TASC_O | TASC | IRB-528-R | Outdoor |  | 32.5429 | 35.8016 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 43 | Cluster-46 |  | W10 | SMP-WO-1521224 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-02 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2828 | 2828-Samra_Power_Station_PF_Manage_O | ZAIN/M | ZRQ-413-R | Outdoor |  | 32.1436 | 36.1439 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 44 | Cluster-28 |  | W10 | SMP-WO-1521225 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved | 60/240/340 | Baher Obaidat | Approved | Modify note in Remark --> "INSTALL NEW AVQC AT H=7m AZ=230" , should be AZ= 340 | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-16 | Yes |  | Need Access |  | P1 | [6 empty] | Downloaded
2860 | 2860-Eskan_Hashmia_PD_Fiber | TASC | ZRQ-224-R | Indoor | 1822 | 32.1408 | 36.1365 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 45 | Cluster-28 |  | W10 | SMP-WO-1521226 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved | the used antenna is aqqy instead of avqc no TSSR attached | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | No excel sheet attached | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-25 | Yes |  | Need Access |  | RFI | [6 empty] | Downloaded
2859 | 2859-Hashmia_Ave_CTR_PD_Fiber_TASC_O | TASC | ZRQ-351-R | Outdoor |  | 32.1358 | 36.1237 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 46 | Cluster-28 |  | W10 | SMP-WO-1521227 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | Cabinet location should be cleared with another Pic. Clarifying LLVD and BLVD Plugs is needed. Update:approved. | Zaid | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-08 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2831 | 2831-Hashmieh_East_Av_O | TASC | ZRQ-453-R | Outdoor |  | 32.1336 | 36.1303 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 47 | Cluster-28 |  | W10 | SMP-WO-1521228 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | No need for DPs, only rotate the existed DPs Wrong Power solution. Adopt this solution: Connect BBU on BLVD, 63A C.B:FPFH1, 63A C.B:FPFH2, 63A C.B: AMIA Recheck the ACOC space. Update:approved. | Zaid | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2822 | 2822-Zarqa_Hashmia_Municipality_PF_EBand_TASC_O | TASC | ZRQ-439-R | Outdoor |  | 32.1331 | 36.1119 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 48 | Cluster-28 |  | W10 | SMP-WO-1521229 | SMART | SMART |  | Done |  |  | A/B/D | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | Existing 2G3G4G Antenna Azimuth for sectorA (4th tab) should be (sec-D) not (sec-A) There's no 2G technology over 2822 !!! Proposed height for 4G & 5G Antennas are not aligned with existing height (9m), and 5G should follow 4G height | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-02-26 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2844 | 2844-Hashmieh_Omar_Bin_Khattab_Msq_Tasc_O | TASC | ZRQ-501-R | Outdoor | 0 | 36.1156 | 32.1315 | Zarqa | RT |  |  |  |  | ThinLayer | RO3 | 49 | Cluster-28 |  | W10 | SMP-WO-1527891 | SMART | SMART | 37594 | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Zaid | Approved |  | Baher Obaidat | Rejected | Rejected , wrong Azimuth , (A: 65, B:130 ,C: 280 , D: 360 ) | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 4 | A | Approved | Approved | 2025-04-08 | Yes |  | indoor |  | RFI | [6 empty] | Downloaded
2868 | 2868-Petrol_Refinary_North_PE_Fiber_UMN_Manage_O | ZAIN/M | ZRQ-358-R | Outdoor |  | 32.1284 | 36.1184 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 50 | Cluster-28 |  | W10 | SMP-WO-1521230 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | Please provide more clear photos for installation solution of 5G antennas. | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-23 | Yes |  | Need Key From Zain (GF) |  | RFI | [6 empty] | Downloaded
2846 | 2846-Hashmieh_Anbari_School_Tasc_O | TASC | ZRQ-502-R | Outdoor | 0 | 36.1259 | 32.1255 | Zarqa | RT |  |  |  |  | ThinLayer | RO3 | 51 | Cluster-28 |  | W10 | SMP-WO-1527892 | SMART | SMART |  | Done |  |  | A/B/D | 5G | [5 empty] | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | In RF sheet, modify tab name (Existing 2G3G4G Antenna Azimuth for sectorA) to be (Existing 2G3G4G Antenna Azimuth for sectorD) | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-10 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2835 | 2835-Petrol_Refinary_HQ_PF_Manage_O | ZAIN/M | ZRQ-428-R | Outdoor |  | 32.1191 | 36.1125 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 52 | Cluster-28 |  | W10 | SMP-WO-1521231 | SMART | SMART |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Rejected | Modify Azimuth of all sectors ( A: 0 ,B: 90, C: 160. D: 270) --> Done Please correct the "remark" notes for 5G to match our recommendations (Correct Azimuth) --> Done Except for sector "B", should be 90 instead of 120 | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 4 | A | Approved | Approved | 2025-04-08 | Yes |  | Need Access Letter |  | RFI | [6 empty] | Downloaded
2808 | 2808-Hashmia_PC_Fiber_TASC | TASC | ZRQ-75-G | Indoor | 551 | 32.1379 | 36.1139 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 53 | Cluster-28 |  | W10 | SMP-WO-1521232 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-25 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2809 | 2809-Hararieh_PC_Fiber_TASC_O | TASC | ZRQ-187-R | Outdoor |  | 32.1297 | 36.1275 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 54 | Cluster-28 |  | W10 | SMP-WO-1521233 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | need Sectors Re-Disgen | Moath | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-07 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3446 | 3446-Kreymeh_PE_EBand_TASC | TASC | BLQ-43-G | Indoor | 355 | 32.2993 | 35.5872 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 55 | Cluster-34 |  | W10 | SMP-WO-1521234 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | wrong power solution | Moath | Approved |  | Baher Obaidat | Approved | No 4G + in the site 4G Sector A should be AAU | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6113 | 6113-Kreymeh_East_TASC_O | TASC | BLQ-287-R | Outdoor |  | 32.2839 | 35.5999 | Balqa | Tower |  |  |  |  | ThinLayer | RO3 | 56 | Cluster-34 |  | W11 | SMP-WO-1521235 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-16 | Yes |  |  |  | RFI
6119 | 6119-Kreymeh_North_TASC_O | TASC | BLQ-292-R | Outdoor |  | 32.2808 | 35.5976 | Balqa | Tower |  |  |  |  | ThinLayer | RO3 | 57 | Cluster-34 |  | W11 | SMP-WO-1521236 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-27 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3465 | 3465-Kreymeh_CTR_PF_TASC_O | TASC | BLQ-257-R | Outdoor |  | 32.2959 | 35.5972 | Balqa | Tower |  |  |  |  | ThinLayer | RO3 | 58 | Cluster-34 |  | W11 | SMP-WO-1527953 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-16 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3492 | 3492-AbuSeedo_Aghwar_PE_Fiber_Org_Manage_O | ZAIN/M | BLQ-189-G | Outdoor |  | 32.2868 | 35.5949 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 59 | Cluster-34 |  | W11 | SMP-WO-1521238 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved | needs a clear pic for M tilt | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-06 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3469 | 3469-Taqwa_Msq_PC_Fiber_TASC | TASC | BLQ-59-G | Indoor | 343 | 32.2695 | 35.5994 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 60 | Cluster-34 |  | W11 | SMP-WO-1521239 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-12 | Yes |  |  |  | RFI
4644 | 4644-Mazar_Shamali_Ent_PE_O | TASC | IRB-339-R | Outdoor |  | 32.48 | 35.8034 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 61 | Cluster-46 |  | W11 | SMP-WO-1521240 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-06 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6097 | 6097-North_Mazar_Girls_Sch | TASC | IRB-599-R | Outdoor |  | 32.4666 | 35.8013 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 62 | Cluster-46 |  | W11 | SMP-WO-1521241 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-08 | Yes |  |  |  | RFI
4625 | 4625-Northren_Mazar_PD_EBand_TASC | TASC | IRB-39-G | Indoor | 765 | 32.4737 | 35.7994 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 63 | Cluster-46 |  | W11 | SMP-WO-1521242 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-06 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4636 | 4636-Mazar_Shamali_Top_PE_O | TASC | IRB-334-R | Outdoor |  | 32.4682 | 35.7907 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 64 | Cluster-46 |  | W11 | SMP-WO-1521243 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved | I need BLVD Loads , not clear | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-09 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1157 | 1157-Zaatari_Camp_UNICEF_LOC4_PE_Manage_O | ZAIN/M | MFQ-255-R | Outdoor |  | 32.2954 | 36.3265 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 65 | Cluster-11 |  | W11 | SMP-WO-1521244 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | TDD is for SA SC SD | Moath | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in the civil sheet and need clear pictures Need new pole 9m Wrong data in civil sheet approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-22 | Yes | Dismantle 2nd L1800 RRU | Need Access Letter // L1800+ RRU / Approved By E-mail |  | RFI | [6 empty] | Downloaded
1130 | 1130-Zaatari_Camp_PF_Manage_O | ZAIN/M | MFQ-102-G | Outdoor |  | 32.3021 | 36.3277 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 66 | Cluster-11 |  | W11 | SMP-WO-1521245 | SMART | SMART |  | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved |  | Moath | Approved | 5G azimuth should align with 3G/4G | Omar Sami | Approved | ADD NEW DP AND INSTALL NEW AVQC AT H=9m AZ=275, instead of 250 on the photo | Karam Jaber & Akram Abdelrahim | Approved | Wrong requirement in civil requirement sheet and wrong data in civil1 and BTS sheet due to the asking to add two new DPs but the right action is to relocate it and there are no clear pictures | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-26 | Yes |  | Need Access Letter |  | RFI | [6 empty] | Downloaded
4640 | 4640-Enbeh_PD_TASC | TASC | IRB-43-G | Indoor | 721 | 32.4793 | 35.7499 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 67 | Cluster-46 |  | W11 | SMP-WO-1521246 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-18 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | RFI | [6 empty] | Downloaded
4651 | 4651-Enbeh_CTR_PE_TASC_O | TASC | IRB-401-R | Outdoor |  | 32.4792 | 35.7562 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 68 | Cluster-46 |  | W11 | SMP-WO-1521247 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved | Change the azimuth of sector B to 100 rather than 90 for 3G, 4G, and 5G. | Omar Sami | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4622 | 4622-Enbeh_2_PE_EBand_TASC | TASC | IRB-244-R | Indoor | 2132 | 32.4723 | 35.7678 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 69 | Cluster-46 |  | W11 | SMP-WO-1521248 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved | BTS Cabinet Location , Mirage Huw Cabinets to be one only & use other Location | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-10 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6120 | 6120-Masharee_Hay_Saqer | TASC | IRB-601-R | Outdoor |  | 32.4652 | 35.5955 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 70 | Cluster-34 |  | W11 | SMP-WO-1521249 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-10 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6518 | 6518-Masharee_Othman_Msq_O | TASC | IRB-617-R | Outdoor | 0 | 35.5958 | 32.4403 | Irbid | RT |  |  |  |  | ThinLayer | RO3 | 71 | Cluster-34 |  | W11 | SMP-WO-1527893 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-10 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6112 | 6112-Masharee_Health_Center | TASC | IRB-614-R | Outdoor |  | 32.4378 | 35.5995 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 72 | Cluster-34 |  | W11 | SMP-WO-1521250 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved | set az to 15/215/300 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3494 | 3494-Masharee_South_Ent_PD_Fiber_TASC_O | TASC | IRB-390-R | Outdoor |  | 32.4331 | 35.5942 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 73 | Cluster-34 |  | W11 | SMP-WO-1521251 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  | ABC |  |  | Approved |  | Obieda | Approved | set sector C az to 355 , shift it to D | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-05 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3404 | 3404-Ghazawi_PF_TASC | TASC | BLQ-20-G | Indoor | 199 | 32.4607 | 35.5866 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 74 | Cluster-34 |  | W11 | SMP-WO-1521252 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT | Done | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved | The photos of the BTS cabinet and the cable route inside the shelter are not clear!!/solved The photos of all antennas on all sectors are not clear!!/solved There are two power solutions!!!/solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-05-06 | Yes |  | Need Contact with Farm Key access 17-Feb |  | RFI | [6 empty] | Downloaded
3497 | 3497-Masharee_North_Ent_PE_Fiber_TASC_O | TASC | IRB-386-R | Outdoor |  | 32.4518 | 35.5949 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 75 | Cluster-34 |  | W11 | SMP-WO-1521253 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | Accepted, however fix sec.A 5G azimuth in BTS remarks. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-23 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3406 | 3406-Masharee_PC_Fiber_TASC | TASC | BLQ-41-G | Indoor | 498 | 32.4291 | 35.5857 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 76 | Cluster-34 |  | W11 | SMP-WO-1521254 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-08 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3457 | 3457-Deir_Abu_Saeed_CRL_PE_Fiber_TASC_O | TASC | IRB-353-R | Outdoor |  | 32.5059 | 35.6841 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 77 | Cluster-34 |  | W11 | SMP-WO-1521255 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | Where are the photos!/solved | Obieda | Approved | please provide pictures, area is not military | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-18 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6109 | 6109-Deir_Abu_Saeid_East_O | TASC | IRB-609-R | Outdoor |  | 32.5031 | 35.689 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 78 | Cluster-34 |  | W11 | SMP-WO-1521256 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved | set sector B az to 210 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6107 | 6107-Deir_Abu_Saeid_West_O | TASC | IRB-600-R | Outdoor |  | 32.4969 | 35.6782 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 79 | Cluster-34 |  | W11 | SMP-WO-1521257 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved | set sec C az to 340 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6108 | 6108-Deir_Abu_Saeid_South_O | TASC | IRB-607-R | Outdoor |  | 32.4975 | 35.6872 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 80 | Cluster-34 |  | W11 | SMP-WO-1521258 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-10 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3491 | 3491-Deir_Abu_Saeed_PD_UMN_Manage_O | ZAIN/M | IRB-395-R | Outdoor |  | 32.4972 | 35.6835 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 81 | Cluster-34 |  | W12 | SMP-WO-1521259 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3401 | 3401-Princess_Raya_Hospital_PB_Fiber_TASC | TASC | IRB-54-G | Indoor | 650 | 32.4999 | 35.6923 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 82 | Cluster-34 |  | W12 | SMP-WO-1521260 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | need clear photos for all sectors/solved Change the power solution to require a rectifier upgrade./solved | Obieda | Approved | set az to 160/250/330 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-16 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1905 | 1905-Zarqa_New_Hospital_PF_DIBS_Manage_O | ZAIN/M | ZRQ-276-R | Outdoor |  | 32.0752 | 36.1304 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 83 | Cluster-19 |  | W12 | SMP-WO-1521261 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 | D |  |  |  | Approved | Need more clear photos for Rectifier. | Obieda | Approved |  | Baher Obaidat | Approved | Add "4G sec E" tab in RF table, either it's not active yet, but it's important to mention that sec-E is 3G & L2100 | Karam Jaber & Akram Abdelrahim | Approved | Decrease sector B to be at 6m wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  | Need Access Letter/ Approved By E-mail |  | P1 | [6 empty] | Downloaded
4208 | 4208-Sharq_City_CTR_PE_EBand_Zain_TASC_O | TASC | ZRQ-318-G | Outdoor |  | 32.0675 | 36.1087 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 84 | Cluster-42 |  | W12 | SMP-WO-1521262 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4204 | 4204-Old_CPLX_Zarqa_PF_TASC_O | TASC | ZRQ-286-R | Outdoor |  | 32.0621 | 36.0949 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 85 | Cluster-42 |  | W12 | SMP-WO-1521263 | SMART | SMART |  | Done |  |  | A/D | 5G | 2 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved | Make sure If sec-D is truly 3 mechanical degrees up? or it's caused from civil? | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI
4220 | 4220-Sharq_City_Sakan_Karem_PE_UMN_O | ZAIN | ZRQ-313-G | Outdoor |  | 32.0612 | 36.1233 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 86 | Cluster-42 |  | W12 | SMP-WO-1521264 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-18 | Yes |  |  |  | P1 | [6 empty] | Downloaded
2837 | 2837-Zarqa_Uni_PC_Fiber_TASC | TASC | ZRQ-89-G | Indoor | 505 | 32.0607 | 36.1528 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 87 | Cluster-28 |  | W12 | SMP-WO-1521265 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | BTS cabinets should be merged. Missing some RRUs connection in Power sheet. 5G Antenna location on sector A should be revised Second time: Missing some RRUs connection in Power sheet (Another DCDU is missing). update:approved | Zaid | Approved | set az to 80/150/230 | Baher Obaidat | Approved | Sec-A compass degree and view is not mapped with RF table for sec-A (Compass degree is 50 but on the table is 80)!! Please modify it to stay mapped. | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | B | Approved | Approved | 2025-05-07 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4221 | 4221-Sharq_City_Uni_Sch_PE_UMN_O | ZAIN | ZRQ-315-G | Outdoor |  | 32.0604 | 36.1147 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 88 | Cluster-42 |  | W12 | SMP-WO-1521266 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  | increase 5G Height 1.5m |  | P1 | [6 empty] | Downloaded
4210 | 4210-Sharq_City_South_PE_Zain_TASC_O | TASC | ZRQ-319-G | Outdoor |  | 32.0544 | 36.1201 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 89 | Cluster-42 |  | W12 | SMP-WO-1521267 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | Please to clarify the LLVD and BLVD with pics replace all Dps with Std to avoid blockage Update:approved. | Zaid | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1297 | 1297-Aqaba-Alamieh-Market-PF-Fiber-TASC-O | TASC | AQB-236-R | Outdoor |  | 29.5428 | 35.0096 | Aqaba | Pole |  |  |  |  | ThinLayer | RO3 | 90 | Cluster-12 |  | W12 | SMP-WO-1521268 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | please to propose a 14-port solution Update: approved. | Zaid | Approved |  | Laith | Approved | Approved with note: Azi sector C in sheet (BTS) is wrong, please change it from 215 to 235 | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1255 | 1255-Aqaba-Alamieh-PE-Fiber-TASC-O | TASC | AQB-218-R | Outdoor |  | 29.5408 | 35.0106 | Aqaba | Pole |  |  |  |  | ThinLayer | RO3 | 91 | Cluster-12 |  | W12 | SMP-WO-1521269 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/C/D | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6049 | 6049-Zaatari_Camp_Hussein_Mosque_TASC_O | TASC | MFQ-270-G | Outdoor | 0 | 36.3372 | 32.2874 | Mafraq | GF |  |  |  |  | ThinLayer | RO3 | 92 | Cluster-11 |  | W12 | SMP-WO-1527894 | SMART | SMART |  | Done |  |  | B/C/D | 5G | [5 empty] | Approved |  | Zaid | Approved |  | Omar Sami | Approved | Please re-chcek azimuth of sector-D ,, based on the provided view it should be on 325-330 max (not 355 !) | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  | Need Access Letter |  | RFI | [6 empty] | Downloaded
4519 | 4519-Jordan_St_6_PE_TASC | TASC | AMW-503-G | Indoor | 23 | 32.1101 | 35.8798 | Balqa | Tower |  |  |  |  | ThinLayer | RO3 | 93 | Cluster-45 |  | W12 | SMP-WO-1679947 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Rejected | mismatch between Sec.D azimuth in BTS sheet (solution and remarks) Pleases revise all BTS sheet and solution azimuth for sector A & B This is the same rejected excel sheet, no changes were conducted please check and advise. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 4 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4571 | 4571-Moobes_Ain_AlBasha_PE_TASC_O | TASC | AMW-993-R | Outdoor |  | 32.0967 | 35.8857 | Balqa | Pole |  |  |  |  | ThinLayer | RO3 | 94 | Cluster-45 |  | W12 | SMP-WO-1679948 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved | please to propose reducing 12-port height on sector C & D with 70 cm to install AVQC on the top of the same DP LLVD empty plugs should be clarified with pics. 2nd time: How much empty plugs we have? we need two empty plugs.. Update: approved. | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4546 | 4546-Salhoub_Bridge_PE_TASC_O | TASC | AMW-809-R | Outdoor |  | 32.0947 | 35.8456 | Balqa | Tower |  |  |  |  | ThinLayer | RO3 | 95 | Cluster-45 |  | W12 | SMP-WO-1521272 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-18 | Yes | Dismantle 2nd L1800 RRU | Dismantle 2nd L1800 RRU |  | RFI | [6 empty] | Downloaded
6149 | 6149-Moobis_Center_Tasc_O | TASC | BLQ-316-R | Outdoor | 0 | 35.8819 | 32.0939 | Balqa | RT |  |  |  |  | ThinLayer | RO3 | 96 | Cluster-45 |  | W12 | SMP-WO-1527895 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/E | 5G | [5 empty] | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-03 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4527 | 4527-Moobes_PC_EBand_TASC | TASC | AMW-263-G | Indoor | 353 | 32.0851 | 35.8642 | Balqa | Tower |  |  |  |  | ThinLayer | RO3 | 97 | Cluster-45 |  | W12 | SMP-WO-1521273 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved | set sector C to 350 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
450 | 450-Hakama_North_PD_Fiber_TASC_O | TASC | IRB-350-R | Outdoor |  | 32.5969 | 35.8816 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 98 | Cluster-4 |  |  |  | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  |  |  | A/B/D | 5G | 4 | [6 empty] | Zaid |  |  | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Yousef Al-Natour |  | Akram Elturk / Ahmad Al-khateeb
424 | 424-Hakama_2_PC_Fiber_TASC | TASC | IRB-225-R | Indoor | 2128 | 32.5912 | 35.8906 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 99 | Cluster-4 |  | W12 | SMP-WO-1521275 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-25 | Yes | [10 empty] | Downloaded
421 | 421-Hakama_1_PD_Fiber_TASC | TASC | IRB-226-R | Indoor | 2101 | 32.5893 | 35.8805 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 100 | Cluster-4 |  | 421 | SMP-WO-1521276 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C | 5G | 2 |  |  |  |  | Approved | Non-Priority Update: approved. | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | No excel sheet attached | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-18 | Yes
851 | 851-Karak_Qaser_End_O | TASC | KRK-295-R | Outdoor |  | 31.322 | 35.7431 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 101 | Cluster-8 |  | W12 | SMP-WO-1521277 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/D | 5G | 3 |  |  |  |  | Approved | please to mention the detailed connection of BLVD, we can't connect RTN on DCDU Update: approved. | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-17 | Yes |  |  |  | RFI | [6 empty] | Downloaded
838 | 838-Qaser_Karak_North_PE_Fiber_TASC_O | TASC | KRK-244-R | Outdoor |  | 31.3171 | 35.7434 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 102 | Cluster-8 |  | W12 | SMP-WO-1521278 | Al-Tawseaa | TWASEAA |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved | Missing data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
818 | 818-Qaser_East_PD_Fiber_Org_Manage_O | ZAIN/M | KRK-219-G | Outdoor |  | 31.312 | 35.744 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 103 | Cluster-8 |  | W12 | SMP-WO-1521279 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/D | 5G | 4 |  | ABC |  |  | Approved | please don't mention that we need to upgrade the rectifier. Update: approved. | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved | Wrong and missed data in the provided civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
821 | 821-Qaser_West_PB_Fiber_TASC | TASC | KRK-151-G | Indoor | 996 | 31.3102 | 35.7426 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 104 | Cluster-8 |  | W12 | SMP-WO-1679949 | Al-Tawseaa | TWASEAA |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved | power sheet:Please specify each of the (LLVD&BLVD) /BTS Sheet:Duplicate image for the same sector B&C the rectifier will be change &add MTS power solution | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | B | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI | [6 empty] | Downloaded
826 | 826-Karak_Qaser_Hay_Mashhour_Sch_Back_PF_EBand_TASC_O | TASC | KRK-283-R | Outdoor |  | 31.3069 | 35.7394 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 105 | Cluster-8 |  | W12 | SMP-WO-1521281 | Al-Tawseaa | TWASEAA |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-10 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1025 | 1025-Jabal_Tareq_East_PE_EBand_TASC_O | TASC | ZRQ-393-R | Outdoor |  | 32.0421 | 36.1033 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 106 | Cluster-10 |  | W13 | SMP-WO-1521282 | SMART | SMART |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved | The location you chose for the cabinet is not suitable, and we need more pictures. will be change rectifier &add mts power solution /Please change the new location on all sub sheets . | Waed | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | B | Approved | Approved | 2025-04-23 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1003 | 1003-Jabal_Tareq_Police_Station_PB_Fiber_TASC | TASC | ZRQ-199-R | Indoor | 506 | 32.0457 | 36.0972 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 107 | Cluster-10 |  | W13 | SMP-WO-1521283 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data and the poles height not matched with the pictures and determine the poles name A,B,C on each picture, in addition the total EPA wrong Why you need 6 DPs?? | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-28 | Yes | NS |  |  | RFI
2853 | 2853-Zarqa_Hashmia_HSG_PD_Fiber_TASC_O | TASC | ZRQ-349-R | Outdoor |  | 32.1407 | 36.1288 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 108 | Cluster-28 |  | W13 | SMP-WO-1521284 | SMART | SMART |  | Done |  |  | A/B/D | 5G | 4 |  | ABC |  |  | Approved | the rectifier will be change it & add MTS outdoor 4 sectors site solution / | Waed | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Not mentioning which pole is A and B, and wrong data regarding the number of bracing for each pole | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | B | Approved | Approved | 2025-04-22 | Yes | NS |  |  | RFI | [6 empty] | Downloaded
5837 | 5837-Ghor_Mazraah_Haditheh_PC_EBand_Zain_TASC | TASC | KRK-142-G | Indoor | 981 | 31.2799 | 35.5308 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 109 | Cluster-58 |  | W13 | SMP-WO-1521285 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | power sheet: we will change the rectifier &please add MTS power solution/we need to more pic's for all sectors, Are the antennas in the sectorA on the same DP? | Waed | Approved |  | Laith | Approved | Approved with note: we will change the naming for this sectors (A , B and C) as follows: A instead of B & B instead of C & C instead of A, so please reflect it over the site from your side Based on the above note, sector A will become after change the naming instead of sec B then, we need to change Azi A from old value 90 to new value 70. | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-17 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
1175 | 1175-Zaatari_Mafraq_PD_Fiber_TASC_O | TASC | MFQ-163-R | Outdoor |  | 32.309 | 36.3002 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 110 | Cluster-11 |  | W13 | SMP-WO-1521286 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  | ABC |  |  | Approved | we need to add power solution senario :MTS outdoor 4 sectors site | Waed | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-03-27 | Yes |  |  |  | RFI
1134 | 1134-Zaatari_Village_North_PE_Fiber_TASC_O | TASC | MFQ-214-R | Outdoor |  | 32.3241 | 36.3074 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 111 | Cluster-11 |  | W13 | SMP-WO-1521287 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | power sheet:we need to add Rectifier pictures &showing the (LLVD&BLVD) | Waed | Approved |  | Omar Sami | Approved | For next time, please provide height next to proposed 4G/5G installation | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-07 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1143 | 1143-Zaatari_Village_South_PE_Fiber_TASC_O | TASC | MFQ-215-R | Outdoor |  | 32.3029 | 36.2979 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 112 | Cluster-11 |  | W13 | SMP-WO-1521288 | SMART | SMART |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved | please we need to specify the LLVD & BLVD | Waed | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-08 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1136 | 1136-Zaatari_Camp_North_PF_EBand_TASC_O | TASC | ZRQ-259-G | Outdoor |  | 32.3024 | 36.3344 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 113 | Cluster-11 |  | W13 | SMP-WO-1521289 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved | power sheet:The rectifier will be change , and add MTS power solution | Waed | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-15 | Yes |  | need Access Letter |  | RFI | [6 empty] | Downloaded
1132 | 1132-Zaatari_Camp_West_PE_O | TASC | MFQ-104-R | Outdoor |  | 32.2973 | 36.3071 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 114 | Cluster-11 |  | W13 | SMP-WO-1521290 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved | Change the azimuth of sector A to 40 (3G.4G.5G) In Azimuth its 40 but in the recommendation its 60 Install NEW AVQC/SA on existing FREE DP ON STD at H :19.85m ,""""""AZ:60 """"""" change to 40 | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | We need pictures for the needed C.T and the civil requirement shall include hexagon base/// not concrete base 1X.8m | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-05-07 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1166 | 1166-Zaatari_Tazweedona_PF_M | ZAIN | MFQ-102-G_CO | Micro Cell |  | 32.2965 | 36.3411 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 115 | Cluster-11 |  | W13 | SMP-WO-1521291 | SMART | SMART |  | Done |  |  | B/C | 5G | 2 |  |  |  |  | Approved | The microcell must be hexagonal to install the ACOC and should include the FPRP The same note was repeated, we need to add(power sheet)FPRP | Waed | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-28 | Yes |  | Need Access Letter |  | RFI | [6 empty] | Downloaded
6091 | 6091-Ajloun_Zobya_Sch_O | TASC | AJL-69-R | Outdoor | 0 | 35.7852 | 32.4257 | Irbid | RT |  |  |  |  | ThinLayer | RO3 | 116 | Cluster-46 |  | W13 | SMP-WO-1527896 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | [5 empty] | Approved | note:All 10 ports antennas will be replaced with 12 ports antennas. | Waed | Approved | Change Azimuth of sector B to 70 ( All Technologies) | Omar Sami | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-26 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4653 | 4653-Zobya_PD_TASC | TASC | IRB-48-G | Indoor | 662 | 32.4305 | 35.7762 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 117 | Cluster-46 |  | W13 | SMP-WO-1521292 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | The sector D no need to swap antenna to 12 port becuase we have just 2g / indicate all CB's( LLVD & BLVD) on the pictures. | Waed | Approved |  | Omar Sami | Approved | Approved, but fix sec.B 2G compass | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4616 | 4616-Irhaba_Ajloun_PE_EBand_TASC | TASC | AJL-22-R | Indoor | 798 | 32.4266 | 35.7986 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 118 | Cluster-46 |  | W13 | SMP-WO-1521293 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C | 5G | 2 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved | Approved, however fix sec.B 3G compass | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-03-27 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6096 | 6096-Ajloun_Rhaba_Mid_O | TASC | AJL-71-R | Outdoor |  | 32.4205 | 35.8054 | Ajloun | Tower |  |  |  |  | ThinLayer | RO3 | 119 | Cluster-46 |  | W13 | SMP-WO-1521294 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved | Align 4G with 5G azimuth ( sector D ) | Omar Sami | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in the civil sheet and not clear tower type RT or GF and the base of this tower not clear also what it is, and the total EPA not calculated in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2816 | 2816-Khaldieh_North_PD_Fiber_TASC_O | TASC | MFQ-180-R | Outdoor |  | 32.1842 | 36.3053 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 120 | Cluster-28 |  | W13 | SMP-WO-1521295 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved | Please re-check all the TSSR. the CB 63A are referring NOT correct, the correct CBs are 50 A and we need to 2*50A for each FPFH& 1*50A for AMIA | Waed | Approved | set az to 40/190/260 | Baher Obaidat | Approved | Wrong Antenna Model for FDD sectors Missing 5G Suggestion notes and remarks | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | B | Approved | Approved | 2025-04-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2819 | 2819-Khaldieh_South_PD_TASC_O | TASC | MFQ-183-R | Outdoor |  | 32.1729 | 36.3 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 121 | Cluster-28 |  | W13 | SMP-WO-1521296 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved | set az to 30/210/285 | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-28 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
2840 | 2840-Delail_Khaldieh_St_PC_TASC | TASC | ZRQ-209-G | Indoor | 1808 | 32.1584 | 36.2933 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 122 | Cluster-28 |  | W13 | SMP-WO-1521297 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved | set az to 50/210/315 | Baher Obaidat | Approved | Why 5G installation suggestion not aligned with 4G? | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
2882 | 2882-Khaldieh_CRL_PD_Fiber_TASC_O | TASC | ZRQ-343-R | Outdoor |  | 32.1906 | 36.3082 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 123 | Cluster-28 |  | W13 | SMP-WO-1521298 | SMART | SMART |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-08 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4681 | 4681-Jdeita_PD_EBand_Zain_TASC | TASC | IRB-34-G | Indoor | 761 | 32.4115 | 35.7029 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 124 | Cluster-46 |  | W13 | SMP-WO-1521299 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C | 5G | 2 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved | Accepted, however please correct the azimuth in BTS sheet make sure it's 130 not 110 just like in RF tab. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-17 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4695 | 4695-Jdeita_South_PF_O | TASC | IRB-570-R | Outdoor |  | 32.4078 | 35.7057 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 125 | Cluster-46 |  | W13 | SMP-WO-1521300 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | No total EPA in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI
1413 | 1413-Jdeita_East_PE_TASC_O | TASC | IRB-460-R | Outdoor |  | 32.4064 | 35.7112 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 126 | Cluster-14 |  | W13 | SMP-WO-1521301 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6009 | 6009-Jdeita_Secondary_School | TASC | IRB-592-R | Outdoor |  | 32.4078 | 35.7057 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 127 | Cluster-14 |  | W13 | SMP-WO-1521302 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6538 | 6538-North_Azraq_West_Tasc_O | TASC | ZRQ-488-R | Outdoor | 0 | 36.8209 | 31.8815 | Zarqa | RT |  |  |  |  | ThinLayer | RO3 | 128 | Cluster-11 |  | W13 | SMP-WO-1527897 | SMART | SMART |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1191 | 1191-North_Azraq_East_Ave_PD_Fiber_TASC_O | TASC | MFQ-219-R | Outdoor |  | 31.8788 | 36.8359 | Zarqa | Pole |  |  |  |  | ThinLayer | RO3 | 129 | Cluster-11 |  | W13 | SMP-WO-1521303 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Need New Pole wrong data in civil sheet approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-13 | Yes |  | Approved By E-mail |  | RFI | [6 empty] | Downloaded
6079 | 6079-Southern_Azraq_O | TASC | MFQ-278-R | Outdoor |  | 31.878 | 36.8243 | Mafraq | Tower |  |  |  |  | ThinLayer | RO3 | 130 | Cluster-11 |  | W13 | SMP-WO-1521305 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved | Modify Tilt (mech.) to be "down" except of "up" | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1137 | 1137-North_Azraq_PC_Fiber_TASC | TASC | MFQ-238-R | Indoor |  | 31.8805 | 36.8303 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 131 | Cluster-11 |  | W15 | SMP-WO-1521306 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | Replacing Empty Huw Cabinet & install Nokia BTS then Relocation BBU , DCDU to it | Moath | Approved |  | Omar Sami | Approved | Wrong Azimuth for sectors A & B which led to wrong views for all sectors, please re-do the TSSR following these bores [ A:70, B: 200, C:290, D:350] Still same reject cause (wrong views and azimuth compared to Zain's data), correct bores are [ A:70, B: 200, C:290, D:350], please re-do the TSSR with the correct bores | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-13 | Yes |  | Need New Location // Need new arrangment by Moath TI |  | RFI | [6 empty] | Downloaded
1925 | 1925-Hararieh_HSG_PE_EBand_TASC | TASC | ZRQ-142-R | Indoor | 582 | 32.1067 | 36.1053 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 132 | Cluster-19 |  | W15 | SMP-WO-1521307 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved | Replacing Empty Huw Cabinet & install Nokia BTS then Relocation BBU , DCDU to it | Moath | Approved |  | Baher Obaidat | Approved | Not aligned with zain naming, please correct azimuth and photos as follows: [A:105, B: 225, C: 305, D:30] | Karam Jaber & Akram Abdelrahim | Approved | C.T location not mentioned in civil1 sheet & wrong EPA | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-23 | Yes |  |  |  | P4 | [6 empty] | Downloaded
1928 | 1928-Prince_Mohammad_Stadium_PE_EBand_TASC | TASC | ZRQ-83-R | Indoor | 528 | 32.1025 | 36.1094 | Zarqa | Tower |  |  |  |  | ThinLayer | RO3 | 133 | Cluster-19 |  | W15 | SMP-WO-1521308 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | BTS Location , Replacing empty HUW Cabinets , add 3 DPs for new 5G | Moath | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-27 | Yes |  |  |  | P4 | [6 empty] | Downloaded
801 | 801-Karak_PB_Fiber_TASC | TASC | KRK-1-G | Indoor | 892 | 31.1962 | 35.7107 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 134 | Cluster-8 |  | W15 | SMP-WO-1521309 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes | Configuration Removed L1800+ | L1800+ RRU / No Need To Dismantle |  | RFI | [6 empty] | Downloaded
846 | 846-Ader_Manshieh_Sch_Back_PF_Fiber_TASC_O | TASC | KRK-284-R | Outdoor |  | 31.1846 | 35.7426 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 135 | Cluster-8 |  | W15 | SMP-WO-1521310 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Laith | Approved | Approved with note : Azi A = 35 | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
825 | 825-Karak_Abu_Hammour_PF_Org_Manage_O | ZAIN/M | KRK-220-G | Outdoor |  | 31.1838 | 35.7371 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 136 | Cluster-8 |  | W15 | SMP-WO-1521311 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/C | 5G | 4 |  | ABD |  |  | Approved |  | Moath | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | B | Approved | Approved | 2025-04-28 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | P4 | [6 empty] | Downloaded
822 | 822-BSC_Ader_PA_Fiber_Zain_TASC | TASC | KRK-22-G | Indoor | 948 | 31.191 | 35.7414 | Karak | Tower |  |  |  |  | ThinLayer | RO3 | 137 | Cluster-8 |  | W15 | SMP-WO-1521312 | Al-Tawseaa | TWASEAA |  | Done |  |  | B/C/D | 5G | 4 |  | ABC |  |  | Approved |  | Moath | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2977 | 2977-Qafqafa_North_PF_TASC_O | TASC | IRB-515-R | Outdoor |  | 32.4031 | 35.9427 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 138 | Cluster-29 |  | W15 | SMP-WO-1521313 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | incorrect ACOC Location - unclear photos/solved | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-23 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2924 | 2924-Qafqafa_Rd_PF_TASC_O | TASC | IRB-193-R | Outdoor |  | 32.3954 | 35.9497 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 139 | Cluster-29 |  | W15 | SMP-WO-1521314 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C | 5G | 2 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2990 | 2990-Balila_Irbid_PE_TASC_O | TASC | IRB-489-R | Outdoor |  | 32.3882 | 35.9385 | Jarash | Pole |  |  |  |  | ThinLayer | RO3 | 140 | Cluster-29 |  | W15 | SMP-WO-1521315 | SMART | SMART |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved | Accepted after resubmission, however update 5G azimuth for sector D solution in remark should be 310 not 330 | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2937 | 2937-Qafqafa_PB_EBand_TASC | TASC | IRB-111-G | Indoor | 628 | 32.38 | 35.93 | Jarash | Tower |  |  |  |  | ThinLayer | RO3 | 141 | Cluster-29 |  | W15 | SMP-WO-1521316 | SMART | SMART | Done | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | Incorrect ACOC Location/solved Sector A - where is the 4 Ports antenna./solved incorrect antenna information - missing information/solved | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-17 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4623 | 4623-Deir_Esseneh_Rd_PC_Fiber_TASC | TASC | IRB-242-R | Indoor | 2133 | 32.5311 | 35.7787 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 142 | Cluster-46 |  | W15 | SMP-WO-1521317 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | incorrect power solution : connect AMIA on DCDU dirctly/solved | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-15 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6090 | 6090-BeitYafa_End_O | TASC | IRB-587-R | Outdoor |  | 32.5273 | 35.7786 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 143 | Cluster-46 |  | W15 | SMP-WO-1521318 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6089 | 6089-BaitYafa_Secondary_Sch | TASC | IRB-585-R | Outdoor |  | 32.5263 | 35.7844 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 144 | Cluster-46 |  | W15 | SMP-WO-1521319 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4611 | 4611-BeitYafa_PC_Fiber_TASC | TASC | IRB-217-R | Indoor | 731 | 32.516 | 35.7887 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 145 | Cluster-46 |  | W15 | SMP-WO-1521320 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | incorrect power solution : wrong information for existing CBs./solved incorrect ACOC solution : why we need to dismantle the existing DCDU./solved incorrect antenna solution : need to mention that we will dismantle the other 4 ports antenna on sector D./solved | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-23 | Yes |  |  |  | RFI | [6 empty] | Downloaded
6003 | 6003-Wadi_Deir_Al_Gharbi_O | TASC | JRS-109-R | Outdoor |  | 32.2861 | 35.8881 | Jarash | Tower |  |  |  |  | ThinLayer | RO3 | 146 | Cluster-14 |  | W15 | SMP-WO-1521321 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1416 | 1416-Jerash_Festival_PC_Fiber_TASC | TASC | JRS-6-R | Indoor | 708 | 32.2816 | 35.8857 | Jarash | Tower |  |  |  |  | ThinLayer | RO3 | 147 | Cluster-14 |  | W15 | SMP-WO-1521322 | SMART | SMART |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved | incorrect power solution : not enough information/solved incorrect ACOC Location/solved incorrect antenna solution | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | B | Approved | Approved | 2025-04-23 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1451 | 1451-Dahr_Serw_CTR_PF_TASC_O | TASC | JRS-84-R | Outdoor |  | 32.2756 | 35.8797 | Jarash | Pole |  |  |  |  | ThinLayer | RO3 | 148 | Cluster-14 |  | W15 | SMP-WO-1521323 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | incorrect power solution: Need rectifier upgrade/solved | Obieda | Approved |  | M. Al-Amro | Approved | Approved, but fix 5g remarks azimuth sequence. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-23 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4751 | 4751-20_St_Mafraq_PD_Fiber_TASC_O | TASC | MFQ-189-R | Outdoor |  | 32.3327 | 36.2055 | Mafraq | Pole |  |  |  |  | ThinLayer | RO3 | 149 | Cluster-47 |  | W15 | SMP-WO-1521324 | SMART | SMART |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | incorrect power solution!/solved | Obieda | Approved |  | Omar Sami | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-13 | Yes |  |  |  | RFI | [6 empty] | Downloaded
439 | 439-Sal_Alia_Ave_PF_TASC_O | TASC | IRB-525-R | Outdoor |  | 32.5797 | 35.9084 | Irbid | Tower |  |  |  |  | ThinLayer | RO3 | 150 | Cluster-4 |  | W15 | SMP-WO-1521325 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved | incorrect antenna solution/solved | Obieda | Approved |  | Baher Obaidat | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-28 | Yes | [10 empty] | Downloaded
452 | 452-Saal_PF_O | TASC | IRB-27-R | Outdoor |  | 32.5715 | 35.9228 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 151 | Cluster-4 |  | W15 | SMP-WO-1521326 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | incorrect antenna solution: where is the existing DP mentioned on Sector B/solved | Obieda | Approved | set az to 60/260/330 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-28 | Yes | Dismantle 2nd L1800 RRU | Need Conatct Person to arrange //L1800+ RRU | [8 empty] | Downloaded
426 | 426-Saal_CTR_PE_TASC | TASC | IRB-253-R | Indoor | 2144 | 32.5681 | 35.9119 | Irbid | Pole |  |  |  |  | ThinLayer | RO3 | 152 | Cluster-4 |  | W15 | SMP-WO-1521327 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | incorrect ACOC solution./solved the plastic cover of each rectifier must be removed to inspect the copper plate connections/solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-04-17 | Yes | [10 empty] | Downloaded
4181 | 4181-Aqaba-Karama-PF-EBand-TASC-O | TASC | AQB-295-R | Outdoor |  | 29.5625 | 35.0246 | Aqaba | Pole |  |  |  |  | ThinLayer | RO3 | 153 | Cluster-41 |  | W15 | SMP-WO-1521328 | Al-Tawseaa | TWASEAA |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | Incorrect Antenna Solution./solved | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-04-23 | Yes |  |  |  | RFI | [6 empty] | Downloaded
465 | 465-Turra_Farouq_Msq_PF_EBand_TASC_O | TASC | IRB-555-R | Outdoor |  | 32.6492 | 35.9942 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 154 | Cluster-4 |  | W15 | SMP-WO-1521329 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved | change the selected sectors from ABC to ACD | Baher Obaidat | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
460 | 460-Irbid_Turra_CTR_PF_EBand_TASC_O | TASC | IRB-539-R | Outdoor |  | 32.6361 | 35.9922 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 155 | Cluster-4 |  | W15 | SMP-WO-1521330 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved | need to modify the az of all sectors forr 3g+4G to be 60/170/280/360 and set the 5G az to ABC 60/160/280 | Baher Obaidat | Approved | Approved after changing azimuth. | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil and BTS and Civil requirement sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-22 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
461 | 461-Ramtha_Turra_West_PE_UMN_Manage_O | ZAIN/M | IRB-534-R | Outdoor |  | 32.6431 | 35.9848 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 156 | Cluster-4 |  | W16 | SMP-WO-1521331 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | RAN Only | 4 |  |  |  |  | Approved |  | Waed | Approved | change the selected sector from BCD to ACD | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
442 | 442-Turra_DCME_PC_TASC | TASC | IRB-22-R | Indoor | 681 | 32.6416 | 35.9905 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 157 | Cluster-4 |  | W16 | SMP-WO-1521332 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Released |  | Waed | Released |  | Baher Obaidat | Approved | Approved, however follow Sec.B 3g azimuth 170 not 180 as 4g. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-07-21 | Yes |  | Relocation site // Was Approved |  | RFI |  |  | Laith |  |  |  | Downloaded
474 | 474-Turra_Cemetary_PF_TASC_O | TASC | IRB-450-R | Outdoor |  | 32.6329 | 35.9871 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 158 | Cluster-4 |  | W16 | SMP-WO-1521333 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved | change all sec az(3G/4g/5g ) to 35/135/215/335 | Baher Obaidat | Approved | Approved after changing azimuth. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-14 | Yes |  | ExtraFPFH needed to connect ACOC |  | RFI |  |  | Mofeed |  |  |  | Downloaded
423 | 423-Turra_East_PC_TASC | TASC | IRB-228-R | Indoor | 2108 | 32.6318 | 35.9957 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 159 | Cluster-4 |  | W16 | SMP-WO-1521334 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved | change all antennas (3g/4g/5g) az to 40/185/300 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
486 | 486-Turrah_Khawla_Bint_Awzar_Msq_TASC_O | TASC | IRB-662-R | Outdoor |  | 36.0022 | 32.6241 | Irbid | RT |  |  |  |  | Full Swap | PO3 | 160 | Cluster-4 |  | W16 | SMP-WO-1527898 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-07 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
457 | 457-Sahel_Horan_PSD_PE_TASC_O | TASC | IRB-501-R | Outdoor |  | 32.6381 | 35.9676 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 161 | Cluster-4 |  | W16 | SMP-WO-1521335 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-07 | Yes |  | Remove 2G Technology |  | RFI |  |  | Mofeed |  |  |  | Downloaded
420 | 420-Mughayer_CTR_Irbid_PD_TASC | TASC | IRB-220-R | Indoor | 601 | 32.6138 | 35.9402 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 162 | Cluster-4 |  | W16 | SMP-WO-1521336 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
468 | 468-Mughayer_South_PD_TASC_O | TASC | IRB-443-R | Outdoor |  | 32.6086 | 35.9391 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 163 | Cluster-4 |  | W16 | SMP-WO-1521337 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
481 | 481-Mughayyer_Jaafar_Tayyar_Schools | TASC | IRB-633-R | Outdoor |  | 32.5997 | 35.9265 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 164 | Cluster-4 |  | W16 | SMP-WO-1521338 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-07 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
410 | 410-Mughayer_Irbid_PC_TASC | TASC | IRB-203-G | Indoor | 794 | 32.6 | 35.9327 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 165 | Cluster-4 |  | W16 | SMP-WO-1521339 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
419 | 419-Alaal_PC_Fiber_TASC | TASC | IRB-206-R | Indoor | 800 | 32.6334 | 35.9056 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 166 | Cluster-4 |  | W16 | SMP-WO-1521340 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
471 | 471-Alaal_South_PD_Fiber_TASC_O | TASC | IRB-449-R | Outdoor |  | 32.627 | 35.8997 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 167 | Cluster-4 |  | W16 | SMP-WO-1521341 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved | No 5G data in BTS sheet. | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-13 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
401 | 401-Maru_Irbid_PD_Fiber_TASC | TASC | IRB-176-R | Indoor | 767 | 32.6072 | 35.8918 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 168 | Cluster-4 |  | W16 | SMP-WO-1521342 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
403 | 403-Shajara_CTR_PE_UMN_Manage_O | ZAIN/M | IRB-317-G | Outdoor |  | 32.6463 | 35.9413 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 169 | Cluster-4 |  | W16 | SMP-WO-1521343 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved | select ACD instead of ABC, set az to 55/270/355 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-26 | Yes |  |  |  | RFI |  |  | Laith
477 | 477-Turrah_Qubtieh_Sch_O | TASC | IRB-589-R | Outdoor |  | 32.6366 | 35.9495 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 170 | Cluster-4 |  | W16 | SMP-WO-1521344 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved | the current sectors az 20/70/115/290 related to D/A/B/C ... az must be changed to 60/125/290/355 .. az 20/SD must be changed to 355 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-26 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
484 | 484-Turrah_Mansour_Msq_O | TASC | IRB-630-R | Outdoor |  | 32.6378 | 35.9412 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 171 | Cluster-4 |  | W16 | SMP-WO-1521345 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved | change the selected sectors from ABC to BCD and the az to 115/270/340 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
431 | 431-Shajara_East_PE_TASC_O | TASC | IRB-509-R | Outdoor |  | 32.6432 | 35.9458 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 172 | Cluster-4 |  | W16 | SMP-WO-1521346 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-17 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
453 | 453-Shajara_PC_TASC | TASC | IRB-28-G | Indoor | 672 | 32.6416 | 35.9356 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 173 | Cluster-4 |  | W16 | SMP-WO-1521347 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved | for both all 3g 4g 5g , change antenna az to 0/80/155 | Baher Obaidat | Approved | Approved after changing azimuth. | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-26 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
466 | 466-Ramtha_Turra_Ent_PD_TASC_O | TASC | IRB-438-R | Outdoor |  | 32.6135 | 35.9927 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 174 | Cluster-4 |  | W16 | SMP-WO-1521348 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in the civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
429 | 429-Thnebeh_PE_O | TASC | IRB-283-R | Outdoor |  | 32.6928 | 35.9066 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 175 | Cluster-4 |  | W16 | SMP-WO-1521349 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
445 | 445-Shajara_Umrawa_Rd_PF_O | TASC | IRB-567-R | Outdoor |  | 32.6724 | 35.9399 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 176 | Cluster-4 |  | W16 | SMP-WO-1521350 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 2 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil and BTS sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-13 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
418 | 418-Umrawa_PE_TASC | TASC | IRB-17-G | Indoor | 713 | 32.6916 | 35.9206 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 177 | Cluster-4 |  | W16 | SMP-WO-1521351 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 2 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-07 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
430 | 430-Umrawa_Irbid_2_PD_EBand_TASC_O | TASC | IRB-331-R | Outdoor |  | 32.6864 | 35.9367 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 178 | Cluster-4 |  | W16 | SMP-WO-1521352 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
436 | 436-Kufer_Soum_East_PE_O | TASC | IRB-397-R | Outdoor |  | 32.6841 | 35.8046 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 179 | Cluster-4 |  | W16 | SMP-WO-1521353 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  | CD |  |  | Approved |  | Moath | Approved | set the az of sector A to 25 instead of zero | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-26 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
416 | 416-Kufer_Soum_CTR_PE_TASC | TASC | IRB-212-R | Indoor | 799 | 32.6834 | 35.8004 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 180 | Cluster-4 |  | W16 | SMP-WO-1521354 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
492 | 492-Kufer_Soum_Mwajeh_Intersection_Tasc_O | TASC | IRB-678-R | Outdoor | 0 | 35.7973 | 32.6718 | Irbid | RT |  |  |  |  | Full Swap | PO3 | 181 | Cluster-4 |  | W17 | SMP-WO-1527899 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | [5 empty] | Approved |  | Moath | Approved | set az for 4g and 5g to : 55/275/335 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-26 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
407 | 407-Kufer_Soum_Ent_PE | TASC | IRB-32-G | Indoor | 739 | 32.6703 | 35.8066 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 182 | Cluster-4 |  | W17 | SMP-WO-1521355 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
408 | 408-Kufer_Soum_PB_Fiber_TASC | TASC | IRB-7-G | Indoor | 694 | 32.6636 | 35.8276 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 183 | Cluster-4 |  | W17 | SMP-WO-1521356 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil requirement sheet and BTS Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
459 | 459-Hubras_East_PF_TASC_O | TASC | IRB-526-R | Outdoor |  | 32.6738 | 35.8486 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 184 | Cluster-4 |  | W17 | SMP-WO-1521357 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
469 | 469-Hubras_CTR_PD_Fiber_TASC_O | TASC | IRB-468-R | Outdoor |  | 32.6713 | 35.8314 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 185 | Cluster-4 |  | W17 | SMP-WO-1521358 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
413 | 413-Kharja_North_PC_Fiber_TASC | TASC | IRB-196-G | Indoor | 782 | 32.6693 | 35.8713 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 186 | Cluster-4 |  | W17 | SMP-WO-1521359 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
479 | 479-Hubras_Hartha_St_O | TASC | IRB-595-R | Outdoor |  | 32.6641 | 35.8374 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 187 | Cluster-4 |  | W17 | SMP-WO-1521360 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
470 | 470-Hubras_Qsayreen_PE_Fiber_TASC_O | TASC | IRB-466-R | Outdoor |  | 32.656 | 35.8363 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 188 | Cluster-4 |  | W17 | SMP-WO-1521361 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C | 5G | 2 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
485 | 485-Saham_Health_Ctr_South | TASC | IRB-643-R | Outdoor |  | 32.697 | 35.7722 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 189 | Cluster-4 |  | W17 | SMP-WO-1521362 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil and BTS sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
415 | 415-Saham_Kfarat_End_PF_TASC_O | TASC | IRB-517-R | Outdoor |  | 32.7009 | 35.7749 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 190 | Cluster-4 |  | W17 | SMP-WO-1521363 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved | change the az of sector D to 310 , and change the selected sectors from ABC to BCD // 130/230/310 | Baher Obaidat | Approved | AAU should be SB and SC not SD missing 2G L9 data | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
464 | 464-Saham_Kfarat_West_PF_BTS_O | TASC | IRB-560-R | Outdoor |  | 32.6996 | 35.7627 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 191 | Cluster-4 |  | W17 | SMP-WO-1521364 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | Meter type 1 Phase | Moath | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
455 | 455-Saham_Kfarat_PE_TASC | TASC | IRB-29-R | Indoor | 665 | 32.6966 | 35.7763 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 192 | Cluster-4 |  | W17 | SMP-WO-1521366 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | incorrect ACOC location : Why do we need to install the ACOC next to cabinets that are going to be dismantled!/solved Incorrect antenna solution: 1.Why is the note "Need DP NA" included? 2. How can the DP be shifted for the 5G Sector D solution? 3.It does not mention dismantling the other existing 2G antenna on Sector C./solved incorrect power solution: Need Rectifier upgrade. | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Najjar
488 | 488-Saham_South_End_TASC_O | TASC | IRB-657-R | Outdoor | 0 | 35.7788 | 32.6915 | Irbid | RT |  |  |  |  | Full Swap | PO3 | 193 | Cluster-4 |  | W17 | SMP-WO-1527900 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | [5 empty] | Approved | Incorrect antenna solution: The 10-port antenna needs to be swapped with a 12-port antenna./solved Incorrect power solution: There is no 2G service on the site, so why is AHDA mentioned in the power solution?/solved | Obieda | Approved |  | Baher Obaidat | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
414 | 414-Hartha_West_PF_TASC_O | TASC | IRB-416-R | Outdoor |  | 32.6933 | 35.8481 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 194 | Cluster-4 |  | W17 | SMP-WO-1521367 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 4 |  |  |  |  | Approved | Incorrect power solution: AMIA must not be installed on FPFH!/solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
405 | 405-Aqraba_PE_TASC | TASC | IRB-152-G | Indoor | 741 | 32.7283 | 35.8052 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 195 | Cluster-4 |  | W17 | SMP-WO-1521368 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Obieda | Approved | change the ant az to 125/200/270 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
412 | 412-Harema_PD_Fiber_TASC | TASC | IRB-11-G | Indoor | 764 | 32.6265 | 35.885 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 196 | Cluster-4 |  | W17 | SMP-WO-1521369 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 4 |  |  |  |  | Approved |  | Obieda | Approved | no 5g | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-17 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
427 | 427-Kharja_CTR_PE_Org_Manage_O | ZAIN/M | IRB-267-R | Outdoor |  | 32.6583 | 35.8876 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 197 | Cluster-4 |  | W17 | SMP-WO-1521370 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Obieda | Approved | install all 5g antennas at 30m height, move DB if required | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
434 | 434-Yarmouk_Irbid_PF_TASC_O | TASC | IRB-399-R | Outdoor |  | 32.7084 | 35.8726 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 198 | Cluster-4 |  | W17 | SMP-WO-1521371 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 2 |  |  |  |  | Approved |  | Obieda | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
440 | 440-Hartha_East_PD_EBand_TASC_O | TASC | IRB-410-R | Outdoor |  | 32.6923 | 35.8494 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 199 | Cluster-4 |  | W17 | SMP-WO-1521372 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 4 |  |  |  |  | Approved |  | Obieda | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-17 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
476 | 476-Aqraba_West_PF_BTS_O | TASC | IRB-557-R | Outdoor |  | 32.7307 | 35.7911 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 200 | Cluster-4 |  | W17 | SMP-WO-1521373 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | accepted after resubmission | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
462 | 462-Yubla_Irbid_South_PF_O | TASC | IRB-569-R | Outdoor |  | 32.6874 | 35.8217 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 201 | Cluster-4 |  | W17 | SMP-WO-1521374 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 4 |  |  |  |  | Approved |  | Obieda | Approved | modify the 4G/5G az for sec A to be 80 instead of 105// replace sector C with D // ABD // 80/140/315 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-15 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
433 | 433-Kharja_East_Irbid_PF_TASC_O | TASC | IRB-400-R | Outdoor |  | 32.6626 | 35.905 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 202 | Cluster-4 |  | W17 | SMP-WO-1521375 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Obieda | Approved | set the az of sector A to 180 | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
435 | 435-Abu_Luqas_PE_Fiber_TASC_O | TASC | IRB-389-R | Outdoor |  | 32.6356 | 35.8887 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 203 | Cluster-4 |  | W17 | SMP-WO-1521376 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 4 |  |  |  |  | Approved |  | Obieda | Approved | change the sectors from ABC to ACD | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-13 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
438 | 438-Seeleh_Irbid_PE_Fiber_TASC_O | TASC | IRB-408-R | Outdoor |  | 32.6489 | 35.8685 | Irbid | Pole |  |  |  |  | Full Swap | PO3 | 204 | Cluster-4 |  | W17 | SMP-WO-1521377 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-14 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
437 | 437-Rafeed_Irbid_PF_TASC_O | TASC | IRB-393-R | Outdoor |  | 32.7056 | 35.8219 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 205 | Cluster-4 |  | W17 | SMP-WO-1521378 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-13 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
411 | 411-Yubla_Irbid_PE_O | TASC | IRB-310-R | Outdoor |  | 32.6867 | 35.8292 | Irbid | Tower |  |  |  |  | Full Swap | PO3 | 206 | Cluster-4 |  | W18 | SMP-WO-1521379 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | No 5G | RAN Only | 3 |  |  |  |  | Approved |  | Obieda | Approved | set az of sector A to zero | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
809 | 809-Karak_City_2_PD_Fiber_TASC | TASC | KRK-123-R | Indoor | 926 | 31.1808 | 35.7111 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 207 | Cluster-8 |  | W18 | SMP-WO-1521380 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-14 | Yes |  |  |  | RFI | [6 empty] | Downloaded
803 | 803-Abu_Hammour_PD_Fiber_TASC | TASC | KRK-55-R | Indoor | 964 | 31.1768 | 35.7355 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 208 | Cluster-8 |  | W18 | SMP-WO-1521381 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-14 | Yes |  |  |  | RFI | [6 empty] | Downloaded
869 | 869-Shihabieh_Karak_PC_Fiber_TASC | TASC | KRK-153-G | Indoor |  | 31.1743 | 35.7001 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 209 | Cluster-8 |  | W18 | SMP-WO-1521382 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
841 | 841-Thanieh_Karak_CTR_PE_Fiber_TASC_O | TASC | KRK-251-R | Outdoor |  | 31.1701 | 35.7313 | Karak | Pole |  |  |  |  | ThinLayer | PO3 | 210 | Cluster-8 |  | W18 | SMP-WO-1521383 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | RFI | [6 empty] | Downloaded
845 | 845-Zahoum_Dahyet_karak_Msq_PE_Fiber_TASC_O | TASC | KRK-285-R | Outdoor |  | 31.1683 | 35.7485 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 211 | Cluster-8 |  | W18 | SMP-WO-1521384 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | RFI | [6 empty] | Downloaded
881 | 881-Rabieh_Karak_PE_Fiber_TASC_O | TASC | KRK-163-G | Outdoor |  | 31.1677 | 35.7125 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 212 | Cluster-8 |  | W18 | SMP-WO-1521385 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | RFI | [6 empty] | Downloaded
824 | 824-Karak_Ind_PD_Fiber_TASC_O | TASC | KRK-54-R | Outdoor | 939 | 31.1536 | 35.7032 | Karak | Pole |  |  |  |  | ThinLayer | PO3 | 213 | Cluster-8 |  | W18 | SMP-WO-1521386 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-26 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2946 | 2946-Ramtha_PA_Fiber_TASC | TASC | IRB-118-G | Indoor | 658 | 32.5616 | 36.0129 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 214 | Cluster-29 |  | W18 | SMP-WO-1521387 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
2920 | 2920-Ramtha_West_PD_Fiber_TASC | TASC | IRB-108-R | Indoor | 714 | 32.5589 | 36.0091 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 215 | Cluster-29 |  | W18 | SMP-WO-1521388 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-26 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4689 | 4689-Huson_Sareeh_Ent_PF_TASC_O | TASC | IRB-532-R | Outdoor |  | 32.4962 | 35.8836 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 216 | Cluster-46 |  | W18 | SMP-WO-1521389 | Al-Tawseaa |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
4626 | 4626-Huson_Qanater_PE | TASC | IRB-258-R | Indoor | 2154 | 32.4897 | 35.8774 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 217 | Cluster-46 |  | W18 | SMP-WO-1521390 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | the AMIA will be connected to theDCDU1 &upgrade CB63(DCDU1) TO 100 A | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4645 | 4645-Huson_CTR_PE_EBand_TASC | TASC | IRB-117-R | Indoor | 641 | 32.4844 | 35.8793 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 218 | Cluster-46 |  | W18 | SMP-WO-1521391 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved | all power sheet not clear | Waed | Approved |  | Omar Sami | Approved | Incorrect Sec.B Az, check 360 view | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
4610 | 4610-Huson_East_PF_TASC | TASC | IRB-213-R | Indoor | 610 | 32.4887 | 35.9002 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 219 | Cluster-46 |  | W18 | SMP-WO-1521392 | Al-Tawseaa |  |  | Done |  |  | A/C | 5G | 2 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved | wrong antenna view for 2G3G SA wrong Mtilt for 2G3G SA 5G Azimuth for SC should be 265 not 230 | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-11 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
4677 | 4677-Huson_East_College_Ave_PF_TASC_O | TASC | IRB-455-R | Outdoor |  | 32.4814 | 35.8939 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 220 | Cluster-46 |  | W18 | SMP-WO-1521393 | Al-Tawseaa |  |  | Done |  |  | A/B/D | 5G | 3 |  |  |  |  | Approved | Extension Concrete For Install ACOC | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4633 | 4633-Huson_Thufar_Msq_PF_TASC_O | TASC | IRB-314-R | Outdoor |  | 32.4761 | 35.8891 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 221 | Cluster-46 |  | W18 | SMP-WO-1521394 | Al-Tawseaa |  |  | Done |  |  | A/C/D | 5G | 5 |  |  |  |  | Approved | There is no 4g in sectorD &and no need to add AHEB to sectorE and Must be added AHEB to the sector D/and add MTS power distribution | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil and BTS sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
4612 | 4612-Huson_PF_TASC_O | TASC | IRB-529-R | Outdoor |  | 32.4705 | 35.8797 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 222 | Cluster-46 |  | W18 | SMP-WO-1521395 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | ensure that the selected location does not ( the mast bracing )obstructing the opening or closing of the cabinet door./Redistribution:FPFH1(2*30A):3AHEB,FPFH2(ADD PDU 100A):3AQQY, 1*30A:AMIA | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
4601 | 4601-Huson_Camp_PC_EBand_TASC | TASC | IRB-105-G | Indoor | 719 | 32.4676 | 35.9196 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 223 | Cluster-46 |  | W18 | SMP-WO-1521396 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4665 | 4665-Huson_Teachers_HSG_PF_TASC_O | TASC | IRB-352-R | Outdoor |  | 32.4655 | 35.9078 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 224 | Cluster-46 |  | W18 | SMP-WO-1521397 | Al-Tawseaa |  |  | Done |  |  | B/C | 5G | 2 |  |  |  |  | Approved | we need to hexagon for ACOC | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2985 | 2985-Ramtha_Salman_AlFaresi_Msq_North_PF_EBand_TASC_O | TASC | IRB-547-R | Outdoor |  | 32.5505 | 36.0147 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 225 | Cluster-29 |  | W18 | SMP-WO-1521399 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2910 | 2910-Ramtha_Bridge_PC_Fiber_TASC | TASC | IRB-100-G | Indoor | 660 | 32.514 | 35.9997 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 226 | Cluster-29 |  | W18 | SMP-WO-1521400 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2927 | 2927-Ramtha_South_Ent_PD_O | TASC | IRB-285-R | Outdoor |  | 32.536 | 36.0039 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 227 | Cluster-29 |  | W18 | SMP-WO-1521401 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet wrong data in civil sheet approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2973 | 2973-Ramtha_Howara_St_PF_EBand_TASC_O | TASC | IRB-485-R | Outdoor |  | 32.5117 | 35.9816 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 228 | Cluster-29 |  | W18 | SMP-WO-1521402 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2931 | 2931-JUST_Uni_CRL_PF_UMN_Manage_O | ZAIN/M | IRB-295-G | Outdoor |  | 32.4989 | 35.9838 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 229 | Cluster-29 |  | W18 | SMP-WO-1521403 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | No need to hexagon we have RFC empty need to dismantle /WE NEED JUST 1 PDU no need to another PDU we have dcdu2 empte ,just L6 FAN we will transfer to dcdu 1 The previous note was repeated for the second time :No need to hexagon we have RFC empty need to dismantle | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2949 | 2949-JUST_PH_PF_Fiber_TASC_O | TASC | IRB-367-R | Outdoor |  | 32.4988 | 35.9931 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 230 | Cluster-29 |  | W18 | SMP-WO-1521404 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | we have 3*(2G Radio+ katrrin antenna ) and active (l900) | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2951 | 2951-JUST_Library_PF_Fiber_TASC_O | TASC | IRB-368-R | Outdoor |  | 32.4956 | 35.9912 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 231 | Cluster-29 |  | W19 | SMP-WO-1521405 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2922 | 2922-Hassan_Ind_2_PE_TASC | TASC | IRB-109-G | Indoor | 735 | 32.4954 | 36.0145 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 232 | Cluster-29 |  | W19 | SMP-WO-1521406 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | RFI | [6 empty] | Downloaded
2952 | 2952-JUST_Girls_HSG_PE_Fiber_TASC_O | TASC | IRB-369-R | Outdoor |  | 32.4871 | 35.9916 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 233 | Cluster-29 |  | W19 | SMP-WO-1521407 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2933 | 2933-JUST_PA_Fiber_TASC | TASC | IRB-113-G | Indoor | 630 | 32.4825 | 35.9772 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 234 | Cluster-29 |  | W19 | SMP-WO-1521408 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A | 5G | 1 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Change that action applied for the not used antenna and input the EPA for the MW links | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI
2940 | 2940-Flour_Mill_Irbid_PF_O | TASC | IRB-297-R | Outdoor |  | 32.4757 | 35.968 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 235 | Cluster-29 |  | W19 | SMP-WO-1521409 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2905 | 2905-Cyber_City_PF_Manage_O | ZAIN/M | IRB-197-R | Outdoor |  | 32.4555 | 35.9676 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 236 | Cluster-29 |  | W19 | SMP-WO-1521410 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3373 | 3373-Enjasah_Karak_PD_Fiber_TASC | TASC | KRK-149-R | Indoor | 989 | 31.1016 | 35.694 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 237 | Cluster-33 |  | W19 | SMP-WO-1521411 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | On Sec.A,B &C switch between 12-port & AVQC. DPs vary with their length make sure that there is no cable shortage will occur when merging BTS cabinets. Also, remove "AMIA inside BTS" merging DCDUs should be occurred. Also, i can't figure out where 3rd DCDU connected (LLVD or BLVD) Update:approved. | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3374 | 3374-Mutah_Uni_PF_EBand_TASC | TASC | KRK-152-R | Indoor | 991 | 31.0935 | 35.717 | Karak | Pole |  |  |  |  | ThinLayer | PO3 | 238 | Cluster-33 |  | W19 | SMP-WO-1521412 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3339 | 3339-Karak_Mutah_West_TASC_O | TASC | KRK-321-R | Outdoor | 0 | 35.6883 | 31.0926 | Karak | RT |  |  |  |  | ThinLayer | PO3 | 239 | Cluster-33 |  | W19 | SMP-WO-1527901 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
3349 | 3349-Mutah_Uni_TL_Back_PD_Fiber_TASC_O | TASC | KRK-259-R | Outdoor |  | 31.0907 | 35.7075 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 240 | Cluster-33 |  | W19 | SMP-WO-1521413 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  | BCD |  |  | Approved | Connect AMIA on one of 100A DCDUs, due to fuses shortage Update: approved. | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved | Wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4475 | 4475-Turkman_Ave_West_PE_TASC_O | TASC | IRB-482-R | Outdoor |  | 32.5561 | 35.8259 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 241 | Cluster-44 |  | W19 | SMP-WO-1521414 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved | short arm DPs are needed for 5G to avoid blockage | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in BTS sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
4457 | 4457-Barha_PA_Fiber_TASC | TASC | IRB-30-R | Indoor | 604 | 32.5559 | 35.8318 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 242 | Cluster-44 |  | W19 | SMP-WO-1521415 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Released |  | Zaid | Released |  | Omar Sami | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Pending | Approved | 2025-07-17 | Yes |  | Tower ladder is missing | [8 empty] | Downloaded
2932 | 2932-Sareeh_Howara_Ent_PE_EBand_TASC_O | TASC | IRB-270-R | Outdoor |  | 32.5165 | 35.8983 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 243 | Cluster-29 |  | W19 | SMP-WO-1521416 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved | Wrong Power Solution. Use PDU & Plug solution. shall we extend the power cables length for sector D or they may be enough? Is there any space surrounding the rectifier cabinet to install ACOC? Update:approved. | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2965 | 2965-Irbid_Petra_Rd_Dentists_HSG_PF_TASC_O | TASC | IRB-516-R | Outdoor |  | 32.5208 | 35.8869 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 244 | Cluster-29 |  | W19 | SMP-WO-1521417 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved | Free LLVD fuses are not clear. | Zaid | Approved |  | M. Al-Amro | Approved | Mtilt PIC for SC not clear | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2971 | 2971-Ramtha_Trucks_City_PF_TASC_O | TASC | IRB-462-R | Outdoor |  | 32.5138 | 35.9496 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 245 | Cluster-29 |  | W19 | SMP-WO-1521418 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4648 | 4648-Sareeh_PC_EBand_TASC | TASC | IRB-120-R | Indoor | 676 | 32.5054 | 35.8926 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 246 | Cluster-46 |  | W19 | SMP-WO-1521419 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved | Wrong power solution. Sec. B Antenna installation location should be marked on BTS sheet. Update:approved. | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4660 | 4660-Sareeh_East_PF | TASC | IRB-260-R | Indoor | 2156 | 32.5047 | 35.9044 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 247 | Cluster-46 |  | W19 | SMP-WO-1521420 | Al-Tawseaa |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
4632 | 4632-Sareeh_West_PF_TASC_O | TASC | IRB-328-R | Outdoor |  | 32.5032 | 35.8867 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 248 | Cluster-46 |  | W19 | SMP-WO-1521421 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | wrong 5G solution on BTS sheet for Sec.B &C. Please don't mention "Need Rectifier Upgrade". Update:approved. | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2912 | 2912-Petra_Rd_Irbid_PE_TASC | TASC | IRB-223-R | Indoor | 699 | 32.5027 | 35.9383 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 249 | Cluster-29 |  | W19 | SMP-WO-1521422 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
4449 | 4449-Barha_Rahbat_Sch_PF_TASC_O | TASC | IRB-523-R | Outdoor |  | 32.5595 | 35.8406 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 250 | Cluster-44 |  | W19 | SMP-WO-1521423 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | C | Approved | Approved | 2025-06-04 | Yes | [10 empty] | Downloaded
4443 | 4443-Palestine_St_PD_EBand_TASC | TASC | IRB-131-R | Indoor | 752 | 32.5609 | 35.8298 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 251 | Cluster-44 |  | W19 | SMP-WO-1521424 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
2866 | 2866-Delail_Maliban_Ind_PE_O | ZAIN | ZRQ-292-R | Outdoor |  | 32.1243 | 36.2852 | Zarqa | Pole |  |  |  |  | ThinLayer | PO3 | 252 | Cluster-28 |  | W19 | SMP-WO-1521425 | Al-Tawseaa |  |  | Done |  |  | B/C/D | 5G | 3 |  |  |  |  | Approved | Regarding Plugs, LLVD & BLVD should be specified clearly. Dismantling 4-port antenna should be mentioned to allow us installing AVQC. Update:approved. | Zaid | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in civil and BTS sheet need new pole | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | T2 |  |  | Laith |  |  |  | Downloaded
2801 | 2801-Delail_Police_Station_PC_Fiber_TASC | TASC | ZRQ-119-G | Indoor | 565 | 32.1206 | 36.2959 | Zarqa | Tower |  |  |  |  | ThinLayer | PO3 | 253 | Cluster-28 |  | W19 | SMP-WO-1521426 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | cabinets should be merged. power solution not clear. Update:approved. | Zaid | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | RFI |  |  | Najjar
2430 | 2430-Irbid_Hay_Qaseleh_PF | TASC | IRB-264-R | Indoor | 2146 | 32.5486 | 35.8405 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 254 | Cluster-24 |  | W19 | SMP-WO-1521427 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved | 5G DP arms should be replaced to be shorten "Need DP No Need",The way that sentence is written is a little confusing. Update:approved. | Zaid | Approved |  | M. Al-Amro | Approved | wrong compass value for 2G4G Antenna Azimuth for sectorC | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil and BTS sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2401 | 2401-Aghwar_Irbid_Bus_Station_PC_Fiber_TASC | TASC | IRB-177-R | Indoor | 771 | 32.5509 | 35.8377 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 255 | Cluster-24 |  | W19 | SMP-WO-1521428 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved | No need for DPs, Install AVQC above TDD after reducing its height Power table need to be revised; there is no sector D! Update:approved. | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2437 | 2437-Irbid_Alqasileh_Sch_PF_TASC_O | TASC | IRB-512-R | Outdoor |  | 32.5461 | 35.837 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 256 | Cluster-24 |  | W20 | SMP-WO-1521429 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-17 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
2425 | 2425-UNRWA_Sch_Irbid_PD_EBand_TASC | TASC | IRB-75-R | Indoor | 624 | 32.543 | 35.843 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 257 | Cluster-24 |  | W20 | SMP-WO-1521430 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-29 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | RFI |  |  | Najjar |  |  |  | Downloaded
3335 | 3335-Karak_Southern_Mazar_TASC_O | TASC | KRK-320-R | Outdoor | 0 | 35.6821 | 31.0541 | Karak | RT |  |  |  |  | ThinLayer | PO3 | 258 | Cluster-33 |  | W20 | SMP-WO-1527902 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
3308 | 3308-Mazar_PA_Fiber_TASC | TASC | KRK-8-G | Indoor | 900 | 31.0738 | 35.6985 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 259 | Cluster-33 |  | W20 | SMP-WO-1521431 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
3377 | 3377-Mazar_West_Karak_PE_TASC_O | TASC | KRK-170-R | Outdoor |  | 31.0594 | 35.687 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 260 | Cluster-33 |  | W20 | SMP-WO-1521432 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-21 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
4464 | 4464-Hay_Nasser_West_PE_Fiber_TASC_O | TASC | IRB-439-R | Outdoor |  | 32.5721 | 35.8459 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 261 | Cluster-44 |  | W20 | SMP-WO-1521433 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-20 | Yes | [10 empty] | Downloaded
4454 | 4454-Hay_Jawhara_East_PE_Fiber_TASC_O | TASC | IRB-423-R | Outdoor |  | 32.5698 | 35.8494 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 262 | Cluster-44 |  | W20 | SMP-WO-1521434 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes | [6 empty] | Najjar |  |  |  | Downloaded
2975 | 2975-Ramtha_Dahdah_North_PE_TASC_O | TASC | IRB-513-R | Outdoor |  | 32.584 | 35.9983 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 263 | Cluster-29 |  | W20 | SMP-WO-1521435 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
2983 | 2983-Ramtha_Dahdah_West_PE_EBand_TASC_O | TASC | IRB-540-R | Outdoor |  | 32.5701 | 35.9942 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 264 | Cluster-29 |  | W20 | SMP-WO-1521436 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
2939 | 2939-Ramtha_Shaqran_Gas_Station_PF_O | TASC | IRB-296-R | Outdoor |  | 32.569 | 35.9793 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 265 | Cluster-29 |  | W20 | SMP-WO-1521437 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
4436 | 4436-Barha_2_PC_Fiber_TASC | TASC | IRB-85-R | Indoor | 626 | 32.556 | 35.8401 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 266 | Cluster-44 |  | W20 | SMP-WO-1521438 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
2906 | 2906-Ramtha_Hay_Masarah_PF_O | TASC | IRB-316-R | Outdoor |  | 32.5515 | 35.9851 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 267 | Cluster-29 |  | W20 | SMP-WO-1521439 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
4418 | 4418-Hay_Matlaa_2_PE_TASC_O | TASC | IRB-266-R | Outdoor |  | 32.5648 | 35.8394 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 268 | Cluster-44 |  | W20 | SMP-WO-1521440 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes | [10 empty] | Downloaded
1456 | 1456-Jerash_PB_Fiber_TASC | TASC | JRS-13-R | Indoor | 632 | 32.2835 | 35.897 | Jarash | Tower |  |  |  |  | ThinLayer | PO3 | 269 | Cluster-14 |  | W20 | SMP-WO-1521441 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
1480 | 1480-Jabal_Sheikh_Musleh_PD | TASC | IRB-268-R | Indoor | 2155 | 32.2809 | 35.9026 | Jarash | Tower |  |  |  |  | ThinLayer | PO3 | 270 | Cluster-14 |  | W20 | SMP-WO-1521442 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
1429 | 1429-Jerash_Market_PD_Fiber_TASC_O | TASC | JRS-60-R | Outdoor |  | 32.2788 | 35.8962 | Jarash | Pole |  |  |  |  | ThinLayer | PO3 | 271 | Cluster-14 |  | W20 | SMP-WO-1521443 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 5 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1493 | 1493-Jerash_Mall_Back_PD_Fiber_TASC_O | TASC | JRS-55-R | Outdoor |  | 32.278 | 35.9033 | Jarash | Pole |  |  |  |  | ThinLayer | PO3 | 272 | Cluster-14 |  | W20 | SMP-WO-1521444 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
2936 | 2936-Nusaibah_College_PF_O | TASC | IRB-277-R | Outdoor |  | 32.5339 | 35.8999 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 273 | Cluster-29 |  | W20 | SMP-WO-1521445 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2935 | 2935-Howara_2_PE_TASC | TASC | IRB-123-R | Indoor | 751 | 32.5336 | 35.9071 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 274 | Cluster-29 |  | W20 | SMP-WO-1521446 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  | ABC |  |  | Approved | no need to Add DPs for 5G | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2943 | 2943-Petra_St_End_PF_TASC_O | TASC | IRB-357-R | Outdoor |  | 32.5325 | 35.8885 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 275 | Cluster-29 |  | W20 | SMP-WO-1521447 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
2947 | 2947-Howara_East_PE_EBand_TASC_O | TASC | IRB-406-R | Outdoor |  | 32.5267 | 35.9136 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 276 | Cluster-29 |  | W20 | SMP-WO-1521448 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | T2 | [6 empty] | Downloaded
2915 | 2915-Petra_Rd_TL_PE_TASC_Relo_O | TASC | IRB-514-R | Outdoor |  | 32.5264 | 35.8973 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 277 | Cluster-29 |  | W20 | SMP-WO-1521449 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 5 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4413 | 4413-Hay_Torkman_Irbid_PE_EBand_TASC | TASC | IRB-249-R | Indoor | 2141 | 32.5594 | 35.8252 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 278 | Cluster-44 |  | W20 | SMP-WO-1521450 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes | [6 empty] | Mofeed |  |  |  | Downloaded
2929 | 2929-Ramtha_2_PC_Fiber_TASC | TASC | IRB-110-R | Indoor | 659 | 32.5442 | 36.0052 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 279 | Cluster-29 |  | W20 | SMP-WO-1521451 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Change the solution for the requested new DP and recheck the BTS Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-01 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4470 | 4470-Irbid_Mahajer_CRL_PF_TASC_O | TASC | IRB-471-R | Outdoor |  | 32.5741 | 35.8405 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 280 | Cluster-44 |  | W20 | SMP-WO-1521452 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes | [6 empty] | Mofeed |  |  |  | Downloaded
4437 | 4437-Barha_Almarj_Ave_PF_EBand_TASC_O | TASC | IRB-405-R | Outdoor |  | 32.5709 | 35.837 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 281 | Cluster-44 |  | W21 | SMP-WO-1521453 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes | [10 empty] | Downloaded
4421 | 4421-Quds_St_Irbid_PC_EBand_O | TASC | IRB-18-R | Outdoor | 613 | 32.569 | 35.8415 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 282 | Cluster-44 |  | W21 | SMP-WO-1521454 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes | [10 empty] | Downloaded
4580 | 4580-Mustaba_East_PF_EBand_TASC_O | TASC | JRS-103-R | Outdoor |  | 32.1873 | 35.8713 | Jarash | Pole |  |  |  |  | ThinLayer | PO3 | 283 | Cluster-45 |  | W21 | SMP-WO-1521455 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4594 | 4594-Mustaba_PC_Fiber_TASC | TASC | JRS-30-R | Indoor | 792 | 32.1854 | 35.8551 | Jarash | Tower |  |  |  |  | ThinLayer | PO3 | 284 | Cluster-45 |  | W21 | SMP-WO-1521456 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
4593 | 4593-Mustaba_Bridge_PD_Fiber_TASC_O | TASC | JRS-82-R | Outdoor |  | 32.1834 | 35.8497 | Jarash | Tower |  |  |  |  | ThinLayer | PO3 | 285 | Cluster-45 |  | W21 | SMP-WO-1521457 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-05 | Yes | Dismantle 2nd L1800 RRU | L1800+ RRU |  | RFI |  |  | Laith |  |  |  | Downloaded
4553 | 4553-Philadelphia_Uni_Nursery_PE_Fiber_TASC_O | TASC | AMW-1049-R | Outdoor |  | 32.1642 | 35.8526 | Balqa | Pole |  |  |  |  | ThinLayer | PO3 | 286 | Cluster-45 |  | W21 | SMP-WO-1521458 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C | 5G | 2 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
4595 | 4595-Rumman_Hill_PE_Fiber_O | TASC | JRS-47-G | Outdoor |  | 32.1639 | 35.8474 | Balqa | Tower |  |  |  |  | ThinLayer | PO3 | 287 | Cluster-45 |  | W21 | SMP-WO-1521459 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4448 | 4448-Quds_St_End_PE_TASC_O | TASC | IRB-402-R | Outdoor |  | 32.5659 | 35.8326 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 288 | Cluster-44 |  | W21 | SMP-WO-1521460 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-21 | Yes | [6 empty] | Laith |  |  |  | Downloaded
886 | 886-Karak_Thanieh_Market_PD_Fiber_TASC_O | TASC | KRK-186-R | Outdoor |  | 31.1708 | 35.7276 | Karak | Pole |  |  |  |  | ThinLayer | PO3 | 289 | Cluster-8 |  | W21 | SMP-WO-1521461 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
885 | 885-Thanieh_Bus_Station_PE_Fiber_TASC_O | TASC | KRK-184-R | Outdoor |  | 31.1666 | 35.735 | Karak | Pole |  |  |  |  | ThinLayer | PO3 | 290 | Cluster-8 |  | W21 | SMP-WO-1521462 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved | Wrong in BTS sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2820 | 2820-FreeZone_Back_PF_TASC_O | TASC | ZRQ-194-R | Outdoor |  | 32.1053 | 36.2155 | Zarqa | Pole |  |  |  |  | ThinLayer | PO3 | 291 | Cluster-28 |  | W21 | SMP-WO-1521463 | Al-Tawseaa |  |  | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-17 | Yes |  |  |  | T3 |  |  | Laith |  |  |  | Downloaded
2810 | 2810-Delail_Ent_PE_TASC | TASC | ZRQ-120-G | Indoor | 569 | 32.0933 | 36.2407 | Zarqa | Tower |  |  |  |  | ThinLayer | PO3 | 292 | Cluster-28 |  | W21 | SMP-WO-1521464 | Al-Tawseaa |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-18 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI |  |  | Laith |  |  |  | Downloaded
2834 | 2834-FreeZone_PA_Fiber_TASC | TASC | ZRQ-185-G | Indoor | 1533 | 32.085 | 36.2126 | Zarqa | Tower |  |  |  |  | ThinLayer | PO3 | 293 | Cluster-28 |  | W21 | SMP-WO-1521465 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  | AB |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Pending | Approved | 2025-07-17 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2942 | 2942-Ramtha_Hadeqa_Camp_PD_Fiber_TASC_O | TASC | IRB-358-R | Outdoor | 2201 | 32.532 | 36.0262 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 294 | Cluster-29 |  | W21 | SMP-WO-1521466 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-11 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2974 | 2974-Hassan_Ind_North_PF_TASC_O | TASC | IRB-491-R | Outdoor |  | 32.5048 | 36.0303 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 295 | Cluster-29 |  | W21 | SMP-WO-1521467 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2938 | 2938-Hassan_Ind_3_PC_Fiber_TASC | TASC | IRB-178-G | Indoor | 692 | 32.5002 | 36.03 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 296 | Cluster-29 |  | W21 | SMP-WO-1521468 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | C |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
2953 | 2953-Hassan_Ind_WaterTank_PD_Fiber_O | TASC | IRB-359-R | Outdoor |  | 32.4988 | 36.0218 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 297 | Cluster-29 |  | W21 | SMP-WO-1521469 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | T3 |  |  | Laith |  |  |  | Downloaded
2945 | 2945-Ramtha_Daraa_Border_PE_Fiber_TASC | TASC | IRB-255-R | Indoor | 2147 | 32.5758 | 36.0382 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 298 | Cluster-29 |  | W21 | SMP-WO-1521470 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B | 5G | 2 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
4408 | 4408-Barha_Irbid_Ring_Rd_PF_O | TASC | IRB-564-R | Outdoor |  | 32.5835 | 35.8162 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 299 | Cluster-44 |  | W21 | SMP-WO-1521471 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
4465 | 4465-Barha_Aban_PD_TASC_O | TASC | IRB-446-R | Outdoor |  | 32.5769 | 35.8245 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 300 | Cluster-44 |  | W21 | SMP-WO-1521472 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
4407 | 4407-Barha_3_PC_EBand_TASC | TASC | IRB-204-R | Indoor | 791 | 32.5736 | 35.829 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 301 | Cluster-44 |  | W21 | SMP-WO-1521473 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 5 |  | ABC |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
1423 | 1423-Ajloun_Bus_Station_PF_O | TASC | AJL-61-R | Outdoor |  | 32.3319 | 35.753 | Ajloun | Pole |  |  |  |  | ThinLayer | PO3 | 302 | Cluster-14 |  | W21 | SMP-WO-1521474 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-11 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1410 | 1410-Rabad_PC_TASC | TASC | AJL-4-G | Indoor | 657 | 32.3296 | 35.7442 | Ajloun | Tower |  |  |  |  | ThinLayer | PO3 | 303 | Cluster-14 |  | W21 | SMP-WO-1521475 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Obieda | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
4427 | 4427-Barha_4_PE_TASC_O | TASC | IRB-287-R | Outdoor |  | 32.5661 | 35.8222 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 304 | Cluster-44 |  | W21 | SMP-WO-1521476 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes | [10 empty] | Downloaded
726 | 726-Maan_Big_Msq_PF_EBand_TASC_O | TASC | MAN-209-R | Outdoor |  | 30.1992 | 35.7345 | Ma'an | Pole |  |  |  |  | ThinLayer | PO3 | 305 | Cluster-7 |  | W21 | SMP-WO-1521477 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
742 | 742-Maan_CTR_PE_EBand_TASC_O | TASC | MAN-27-R | Outdoor | 903 | 30.1949 | 35.7351 | Ma'an | Tower |  |  |  |  | ThinLayer | PO3 | 306 | Cluster-7 |  | W22 | SMP-WO-1521478 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved |  | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
2978 | 2978-Ramtha_East_Ave_PF_TASC_O | TASC | IRB-520-R | Outdoor |  | 32.552 | 36.0277 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 307 | Cluster-29 |  | W22 | SMP-WO-1521479 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
5803 | 5803-Tafilah_2_PC_Fiber_TASC | TASC | TAF-10-R | Indoor | 853 | 30.8372 | 35.6031 | Tafila | Tower |  |  |  |  | ThinLayer | PO3 | 308 | Cluster-58 |  | W22 | SMP-WO-1521480 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  | ABC |  |  | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2418 | 2418-Zabda_Mosque_Irbid_PF_Manage_O | ZAIN/M | IRB-510-R | Outdoor |  | 32.5402 | 35.8323 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 309 | Cluster-24 |  | W22 | SMP-WO-1521481 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-07 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4629 | 4629-Wadi_AlGhafr_Irbid_PF_O | TASC | IRB-250-R | Outdoor |  | 32.5105 | 35.8415 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 310 | Cluster-46 |  | W22 | SMP-WO-1521482 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
1477 | 1477-Jerash_South_Ent_PE_Fiber_O | TASC | JRS-46-R | Outdoor |  | 32.2709 | 35.8917 | Jarash | Pole |  |  |  |  | ThinLayer | PO3 | 311 | Cluster-14 |  | W22 | SMP-WO-1521483 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4442 | 4442-Irbid_Camp_North_PD_Fiber_TASC_O | TASC | IRB-326-R | Outdoor |  | 32.5656 | 35.8465 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 312 | Cluster-44 |  | W22 | SMP-WO-1521484 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
4482 | 4482-AlOdeh_Irbid_Camp_Mid_O | TASC | IRB-583-R | Outdoor |  | 32.5625 | 35.8517 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 313 | Cluster-44 |  | W22 | SMP-WO-1521485 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
4481 | 4481-Hakama_St_Market_PF_TASC_O | TASC | IRB-435-R | Outdoor |  | 32.5589 | 35.8507 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 314 | Cluster-44 |  | W22 | SMP-WO-1521486 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
4480 | 4480-AlOdeh_Irbid_Camp_End_O | TASC | IRB-584-R | Outdoor |  | 32.5664 | 35.8541 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 315 | Cluster-44 |  | W22 | SMP-WO-1521487 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
4426 | 4426-Irbid_Camp_West_PF_TASC_O | TASC | IRB-521-R | Outdoor |  | 32.5628 | 35.8465 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 316 | Cluster-44 |  | W22 | SMP-WO-1521488 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes | [6 empty] | Mofeed |  |  |  | Downloaded
2411 | 2411-Irbid_Mahakem_Rising_PE_TASC_O | TASC | IRB-409-R | Outdoor |  | 32.5298 | 35.8496 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 317 | Cluster-24 |  | W22 | SMP-WO-1521489 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2404 | 2404-Yarmouk_CRL_PA_Fiber_TASC | TASC | IRB-54-R | Indoor | 609 | 32.5419 | 35.8506 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 318 | Cluster-24 |  | W22 | SMP-WO-1521490 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-05 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2432 | 2432-Yarmouk_Uni_PB_Fiber_TASC | TASC | IRB-81-R | Indoor | 603 | 32.5391 | 35.8514 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 319 | Cluster-24 |  | W22 | SMP-WO-1521491 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes |  |  |  | T3 |  |  | Mofeed |  |  |  | Downloaded
2410 | 2410-Yarmouk_St_2_PC_Fiber_TASC | TASC | IRB-60-R | Indoor | 725 | 32.5364 | 35.8517 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 320 | Cluster-24 |  | W22 | SMP-WO-1521492 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2452 | 2452-Huston_HSG_Back_PE_TASC_O | TASC | IRB-465-R | Outdoor |  | 32.5347 | 35.8502 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 321 | Cluster-24 |  | W22 | SMP-WO-1521493 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-12 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2439 | 2439-Irbid_Badiaa_CRL_PE_O | TASC | IRB-346-R | Outdoor |  | 32.5283 | 35.8453 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 322 | Cluster-24 |  | W22 | SMP-WO-1521494 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4215 | 4215-Zarqa_Ent_PB_Fiber_TASC | TASC | ZRQ-45-R | Indoor | 541 | 32.0605 | 36.0923 | Zarqa | Tower |  |  |  |  | ThinLayer | PO3 | 323 | Cluster-42 |  | W22 | SMP-WO-1521495 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4229 | 4229-Bab_Wad_PB_Fiber_TASC | TASC | ZRQ-145-R | Indoor | 568 | 32.0666 | 36.0885 | Zarqa | Pole |  |  |  |  | ThinLayer | PO3 | 324 | Cluster-42 |  | W22 | SMP-WO-1521496 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-08 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4203 | 4203-Luqman_PE_Fiber_TASC_Relo_O | TASC | ZRQ-405-R | Outdoor |  | 32.0642 | 36.09 | Zarqa | Pole |  |  |  |  | ThinLayer | PO3 | 325 | Cluster-42 |  | W22 | SMP-WO-1521497 | Al-Tawseaa |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4207 | 4207-Zarqa_CTR_PE_Fiber_TASC | TASC | ZRQ-37-R | Indoor | 522 | 32.0641 | 36.0856 | Zarqa | Tower |  |  |  |  | ThinLayer | PO3 | 326 | Cluster-42 |  | W22 | SMP-WO-1521498 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4231 | 4231-Saada_St_PF_TASC | TASC | ZRQ-146-R | Indoor | 574 | 32.0633 | 36.0906 | Zarqa | Tower |  |  |  |  | ThinLayer | PO3 | 327 | Cluster-42 |  | W22 | SMP-WO-1521499 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4213 | 4213-Zarqa_National_Paints_PF_TASC | TASC | ZRQ-173-R | Indoor | 589 | 32.0601 | 36.0885 | Zarqa | Pole |  |  |  |  | ThinLayer | PO3 | 328 | Cluster-42 |  | W22 | SMP-WO-1521500 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | M. Al-Amro | Approved |  | Karam Jaber & Akram Abdelrahim | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-11 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4445 | 4445-Irbid_Zabda_CRL_PE_EBand_TASC_O | TASC | IRB-320-R | Outdoor |  | 32.5523 | 35.8423 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 329 | Cluster-44 |  | W22 | SMP-WO-1521501 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
4411 | 4411-Rasheed_St_Irbid_PD_EBand_TASC | TASC | IRB-61-R | Indoor | 612 | 32.551 | 35.845 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 330 | Cluster-44 |  | W22 | SMP-WO-1521502 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
4469 | 4469-Irbid_Manara_District_O | TASC | IRB-573-R | Outdoor |  | 32.5484 | 35.8473 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 331 | Cluster-44 |  | W24 | SMP-WO-1521503 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 3 |  |  |  |  | Approved |  | Waed | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
2413 | 2413-Zamzam_Irbid_PE_TASC | TASC | IRB-154-R | Indoor | 746 | 32.546 | 35.8478 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 332 | Cluster-24 |  | W24 | SMP-WO-1521504 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes |  |  |  | T3 |  |  | Najjar |  |  |  | Downloaded
4669 | 4669-Huson_Camp_East_PF_TASC_O | TASC | IRB-530-R | Outdoor |  | 32.478 | 35.9098 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 333 | Cluster-46 |  | W24 | SMP-WO-1521505 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4688 | 4688-Huson_Camp_Mid_PF_EBand_TASC_O | TASC | IRB-531-R | Outdoor |  | 32.4765 | 35.9051 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 334 | Cluster-46 |  | W24 | SMP-WO-1521506 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  | Need contact number |  | RFI | [6 empty] | Downloaded
4692 | 4692-Huson_Camp_South_PF_TASC_O | TASC | IRB-537-R | Outdoor |  | 32.473 | 35.903 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 335 | Cluster-46 |  | W24 | SMP-WO-1521507 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4440 | 4440-Huson_St_PD_Fiber_TASC | TASC | IRB-89-R | Indoor | 671 | 32.5544 | 35.8507 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 336 | Cluster-44 |  | W24 | SMP-WO-1521508 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
2454 | 2454-Irbid_Ammar_Bakery_PE_TASC_O | TASC | IRB-494-R | Outdoor |  | 32.5525 | 35.8569 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 337 | Cluster-24 |  | W24 | SMP-WO-1521509 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved | The attached TSSR related to another site Update: approved. | Zaid | Approved |  | M. Al-Amro | Approved | The attached TSSR related to another site | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong attachment file for different site Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-11 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
2435 | 2435-Qubeh_CRL_MGS_PE_TASC_O | TASC | IRB-278-R | Outdoor |  | 32.5441 | 35.8584 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 338 | Cluster-24 |  | W24 | SMP-WO-1521510 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
480 | 480-Irbid_AlKarama_Top_O | TASC | IRB-606-R | Outdoor |  | 32.578 | 35.8606 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 339 | Cluster-4 |  | W24 | SMP-WO-1521511 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
2445 | 2445-SOS_Irbid_PA_Fiber | TASC | IRB-511-R | Indoor | 2200 | 32.5431 | 35.8628 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 340 | Cluster-24 |  | W24 | SMP-WO-1521512 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2409 | 2409-Arbella_Mall_Irbid_PE_Fiber_DIBS_Manage | ZAIN/M | IRB-210-R | Indoor | 2121 | 32.5384 | 35.8628 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 341 | Cluster-24 |  | W24 | SMP-WO-1521513 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 | D | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-07-17 | Yes |  |  |  | T3 | [6 empty] | Downloaded
444 | 444-Zubeir_St_Hanenah_PB_Fiber_TASC | TASC | IRB-156-R | Indoor | 757 | 32.5786 | 35.8578 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 342 | Cluster-4 |  | W24 | SMP-WO-1521514 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
4478 | 4478-Hay_Matareq_East_PE_Fiber_TASC_O | TASC | IRB-474-R | Outdoor |  | 32.5769 | 35.8536 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 343 | Cluster-44 |  | W24 | SMP-WO-1521515 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | [10 empty] | Downloaded
3755 | 3755-Salt_CTR_PF_TASC | TASC | BLQ-18-R | Indoor | 1539 | 32.0385 | 35.7292 | Balqa | Pole |  |  |  |  | ThinLayer | PO3 | 344 | Cluster-37 |  | W24 | SMP-WO-1521516 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
2428 | 2428-Badiaa_Hospital_Rising_PF_O | TASC | IRB-309-R | Outdoor |  | 32.535 | 35.8384 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 345 | Cluster-24 |  | W24 | SMP-WO-1521517 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
2456 | 2456-Doctors_HSG_Irbid_PE_TASC_O | TASC | IRB-436-R | Outdoor |  | 32.5349 | 35.8432 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 346 | Cluster-24 |  | W24 | SMP-WO-1521518 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2434 | 2434-Badiaa_Hospital_East_PC_Fiber_TASC | TASC | IRB-83-R | Indoor | 700 | 32.5306 | 35.8412 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 347 | Cluster-24 |  | W24 | SMP-WO-1521519 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-07 | Yes |  |  |  | RFI |  |  | Najjar |  |  |  | Downloaded
2402 | 2402-Badiaa_Hospital_PD_EBand_TASC_O | TASC | IRB-194-R | Outdoor |  | 32.5286 | 35.8356 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 348 | Cluster-24 |  | W24 | SMP-WO-1521520 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/C/D | 5G | 4 |  | ABC |  |  | Released |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | T3 |  |  | Najjar |  |  |  | Downloaded
4405 | 4405-Lebanon_CTR_PB_TASC | TASC | IRB-150-R | Indoor | 743 | 32.5567 | 35.8535 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 349 | Cluster-44 |  | W24 | SMP-WO-1521521 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes | [10 empty] | Downloaded
1509 | 1509-Madaba_PA_Fiber_TASC | TASC | MAD-9-G | Indoor | 233 | 31.7143 | 35.7941 | Madaba | Tower |  |  |  |  | ThinLayer | PO3 | 350 | Cluster-15 |  | W24 | SMP-WO-1521522 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved |  | Yes |  |  |  | T3 | [6 empty] | Downloaded
4439 | 4439-Queen_Nour_CRL_PA_Fiber_TASC | TASC | IRB-88-R | Indoor | 652 | 32.5569 | 35.863 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 351 | Cluster-44 |  | W24 | SMP-WO-1521523 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes | [10 empty] | Downloaded
2448 | 2448-Hussein_Sport_Club_PE_Fiber_TASC_O | TASC | IRB-433-R | Outdoor |  | 32.5536 | 35.8599 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 352 | Cluster-24 |  | W24 | SMP-WO-1521524 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved | Changing the solution on sector D is needed to avoid blockage by installing 12-port on the free DP and AVQC on the short arm DP. Power solution needs to be replaced with: FPFH100A:3AVQC+1 or 2 AHEB, FPFH30A: 2 or 3 AHEB edit "Need DP No Need" | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-11 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2450 | 2450-East_Irbid_PD_Fiber_TASC | TASC | IRB-91-R | Indoor | 606 | 32.5507 | 35.8614 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 353 | Cluster-24 |  | W24 | SMP-WO-1521525 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | T3 |  |  | Laith |  |  |  | Downloaded
2423 | 2423-Yarmouk_Tarbieh_PF_TASC_O | TASC | IRB-292-R | Outdoor |  | 32.5388 | 35.8546 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 354 | Cluster-24 |  | W24 | SMP-WO-1521526 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-07-17 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2424 | 2424-Irbid_Hay_Janouby_PE_EBand_TASC | TASC | IRB-74-R | Indoor | 605 | 32.5488 | 35.851 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 355 | Cluster-24 |  | W24 | SMP-WO-1521527 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-03 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2406 | 2406-Irbid_Shop_PE_TASC_O | TASC | IRB-56-R | Outdoor | 615 | 32.5456 | 35.8561 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 356 | Cluster-24 |  | W25 | SMP-WO-1521528 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-20 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2444 | 2444-Prince_Hassan_Stadium_PC_Fiber_TASC | TASC | IRB-164-R | Indoor | 749 | 32.5332 | 35.8651 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 357 | Cluster-24 |  | W25 | SMP-WO-1521529 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | T4 |  |  | Laith |  |  |  | Downloaded
2407 | 2407-Yarmouk_Uni_South_Gate_PC_Fiber_TASC | TASC | IRB-215-R | Indoor | 717 | 32.5331 | 35.8564 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 358 | Cluster-24 |  | W25 | SMP-WO-1521530 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2417 | 2417-Edoon_Economic_College_PE_TASC | TASC | IRB-265-R | Indoor | 2151 | 32.5296 | 35.856 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 359 | Cluster-24 |  | W25 | SMP-WO-1521531 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
3706 | 3706-Salt_PC_Fiber_TASC | TASC | BLQ-5-G | Indoor | 140 | 32.0363 | 35.7253 | Balqa | Tower |  |  |  |  | ThinLayer | PO3 | 360 | Cluster-37 |  | W25 | SMP-WO-1521532 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | AB |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-29 | Yes |  |  |  | T4 |  |  | Laith |  |  |  | Downloaded
1573 | 1573-Madaba_CTR_PD_Fiber_O | TASC | MAD-220-R | Outdoor |  | 31.7193 | 35.7938 | Madaba | Pole |  |  |  |  | ThinLayer | PO3 | 361 | Cluster-15 |  | W25 | SMP-WO-1521533 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Zaid | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
2422 | 2422-Irbid_CC_Mall_PE_Fiber_IBS_Zain | ZAIN/M | IRB-282-R | Indoor | 2158 | 32.5358 | 35.8651 | Irbid | [5 empty] | ThinLayer | PO3 | 362 | Cluster-24 |  | W25 | SMP-WO-1521534 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 | IBS |  |  |  | Released |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved |  | Yes |  | Need arrangement before |  | T4
2427 | 2427-East_Irbid_2_PC_EBand_TASC | TASC | IRB-192-R | Indoor | 777 | 32.5451 | 35.8733 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 363 | Cluster-24 |  | W25 | SMP-WO-1521535 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-04-22 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2453 | 2453-Justice_Palace_North_PE_TASC_O | TASC | IRB-493-R | Outdoor |  | 32.5449 | 35.867 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 364 | Cluster-24 |  | W25 | SMP-WO-1521536 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-20 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2436 | 2436-Barda_Court_Back_Irbid_PD_EBand_TASC_O | TASC | IRB-302-R | Outdoor |  | 32.5425 | 35.8782 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 365 | Cluster-24 |  | W25 | SMP-WO-1521537 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved | Please to mention that we need to replace DP on sector B with 2 separated DPs. please to edit "Need DP No Need" . We need only one fuse for 2nd FPFH | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | B | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2408 | 2408-Amman_Buses_CPLX_Irbid_PC_EBand_TASC | TASC | IRB-231-R | Indoor | 2110 | 32.5401 | 35.8704 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 366 | Cluster-24 |  | W25 | SMP-WO-1521538 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | 4 |  | ABC |  |  | Released |  | Zaid | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Pending | Approved | 2025-07-17 | Yes |  |  |  | T4 | [6 empty] | Downloaded
2443 | 2443-Rotana_Hala_Irbid_PD_TASC_O | TASC | IRB-371-R | Outdoor |  | 32.5311 | 35.8698 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 367 | Cluster-24 |  | W25 | SMP-WO-1521539 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved | Wrong data in civil sheet Approved | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
2403 | 2403-Zabda_HSG_Irbid_PE | TASC | IRB-261-R | Indoor | 2152 | 32.5323 | 35.8317 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 368 | Cluster-24 |  | W25 | SMP-WO-1521540 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-19 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2451 | 2451-Sahara_CRL_Ave_PE_TASC_O | TASC | IRB-445-R | Outdoor |  | 32.5248 | 35.845 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 369 | Cluster-24 |  | W25 | SMP-WO-1521541 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-05 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2447 | 2447-Irbid_Istiqlal_Gardens_PE_EBand_TASC_O | TASC | IRB-374-R | Outdoor |  | 32.5248 | 35.8419 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 370 | Cluster-24 |  | W25 | SMP-WO-1521542 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
4608 | 4608-Awwadeen_Castle_Irbid_PE_O | TASC | IRB-300-R | Outdoor |  | 32.5181 | 35.8445 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 371 | Cluster-46 |  | W25 | SMP-WO-1521543 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C/D | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-04 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4690 | 4690-Edoon_East_Ave_PF_EBand_TASC_O | TASC | IRB-533-R | Outdoor |  | 32.5143 | 35.8647 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 372 | Cluster-46 |  | W25 | SMP-WO-1521544 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4646 | 4646-Edoon_Hay_Ghrabeyeh_PF_O | TASC | IRB-378-R | Outdoor |  | 32.5116 | 35.8521 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 373 | Cluster-46 |  | W25 | SMP-WO-1521545 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4634 | 4634-Huson_Edoun_PA_Fiber_TASC | TASC | IRB-114-G | Indoor | 623 | 32.5062 | 35.8628 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 374 | Cluster-46 |  | W25 | SMP-WO-1521546 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  | AB |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes | Configuration Removed L1800+ | L1800+ RRU |  | RFI | [6 empty] | Downloaded
4680 | 4680-Huson_Rd_Ashour_Gas_Station_PF_TASC_O | TASC | IRB-524-R | Outdoor |  | 32.5034 | 35.8757 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 375 | Cluster-46 |  | W25 | SMP-WO-1521547 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
2431 | 2431-Irbid_Wasfi_Tal_St_PD_EBand_TASC_O | TASC | IRB-348-R | Outdoor |  | 32.5353 | 35.8776 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 376 | Cluster-24 |  | W25 | SMP-WO-1521548 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved | 2025-05-17 | Yes |  |  |  | RFI |  |  | Mofeed |  |  |  | Downloaded
2446 | 2446-North_Rahbat_Ave_PD_O | TASC | IRB-325-R | Outdoor |  | 32.5269 | 35.865 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 377 | Cluster-24 |  | W25 | SMP-WO-1521549 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | 3 |  | ABC |  |  | Approved |  | Moath | Approved |  | M. Al-Amro | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-05-28 | Yes |  |  |  | RFI |  |  | Laith |  |  |  | Downloaded
4664 | 4664-Edoon_Clinics_Ave_West_PE_TASC_O | TASC | IRB-360-R | Outdoor |  | 32.5236 | 35.8504 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 378 | Cluster-46 |  | W25 | SMP-WO-1521550 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | Yes | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
4678 | 4678-Rosary_Hospital_Back_MK_PE_TASC_O | TASC | IRB-481-R | Outdoor |  | 32.5224 | 35.8638 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 379 | Cluster-46 |  | W25 | SMP-WO-1521551 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4615 | 4615-Edoon_City_1_PC_EBand_TASC | TASC | IRB-191-R | Indoor | 776 | 32.5213 | 35.8539 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 380 | Cluster-46 |  | W25 | SMP-WO-1521552 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  | ABC |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4621 | 4621-Rosary_Hospital_Irbid_PF_TASC | TASC | IRB-233-R | Indoor | 2112 | 32.5206 | 35.8679 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 381 | Cluster-46 |  | W26 | SMP-WO-1521553 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 3 |  |  |  |  | Approved |  | Moath | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
6081 | 6081-Edoun_Oyoun_District_O | TASC | IRB-571-R | Outdoor |  | 32.5194 | 35.8577 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 382 | Cluster-46 |  | W26 | SMP-WO-1521554 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4650 | 4650-Edoon_Hay_Wateyyeh_PF_TASC_O | TASC | IRB-384-R | Outdoor |  | 32.5159 | 35.8505 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 383 | Cluster-46 |  | W26 | SMP-WO-1521555 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-06-12 | Yes |  |  |  | RFI | [6 empty] | Downloaded
4679 | 4679-Edoon_Hospital_Ave_PF_TASC_O | TASC | IRB-487-R | Outdoor |  | 32.4966 | 35.8663 | Irbid | Pole |  |  |  |  | ThinLayer | PO3 | 384 | Cluster-46 |  | W26 | SMP-WO-1521556 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
4403 | 4403-Irbid_PA_Fiber_TASC | TASC | IRB-53-R | Indoor | 602 | 32.557 | 35.8464 | Irbid | Tower |  |  |  |  | ThinLayer | PO3 | 385 | Cluster-44 |  | W26 | SMP-WO-1521557 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | 4 |  | ABC |  |  | Approved |  | Obieda | Approved |  | Omar Sami | Released |  | Thabet Jaradat & Ahmad Hajdawood | Released |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-07-17 | Yes | [6 empty] | Mofeed |  |  |  | Downloaded
1481 | 1481-Ain_Jana_Ajloun_PD | TASC | AJL-27-R |  | 2157 | 32.3319 | 35.7611 | Ajloun | Pole |  |  |  |  | ThinLayer | PO3 | 386 | Cluster-14 |  |  | SMP-WO-1570626 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
1407 | 1407-Wadi_Deir_Sharqy_PE | TASC | JRS-37-R |  | 2139 | 32.2883 | 35.8995 | Jarash | Pole |  |  |  |  | ThinLayer | PO3 | 387 | Cluster-14 |  |  | SMP-WO-1570627 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
1570 | 1570-Madaba_4_PB_Fiber_TASC | TASC | MAD-65-R |  | 237 | 31.7176 | 35.8011 | Madaba | Tower |  |  |  |  | ThinLayer | PO3 | 388 | Cluster-15 |  |  | SMP-WO-1570628 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
3318 | 3318-Karak_Work_Ministry_PE_Fiber_Manage_O | ZAIN/M | KRK-130-R | Karak |  | 31.158 | 35.7294 | Karak | Pole |  |  |  |  | ThinLayer | PO3 | 389 | Cluster-33 |  |  | SMP-WO-1570629 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | T4 | [6 empty] | Downloaded
5892 | 5892-Tafilah_As_Salma_Ave_PF_Fiber_TASC_O | TASC | TAF-42-R | Tafila |  | 31.9226 | 35.784 | Tafila | Pole |  |  |  |  | ThinLayer | PO3 | 390 | Cluster-58 |  |  | SMP-WO-1570630 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C/D | 5G | [5 empty] | Released |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-07-22 |  |  |  |  | T4 | [6 empty] | Downloaded
859 | 859-Thanieh_Secondary_School_Back_O | TASC | KRK-308-R | Karak |  | 31.1647 | 35.7282 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 391 | Cluster-85 |  |  | SMP-WO-1570631 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
5883 | 5883-Barnees_Tafilah_PE_Fiber_TASC_O | TASC | TAF-31-R | Tafila |  | 30.8339 | 35.6174 | Tafila | Tower |  |  |  |  | ThinLayer | PO3 | 392 | Cluster-58 |  |  | SMP-WO-1570632 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
870 | 870-Thanieh_Karak_PD_Fiber_TASC_O | TASC | KRK-160-R | Karak |  | 31.1658 | 35.7229 | Karak | Tower |  |  |  |  | ThinLayer | PO3 | 393 | Cluster-87 |  |  | SMP-WO-1570633 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
5890 | 5890-Barnees_South_PF_Fiber_TASC_O | TASC | TAF-54-R | Tafila |  | 30.8308 | 35.6212 | Tafila | Tower |  |  |  |  | ThinLayer | PO3 | 394 | Cluster-58 |  |  | SMP-WO-1570634 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  | Yes |  |  |  | RFI | [6 empty] | Downloaded
772 | 772-Maan_Palestine_St_PF_TASC_O | TASC | MAN-189-R | Ma'an |  | 30.1937 | 35.729 | Ma'an | Tower |  |  |  |  | ThinLayer | PO3 | 395 | Cluster-77 |  |  | SMP-WO-1570635 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/C/D | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
719 | 719-Souq_Maan_PF_TASC_O | TASC | MAN-163-R | Ma'an |  | 30.2025 | 35.7331 | Ma'an | Pole |  |  |  |  | ThinLayer | PO3 | 396 | Cluster-71 |  |  | SMP-WO-1570636 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | [5 empty] | Approved |  | Obieda | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
1202 | 1202-Aqaba-Education-PC-Fiber-TASC | TASC | AQB-13-R |  | 856 | 29.5263 | 35.0046 | Aqaba | Tower |  |  |  |  | ThinLayer | PO3 | 397 | Cluster-12 |  |  | SMP-WO-1570637 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/D | 5G | [5 empty] | Approved |  | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
1222 | 1222-Aqaba-TCC-PF-Org-Manage-O | ZAIN/M | AQB-32-G |  | 871 | 29.5286 | 35.0041 | Aqaba | Tower |  |  |  |  | ThinLayer | PO3 | 398 | Cluster-12 |  |  | SMP-WO-1570638 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved |  |  |  | Sharing Site |  | RFI | [6 empty] | Downloaded
788 | 788-Public_Works_Maan_PF_EBand_TASC_O | TASC | MAN-147-R | Ma'an |  | 30.1991 | 35.7273 | Ma'an | Pole |  |  |  |  | ThinLayer | PO3 | 399 | Cluster-12 |  |  | SMP-WO-1570639 | AL-LEWAN FOR CONSTRUCTIVE CONT |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  | Obieda | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | [5 empty] | RFI | [6 empty] | Downloaded
1247 | 1247-Aqaba-Cornich-St-PE-EBand-TASC-O | TASC | AQB-209-R | Aqaba |  | 29.5235 | 35.002 | Aqaba | Pole |  |  |  |  | ThinLayer | PO3 | 400 | Cluster-12 |  |  | SMP-WO-1627776 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B/D | 5G | [5 empty] | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-08-03
1245 | 1245-Fayoumi-CTR-PC-Fiber-TASC | TASC | AQB-50-R | Aqaba | 866 | 29.5231 | 35.0031 | Aqaba | Pole |  |  |  |  | ThinLayer | PO3 | 401 | Cluster-12 |  |  | SMP-WO-1627777 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/D | 5G | [5 empty] | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-08-03
1253 | 1253-Souq-Aqaba-PF-TASC-O | TASC | AQB-217-R | Aqaba |  | 29.5257 | 35.0039 | Aqaba | Pole |  |  |  |  | ThinLayer | PO3 | 402 | Cluster-12 |  |  | SMP-WO-1627778 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | B | 5G | [5 empty] | Approved |  | Waed | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2025-08-03
605 | 605-Sahab_QIZ_PC_Fiber_TASC | TASC | AME-600-R | Amman | 1527 | 31.8712 | 35.9815 | Amman | Tower |  |  |  |  | ThinLayer | PO3 | 403 | Cluster-6 |  |  | SMP-WO-1627779 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | 5 | A | Approved | Approved | 2025-08-03
678 | 678-Sahab_Ind_End_PE_Fiber_TASC_O | TASC | AMS-236-G | Amman |  | 31.8482 | 36.0179 | Amman | Tower |  |  |  |  | ThinLayer | PO3 | 404 | Cluster-6 |  |  | SMP-WO-1627780 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | 5 | A | Approved | Approved | 2025-08-03
612 | 612-Sahab_Ind_PB_Fiber_Zain_TASC | TASC | AME-70-G | Amman | 131 | 31.8429 | 36.0154 | Amman | Tower |  |  |  |  | ThinLayer | PO3 | 405 | Cluster-6 |  |  | SMP-WO-1627781 | AL-LEWAN FOR CONSTRUCTIVE CONT | AL-LEWAN FOR CONSTRUCTIVE CONT |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | 5 | A | Approved | Approved | 2025-08-03 |  |  | Need Locker key / Missing
4109 | 4109-Aqaba-QIZ-PE-TASC | TASC | AQB-145-R | Aqaba | 958 | 29.5976 | 35.0344 | Aqaba | Pole | [10 empty] | SMP-WO-1636203 | Al-Tawseaa |  |  | Done |  |  | A/B/C | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | 5 | A | Approved | Approved | 2025-08-20 |  |  | Need Access/ Permission letter
334 | 334-Anany_CTR_PE_EBand_TASC | TASC | AME-32-R | Indoor | 261 | 35.9123 | 31.9551 | East Amman | Roof Top | husam aldiyn ratib eabd almuhsin alenany | 079/5532854 | Pole P4+P6+P2.4+P2.7 | 25 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | NEW | SMP-WO-1414299 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved | Sector B azimuth does not match the view New 12-ports antenna azimuth of sector C should match the existing one. update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-30 | Yes | W31 |  | 518 | RFI |  | Approved
302 | 302-3rd_CRL_Back_PC_Fiber_TASC | TASC | AME-2-R | Indoor | 97 | 35.9085 | 31.9597 | East Amman | Roof Top | yusraa muhamad eisaa dbsh |  | Tower T 6 | 21 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Digital | SMP-WO-1414594 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | One of Old cabinet need to be dismantled for Nokia's cabinet installation. Wrong Power Solution: Choose a power solution with 2 FPFH for Two C.B Mention that we will re-use the free DCDU C.B as a source for FPFH Wrong position for 5G Antenna. Update: approved | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 | Digital | 498 | RFI
301 | 301-King_Hussein_St_PD_Fiber_Manage | ZAIN/M | AME-1-R | Indoor | 156 | 35.9263 | 31.9579 | East Amman | Roof Top | sharikat ahmad yusf |  | Tower T 12 | 28 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Digital | SMP-WO-1414580 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Wrong power solution. Huw. Power table is missing. Update: Approved | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-05 | Yes | W32 | Digital | 512 | RFI
304 | 304-Diana_Hotel_PF_EBand_TASC | TASC | AME-4-R | Indoor | 204 | 35.9251 | 31.9523 | East Amman | Roof Top | nawal mustafaa ahmad shrf | 0779356538/0777781700 | Tower T 12 | 26 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414497 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Power solution incorrect; insufficient information about the connections on the other LLVD CBs. Update:Approved | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-08 | Yes | W32 | Digital | 509 | RFI
306 | 306-Islamic_College_PF_EBand_TASC | TASC | AME-5-R | Indoor | 224 | 35.9211 | 31.9506 | East Amman | Roof Top | hisan jamil salim zakariaaan wa awladha |  | Pole Tripod 6m*2+ Tripod 4m*1+P6*1 | 22 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Digital | SMP-WO-1414595 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved | Najeh Ghawanmeh: Double Check the Azimuth of Sec A Check the new Antenna Solution Azimuth of Sec A | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-05 | Yes | W32 | Digital | 512 | RFI
355 | 355-Motran_PF_TASC_O | TASC | AME-48-R | Outdoor |  | 35.9259 | 31.9482 | East Amman | Roof Top | mustafaa salih eabd alrahmin smar | 079-5589905/0775566259/0795024855 | Pole P6 | 18 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | NEW | SMP-WO-1414301 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 1 |  |  |  |  | Approved | Install the Nokia cabinet next to the Huawei cabinets Update:Approved | Obaidah & Zaid | Approved |  | M. Amro | Approved | Sector B azimuth does not match with the view Sector C M-tilt direction (Down) does not match with the clamp image What about sector E (2G), will be maintained as is ? Update: Same issues still exist (No changes) update: issues were tackled, but clarify if sector E 2G will be exposed any change | Rabie Otoum | Approved | civil SHEET civil sheet // Mast 1 overloaded | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-28 | Yes | W31 |  | 520 | RFI |  | Approved
343 | 343-Electricity_Company_PD_EBand_TASC | TASC | AME-41-R | Indoor | 384 | 35.9219 | 31.9528 | East Amman | Roof Top | husni ealia mahmud sharim | 06/4636775 079/5765156 | Pole P6 X 2 + P9 X1 | 18 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | NEW | SMP-WO-1414300 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Empty Cabinet should be dismantled. No need for DPs on all sectors + TDD should be sliding down on all sectors as: SecA with 30CM Sec.B&C with 50 cm. Update: Approved | Obaidah & Zaid | Approved |  | M. Amro | Approved | How much the TDD antennas will be slided down ? Provide a view images for TDD Provide images for the new TDD view if the difference in height is large ( more than 1 m) | Rabie Otoum | Approved | Mast 2 overloaded | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498 | RFI
314 | 314-Radisson_SAS_Tunnel_PD_Fiber_TASC | TASC | AME-541-R | Indoor | 1506 | 35.9044 | 31.9615 | East Amman | Roof Top | shfyq majid salih narmq | 0777/307055/0777307088 | Tower T 12 | 21 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414293 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Unsuitable cabinet location. Update->Incorrect value: number of CBs not used & unclear picture for rectifier to declare LLVD and BLVD. Pictures for Sector B are needed Update:Accept | Obaidah & Zaid | Approved |  | M. Amro | Approved | Azimuth of sector B (2-port) does not match the view update: issue was tackled | Rabie Otoum | Approved | no need for a DP | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-24 | Yes | W30 |  | 524 | RFI
315 | 315-Weibdeh_Gardens_PE_Fiber_TASC | TASC | AME-13-R | Indoor | 152 | 35.913 | 31.9595 | East Amman | Roof Top | eiz aldiyn hamid eumar hasunatan | 06/4636586 - 06/5159730 079/5723220 | Pole P6*3+ WallMount 3m*1 | 32 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414294 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | To install a Nokia cabinet in the free space next to the rectifier. Incorrect antenna solution. Check the availability to relocate sector B to the MW mast. incorrect power solution Update:Accept | Obaidah & Zaid | Approved |  | M. Amro | Approved | Sector A and B azimuth does not match the view M-tilt clamp direction data (down or up) mismatch with images Wrong sector B height Update: antenna base from roof top level of sector B still wrong update: issues were tackled | Rabie Otoum | Approved | location of the new Anntenas on the masts (civil table) Same note // civil table rejected | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-01 | Yes | W31 |  | 516 | RFI
326 | 326-Weibdeh_PB_Fiber_TASC | TASC | AME-24-R | Indoor | 231 | 35.9147 | 31.9572 | East Amman | Roof Top | rajayiy sawilm yaequb alkhuri | 06/4638992 | Pole P6 X 4 | 14 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414296 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Please to follow the power solution offline sheet for new power distribution. | Obaidah & Zaid | Approved |  | M. Amro | Approved | Mismatch between azimuth of sector C and the view modify the name of sector D to C under the M-tilt images Mismatch between M-tilt values and the inclinometer Mismatch between the new 12-port antenna azimuth and the existing values on sectors A and B Update: still there is mismatch between azimuth of sector C and the view Still mismatch between the new 12-port antenna azimuth and the existing values on sectors A and B update: still there is mismatch between azimuth of sector C and the view (We can discuss it) update: still there is mismatch between azimuth of sector C and the view (We can discuss it) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-28 | Yes | W31 |  | 520 | RFI |  | Approved
331 | 331-UL_Terra_Santa_College_PE_GPON_TASC_O | TASC | AME-1053-R | Outdoor |  | 35.9204 | 31.9572 | East Amman | Roof Top |  |  | Pole P9#2 | 12 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414297 | Ecotel |  | Requested | Done |  |  |  | 5G | 4 |  |  | Rejected | Rejected, Sec D Azimuth view doesn't match with the site view and the panorama Photos. | Approved | Incorrect power solution , there is no enough information about the connection on the other LLVD CBs! Update:Approved | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved | civil SHEET same note // civil sheet & table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-28 | Yes | W31 |  | 520 | RFI |  | Approved
313 | 313-Weibdeh_CRL_PD_Fiber_TASC | TASC | AME-609-R | Indoor | 1536 | 35.9275 | 31.9553 | East Amman | Roof Top | eadilat mahmud khamis ramadan | 079-5803375 | Pole P6 X 5 | 15 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414292 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | Ok , Proceed but make sure the old antenna on the same sector are on the same level (not side loop blocked each other) | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-28 | Yes | W31 |  | 520 | RFI |  | Approved
319 | 319-British_Council_PF_EBand_TASC_O | TASC | AME-639-R | Outdoor |  | 35.9254 | 31.9499 | East Amman | Roof Top | hudana khalil dawud eali muhyar | 06-4629564 079-9053765 | Pole P6X2 | 13 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414295 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Missing Huw. Power table.&Wrong arrows.New solution for 5G Antenna and 12 port antenna.&Renaming all sectors on BTS sheet for 5G solution.&Before submission the TSSR revise the power solution with TI. Update:Approved | Obaidah & Zaid | Approved |  | M. Amro | Approved | Najeh Ghawanmeh: Check the Tilt (mech.) of 2G Sec B | Rabie Otoum | Approved | Civil Requirment New | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-25 | Yes | W30 |  | 523 | RFI |  | Approved
308 | 308-Society_Market_PF_TASC_O | TASC | AME-6-R | Outdoor |  | 35.9219 | 31.9485 | East Amman | Roof Top | bashir ahmad eabdalrhim aldbas | 079-5560765 | Pole P9 X 1 + Tripod 3m X 1 + Tripod 2m x 1 | 13 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414290 | Ecotel |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved | Provide TSSR Excel Sheet Update: Sectors Names are A, C not A, B update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-01 | Yes | W31 |  | 516 | RFI
309 | 309-City_Hotel_PE_TASC | TASC | AME-7-R | Indoor | 202 | 35.9161 | 31.9544 | East Amman | Roof Top | fuad eabd alqadir naghuj | 079-6602033/0777-555512 | Tower T 9.5 | 25 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414291 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Unsuitable cabinet location. Update->Incorrect value: number of CBs not used & unclear picture for rectifier to declare LLVD and BLVD. Pictures for Sector B are needed Update:Accept | Obaidah & Zaid | Approved |  | M. Amro | Approved | clamp of sector B of 6-port antenna is not clear New 12-ports antennas azimuth does not match the exisiting Update: clamp image of sector B of 6-port antenna is not clear. The image should include the clamp and antenna Update: Notes were handled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-24 | Yes | W30 |  | 524 | RFI
332 | 332-Rujm_Malfouf_PE_GPON_BTS_Relo_O | TASC | AME-1071-R | Outdoor |  | 35.9049 | 31.9585 | East Amman | Roof Top | eiza aldiyn eabdalalah khaliyfatan | 077/270215 | Pole 9 * 3 | 18 | ThinLayer | P.O.2 | Group5T | Cluster-3 | 3rd crl | Traditional | SMP-WO-1414298 | Ecotel |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-28 | Yes | W31 |  | 520 | RFI
1724 | 1724-Jabal_Hussein_Mada_PF_TASC_O | TASC | AME-896-R | Outdoor |  | 35.9251 | 31.9621 | East Amman | Roof Top | ahmad eabd alhamid eabd allatif shamrukh | 797135781 | Pole P6X2 | 26 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414312 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  |  | Rejected | Rejected, Correction Compass photo & Tilt (mech.). | Approved | Dismantle old cabinet Sector A no need for DP. Be specified when replace DP from leg to another leg. Update:Accept | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-25 | Yes | W30 |  | 523 | RFI |  | Approved
1723 | 1723-Jabal_Hussein_PD_Fiber_TASC | TASC | AME-154-R | Indoor | 391 | 35.9278 | 31.9608 | East Amman | Roof Top | muhamad salih muhamad albasyuni | 06/4615320 077/4912310 | Pole P6 X 2 + Wall mounted Dp x 2 | 19 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414311 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  | Yes | Rejected | Rejected, Antenna information Not sequential by Tech, Correction Compass photo & Total Height of Antenna from Ground Level. | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | What is the need for the new Mast?? | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-25 | Yes | W30 |  | 523 | RFI |  | Approved
1701 | 1701-Wadi_Hadaddeh_2_PD_Fiber_TASC | TASC | AME-124-R | Indoor | 309 | 35.9306 | 31.9622 | East Amman | Roof Top | mahmud hasan eisaa alhindi | 06-5714529 | Pole P6 X 4 | 15 | ThinLayer | P.O.2 | Group6T | Cluster-17 |  | Traditional | SMP-WO-1414318 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  | Rejected | Rejected, Antenna information Not sequential by Tech., SEC | Approved | Power solution should be for 5 Sectors. Check photos between SecA & SecB. Update: Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | Civil sheet does not match with BTS sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-08 | Yes | W32 |  | 509 | RFI
1715 | 1715-Hussein_Camp_2_PF_TASC | TASC | AME-485-R | Indoor | 451 | 35.9246 | 31.9652 | East Amman | Roof Top | eabd alqadir hasan eabd alhady | 06-4646541 079-6651010 | Pole P6X3+Wall Mounting3m | 18 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414304 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Wrong Civil & Antenna solution for Sector B Need more photos for sector B Update: Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | Dismantle 6 Antennas & Install 6 new // what is the need for the new Mast? | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492 | RFI
1725 | 1725-Hussein_Led_CPLX_PE_Fiber_TASC_O | TASC | AME-902-R | Outdoor |  | 35.9207 | 31.9701 | East Amman | Roof Top | jameiat alladi alkhayriat | 796048615 | Pole P9 | 22 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414313 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Reuse the free DP on Mast A S.A for S.B on Mast B. Mention that we need to use 63A C.B instead of 32A C.B. Update: Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-08 | Yes | W32 | Key From Zain | 509 | RFI
1720 | 1720-Hussein_Istiqlal_PE_Fiber_TASC_O | TASC | AME-766-R | Outdoor |  | 35.9171 | 31.9766 | East Amman | Roof Top | eisaa eabd alhadi iismaeil abu nhlt | 796904790 | Pole P9 x 3 | 24 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414309 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Sector C azimuth does not match the view Missing M-tilt data of sector C update: issues were tackled | Rabie Otoum | Approved | Mast 1 overloaded | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-31 | Yes | W31 |  | 517 | RFI
1738 | 1738-Justice_Palace_PF_EBand_ADIBS_O | ZAIN | AME-12-R | Outdoor |  | 35.9104 | 31.9616 | East Amman | Roof Top | sharikat dubayin lilansha at dhi.ma.m |  | Pole 6 | 13 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414316 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 | IBS-D |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | civil sheet // civil table // location for the new Antennas // poles details | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 | Access letter level 1 / Missmatch with LLD | 498 | RFI
1762 | 1762-Sayegh_PA_Fiber_DIBS_TASC | TASC | AME-53-R | Indoor | 168 | 35.9182 | 31.959 | East Amman | Roof Top | eabd alhamid rajab alsaaygh |  | Pole P6 X 6 | 15 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414321 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 5 | IBS-D | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Double Check the Azimuth of Sector B | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 | Key From Zain | 489 | RFI
1727 | 1727-Abdali_PF_EBand_TASC | TASC | AME-3-R | Indoor | 188 | 35.913 | 31.9656 | East Amman | Roof Top | dayirat almukhabarat aleamat |  | Pole P6 X 2 + Wall mount DP x 6 | 15 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414314 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Layout is missing 2g sector c is missing view for the proposed relocation is missing/ we may need a new mast. Merge DCDUs is needed /2*100A C.B is needed Update: approved. | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Sector B azimuth does not match the view update: issue was tackled | Rabie Otoum | Approved | civil SHEET | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-03 | Yes | W36 | Access letter | 483 | RFI
1722 | 1722-Aqarko_PD_EBand_DIBS_TASC | TASC | AME-299-R | Indoor | 194 | 35.9104 | 31.9665 | East Amman | Roof Top | alsharikat aleaqariat altijariat eaqarku | 06/5606186 | Pole P6 X 4 + Wall mounted Dp x 3 | IBS | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414310 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 | IBS-D | Yes |  |  | Approved | Wrong power solution. Wall mount PIC is missing. layout is missing. Update:Accepted | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Azimuth data does not match with view photos New antenna azimuth and height mismatch with audit data update: issues were tackled Note: mismatch between actual azimuth and the new is due to antennas location change | Rabie Otoum | Approved | Missing site pictures for the wall mounts | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 | Missmatch with LLD | 489 | RFI
1730 | 1730-UL_Hussein_Kindi_Hospital_PF_CDIBS_O | ZAIN | AMS-226-R | Outdoor |  | 35.912 | 31.969 | East Amman | Roof Top | mustashfaa alkanadi |  | Pole 9 | 12 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414315 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 | IBS-D |  |  |  | Approved | Concrete expansion may differ in real life. | Obaidah & Zaid | Approved | No solution has suggested for Sec A | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 | Missmatch with LLD | 492 | RFI
1719 | 1719-Firas_Traffic_PE_TASC | TASC | AME-140-R | Indoor | 16 | 35.9175 | 31.9681 | East Amman | Roof Top | mahmud hamadat mahmud eatyt | 06/5690531 | Pole P6*2+P9*1 | 24 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414308 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | Install the Nokia cabinet next to the Huawei cabinets Update:Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Sector B azimuth does not match with the view Sector C M-tilt direction (Down) does not match with the clamp image What about sector E (2G), will be maintained as is ? Update: Same issues still exist (No changes) update: issues were tackled, but clarify if sector E 2G will be exposed any change | Mo'taz Al-Khateeb | Approved | civil SHEET civil sheet // Mast 1 overloaded | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498 | RFI
1714 | 1714-MOH_PB_Fiber_TASC | TASC | AME-135-R | Indoor | 321 | 35.9158 | 31.973 | East Amman | Roof Top | ghalib ahmad fiad abwalifilat | 06/5667770 | Pole P9 X 3 + P6 X 4 | 18 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414303 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | no DP needed to add 5G | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | civil table // what is the need for 6DP?? | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-07-25 | Yes | W30 |  | 523 | RFI |  | Approved
1746 | 1746-Hussein_Sokaina_Sch_PF_TASC_O | TASC | AME-948-R | Outdoor |  | 35.9152 | 31.9697 | East Amman | Roof Top | muhamad nabil eabd allatif sakajha | 777316096 | Pole P9 + P6 | 20 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414319 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 5 |  |  |  |  | Approved | Power solution should be for 5 Sectors. Check photos between SecA & SecB. Update: Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Sector C azimuth does not match with the view update: issue was tackled | Mo'taz Al-Khateeb | Approved | civil sheet not | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-08 | Yes | W32 |  | 509 | RFI
1712 | 1712-Education_Ministry_1_PF_TASC_O | TASC | AME-10-R | Outdoor |  | 35.9148 | 31.9614 | East Amman | Roof Top | wizarat altarbiat waltaelim |  | Pole P2#1 + Tripod 3#1 + Tripod 2#1 | 9 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414302 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  |  | Rejected | Rejected, Antenna information Not sequential by Tech., Correction Compass photo & Tilt (mech.). | Approved | The ACOC location should be installed to the left of the Huawei cabinets Not mentioned to dismantle the 2 ports antenna on two sectors need new mast for sector C Update:Accept | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | civil SHEET civil sheets & requirements new | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-01 | Yes | W31 |  | 516 | RFI
1765 | 1765-Hussein_Mamounieh_PF_EBand_TASC | TASC | AME-744-R | Indoor | 1670 | 35.9187 | 31.9642 | East Amman | Roof Top | shaeban sulayman euthman eathman | 079-5210182 | Pole P6X3 | 16 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414323 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Sector are A, C not A, B Antennas clamp direction (Down) is wrong Update: Antennas clamp direction (Down) still wrong update: issues were tackled | Mo'taz Al-Khateeb | Approved | Civil Requirment New ! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498 | RFI |  | Approved
1716 | 1716-Hussein_Camp_CTR_PD_Fiber_TASC_O | TASC | AME-870-R | Outdoor |  | 35.9251 | 31.9675 | East Amman | Roof Top | lajnat khadamat Camp alhusayn | 06-4649485 795562588 | Tower T 16 | 25 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414305 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Solved\ Azimuth values not provided | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-01 | Yes | W31 |  | 516 | RFI
1718 | 1718-Hussein_Electrical_St_PD_Fiber_TASC | TASC | AME-743-R | Indoor | 1673 | 35.9215 | 31.9613 | East Amman | Roof Top | ahmad salih asead alkhsawnt | 079-5944496 | Pole P6 X 3 | 37 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414307 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Clear photo for sector A. Photo for second BTS. Power to be matched and clear. Update:Accept | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Missing M-tilt Data update: issue was tackled | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-31 | Yes | W31 |  | 517 | RFI
1717 | 1717-Firas_PC_Fiber_TASC | TASC | AME-138-R | Indoor | 200 | 35.9207 | 31.9668 | East Amman | Roof Top | iibrahim khalil sulayman alfityani |  | Tower T 6 | 24 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414306 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | Missing Huw. Power table.&Wrong arrows.New solution for 5G Antenna and 12 port antenna.&Renaming all sectors on BTS sheet for 5G solution.&Before submission the TSSR revise the power solution with TI. Update:Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Najeh Ghawanmeh: Check the Tilt (mech.) of 2G Sec B | Mo'taz Al-Khateeb | Approved | Civil Requirment New | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-05 | Yes | W32 |  | 512 | RFI
1705 | 1705-Qalaa_St_PC_Fiber_TASC | TASC | AME-619-R | Indoor | 1548 | 35.9322 | 31.9594 | East Amman | Roof Top | muhamad eali eabd alwahhab mustafaa alqwadri | 02-7277933 079-5254804 | Pole P9 x 2 + P6 X 1 | 17 | ThinLayer | P.O.2 | Group6T | Cluster-17 |  | Traditional | SMP-WO-1414320 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Sector B will be relocate to AAU mast with adding DP for 5G. Sector C needs clear photo. 125A C.B & 63A C.B needed with 2FPFH. Choose one of Cabinet Soultions. Sector D should be removed from Swap. Update: Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-01 | Yes | W31 |  | 516 | RFI
1764 | 1764-Jabal_Hussein_Lema_PE_Fiber_TASC | TASC | AME-758-R | Indoor | 1705 | 35.9197 | 31.9723 | East Amman | Roof Top | muhamad abu talib | 079-6702238 | Pole P9 x 2 + P6 X 1 | 19 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414322 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | No Need for mentioning for Rectifier upgrade. Sector A should be at 160 for both 10 port and 5g. No Need for DPs on Sector A & B, Sliding down the TDD with 40-50CM instead of. Update:Accepted | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Update: For TDD changes Sector A can be slided down by max 1 m Sector B can be slided down for max 0.5 m | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498 | RFI
1745 | 1745-Hussein_Camp_Ent_PE_Fiber_TASC_O | TASC | AME-941-R | Outdoor |  | 35.9196 | 31.9754 | East Amman | Roof Top | sadiq ahmad muhamad muhisan | 0795367621/0790409506 | Pole P9 + P6 | 24 | ThinLayer | P.O.2 | Group6T | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414317 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-30 | Yes | W31 |  | 518 | RFI |  | Approved
1735 | 1735-Sinaa_Sch_PD_Fiber_TASC | TASC | AME-495-R | Indoor | 445 | 35.9327 | 31.9637 | East Amman | Roof Top | eimad eabd alfattah fayat | 079/5340601079/6674170 | Tower T 12 + P6 | 21 | ThinLayer | P.O.2 | Group6T | Cluster-17 |  | Traditional | SMP-WO-1414324 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Dismantle old cabinet Sector A no need for DP. Be specified when replace DP from leg to another leg. Update:Accept | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-25 | Yes | W30 |  | 523 | RFI
2719 | 2719-Wadi_Hadaddeh_Tunnel_PE_GPON_TASC_O | TASC | AME-603-R | Outdoor |  | 35.9302 | 31.9564 | East Amman | Roof Top | rasmiat khalil saeid alhars | 079-5396535/079-55388750 | Pole P6*2 | 16 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad |  | SMP-WO-1414581 | SMART | SMART | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-29 | Yes | W31 |  | 519 | RFI
2713 | 2713-Basman_St_PF_Org_O | ZAIN | AME-887-R | Outdoor |  | 35.9295 | 31.9534 | East Amman | Roof Top | Basman st Org |  | Tower 12 | 12 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414498 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-11-03 | Yes | W45 | Need Access Pollywood | 422
2712 | 2712-ULN_Amman_Municipality_HQ_PE_Fiber_Manage_O | ZAIN | AME-840-R | Outdoor |  | 35.9241 | 31.9455 | East Amman | Roof Top | amanat eamman alkubraa |  | Pole P6 X 3 + P3 X 1 | 21 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414499 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | No need for DP on Sector 5 Readjust the AAU DP on Sector 4 to be behind the bracing and install AQQY direct on mast Sector A and C need to be revised Propose a Power solution for MTS and don't mention that we need to upgrade the rectifier. Update: approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | location of the new Antennas on each mast / confirm the reused Antennas in the civil table since it is not mentioned in the BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-26 | Yes | W35 |  | 491 | RFI
2724 | 2724-Musdar_2_PC_Fiber_TASC | TASC | AME-347-R | Indoor | 268 | 35.9247 | 31.9437 | East Amman | Roof Top | eumar muhamad ahmad shrart |  | Pole P6 X 2 + Wall mounted Dp | 12 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414500 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Reuse the free DP on Mast A S.A for S.B on Mast B. Mention that we need to use 63A C.B instead of 32A C.B. Update: Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes | W34 |  | 499 | RFI
2711 | 2711-Musdar_PB_Fiber_TASC | TASC | AME-335-R | Indoor | 267 | 35.9263 | 31.9432 | East Amman | Roof Top | nawaf ahmad iislam hayana | 06-5933394 0777-326000 | Tower T 12 | 21 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414501 | SMART | SMART | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved | ACOC Location not clear Civil DP needed no clear very bad Pictures | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-11 | Yes | W33 |  | 506 | RFI
2704 | 2704-Zahran_PC_EBand | ZAIN/M | AME-329-R | Indoor | 363 | 35.9332 | 31.9537 | East Amman | Roof Top | malik muhamad kamal albatikhi | 06/4627072 | Pole 6 | 11 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414502 | SMART | SMART | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved | Install AQQY Direct on mast for sector C. Update:Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | civil table (missing the location for new antennas & the MW details) // no space for the new DP as the provided pics | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-28 | Yes | W35 | Magnatic Card | 489 | RFI
2708 | 2708-Shabsogh_PA_Fiber_EIBS_TASC | TASC | AME-332-R | Indoor | 149 | 35.9351 | 31.9516 | East Amman | Roof Top | alsharikat al urduniyat lilmujamieat aleaqariat | 06-4629471 | Pole P6 X 8 | 20 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414503 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 | IBS-E | Yes |  |  | Approved | no need to Replace the Antenna / Already 10 Ports all sectors | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 | Magnatic Card | 498 | RFI
2701 | 2701-Ahlieh_Sch_PF_TASC | TASC | AME-326-R | Indoor | 274 | 35.9288 | 31.9478 | East Amman | Roof Top | munaa jamil salim zakariana | 06-4624985 079-6844539 | Pole P6*3 | 15 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414504 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Reuse the free DP on Mast A S.A for S.B on Mast B. Mention that we need to use 63A C.B instead of 32A C.B. Update: Approved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | No need for the DP | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-29 | Yes | W31 |  | 519 | RFI
2703 | 2703-Rainbow_St_End_PF_TASC | TASC | AME-652-R | Indoor | 1579 | 35.9312 | 31.9493 | East Amman | Roof Top | falnatina khalid yaequb hamshawi | 079-5302090/079-5524200 | Pole P9*1+P6*2 | 15 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414505 | SMART | SMART | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-11 | Yes | W33 |  | 506 | RFI
2586 | 2586-UL_Applied_Science_Uni_Sport_PF_Fiber_TASC_O | TASC | AMW-1011-R | Outdoor |  | 35.9016 | 32.0396 | West Amman | Roof Top | jamieat aleulum altatbiqiat | 06/5609999 | Pole P6 | 14 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414507 | PIS |  | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-12 | Yes | W37 | Need Access | 474 | RFI
2585 | 2585-Applied_Science_Uni_Alale_PF_Fiber_TASC_O | TASC | AMW-1010-R | Outdoor |  | 35.9017 | 32.0412 | West Amman | Roof Top | jamieat aleulum altatbiqiat | 06/5609999 | Pole P9+P6X2 | 17 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414508 | PIS |  | Requested1 | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | location of the Antennas on the masts (civil table) & civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-05 | Yes | W36 | Need Access | 481 | RFI
2552 | 2552-Khadra_Yajouz_Rd_PE_TASC | TASC | AMW-729-R | Indoor | 1628 | 35.9098 | 32.0295 | West Amman | Roof Top | jamal muhamad saeid alkhtyb | 06-5230159 0777-424611 | Pole P6*2+P9*1 | 18 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Digital | SMP-WO-1414337 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | no DP needed to add 5G | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | civil table // what is the need for 6DP?? | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-04 | Yes | W32 |  | 513 | RFI
2584 | 2584-Shafa_Badran_TL_PF_TASC_O | TASC | AMW-1009-R | Outdoor |  | 35.909 | 32.0398 | West Amman | Roof Top | hamid husni yasin abu twq | 06/5234975 795020861 | Pole P9 + P6 | 21 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414509 | PIS |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Solved\ the site structure was changed recently, please redo the TSSR | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-17 | Yes | W38 | Extra Work for Tawseaa | 469 | RFI
2551 | 2551-Applied_Science_Uni_PB_Fiber_TASC | TASC | AMW-862-R | Indoor | 2159 | 35.8998 | 32.0441 | West Amman | Roof Top | eabd abu husayn | 079-0622042/079-60220231 | Tower T 18 | 23 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Digital | SMP-WO-1414336 | Al-Tawseaa |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | no the 5g solution is not suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-04 | Yes | W32 |  | 513 | RFI
2583 | 2583-Applied_Science_Uni_Back_PF_TASC_O | TASC | AMW-1002-R | Outdoor |  | 35.9055 | 32.0463 | West Amman | Roof Top | muhamad ahmad fayad alkayd | 0772430918/0795801432 | Pole P9#2 | 17 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414510 | PIS |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Solved\ Sector D view not provided | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-08-11 | Yes | W33 |  | 506 | RFI
2531 | 2531-Shafa_Badran_2_PC | TASC | AMW-775-R | Indoor | 1712 | 35.9041 | 32.0494 | West Amman | Roof Top | saed mufalah mutlaq aleadwan | 079-5003203 | Tower T 16 | 18 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414333 | Al-Tawseaa |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Solved\ Azimuth values not provided | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-11 | Yes | W33 |  | 506 | RFI
2529 | 2529-ULT_Shafa_Badran_1_PE | TASC | AMW-759-R | Indoor | 1674 | 35.9017 | 32.0554 | West Amman | Roof Top | mahmud salih eabd alkarim aledwan | 0777-215800 | Tower T 12 | 14 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414332 | Al-Tawseaa |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 |  | Approved | Approved | 2024-08-04 | Yes | W32 |  | 513 | RFI
2576 | 2576-Thuhebe_Tab_Kraa_Ave_PF_TASC_O | TASC | AMW-989-R | Outdoor |  | 35.9035 | 32.0635 | West Amman | Roof Top | iibrahim hamid nazal eanizat almahdawi | 0777738281/077399984 | Pole P9#2 | 18 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414511 | PIS |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-11 | Yes | W33 |  | 506 | RFI
2514 | 2514-Marine_Academy_Back_PF_TASC_O | TASC | AMW-1095-R | Outdoor |  | 35.9085 | 32.0708 | West Amman | Roof Top |  |  | Pole P9#2 | 14 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Digital | SMP-WO-1414326 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Double Check M-TILT of Sec C (2G) Double Check the Azimuth of the new Solution | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-04 | Yes | W32 |  | 513 | RFI
2541 | 2541-Shafa_Badran_End_PF_O | TASC | AMW-875-R | Outdoor |  | 35.9165 | 32.0722 | West Amman | Roof Top | samir kamil salim aleadwan |  | Tower T 16 | 18 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414335 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | No 5G Data ... So no installation for 5G | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-06 | Yes | W32 |  | 511 | RFI
2526 | 2526-Shafa_Badran_Berin_Rd_PD_Fiber_TASC_O | TASC | AMW-882-R | Outdoor |  | 35.9138 | 32.0623 | West Amman | Roof Top | zahir yusif eali hmd | 079-6643172 | Tower T 16 | 24 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414331 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved | civil table is not matching with the BTS and the BTS missing data in the summery | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-07-31 | Yes | W31 |  | 517 | RFI
2518 | 2518-Shafa_Badran_3_PF_Manage | ZAIN/M | AMW-764-R | Indoor | 1725 | 35.915 | 32.056 | West Amman | Roof Top | laynah tawfiq ahmad shbyb | 079-9099191/079-8974789 | Tower T 18 | 24 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414328 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-11 | Yes | W33 |  | 506 | RFI
2515 | 2515-Marj_Faras_3_PC_EBand_TASC | TASC | AMW-698-R | Indoor | 195 | 35.9229 | 32.0481 | West Amman | Roof Top | rbyet eabd alkarim saeid esfwr | 079-5355559 | Tower T 12 | 12 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414327 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Double Check the new solution azimuth deployment | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-22 | Yes | W34 |  | 495 | RFI
2570 | 2570-Tarkhees_Shafa_Badran_PF_Org_O | ZAIN | AMW-964-G | Outdoor |  | 35.9334 | 32.0575 | West Amman | Green Field | Tarkhes_Shafa_Badran_Org |  | Tower 45 | 20 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Digital | SMP-WO-1414338 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | no need to Replace the Antenna / Already 10 Ports all sectors | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-06 | Yes | W32 |  | 511 | RFI
2591 | 2591-UL_Shafa_Badran_Tarkhees_Front_PF_O | TASC | AMW-1145-R | Outdoor |  | 35.9425 | 32.0481 | West Amman | Roof Top |  |  | Pole 9 * 1 | 21 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414512 | PIS |  | Requested1 | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | ??????? reuse or Swap?? | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-24 | Yes | W39 | Need Access | 462
2532 | 2532-The_Arab_Academy_PF_TASC_O | TASC | AMW-615-R | Outdoor |  | 35.9485 | 32.0365 | West Amman | Roof Top | khalid nasir sabh alhajaja | 079-9593298/078-5190410 | Pole P9 + P6 | 15 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Digital | SMP-WO-1414334 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved | AAU'S reuse or dismantle?? | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-12 | Yes | W33 |  | 505 | RFI
2505 | 2505-Marj_Faras_2_PE_TASC_O | TASC | AMW-600-R | Outdoor |  | 35.9316 | 32.034 | West Amman | Roof Top | muhamad khalf eayid alsuwilmin | 07777-24942/079-9072681 | Pole P6X2+P9 | 12 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Digital | SMP-WO-1414325 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved | ACOC Location not clear Civil DP needed no clear very bad Pictures | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-04 | Yes | W32 |  | 513 | RFI
2575 | 2575-JFDA_PE_O | ZAIN | AMW-985-R | Outdoor |  | 35.9217 | 32.042 | West Amman | Roof Top | almuasasat aleamat lilghidha waldawa |  | Pole 6 | 17 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Digital | SMP-WO-1414545 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | approved since the overlapping occres between OD in IBS sectors | Baher Obaidat | Approved | Solved\ We will change the azimuth from our side | Rabie Otoum | Approved | location of Antennas in civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-24 | Yes | W39 | Need Access | 462 | RFI
2592 | 2592-UL_Marj_Faras_Solar_Farm_Av_PF_O | TASC | AMW-1162-R | Outdoor |  | 35.92 | 32.036 | West Amman | Roof Top |  |  | Tower 16 | 22 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414513 | PIS |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | no need to Replace the Antenna / Already 10 Ports all sectors | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498 | RFI
2577 | 2577-Marj_Faras_Mall_PE_TASC_O | TASC | AMW-977-R | Outdoor |  | 35.9206 | 32.029 | West Amman | Roof Top | eimad amin eabd alkhatib | 795602209 | Tower T 20 | 26 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414514 | PIS |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | 5G Sectors Wrong ( ACD ) | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Solved\ Sectors A & D are AAU | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-02 | Yes | W36 |  | 484 | RFI
2523 | 2523-Koam_Ahmar_PC_EBand_TASC | TASC | AMW-272-R | Indoor | 227 | 35.9325 | 32.0299 | West Amman | Roof Top | muhamad ahmad eatiat muhamad abu mlwh | 06/5231518 | Tower T 10 | 17 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414329 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | sector c 5G Match Azimuth with 4g | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-29 | Yes | W35 |  | 488 | RFI
2589 | 2589-Koam_Ahmar_Taqwa_Msq_PF_TASC_O | TASC | AMW-1025-R | Outdoor |  | 35.929 | 32.0258 | West Amman | Roof Top | nahaa ahmad eubdallah alqadi | 06/5233648 0799915088/0796682825 | Pole P9 + P6 | 18 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414515 | PIS |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-11 | Yes | W33 |  | 506 | RFI
2594 | 2594-UL_Koam_Alahmar_East_PF_O | TASC | AMW-1158-R | Outdoor |  | 35.9346 | 32.0222 | West Amman | Roof Top |  |  | Tower 16 | 22 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414516 | PIS |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | We need to note that there are two antennas and they will be dismantle | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | azimuth does not match the views update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-06 | Yes | W32 |  | 511 | RFI
2524 | 2524-Police_Academy_Jordan_St_PF_TASC | TASC | AMW-732-R | Indoor | 1663 | 35.9158 | 32.0163 | West Amman | Roof Top | muhamad eisaa ahmad shnyur | 079-5666592/079-6279641 | Tower T 12 | 27 | Full Swap | P.O.2 | Group4S | Cluster-25 |  | Traditional | SMP-WO-1414330 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  | Rejected | Rejected, Update Tilt (mech.), Missing height of Building and pent house & height of Tower. | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Provide the m-tilt direction (up or down) update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-02 | Yes | W36 |  | 484 | RFI
2709 | 2709-Amman_Hall_PF_TASC_O | TASC | AME-803-R | Outdoor |  | 35.9216 | 31.9463 | East Amman | Roof Top | ghaliatan tahir salih altamimi | 079-5151855 | Pole P9X2+P6X2 | 18 | ThinLayer | P.O.2 | Group7T | Cluster-27 | Albalad | Traditional | SMP-WO-1414506 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | 5G & 12 Port to be switched at installation. | Obaidah & Zaid | Approved | azimuths are not mentioned | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-08 | Yes | W32 |  | 509 | RFI
5003 | 5003-Khaldi_Plaza_PF_TASC_O | TASC | AME-592-R | Outdoor |  | 35.9042 | 31.951 | East Amman | Roof Top | markaz aleafiat lileilaj walnaqaahat | 06-659700/06-4644377 | Pole WallMount6m*2+ P6*1 | 14 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414582 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 | IBS-B |  |  |  | Approved | no 5G on SB | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 |  | 489 | RFI
5018 | 5018-Khaldi_Hospital_PF_CIBS_O | ZAIN | AME-1014-R | Outdoor |  | 35.9038 | 31.9505 | East Amman | Roof Top | mustashfaa wamarkaz alkhalidii altibiyi |  | --- --- | 20 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414583 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 4 | IBS-C |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved | Civil Requirment New ( no space for the cabinet base and the location for the cable tray) No space for Cable try | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-02 | Yes | W40 | Access letter & Email | 454 | RFI
5007 | 5007-UL_Farah_Hospital_St_PF_TASC_O | TASC | AME-825-R | Outdoor |  | 35.9053 | 31.9526 | East Amman | Roof Top | yusraa eizat eabd alrahim aleaqad | 079-5530788/079-5521307 | Pole P9#2 | 15 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414584 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is not suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 |  | 489 | RFI
5034 | 5034-2nd_CRL_PF_M | ZAIN | AME-184-R | Micro Cell |  | 35.9132 | 31.9515 | Amman | Roof Top |  |  | Pole |  | Full Swap | P.O.2 | Group5S | Cluster-50 |  | NEW | SMP-WO-1414629 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes | W34 | Need Access / Civil issue
5039 | 5039-Hay_Masarweh_PC_Fiber_TASC | TASC | AME-189-R | Indoor | 358 | 35.9178 | 31.949 | East Amman | Roof Top | amjad sulayman khalil hadad | 06/4659480 079/6699907 | Pole P6 X 4 + Wall mounted Dp x 3 | 21 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414585 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | 2G sectors Names are A, B not A, C Sector C azimuth does not match with the view sector A m-tilt direction (up or down) does not match with the image modify the azimuth of the 5G sector C in BTS sheet Which mast is the new mast based on the layout you provided (A, B, or C) Update: Need to relocate the empty mast as the view from its current location is blocked by other antennas No need to install new mast to move sector C as there is already existing mast No need to install new mast to move sector C as there is already existing mast update: issues were tackled | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-03 | Yes | W36 |  | 483 | RFI
5005 | 5005-Aqleh_PB_Fiber_TASC | TASC | AME-159-R | Indoor | 186 | 35.9085 | 31.9509 | East Amman | Roof Top | mamun salah mahmud aljamal |  | Pole P6 X 2 + P9 X 1 + P3 X1 | 18 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414586 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Double Check M-TILT of Sec C (2G) Double Check the Azimuth of the new Solution | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498 | RFI
5077 | 5077-Dar_Alomran_Bldg_PF_BIBS_O | ZAIN | AME-1009-R | Outdoor |  | 35.9043 | 31.9489 | East Amman | Roof Top | dar aleumran |  | Pole 6 | 6 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414587 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 2 | IBS-B |  |  |  | Approved |  | Obaidah & Zaid | Approved | No 5G Data ... So no installation for 5G | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492 | RFI
5006 | 5006-3rd_CRL_Mohajereen_St_PE_Fiber_TASC_O | TASC | AME-778-R | Outdoor |  | 35.9101 | 31.9487 | East Amman | Roof Top | khalil iishaq muhamad alfakhwry | 079-5334365 | Pole P9 | 14 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414588 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 2 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Malek | Approved | civil table is not matching with the BTS and the BTS missing data in the summery | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes | W34 | Access level 4 | 499 | RFI
5056 | 5056-Mohajereen_PSD_PF_TASC_O | TASC | AME-1006-R | Outdoor |  | 35.9138 | 31.9486 | East Amman | Roof Top | mudiriat alamn aleami |  | Pole P9 | 9 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414589 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-24 | Yes | W43 | PSD Access - Maram Tasc | 432
5023 | 5023-Akhdar_Amawi_PC_Fiber_TASC | TASC | AME-490-R | Indoor | 412 | 35.9086 | 31.9433 | East Amman | Roof Top | jawayriat yusif eabd alruhmin al aghbara | 06-4779853 079-6301016/079-5934550 | Tower T 16 | 22 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414590 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Double Check the new solution azimuth deployment | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 |  | 489 | RFI
5043 | 5043-UL_Akhdar_Amawi_CTR_PE_O | TASC | AME-1104-R | Outdoor |  | 35.9123 | 31.9429 | East Amman | Roof Top |  |  | Tower 16 | 48 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414591 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | no need to Replace the Antenna / Already 10 Ports all sectors | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-06 | Yes | W32 |  | 511 | RFI
5008 | 5008-Akhdar_Mountain_Top_PD_Fiber_TASC | TASC | AME-162-R | Indoor | 65 | 35.913 | 31.9462 | East Amman | Roof Top | rajab salim rajab qawaydran | 06/4390892 079/5955004 - 0 795506667 | Pole P9 X 2 + P6 X 1 + P4 X 2 + Wallmounted Dp(3 m) x 4 | 17 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414592 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 4 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-14 | Yes | W33 |  | 503 | RFI
5041 | 5041-Refco_2_PE_Fiber_TASC | TASC | AME-745-R | Indoor | 1681 | 35.9151 | 31.9444 | East Amman | Roof Top | muhamad eabd almuhasin eawdat alkhtyb | 079-9323109/079-5855811 | Pole P9 + P6 | 21 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414593 | SMART |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved | AAU'S reuse or dismantle?? | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 | contact Owner | 482 | RFI
5046 | 5046-UL_Akhdar_Reefco_North_O | TASC | AME-1117-R | Outdoor |  | 35.9177 | 31.9434 | East Amman | Roof Top |  |  | Tower 16 | 28 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414596 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Sectors are B, C, D not A, B, C modify azimuth of sector A in Remark in the BTS sheet. update: issues were tackled | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-22 | Yes | W39 | OG | 464 | RFI
5011 | 5011-Refco_3_PE_Fiber_TASC_O | TASC | AME-165-R | Outdoor |  | 35.9183 | 31.9424 | East Amman | Roof Top | fady ahmad musaa mahmud zayd | 078-5433663/078-8487277 | Pole P6 | 15 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414597 | SMART |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Double Check 2G/4G Electrical tilting of Sec B | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498 | RFI
5053 | 5053-Akhdar_Hamzeh_Msq_PF_EBand_TASC_O | TASC | AME-956-R | Outdoor |  | 35.9157 | 31.9422 | East Amman | Roof Top | manal mahmud muslim aleawrani | 0795143128/0799327668/0795627766 | Pole P9 + P6 | 21 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414598 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Sector C azimuth does not match with the view update: issue was tackled | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 | OG | 489 | RFI
5015 | 5015-Nazzal_Karameh_Sch_PF_TASC_O | TASC | AMS-211-R | Outdoor |  | 35.9189 | 31.9309 | East Amman | Roof Top | mhamad eisaa euthman rsrs | 796616663/0796733006 | Pole P6*1+P9*2 | 24 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414599 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | Install the ACOC cabinet instead of the fiber BOX | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Provide the m-tilt direction (up or down) update: issue was tackled | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 | OG | 489 | RFI
5021 | 5021-UL_Nazzal_Girls_Comprehensive_Sch_PF_EBand_BTS_O | TASC | AME-1089-R | Outdoor |  | 35.9168 | 31.9321 | East Amman | Roof Top |  |  | Tower 16 | 10 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414600 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-26 | Yes | W35 | OG | 491 | RFI
5044 | 5044-UL_Nazzal_Siraj_Sch_Back_O | TASC | AME-1113-R | Outdoor |  | 35.9183 | 31.9347 | East Amman | Roof Top |  |  | Pole 3 * 9 | 24 | Full Swap | P.O.2 | Group5S | Cluster-50 | Nazzal | NEW | SMP-WO-1414601 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | correct the azimuth of the new 12-port antenna of sector A in the BTS sheet update: issue was tackled | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 | OG | 489 | RFI
5026 | 5026-Jabal_Nathef_2_PF_TASC_O | TASC | AME-477-R | Outdoor |  | 35.9239 | 31.9412 | East Amman | Roof Top | farih hasan muhamad abu tayh | 06/4774760 077-6808545 | Pole Wall Mounting 3mx2 + P6+Tripod | 15 | Full Swap | P.O.2 | Group5S | Cluster-50 |  | NEW | SMP-WO-1414602 | SMART |  | Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | We need to note that there are two antennas and they will be dismantle | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | azimuth does not match the views update: issue was tackled | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 | No Access | 489 | RFI
5020 | 5020-Ras_Ain_PE_Fiber_TASC_Relo_O | TASC | AME-1038-R | Outdoor |  | 35.9237 | 31.9403 | East Amman | Roof Top |  |  | Tower T 12 | 21 | Full Swap | P.O.2 | Group5S | Cluster-50 |  | NEW | SMP-WO-1414603 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved | Provide the m-tilt direction (up or down) update: issue was tackled | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 |  | 489 | RFI
5040 | 5040-Ras_Ain_St_PE_Fiber_TASC_O | TASC | AME-790-R | Outdoor |  | 35.9241 | 31.9353 | East Amman | Roof Top | rabihat muhamad iismaeil zetr | 079-7328780/079-7920244 | Pole P6+P9X2 | 18 | Full Swap | P.O.2 | Group5S | Cluster-50 |  | NEW | SMP-WO-1414604 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Thabet Jaradat & Ahmad Hajdawood | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-03 | Yes | W36 | No Access | 483 | RFI
5002 | 5002-Jabal_Nathef_PE_Fiber_TASC | TASC | AME-198-R | Indoor | 1544 | 35.926 | 31.9402 | East Amman | Roof Top | eumar eali bikr alnablsi wakilanaan ean muhamad alnablsi | 079-6654483/078-8144906 | Pole P6 X 2 + Wall mounted Dp x 3 | 17 | Full Swap | P.O.2 | Group5S | Cluster-50 |  | NEW | SMP-WO-1414605 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 | OG | 492 | RFI
5054 | 5054-Zohour_Traffic_Park_PE_Fiber_TASC_O | TASC | AME-978-R | Outdoor |  | 35.9264 | 31.9254 | East Amman | Roof Top | iibrahim fayiz sari alnaabut | 0795391171/0795610624/0796410753 | Pole P6*1+P4*1+P9*1 | 24 | Full Swap | P.O.2 | Group5S | Cluster-50 |  | NEW | SMP-WO-1414606 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492 | RFI
5050 | 5050-Zohour_Garden_Back_PC_Fiber_TASC_O | TASC | AME-867-R | Outdoor |  | 35.923 | 31.9261 | East Amman | Roof Top | mustafaa musaa | 06-4382465 798444040 | Pole P9#2 | 18 | Full Swap | P.O.2 | Group5S | Cluster-50 |  | NEW | SMP-WO-1414607 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492 | RFI
5604 | 5604-P_East_Sweileh_PF | ZAIN | AMW-535-P | Electricity Pole |  | 35.8506 | 32.0303 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  | SMP-WO-1454426 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved | Please fill the antennas dimensions and dismantling antenna as well in the civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
5605 | 5605-P_East_Sweileh_2_PF | ZAIN | AMW-675-P | Electricity Pole |  | 35.8468 | 32.0298 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Incorrect power solution: reuse the existing PDU./solved | Obaidah & Zaid | Approved | Sector A 4G - Azimuth is wrong please double check | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
5601 | 5601-UL_P_Dabouq_Sweileh_Top_1 | ZAIN | ZAIN | Electricity Pole |  | 32.0131 | 32.0131 | Amman | Roof Top |  |  | Electicity Pole |  | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Wrong power Solution: We can use 63A C.B or two of plugs. No need for mentioning that we need new rectifier Update: Approved | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes
5634 | 5634-P_Dabouq_Sweileh_2_PE | ZAIN | AMW-1114-P | Electricity Pole |  | 35.8264 | 32.0119 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved | Sector A should be at the top, the reference for us is the 3g. Azimuth should be as 3g. Update: Approved. | Obaidah & Zaid | Approved | Rejected Sector B & C are to close to each other - refer to optimizer first - Sector B should be 185 | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
5625 | 5625-P_Dabouq_Sweileh_PE_GPON | ZAIN | AMW-549-P | Electricity Pole |  | 35.827 | 32.0099 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  | SMP-WO-1454429 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
5650 | 5650-U_P_Rahmanieh_Villas_PE_GPON | ZAIN | AMW-966-P | Electricity Pole |  | 35.829 | 32.0064 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  | SMP-WO-1454430 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Incorrect power solution: There is no need to add a PDU; reuse the existing PDUs/solved | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
5655 | 5655-P_Hummar_Palace_Ent_PE_GPON | ZAIN | AMW-896-R | Electricity Pole |  | 35.8181 | 31.9973 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  | SMP-WO-1454432 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | Increase 5G sector A to match 3G/4G height | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
5622 | 5622-P_Royal_Palace_Rahmanieh_PE | ZAIN | AMW-1045-P | Electricity Pole |  | 35.8181 | 31.9972 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group6S | Cluster-56 |  |  | SMP-WO-1454433 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Released |  | Qais Malkawi & Baker Asaad | Released | Civil Requirment New Civil Requirment New no cabinet base needed | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2527 | 2527-UL_P_Kamalieh_Cliff_PF | ZAIN | AMW-1102-P | Electricity Pole |  | 35.8179 | 32.0351 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  | SMP-WO-1456422 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | approved | civil table Antennas locations & civil sheet // details for the 4 poles | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2548 | 2548-P_Safoot_End_Back_PF | ZAIN | AMW-1075-P | Electricity Pole |  | 35.8408 | 32.0453 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  | SMP-WO-1456424 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved | Sector B Azimuth is wrong | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2509 | 2509-Princess_Bassma_PF_M | ZAIN | AMW-668-R | Micro Cell |  | 35.866 | 32.0408 | Balqa | Wall-Mount | 0 | 0 | RT | RT WM 1 | Full Swap | P.O.2 | Group7S | Cluster-25 |  | NEW | SMP-WO-1414630 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no the 5g solution is not suggested | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved | What is the need for the DP? // civil table empty sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-14 | Yes | W33 |  |  | RFI
2513 | 2513-U_P_Princess_Bassma_Palace_West_PF | ZAIN | AMW-1117-P | Electricity Pole |  | 35.861 | 32.0388 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Incorrect power solution: There is no need to add a PDU; reuse the existing PDUs./solved | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2535 | 2535-U_P_Manhal_End_PF | ZAIN | AMW-1106-P | Electricity Pole |  | 35.8746 | 32.0392 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2544 | 2544-P_AbuNusair_Jubaiha_St_PF | ZAIN | AMW-813-P | Electricity Pole |  | 35.8703 | 32.0451 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  | SMP-WO-1456428 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved | in BTS sector A wrong azimuth | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2581 | 2581-UL_P_AbuNusair_Market_Back_PF | ZAIN | AMW-960-P | Electricity Pole |  | 35.8723 | 32.0507 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved | There is no need to install the hexagonal./solved The azimuth for Sector A is incorrect./solved | Obaidah & Zaid | Approved | Azimuth of sector A is wrong double check | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2560 | 2560-U_P_Sahara_Mall_West_PF | ZAIN | AMW-1107-P | Electricity Pole |  | 35.8674 | 32.0568 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Omar Sami | Approved | Compass pictures for some sectors are wrong | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2568 | 2568-UL_P_ Hay_Dyaa_AbuNusair | ZAIN | AMW-1170-P | Electricity Pole |  | 35.8774 | 32.0709 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  | SMP-WO-1456431 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2567 | 2567-P_Applied_Science_Hakeem_PF | ZAIN | AMW-1063-P | Electricity Pole |  | 35.9036 | 32.0428 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | AHDA is not mentioned in the power solution./solved Need a cable ladder behind the ACOC./solved Incorrect power solution: There is no need to add a PDU; reuse the existing PDU./solved | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
4554 | 4554-P_Shafa_Badran_Theeb_Ave_PF | ZAIN | AMW-1076-P | Electricity Pole |  | 35.9301 | 32.0709 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-45 |  |  | SMP-WO-1456434 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2522 | 2522-P_Talat_AlNemer_PF | ZAIN | AMW-1073-P | Electricity Pole |  | 35.9433 | 32.0384 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Install Sector A 5G @ height 7.8 not 4.7/ rejected by planning team/solved | Obaidah & Zaid | Approved | Install Sector A 5G @ height 7.8 not 4.7 | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
2561 | 2561-U_P_The_Arab_Academy_South_Ave_PF | ZAIN | AMW-1112-P | Electricity Pole |  | 35.9473 | 32.0309 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group7S | Cluster-25 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved | Incorrect power solution: There is no need to add a PDU; reuse the existing PDUs./solved There are no AHEBs to be added on this site. | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
1807 | 1807-Venezuelan_Embassy_Back_PE_GPON_TASC_O | TASC | AMS-198-R | Outdoor |  | 35.903 | 31.9413 | South Amman | Roof Top | iismaeil muhamad mustafaa rady | 0777824222/0799843888 | Tower T 20 | 29 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414517 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Switching between 14-Port & 5G in installation is needed. Propose a place for AHEB installation Update: Approved. | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-08-28 | Yes | W35 |  | 489 | RFI
1855 | 1855-Nazzal_Rising_PE_TASC | TASC | AME-195-R | Indoor | 291 | 35.9071 | 31.9364 | South Amman | Roof Top | fatimat iibrahim ahmad ramadan | 64393254- 0797292785/0795024644 | Tower T 12 | 24 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414518 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved | Please fill the antennas dimensions and dismantling antenna as well in the civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-10-02 | Yes | W40 | Dismantled/ New Location | 454 | RFI
1849 | 1849-Akhdar_Bader_PD_Org_O | ZAIN | AME-930-R | Outdoor |  | 35.9036 | 31.9348 | South Amman | Roof Top | taysir faris eabd aljawad aleajluni | 0799437990/0797630862/0796841690 | Tower 16 | 21 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414519 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Incorrect power solution: reuse the existing PDU./solved | Obaidah & Zaid | Approved | Sector A 4G - Azimuth is wrong please double check | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-03 | Yes | W36 |  | 483
1813 | 1813-Nazzal_West_1_PF_FiberNode_M | ZAIN | AME-167-R | Micro Cell |  | 35.904 | 31.9322 | Amman | Roof Top | 0 | 0 | RT | RT P 6 X 1 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414631 | SMART |  | Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Wrong power Solution: We can use 63A C.B or two of plugs. No need for mentioning that we need new rectifier Update: Approved | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes
1836 | 1836-Nazzal_West_PC_Fiber_TASC | TASC | AME-186-R | Indoor | 219 | 35.9015 | 31.9324 | South Amman | Roof Top | mahir eabd aljabbar mahmud eabd allh | 06/4399960 079/5568014/078-5197430/078-5217925 | Tower T 12 | 24 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414546 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved | Sector A should be at the top, the reference for us is the 3g. Azimuth should be as 3g. Update: Approved. | Obaidah & Zaid | Approved | Rejected Sector B & C are to close to each other - refer to optimizer first - Sector B should be 185 | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-12 | Yes | W37 |  | 474 | RFI
1847 | 1847-Nazzal_Shoora_CRL_3_PE_Fiber_TASC_O | TASC | AME-928-R | Outdoor |  | 35.897 | 31.9313 | South Amman | Roof Top | dhahab mahmud eyd alashqr | 06/4390170 0795642567/ | Pole P9#2 | 24 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414520 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Is there an unused 2G Kathrine antenna on sector D? and No need for a 1x3m DP on the same sector (sector D)./solved | Obaidah & Zaid | Approved | Install a new 9m pole for Sector A and change its location due to blockage Can you provide me with the AS built file and show me where exactly will be mounted on the roof, it appears that it is a lower location and will not service sector A? | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492
1843 | 1843-Nazzal_Shoora_Gardens_Back_PE_Fiber_TASC_O | TASC | AMS-149-R | Outdoor |  | 35.9002 | 31.929 | South Amman | Roof Top | muhamad murshid muhamad hmdallh | 0797518785/0795865432/0798669212 | Pole P9#2 | 24 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414521 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | Incorrect power solution: There is no need to add a PDU; reuse the existing PDUs/solved | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492
1810 | 1810-Nazzal_Hayat_Hospital_PE_Zain_TASC | TASC | AME-720-G | Indoor | 1696 | 35.8993 | 31.922 | South Amman | Green Field | iibrahim salim muhamad alqarinawi | 078-8712521 | Tower T 30 | 25 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414522 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | Increase 5G sector A to match 3G/4G height | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-03 | Yes | W36 |  | 483 | RFI
3625 | Hayat_Alrantessi_Back_PF_TASC_O | TASC | AME-905-R | Outdoor |  | 35.9055 | 31.9194 | Amman | Pole | 0 | 0 | RT | P9 x 3 | Full Swap | P.O.2 | Group8S | Cluster-36 | Mugablain | NEW | SMP-WO-1414608 | Al-Tawseaa | Old SMP | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved | Civil Requirment New Civil Requirment New no cabinet base needed | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-02 | Yes | W40 |  | 454 | RFI | [6 empty] | Downloaded
3640 | Kobrosieh_PC_EBand_TASC | TASC | AME-196-R | Indoor | 136 | 35.9086 | 31.9231 | Amman | Pole | 136 | 136 | RT | P6 X4 | Full Swap | P.O.2 | Group8S | Cluster-36 | Mugablain | NEW | SMP-WO-1414609 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved | civil table Antennas locations & civil sheet // details for the 4 poles | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-30 | Yes | W40 |  | 456 | RFI | [6 empty] | Downloaded
1801 | 1801-Nazzal_PA_Fiber_TASC | TASC | AME-155-G | Indoor | 289 | 35.9029 | 31.9266 | South Amman | Green Field | dawud musaa ahmad alrbayet | 079/5788055 | Tower T 60 | 35 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414523 | SMART |  | Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved | Sector B Azimuth is wrong | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492 | RFI
1802 | 1802-Shoaa_CTR_PC_EBand_TASC | TASC | AME-156-R | Indoor | 290 | 35.9055 | 31.9266 | South Amman | Roof Top | shieae muhamad eabdallah eabdallh | 06/4390024 | Pole P6 X 5 | 21 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414524 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | Where to install AHDA doesn't mention in TSSR | Obaidah & Zaid | Approved | no 5g solution is suggested | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | C | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492 | RFI
1850 | 1850-Thraa_Amani_Sch_PF_TASC_O | TASC | AMS-170-R | Outdoor |  | 35.9092 | 31.9279 | South Amman | Roof Top | nieamah shakir eali alhmshry | 0791319272/0799092399 | Pole P9#2 | 21 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414525 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Incorrect power solution: There is no need to add a PDU; reuse the existing PDUs./solved | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498
1817 | 1817-Nazzal_Bader_PF_TASC | TASC | AME-533-R | Indoor | 495 | 35.9147 | 31.9296 | South Amman | Roof Top | wajih muhamad eiwad ahmad | 06-4391429 | Pole P6X4 | 22 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414547 | SMART |  | Requested | Done |  |  |  | RAN Only | 2 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved | location for the new Antennas on the poles (civil table) and BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-04 | Yes | W36 | Need Key from Zain | 482 | RFI
1831 | 1831-Nazzal_Exchange_PF_EBand_TASC | TASC | AME-182-R | Indoor | 335 | 35.9142 | 31.9337 | South Amman | Roof Top | shahadat ealia muhamad abu zame w sharkah | 06/4390219 079/5110445 | Pole P6X3 | 18 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414548 | SMART |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Omar Sami | Approved | in BTS sector A wrong azimuth | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes | W38 |  | 469 | RFI
1840 | 1840-UL_Nazzal_Rising_Mid_PF_Fiber_TASC_O | TASC | AME-1066-R | Outdoor |  | 35.9194 | 31.9375 | South Amman | Roof Top | eata muhamad hilmi eata alzuban | 079/5424999 | Pole P9#2 | 15 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414549 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | There is no need to install the hexagonal./solved The azimuth for Sector A is incorrect./solved | Obaidah & Zaid | Approved | Azimuth of sector A is wrong double check | Omar Sami | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-03 | Yes | W36 |  | 483 | RFI
1806 | 1806-Souq_Nazzal_PD_Fiber_TASC | TASC | AME-160-R | Indoor | 292 | 35.917 | 31.9366 | South Amman | Roof Top | muhamad eali husayn aldwhl | 64398863 | Tower T 10 + P6 x 1 | 27 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414526 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | Omar Sami | Approved | Compass pictures for some sectors are wrong | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-30 | Yes | W40 |  | 456 | RFI
1811 | 1811-UL_Nazzal_Maqasid_Hospital_PE_O | TASC | AME-1116-R | Outdoor |  | 35.9159 | 31.9395 | South Amman | Roof Top |  |  | Tower 16 | 22 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414527 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | mismatch between Sec C & D on BTS sheet and RF sheet. Update: approved. | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | as discussed with Mofeed kindly your support to shift the azimuth of sector D from 280 to 310 to avoid high overlap between sector C (260) and sector D . | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-05 | Yes | W36 |  | 481 | RFI
1814 | 1814-Akhdar_Core_PE_Fiber_TASC_O | TASC | AME-168-R | Outdoor |  | 35.9143 | 31.9401 | South Amman | Roof Top | muhamad jamil zakariaa eabd alhafiz alntsht | 06-4391011 079/5526554/0788-147376 | Pole Wall Mounting 3m | 12 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414550 | SMART |  | Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | AHDA is not mentioned in the power solution./solved Need a cable ladder behind the ACOC./solved Incorrect power solution: There is no need to add a PDU; reuse the existing PDU./solved | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498
1845 | 1845-Akhdar_Omair_Sch_PF_TASC_O | TASC | AME-945-R | Outdoor |  | 35.9103 | 31.9408 | South Amman | Roof Top | ahmad eabd alfattah eabd alrahim desan | 0799000235/0797101155 | Pole P9#2 | 21 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414528 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Antenna location on masts is missing. on civil sheet Recheck the 4G if existed on sector D Recheck if the antenna for sector D is 12 or 10 port Update:Accepted. | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-09-17 | Yes | W38 |  | 469 | RFI
1838 | 1838-Karak_St_PE_Fiber_TASC_O | TASC | AMS-66-R | Outdoor |  | 35.9121 | 31.9404 | South Amman | Roof Top | warathat tawfiq eayid mahmud ewdt | 0792060986/0795657082 | Pole P9 + P6 | 15 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414551 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Install Sector A 5G @ height 7.8 not 4.7/ rejected by planning team/solved | Obaidah & Zaid | Approved | Install Sector A 5G @ height 7.8 not 4.7 | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471 | RFI
1846 | 1846-Karak_St_Ent_PE_Fiber_TASC_O | TASC | AMS-147-R | Outdoor |  | 35.9133 | 31.9365 | South Amman | Roof Top | warathat salim salih ealiun ramaanan | 0779279558/0776280871/0777311720 | Pole P9#2 | 15 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414529 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | Incorrect power solution: There is no need to add a PDU; reuse the existing PDUs./solved There are no AHEBs to be added on this site. | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-25 | Yes | W35 |  | 492 | RFI
1809 | 1809-Nazzal_Rising_2_PD_EBand_TASC | TASC | AME-163-R | Indoor | 378 | 35.9097 | 31.9316 | South Amman | Roof Top | eabd alruhmin namur ahmad jubran | 06/4380294/06/4392113 | Pole P6 X 3 + P9 X 2 + P5 X 1 | 15 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414530 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | civil table & poles details | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-24 | Yes | W39 |  | 462 | RFI
1818 | 1818-Nazzal_Shoora_CRL_PD_Fiber_TASC | TASC | AME-737-R | Indoor | 1707 | 35.905 | 31.9309 | South Amman | Roof Top | yasir eabd alrahmn yusif eiwad allh | 079-7514065 | Tower T 18 | 27 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414552 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | if sector A can be increase by 6 meter to enhance coverage | Baher Obaidat | Approved | fix the naming of 5G sectors | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-17 | Yes | W38 | OG | 469
1815 | 1815-Yasmeen_Ave_2_PD_Fiber_O | TASC | AMS-203-R | Outdoor |  | 35.8967 | 31.9266 | South Amman | Roof Top | Mahmoud Saeefan | 0798732534/0097059989611 | Pole P9 X 4 | 21 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414553 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | Incorrect power solution: There is no need to add a PDU; reuse the existing PDUs./solved | Obaidah & Zaid | Approved | Sector A- 5G bore is wrong, should match 4G bore | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-26 | Yes | W35 |  | 491 | RFI
1844 | 1844-Yasmeen_Rabweh_Abdoun_PE_Fiber_TASC_O | TASC | AMS-159-R | Outdoor |  | 35.8935 | 31.9244 | South Amman | Roof Top | riad muhamad rashid alhwrany | 0795988332/0797254779/0796044421 | Pole P9#2 | 18 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414531 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | Baher Obaidat | Approved | Sector C azimuth does not match the view NO TSSR Excel Sheet Update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-03 | Yes | W36 |  | 483 | RFI
1819 | 1819-Yasmeen_Market_CTR_PE_TASC_O | TASC | AMS-50-R | Outdoor |  | 35.8904 | 31.9166 | South Amman | Roof Top | eimad eabd almuhasin eabd alfattah alsalhy | 079-5584966-0796436776 | Pole P9#2 | 25 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414554 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Rabie Otoum | Approved | pictures for the 3 Masts & location of the Antennas in civil table / check the heights of the antennas | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-28 | Yes | W35 | OG | 489 | RFI
1816 | 1816-Yasmeen_2_PC_Fiber_TASC | TASC | AME-641-R | Indoor | 1558 | 35.8876 | 31.9151 | South Amman | Roof Top | muhamad khalil mahmud trysh | 06-4200674 079-59000542 | Pole P6 X4 | 26 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414555 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | Is there an unused 2G Kathrine antenna on sector D? and No need for a 1x3m DP on the same sector (sector D)./solved | Moath & Waed | Approved | Install a new 9m pole for Sector A and change its location due to blockage Can you provide me with the AS built file and show me where exactly will be mounted on the roof, it appears that it is a lower location and will not service sector A? | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-29 | Yes | W35 |  | 488
1805 | 1805-Yasmeen_Nables_Msq_PF_TASC_O | TASC | AMS-3-R | Outdoor |  | 35.8908 | 31.9125 | South Amman | Roof Top | rayid th muhamad dbsh | 797162851 | Tower T 12 | 22 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414532 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | There is no need to install the hexagonal. Please install the ACOC back-to-back with the battery cabinet./solved Wrong antenna numbers, wrong antenna information, and wrong antenna solution./solved | Moath & Waed | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-05 | Yes | W36 | OG | 481
1841 | 1841-UL_Yasmeen_Selwadi_Msq_PE_GPON_TASC_O | TASC | AMS-301-R | Outdoor |  | 35.8821 | 31.9158 | South Amman | Roof Top |  |  | Pole P9#2 | 21 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414556 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | There is no need to install the hexagonal./solved why we need to swap the 10 Ports antennas!/solved | Moath & Waed | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-17 | Yes | W38 |  | 469 | RFI
1804 | 1804-Drugs_Resistance_PSD_PE_Manage | ZAIN/M | AMW-491-R | Indoor | 311 | 35.8809 | 31.9248 | South Amman | Roof Top | mudiriat al amn aleamm |  | Tower T 18 | 21 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414533 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | incorrect antenna solution in BTS sheet./solved Not enough information about the power solution (need rectifier type and details of all circuit breakers)/solved | Moath & Waed | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-09-24 | Yes | W39 | Military Area | 462
1837 | 1837-P_Yasmeen_Faqih_Msq_PF | ZAIN | AME-801-P | Electricity Pole |  | 35.883 | 31.9187 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group8S | Cluster-18 |  |  | SMP-WO-1456439 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
1848 | 1848-Yasmeen_Faqih_Msq_2_PE_Fiber_TASC_O | TASC | AMS-164-R | Outdoor |  | 35.8847 | 31.9187 | South Amman | Roof Top | eali ahmad eudah alwahsh | 0781881916/0798183239 | Pole P6+P9 | 24 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414534 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Install the ACOC under the Mast directly./solved Wrong power solution : there is no need to add PDU, reuse the existing PDU./solved | Moath & Waed | Approved | Increase separation between sector B & C / Sector C should be 210 | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes | W38 | TSSR Done | 469 | RFI
1803 | 1803-Yasmeen_3_PD_Fiber_TASC | TASC | AME-694-R | Indoor | 1631 | 35.8867 | 31.9209 | South Amman | Roof Top | raja shalabi | 079-6559251/078-8000257 | Tower T 16 | 24 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414535 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Switching between 14-Port & 5G in installation is needed. Propose a place for AHEB installation Update: Approved | Moath & Waed | Approved |  | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-26 | Yes | W35 |  | 491 | RFI
1808 | 1808-Yasmeen_Lab_PSD_PF_O | TASC | AME-845-R | Outdoor |  | 35.8885 | 31.9236 | South Amman | Roof Top | mudiriat al amn aleamm |  | Pole P4 X 1 + P3 X1 + WallMount3 X 1 | 16 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414536 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | Approved | Civil Requirment New no matching with BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-22 | Yes | W39 | Military Area | 464 | RFI
1829 | 1829-Yasmeen_PC_Fiber_TASC | TASC | AME-180-R | Indoor | 337 | 35.8934 | 31.9206 | South Amman | Roof Top | taysir euthman abu saed wamuhamad faris dawd |  | Pole P6 X 3 + Wallmounting Dp (1.2 m) | 12 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal |  | SMP-WO-1414557 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | Approved | location for the new Antennas on the poles (civil table) and BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes | W38 | Magnatic Card | 469
1812 | 1812-UL_P_Yasmeen_Rabweh_Abdoun | ZAIN | AMS-335-P | Electricity Pole |  | 35.8882 | 31.9265 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Baher Obaidat | Approved |  | Qais Malkawi & Baker Asaad | approved | civil SHEET | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes
1827 | 1827-P_Hadi_Msq_Rd_PF_Relo | ZAIN | AMS-261-P | Electricity Pole |  | 35.8777 | 31.9241 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group8S | Cluster-18 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
1842 | 1842-Yasmeen_WaterTank_PE_GPON_TASC_O | TASC | AMS-116-R | Outdoor |  | 35.8864 | 31.911 | South Amman | Roof Top | muhamad ziad mahmud abu ghnymh | 06/4203550 799195700 | Pole P6X2 | 15 | Full Swap | P.O.2 | Group8S | Cluster-18 | Nazzal | Traditional | SMP-WO-1414537 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-19 | Yes | W34 |  | 498
3669 | Mugabalein_PA_Fiber_TASC | TASC | AME-89-G | Indoor | 272 | 35.8987 | 31.8964 | Amman | Tower | 272 | 272 | GF | T 30 | Full Swap | P.O.2 | Group8S | Cluster-36 | Mugablain |  | SMP-WO-1448662 | Al-Lewan |  | Not Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | mismatch between Sec C & D on BTS sheet and RF sheet. Update: approved. | Moath & Waed | Approved |  | M. Amro | Approved | as discussed with Mofeed kindly your support to shift the azimuth of sector D from 280 to 310 to avoid high overlap between sector C (260) and sector D . | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-14 | Yes | W42 |  | 442
3620 | 3620-Um_Qsair_Electricity_PE_TASC_O | TASC | AMS-84-R | Outdoor |  | 35.9103 | 31.8923 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group8S | Cluster-36 |  | NEW | SMP-WO-1414632 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | Civil Requirment New | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-05 | Yes | W36 |  | 481 | RFI
3602 | 3602-Customs_HSG_2_PC_Fiber_TASC | TASC | AME-61-R | Indoor | 11 | 35.9131 | 31.8943 | Amman | Pole | 11 | 11 | RT | P6 X 2 + P5 X2 | Full Swap | P.O.2 | Group8S | Cluster-36 |  | NEW | SMP-WO-1414633 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Antenna location on masts is missing. on civil sheet Recheck the 4G if existed on sector D Recheck if the antenna for sector D is 12 or 10 port Update:Accepted. | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-17 | Yes | W38 |  |  | RFI
5042 | 5042-Mareekh_1_PD_Fiber_TASC | TASC | AME-192-R | Indoor | 380 | 35.9331 | 31.9347 | East Amman | Roof Top | mahmud salih ahmad iismaeil hjawy | 06/4744950 0797401446/0796037132 | Pole P6 X 2 | 12 | Full Swap | P.O.2 | Group8S | Cluster-50 |  | NEW | SMP-WO-1414611 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved | no 5g solution is suggested | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-07-31 | Yes | W31 |  | 517 | RFI
5062 | 5062-Ashrafyeh_4_PE_Fiber_TASC_O | TASC | AME-200-R | Outdoor |  | 35.9337 | 31.9364 | East Amman | Roof Top | wadad saeid hasan alqaduwmi washurakayuha | 06-4780011 079-6954084 | Pole P9 | 13 | Full Swap | P.O.2 | Group8S | Cluster-50 |  | NEW | SMP-WO-1414612 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved | no 5g solution is suggested | M. Amro | Approved | Note: site is not equipped by GSM but there exist L900 over sector A. | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-04 | Yes | W32 |  | 513 | RFI
5051 | 5051-Mareekh_Taybat_Village_PD_Fiber_TASC_O | TASC | AME-942-R | Outdoor |  | 35.9299 | 31.934 | East Amman | Roof Top | hamd salman salih alhajawi | 06/4788368 0795219884/0777047361/ | Pole P6*2 | 18 | Full Swap | P.O.2 | Group8S | Cluster-50 |  | NEW | SMP-WO-1414613 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved | Sectors A and C azimuth does not match the view update: issues were tackled | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-07-29 | Yes | W31 |  | 519 | RFI
5001 | 5001-Mareekh_2_PC_Fiber_TASC | TASC | AME-191-R | Indoor | 344 | 35.9284 | 31.9365 | East Amman | Roof Top | faysal eabd alhalim muhamad hamaad | 06/4741934 079-5008386 | Tower T 12 + P6 X 1 | 18 | Full Swap | P.O.2 | Group8S | Cluster-50 |  | NEW | SMP-WO-1414614 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved | TSSR not Submitted | Obaidah & Zaid | Approved | no 5g solution is suggested | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | NO TSSR founded | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-02 | Yes | W36 |  | 484 | RFI
5004 | 5004-Nathef_Mareekh_Police_PF_TASC | TASC | AME-698-R | Indoor | 432 | 35.9261 | 31.936 | East Amman | Roof Top | ahmad muhamad eabd alqadir alhmuwz | 06-4771632 0777-100006/079-6872057 | Pole P6*2 | 18 | Full Swap | P.O.2 | Group8S | Cluster-50 |  | NEW | SMP-WO-1414615 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved | no 5g solution is suggested | M. Amro | Approved | Azimuth of the new 14-ports antenna of sector A is wrong update: issue was tackled | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-29 | Yes | W31 |  | 519 | RFI
5052 | 5052-Mareekh_Hadeed_Msq_PF_TASC_O | TASC | AME-952-R | Outdoor |  | 35.925 | 31.9325 | East Amman | Roof Top | ahmad eabd alrawuwf khalid abu khalid altmymy | 0797455212/0798602554/0799836024 | Pole P6X3 | 18 | Full Swap | P.O.2 | Group8S | Cluster-50 |  | NEW | SMP-WO-1414616 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved | Sector C azimuth does not match the view NO TSSR Excel Sheet Update: issue was tackled | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482 | RFI
5216 | 5216-Sarh_Shaheed_PD_EBand_TASC | TASC | AME-284-R | Indoor | 170 | 35.9127 | 31.9908 | East Amman | Roof Top | sulayman ltfy sulayman khariman | 06/4903838 | Pole P6 X 2+ P3 X 1 | 19 | Full Swap | P.O.2 | Group9S | Cluster-52 |  | Traditional | SMP-WO-1414617 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | pictures for the 3 Masts & location of the Antennas in civil table / check the heights of the antennas | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-30 | Yes | W40 | Need Shelter Key | 456 | RFI
5227 | 5227-Sarh_Shaheed_Traffic_Park_PE_Fiber_TASC_O | TASC | AME-816-R | Outdoor |  | 35.9072 | 31.9901 | East Amman | Roof Top | wanas hasan wanas alhasan | 079-90550673/079-7907720 | Pole P9 | 21 | Full Swap | P.O.2 | Group9S | Cluster-52 |  | Traditional | SMP-WO-1414618 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-02 | Yes | W36 |  | 484 | RFI
5253 | 5253-UL_Sport_City_Mid_PE_Fiber_TASC_O | TASC | AME-1082-R | Outdoor |  | 35.9062 | 31.9957 | East Amman | Roof Top |  |  | Tower T 16 | 32 | Full Swap | P.O.2 | Group9S | Cluster-52 |  | Traditional | SMP-WO-1414619 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-12 | Yes | W37 |  | 474 | RFI
5215 | 5215-Itihad_Sch_PC_Fiber_Zain_TASC | TASC | AME-587-R | Indoor | 1510 | 35.9098 | 31.995 | East Amman | Roof Top | nawaf farhan shafiq mhawsh | 079/5413820 | Tower T 12 + P 6 | 27 | Full Swap | P.O.2 | Group9S | Cluster-52 |  | Traditional | SMP-WO-1414620 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved | no 5g solution is suggested | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | Tower details in civil sheet and match it with the tower load & civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-25 | Yes | W39 | Need Shelter Key | 461 | RFI
5237 | 5237-Lizen_School | TASC | AME-1136-R | Outdoor |  | 35.9158 | 31.9996 | Amman | Tower | 0 | 0 | RT | RT T 20 | Full Swap | P.O.2 | Group9S | Cluster-52 |  | Traditional | SMP-WO-1414634 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | CIVIL SHEET & BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-17 | Yes | W38 |  |  | RFI
3928 | Civil_Defence_Bayader_PC_Fiber_TASC_O | TASC | AMW-624-R | Outdoor |  | 35.8283 | 31.9385 | Amman | Tower | 0 | 0 | RT | T 16 | Full Swap | P.O.2 | Group10S | Cluster-39 | Bayader | Traditional | SMP-WO-1414621 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-26 | Yes | W35 |  | 491 | RFI | [6 empty] | Downloaded
3941 | 3941-AbuAlSous_PD_Fiber_TASC | TASC | AMW-743-R | Indoor | 1669 | 35.8113 | 31.9318 | Amman | Tower | 1669 | 1669 | RT | T 16 | Full Swap | P.O.2 | Group10S | Cluster-39 |  | Traditional | SMP-WO-1414635 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | All antennas on sector C should be 240 Wrong Power solution/We can't add more PDU Update: Approved | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes |  | Need Shelter card Key |  | RFI
3901 | 3901-Bassah_2_PE_TASC_O | TASC | AMW-649-R | Outdoor |  | 35.804 | 31.9374 | Amman | Pole | 0 | 0 | RT | P6+P9X2 | Full Swap | P.O.2 | Group10S | Cluster-39 |  | Traditional | SMP-WO-1414636 | Cellcom |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | civil SHEET | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes |  |  |  | RFI
3936 | 3936-U_Bassah_Ent_PF_TASC_O | TASC | AMS-91-R | Outdoor |  | 35.7925 | 31.9328 | Amman | Pole | 0 | 0 | RT | P9 | Full Swap | P.O.2 | Group10S | Cluster-39 |  | Traditional | SMP-WO-1414637 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | no 5g solution is suggested | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | Civil Requirment New no matching with BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-15 | Yes
3914 | Bassah_PC_Fiber_TASC | TASC | AMW-122-R | Indoor | 312 | 35.8104 | 31.9526 | Amman | Tower | 312 | 312 | RT | T 12 | Full Swap | P.O.2 | Group10S | Cluster-39 | Bayader | Traditional | SMP-WO-1414622 | Cellcom | Old SMP | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-03 | Yes | W36 | Need Shelter Key | 483 | RFI
3944 | 3944-Bassah_Ghrous_Ave_PF_TASC_O | TASC | AMS-154-R | Outdoor |  | 35.7852 | 31.9488 | Amman | Pole | 0 | 0 | RT | P9 + P6 | Full Swap | P.O.2 | Group10S | Cluster-39 |  | Traditional | SMP-WO-1414638 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | civil SHEET | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes |  |  |  | RFI
3022 | 3022-Hadi_Msq_PC_GPON_TASC | TASC | AMW-705-R | Indoor | 496 | 35.8809 | 31.9089 | South Amman | Roof Top | walid muhamad yusif albuz | 078-6111101/078-8880618 | Tower T 16 | 20 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1417644 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 |  | Approved | Approved | 2024-10-06 |  | W41 |  | 450
3066 | Rujm_Omeish | TASC | AMS-352-R | Outdoor |  | 35.8751 | 31.9092 | Amman | Tower | 0 | 0 | RT | RT T 20 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419146 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
3059 | 3059-U_P_Sahaba_Methaq_Compound_PE_GPON | ZAIN | AMS-298-P | Electricity Pole |  | 35.8768 | 31.9116 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | approved | Propose another location for ACOC. Wrong Power solution. Update:approved. | Obaidah & Zaid | Approved |  | M. Amro | approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
3016 | 3016-P_Sahaba_Ave_PE_GPON | ZAIN | AMS-6-P | Electricity Pole |  | 35.8749 | 31.912 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | approved |  | Obaidah & Zaid | Approved |  | M. Amro | approved | in BTS 5G sector B should be 120 not 150 | Qais Malkawi & Baker Asaad | approved | location for the new Antennas on the poles (civil table) same note and match with BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
3018 | 3018-Nakheel_PB_Fiber_TASC | TASC | AME-387-R | Indoor | 338 | 35.871 | 31.9072 | South Amman | Roof Top | sulayman kamal shami ghnmh | 079/5579524/079-5818411 | Tower T 16 + P6 X 1 | 26 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1417645 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Restructure is needed Sec A to be on leg 1, Sec B to be on Leg 2. Wrong Sectors naming on 5G Redesigning power is needed -> FPFH to connected on 63 with switching AHEB with AHDA Update: approved. | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | Civil Requirment New | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-30 | Yes | W40 |  | 456
3044 | 3044-P_Sahaba_PE_GPON | ZAIN | AMS-189-P | Electricity Pole |  | 35.8717 | 31.9042 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | approved | 5G Azimuth should match all remaining tech azimuth. No need to mention that we need to upgrade rectifier. Rectifier pic is missing. Update:Accepted. | Obaidah & Zaid | Approved |  | M. Amro | approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
3079 | 3079-U_P_Nakheel_Back_PE_GPON | ZAIN | AMS-240-P | Electricity Pole |  | 35.8587 | 31.9081 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | approved | LLVD & BLVD should be specified clearly. Update: approved. | Obaidah & Zaid | Approved |  | M. Amro | approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
3020 | 3020-P_Nakheel_Ave_PE_GPON | ZAIN | AMW-703-P | Electricity Pole |  | 35.8619 | 31.9061 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1463720 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | approved | Adopt a Power solution with only 3 PDUs. there is a free space for ACOC | Obaidah & Zaid | Approved |  | M. Amro | approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
3034 | 3034-Nakheel_Ave_PE_GPON_TASC_O | TASC | AMS-68-R | Outdoor |  | 35.8641 | 31.9049 | South Amman | Roof Top | salah eisaa iibrahim dadukh | 06/5713398 0777785237/ | Pole P9 + P6 | 21 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1417641 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Adopt a Power solution with only 3 PDUs. Update: approved. | Obaidah & Zaid | Approved | The 5G solution is not clear | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-24 | Yes | W39 |  | 462 | RFI
3004 | 3004-P_Iskan_Saudi_PE_GPON | ZAIN | AMS-59-P | Electricity Pole |  | 35.8682 | 31.9025 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1463721 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | approved | Layout page is missing "mandatory to be in sheet for this kind of sites" We should mention how much DPs are in site for each mast Update:approved. | Moath & Waed | Approved |  | M. Amro | approved | when being swapped please to re-azimuth sector A to zero | Qais Malkawi & Baker Asaad | approved | Determine the needed DP's reason since we are dismantling 6 Antennas and installing 6 Antennas// the location for old & New antennas on each Mast // location of the needed CT // MASTS details - bracings ... | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
3019 | 3019-Nakheel_Back_PE_GPON_TASC | TASC | AMW-688-R | Indoor | 1605 | 35.863 | 31.9019 | South Amman | Roof Top | rbhy musaa husayn abu elya | 06-57125858 079-5163215 | Tower T 20 | 25 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1417646 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Wrong antenna solution Recheck rectifier. Update:approved. | Obaidah & Zaid | Approved |  | M. Amro | Approved | Please Call baker during installation to double check on sector A azimuth | Qais Malkawi & Baker Asaad | Approved | based on the site history with civil please consider all structures are wrong and need to be updated as is for the current situation the proposal will not get approved from PSD departments (check with Acquisition update and return ) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-22 | Yes | W39 | Need Key from Zain | 464
3032 | 3032-Quds_College_Back_PE_GPON_TASC_O | TASC | AME-881-R | Outdoor |  | 35.8592 | 31.8996 | Amman | Pole | 0 | 0 | RT | P9 + P6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419147 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Wrong azimuth for Sector A. Adopt a Power solution with only 3 PDUs. Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | location for the new Antennas on the poles (civil table) | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-30 | Yes |  |  | 456 | RFI
3047 | 3047-Nakheel_Marj_TL_Back_PE_GPON_TASC_O | TASC | AMW-983-R | Outdoor |  | 35.856 | 31.9022 | Amman | Tower | 0 | 0 | RT | T 12 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419148 | Ecotel | Ecotel | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | no need 2PDU to install FPFH2 ,One PDU(100 A)needed | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-18 | Yes |  |  |  | RFI
3002 | 3002-Marj_AlHamam_CTR_PA_Fiber_TASC | TASC | AME-379-R | Indoor | 484 | 35.8479 | 31.9031 | Amman | Tower | 484 | 484 | RT | T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419149 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Wrong naming for 5G sectors Update:Approved | Obaidah & Zaid | Approved | please set the azimuth of sector B to 260 | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-24 | Yes
3042 | 3042-Souq_Marj_AlHamam_PE_GPON_TASC_O | TASC | AME-787-R | Outdoor |  | 35.8411 | 31.898 | Amman | Pole | 0 | 0 | RT | P9*2+P6*1 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419150 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-18 | Yes |  |  |  | RFI
3026 | 3026-Marj_AlHamam_Bardini_CRL_PE_TASC | TASC | AME-414-R | Indoor | 383 | 35.8439 | 31.8979 | Amman | Tower | 383 | 383 | RT | T 12 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419151 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | It should be noted that the all existing antennas(without tdd) will be dismantled and replaced with 14portes antenna | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-30 | Yes | W40
3064 | 3064-Marj_AlHamam_2_Relo | TASC | AME-1129-R | Indoor |  | 35.8398 | 31.9017 | Amman | Tower | 0 | 0 | RT | T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419152 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | Wrong power solution. Cabinet should be installed instead of old cabinet. Update:approved. | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-08 | Yes
3009 | 3009-Um_Abhara_PD_GPON_TASC_O | TASC | AME-842-R | Outdoor |  | 35.8385 | 31.9051 | Amman | Tower | 0 | 0 | RT | T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419153 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | All antennas on sector C should be 240 Wrong Power solution/We can't add more PDU Update: Approved | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  |  | RFI
3012 | 3012-Um_Abhara_2_PE_TASC_O | TASC | AME-660-R | Outdoor |  | 35.8326 | 31.9134 | Amman | Tower | 0 | 0 | RT | T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419154 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-02 | Yes |  |  |  | RFI
3058 | 3058-UL_P_Tarkhees_West_Amman_PF | ZAIN | AMS-290-P | Electricity Pole |  | 35.8318 | 31.9215 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | approved | Adopt a Power solution with only 3 PDUs. Wrong Antenna solution. Update:approved. | Obaidah & Zaid | Approved |  | M. Amro | approved | AAU sector D azimuth is 335 not 355 | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes | W38 |  | 471
3048 | 3048-Um_Abhara_Sch_Back_PF_TASC_O | TASC | AMS-138-R | Outdoor |  | 35.8188 | 31.9168 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1414639 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | No need for DP on all sectors Wrong Power solution Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-30 | Yes | W40 |  | 456 | RFI
3041 | 3041-U_P_Um_Abhara_PF | ZAIN | AMS-23-R | Electricity Pole |  | 35.8362 | 31.9094 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested |  |  |  |  | RAN Only | 2 | [6 empty] | Moath & Waed |  |  | M. Amro |  |  | Qais Malkawi & Baker Asaad |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Cancelled | 2024-09-15
3065 | 3065-Um_Abhara_Bahath_East | ZAIN |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | SMART | SMART | Requested1 | Done |  |  |  | RAN Only | 4 |  |  |  |  | approved | No need to replace second FPFH C.B. Update: approved. | Moath & Waed | Approved |  | M. Amro | approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 |  |  | Owner Number
3052 | 3052-U_P_Um_Abhara_Bahath_East_PE_GPON | ZAIN | AMS-248-P | Electricity Pole |  | 35.8386 | 31.9102 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | approved | Please to mention that we need a DP on sec D Update: approved. | Obaidah & Zaid | Approved |  | M. Amro | approved |  | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-15 | Yes
3049 | 3049-Marj_Top_PE_TASC_O | TASC | AMS-127-R | Outdoor |  | 35.845 | 31.9113 | Amman | Tower | 0 | 0 | RT | T 12 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419155 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Propose another location for ACOC. Wrong Power solution. Update:approved. | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-30 | Yes |  |  | 456 | RFI
3037 | 3037-Duhair_Khamael_Sch_PE_Org_O | ZAIN | AMS-70-R | Outdoor |  | 35.8494 | 31.9139 | South Amman | Roof Top | Duheir_Khamael_School_O |  | Pole 9 | 18 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1417642 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved | in BTS 5G sector B should be 120 not 150 | Qais Malkawi & Baker Asaad | Approved | location for the new Antennas on the poles (civil table) same note and match with BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-02 | Yes | W40 |  | 454
3099 | 3099-Marj_AlHamam_Shawab_CRL_PD_O | TASC | AMS-7-R | Outdoor |  | 35.8476 | 31.9076 | Amman | Tower | 0 | 0 | RT | T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419156 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Wrong power solution. Recheck the Azimuth. Adopt a one solution for ACOC. Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-30 | Yes
3015 | 3015-Marj_AlHamam_Ent_PD_GPON_TASC | TASC | AME-754-R | Indoor | 1722 | 35.8547 | 31.9095 | South Amman | Roof Top | eabuwd eabd alhalim aljalal alearakuzh | 077-2234384 | Tower T 16 | 15 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1417647 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | 5G Azimuth should match all remaining tech azimuth. No need to mention that we need to upgrade rectifier. Rectifier pic is missing. Update:Accepted. | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-30 | Yes | W40 |  | 456
3013 | 3013-Marj_AlHamam_TL_PD_Fiber_TASC | TASC | AME-415-R | Indoor | 447 | 35.8545 | 31.8995 | Amman | Tower | 447 | 447 | RT | T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419157 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | LLVD & BLVD should be specified clearly. Update: approved. | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-22 | Yes | W39
3045 | 3045-Marj_AlHamam_Bridge_PE_GPON_TASC_O | TASC | AMS-119-R | Outdoor |  | 35.8516 | 31.8953 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1414640 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Adopt a Power solution with only 3 PDUs. there is a free space for ACOC | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-09-22 | Yes | W39 |  | 464 | RFI
3033 | 3033-Quds_College_PF_AIBS_Manage | ZAIN/M | AME-595-R | Indoor | 1523 | 35.8677 | 31.8974 | Amman |  | 1523 | 1523 | RT | P9 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419158 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 3 | IBS-A |  |  |  | Approved | Indoor Sector should be clearer. Cabinet should be installed instead of old cabinet. No need to mention Rectifier swapping. Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved | Civil Requirment New Mast c details !! in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-10-02 | Yes
3008 | 3008-CMD_Control_CTR_PF_Fiber_AIBS_Manage | ZAIN/M | AME-624-R | Indoor |  | 35.8774 | 31.901 | Amman | Pole | 0 | 0 | RT | Wall mount dp 3mX2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1414641 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 5 | A |  |  |  | Approved | Layout page is missing "mandatory to be in sheet for this kind of sites" We should mention how much DPs are in site for each mast Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved | when being swapped please to re-azimuth sector A to zero | Qais Malkawi & Baker Asaad | Approved | Determine the needed DP's reason since we are dismantling 6 Antennas and installing 6 Antennas// the location for old & New antennas on each Mast // location of the needed CT // MASTS details - bracings ... | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-11-10 | Yes | W46 | CMD Access - Alkhawaldeh Zain
3036 | 3036-PSD_Main_Bldg_Ameesh_PF_DEIBS_O | ZAIN | AMW-833-R | Outdoor |  | 35.8762 | 31.9014 | South Amman | Roof Top | PSD Main building ameesh |  | Pole 9 | 15 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1417643 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 5 | IBS-E |  |  |  | Approved | Wrong antenna solution Recheck rectifier. Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved | Please Call baker during installation to double check on sector A azimuth | Qais Malkawi & Baker Asaad | Approved | based on the site history with civil please consider all structures are wrong and need to be updated as is for the current situation the proposal will not get approved from PSD departments (check with Acquisition update and return ) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-23 | Yes | W43 |  | 433
3055 | 3055-UL_P_Benayat_CMD_Back_PE_GPON | ZAIN | AMS-232-P | Electricity Pole |  | 35.8811 | 31.8997 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | approved | Recheck all sectors azimuth. Adopt a Power solution with only 3 PDUs. Update:approved. | Moath & Waed | Approved |  | M. Amro | approved | 3G sector B azimuth data is written wrong (not following the 6 port) | Qais Malkawi & Baker Asaad | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes | W38 |  | 469
3031 | 3031-P_Benayat_Back_PF_GPON | ZAIN | AMS-60-P | Electricity Pole |  | 35.8838 | 31.8986 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes
3010 | 3010-Benayat_PC_Fiber_TASC | TASC | AME-384-R | Indoor | 46 | 35.8832 | 31.8954 | Amman | Tower | 46 | 46 | RT | T 20 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419159 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Wrong naming for 5G sectors Update:Approved | Moath & Waed | Approved | please set the azimuth of sector B to 260 | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-09-15 | Yes |  |  |  | RFI
3046 | 3046-Hasad_Sch_Back_PF_GPON_TASC_O | TASC | AMS-105-R | Outdoor |  | 35.89 | 31.8895 | Amman | Tower | 0 | 0 | RT | T 20 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419160 | Ecotel | Ecotel | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obaidah & Zaid | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-22 | Yes | W39 |  | 464 | RFI
3038 | 3038-Benayat_South_PF_GPON_TASC_O | TASC | AMS-77-R | Outdoor |  | 35.8969 | 31.8802 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419161 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Alternative Installation on S.A is needed (wide Pic for the tower from S.A Angle) Update: approved. | Moath & Waed | Approved |  | M. Amro | Approved | fix the naming of 5G sectors in BTS . | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-22 | Yes | W39 |  | 464 | RFI
3024 | 3024-Benayat_2_PD_EBand_TASC | TASC | AME-708-R | Indoor | 1632 | 35.89 | 31.8831 | Amman | Tower | 1632 | 1632 | RT | T 12 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419162 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Wrong power solution. Cabinet should be installed instead of old cabinet. Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-30 | Yes |  |  |  | RFI
3061 | 3061-UL_P_Benayat_End | ZAIN | AMS-334-P | Electricity Pole |  | 35.8868 | 31.8809 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes
3062 | 3062-UL_P_Benayat_Abdeen_Mosque | ZAIN | AMS-318-P | Electricity Pole |  | 35.8812 | 31.8911 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | M. Amro | Approved |  | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes
3050 | 3050-Benayat_Mada_PF_TASC_O | TASC | AMS-176-R | Outdoor |  | 35.8797 | 31.8928 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1414642 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Adopt a Power solution with only 3 PDUs. Wrong Antenna solution. Update:approved. | Moath & Waed | Approved |  | M. Amro | Approved | AAU sector D azimuth is 335 not 355 | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-02 | Yes
3001 | 3001-Petra_Uni_PE_O | TASC | AME-782-R | Outdoor |  | 35.8739 | 31.8938 | Amman | Pole | 0 | 0 | RT | P9 x 3 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1414643 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | No need for DP on all sectors Wrong Power solution Update:approved. | Obieda | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-02 | Yes | W40
3028 | 3028-P_Harley_Naour_PF_Relo | ZAIN | AMS-277-P | Electricity Pole |  | 35.8424 | 31.884 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1466267 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved | specify the m-tilt clamp position (or m-tilt direction: up or down) update: Sector's A m-tilt direction is wrong | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-17 | Yes
3021 | 3021-Marj_AlHamam_PA_Fiber_TASC | TASC | AME-390-G | Indoor | 258 | 35.846 | 31.8838 | Amman | Tower | 258 | 258 | GF | T 60 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419163 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | No need to replace second FPFH C.B. Update: approved. | Waed & Moath | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-02 | Yes |  |  |  | RFI
3035 | 3035-Marj_AlHamam_Back_PE_GPON_TASC_O | TASC | AMS-72-R | Outdoor |  | 35.8553 | 31.8821 | Amman | Pole | 0 | 0 | RT | P9 x 3 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1414644 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Please to mention that we need a DP on sec D Update: approved. | Obieda | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-30 | Yes |  |  | 456 | RFI
3040 | 3040-Marj_Um_Suummaq_1_PE_TASC_O | TASC | AME-400-R | Outdoor |  | 35.862 | 31.8756 | Amman | Tower | 0 | 0 | RT | T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419164 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | 5G Azimuth should be with remaining tech.. Update: approved. | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-30 | Yes | W40 |  | 456 | RFI
3027 | 3027-Natural_Ressources_HSG_2_PD_GPON_O | TASC | AMS-9-R | Outdoor |  | 35.8635 | 31.8817 | Amman | Pole | 0 | 0 | RT | P6*2+P9*1 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1414645 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Wrong power solution. Don't mention rectifier changing . Update:approved. | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-25 | Yes |  |  |  | RFI
3056 | 3056-U_P_Universal_Sch_Back_PF | ZAIN | AMS-286-P | Electricity Pole |  | 35.8726 | 31.8832 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes
3014 | 3014-Natural_Ressources_HSG_PD_GPON_O | TASC | AME-780-R | Outdoor |  | 35.8703 | 31.8869 | Amman | Pole | 0 | 0 | RT | P9 X 1 + P6 X2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  | NEW | SMP-WO-1419165 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Wrong power solution. No Need for extra PDU. Azimuth on BTS sheet need to be revised. Update:Accepted. | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-09-22 | Yes | W39 |  | 464 | RFI
3060 | 3060-UL_Quds_College_Back_O | TASC | AMS-332-R | Outdoor |  | 35.8679 | 31.8936 | Amman | Tower | 0 | 0 | RT | RT T 16 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419166 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | The azimuth of sectors A and C does not fit the 360 perspective, and I recommend installing all antennas at the top of the tower (refer to the optimizer for this as well). | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-30 | Yes |  |  |  | RFI
3023 | 3023-Quds_College_St_Back_PE_GPON_TASC_O | TASC | AMS-100-R | Outdoor |  | 35.8629 | 31.894 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419167 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | civil sheet & the table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-11-03 | Yes |  |  |  | RFI
3051 | 3051-BARCA_Rest_Marj_Alhamam_PE_GPON_TASC_O | TASC | AMS-223-R | Outdoor |  | 35.8597 | 31.8911 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419168 | SMART | SMART | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-06 | Yes | W41 |  |  | RFI
3003 | 3003-Marj_Um_Suummaq_PB_Fiber_TASC | TASC | AME-615-R | Indoor | 1542 | 35.8591 | 31.888 | Amman | Pole | 1542 | 795111088 | RT | P9 X 2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419169 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-02 | Yes
3030 | 3030-Bakri_CRL_PE_GPON_TASC_O | TASC | AMS-38-R | Outdoor |  | 35.8518 | 31.8872 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419170 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Propose a location for ACOC. Update: approved. | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-09-24 | Yes |  |  |  | RFI
3054 | 3054-Iskan_Alia_CRL_PF_TASC_O | TASC | AME-852-R | Outdoor |  | 35.855 | 31.8939 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419171 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Recheck all sectors azimuth. Adopt a Power solution with only 3 PDUs. Update:approved. | Moath & Waed | Approved |  | Omar Sami | Approved | 3G sector B azimuth data is written wrong (not following the 6 port) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-10-02 | Yes |  |  |  | RFI
3017 | 3017-Marj_AlHamam_3_PD_Fiber_TASC | TASC | AME-679-R | Indoor | 1597 | 35.8469 | 31.8907 | Amman | Pole | 1597 | 1597 | RT | P9 X 1 + P6 X2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419172 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Correct the "antenna base from roof top level" in the RF sheet for sectors B and C Sector D 2G/3G/4G m-tilt direction does not match with images Wrong "antenna base from roof top level" for sectors B and C correct "4G Mechanical tilting Photo" names update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-24 | Yes
3053 | 3053-UL_Marj_AlHamam_Market_PE_GPON_TASC_O | TASC | AMS-255-R | Outdoor |  | 35.8411 | 31.8938 | Amman | Tower | 0 | 0 | RT | T 12 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419173 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved | Try to increase the 5G to max dp height | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-10-06 | Yes |  |  |  | RFI
3043 | 3043-Talhoni_Marj_AlHamam_PF_GPON_TASC_O | TASC | AMS-57-R | Outdoor |  | 35.8362 | 31.8912 | Amman | Pole | 0 | 0 | RT | P9#2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419175 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-22 | Yes | W39 |  | 464 | RFI
3005 | 3005-Dallah_CRL_PB_Fiber | TASC | AME-381-G | Indoor | 101 | 35.8377 | 31.8961 | Amman | Tower | 101 | 0779080090/0795717524 | GF | T 60 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419176 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Alternative Installation on S.A is needed (wide Pic for the tower from S.A Angle) Update: approved. | Moath & Waed | Approved |  | Omar Sami | Approved | fix the naming of 5G sectors in BTS . | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-11-03 | Yes
3057 | 3057-U_P_Prince_Mohammad_Palace_Ent_PF | ZAIN | AMS-274-P | Electricity Pole |  | 35.8203 | 31.9014 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | approved |  | Moath & Waed | Approved |  | Omar Sami | approved | 2G Sector C M-tilt data and image have something wrong Update: As discussed, 2G sector C will be on the same 14-port antenna and the measured 9 degrees are resulted from DP slope not the clamp | Rabie Otoum | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes
3011 | 3011-Iskan_Nwairan_PF_TASC | TASC | AME-649-R | Indoor | 1568 | 35.8272 | 31.8935 | Amman | Pole | 1568 | 1568 | RT | P9X2+P6X2 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1419177 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved | Double-check the azimuth for all sectors with the optimizer. | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-02 | Yes |  |  |  | RFI
3039 | 3039-P_Iskan_Nweran_PF | ZAIN | AMS-181-P | Electricity Pole |  | 35.8264 | 31.89 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  | SMP-WO-1466270 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes
3029 | 3029-U_P_Princess_Dina_Palace_PF | ZAIN | AMS-201-P | Electricity Pole |  | 35.8183 | 31.8903 | Amman | Pole | 0 | 0 | Electicity Pole | E Pole 11 | Full Swap | P.O.2 | Group11S | Cluster-30 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | approved | wrong power solution | Moath & Waed | Approved |  | Omar Sami | approved | (antenna base from roof top level) does not make sense. As agreed it should measured from top of the antenna. Please check them again update: issue was tackled | Rabie Otoum | approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes
2106 | 2106-Alia_Ave_1_PE_Fiber_TASC_O | TASC | AME-206-R | Outdoor |  | 35.9653 | 31.9495 | East Amman | Roof Top | muhamad mahmud hsn | 078-8394560 | Pole WallMount 3.6m*2+P9*1 | 19 | Full Swap | RO2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1350775 | khalilAlOmari |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-04 | Yes | W23 |  | 574 | RFI |  | Approved
2135 | 2135-Aden_PE_Fiber_TASC_O | TASC | AME-428-R | Outdoor |  | 35.969 | 31.9491 | East Amman | Roof Top | mustafaa eabd alrahmin fadil aleatayat | 06-4909866 079/5104539-0777413130 | Pole P9#2 | 21 | Full Swap | RO2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1355254 | SMART |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-06-06 | Yes | W23 |  | 572 | RFI |  | Approved
2125 | 2125-Yarmouk_St_PE_Fiber_TASC | TASC | AME-221-R | Indoor | 157 | 35.962 | 31.9526 | East Amman | Roof Top | ahmad mahfuz khalil salh |  | Tower T 12 | 21 | Full Swap | RO2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1355256 | khalilAlOmari |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-06 | Yes | W23 |  | 572 | RFI |  | Approved
2150 | 2150-Manara_2_PD_Fiber_TASC |  | AME-242-R | Indoor | 277 | 35.9598 | 31.9488 | East Amman | Roof Top | muhamad salim abu ghnit | 06/4789501 079/5585143 | Pole P6 X 3 | 11 | Full Swap | RO2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1355257 | khalilAlOmari |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | Fill all the civil data in the civil table correctly | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-04-21 09:58 | Yes | W17 |  | 617.5847 | RFI |  | Approved
2113 | 2113-Manara_Top_PD_Fiber_TASC | TASC | AME-730-R | Indoor | 1666 | 35.9627 | 31.9457 | East Amman | Roof Top | hisham muhamad salih eabdallh | 079-6792419 | Pole P6 X 1 + P9 X 1 | 18 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | NEW | SMP-WO-1414623 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Sector names are A, B not A, C Sectors A and B azimuth does not match the view M-tilt Clamp direction (up or down) does not match with the image Need clear image for the m-tilt clamp of sector B Update: sector A azimuth still not matching Same note about m-tilt clamp Update: sector A azimuth still not matching Update: sector A azimuth still not matching | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-22 | Yes | W34 |  | 495
2137 | 2137-Manara_Shaheed_Park_PE_Fiber_TASC_O | TASC | AME-940-R | Outdoor |  | 35.9589 | 31.9465 | East Amman | Roof Top | sharif saeid eubdallah alqwasmy | 0796202479/0796828054 | Pole P6X2 | 16 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414539 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | Rejected Sector B & C are to close to each other - refer to optimizer first - no change :( | Omar Sami | Approved | 2G is only two sectors (A and B) 3G m-tilt direction does not match the images sector B of the AAU m-tilt is 4 (85.8 ~ 86) update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
2104 | 2104-Manara_3_PC_Fiber_TASC | TASC | AME-506-R | Indoor | 452 | 35.9578 | 31.9455 | East Amman | Roof Top | saham hasan khalwi alhimuni | 06-4787670 079/5483583 | Tower T 12 | 21 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414540 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | mismatch between sector A and C new 14-port antenna azimuth and the current azimuth 2G and 4G are on the AAU but there is mismatch in m-tilt values for the same sector Since 3G and 4G have varying azimuths, please label the image to indicate which view corresponds to which technology update: first note still exist, please check the azimuth mismatch in the RF and BTS sheets update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-02 | Yes | W36 | Need Shelter card Key | 484
2169 | 2169-Ten_Bridge_2_PD_Fiber_TASC | TASC | AME-742-R | Indoor | 1692 | 35.9606 | 31.9418 | East Amman | Roof Top | muhamad saeid muhamad elyan | 079-5578494 | Pole P6 X 1 + P9 X 1 | 14 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414541 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | wrong 5G Sectors | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449 | RFI
2114 | 2114-Ten_Bridge_PC_Fiber_TASC | TASC | AME-114-R | Indoor | 72 | 35.963 | 31.9401 | East Amman | Roof Top | samir euthman tawfiq mady |  | Tower T 12 + P6 X 2 | 16 | Full Swap | P.O.2 | Group12S | Cluster-21 |  |  | SMP-WO-1439886 | Al-Lewan | Ecotel>> Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | The azimuth of sectors A and C does not fit the 360 perspective, and I recommend installing all antennas at the top of the tower (refer to the optimizer for this as well). | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-11-03 | Yes | W45 | Shelter Key Problem | 422 | RFI
2103 | 2103-Manara_Tatweer_PE_Fiber_TASC_O | TASC | AME-808-R | Outdoor |  | 35.9662 | 31.9384 | East Amman | Roof Top | jbr eabd alqadir husayn alhlaj | 06-4700609 079-6192093/079-7160343 | Tower T 12 | 27 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414542 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved | Azimuth of sector A & B are to close , refer to optimizer to set new values | Omar Sami | Approved | Sectors B and C heights are wrong update: issue was tackled As discussed, sector A azimuth was changed to 60 to mitigate sectors overlapping New Modified TSSR sheet is not found update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-30 | Yes | W44 |  | 426 | RFI
2109 | 2109-Manara_4_PE_Fiber_TASC_O | TASC | AME-669-R | Outdoor |  | 35.9656 | 31.9425 | East Amman | Roof Top | wajih muhamad ahmad abu salim | 06-4704500 07777-4868/079-9025859 | Pole P4+P6 | 13 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414543 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | Azimuth Separation for Sector C & D , recommended values (190,260) | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-22 | Yes | W34 |  | 495 | RFI
2120 | 2120-UL_Aden_Middle_PF_TASC_O | TASC | AME-1048-R | Outdoor |  | 35.9696 | 31.9424 | East Amman | Roof Top |  |  | Pole P9#2 | 19 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414544 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482 | RFI
2119 | 2119-UL_Manarah_AbuTaleb_St_PF_TASC_O | TASC | AME-1036-R | Outdoor |  | 35.969 | 31.94 | East Amman | Roof Top |  |  | Pole P9X2+P6 | 19 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414559 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved | I have two values of azimuth for Sector C please correct them | Omar Sami | Approved | Sector D height is wrong in RF sheet update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449 | RFI
2136 | 2136-Um_Nowarah_Four_Ave_PE_Fiber_TASC_O | TASC | AME-865-R | Outdoor |  | 35.9749 | 31.9361 | East Amman | Roof Top | eisaa ahmad salih hmd | 06-4736743 0796291130/0797155535 | Pole P6X2 | 16 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414560 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | need Rect Change + ACOC location instead of it | Moath & Waed | Approved |  | Omar Sami | Approved | Sectors B & C new 14-port antennas height need to be corrected in the BTS sheet update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449
2134 | 2134-Um_Nowarah_2_PE_Fiber_TASC_O | TASC | AME-1022-R | Outdoor |  | 35.9717 | 31.9349 | East Amman | Roof Top | smih muhamad eali yasin | 795640822/0785059303/0798371356 | Pole P9*2+P6*1 | 15 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414561 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Correct the "antenna base from roof top level" in the RF sheet for sectors B and C Sector D 2G/3G/4G m-tilt direction does not match with images Wrong "antenna base from roof top level" for sectors B and C correct "4G Mechanical tilting Photo" names update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449 | RFI
2123 | 2123-Um_Nowarah_TL_PC | TASC | AME-739-R | Indoor | 1693 | 35.9717 | 31.9326 | East Amman | Roof Top | muhamad eadnan sulayman aleksh | 079-6398163 | Tower T 12 | 12 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414562 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Moath & Waed | Approved | Try to increase the 5G to max dp height | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-07 | Yes | W41 | Need Access Card | 449 | RFI
2127 | 2127-UL_Um_Nowarah_South_PE_O | TASC | AME-1106-R | Outdoor |  | 35.9684 | 31.9333 | East Amman | Roof Top |  |  | Tower 16 | 25 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414563 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
2112 | 2112-Um_Nowarah_PE_Fiber_Org_TASC_O | TASC | AME-211-R | Outdoor |  | 35.9694 | 31.9288 | East Amman | Roof Top | jabir sabri jabir sbh | 06/4748484 078-5956364/079-5285211 | Pole P6 X 3 | 21 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414564 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-08 | Yes | W41 |  | 448
2110 | 2110-Um_Nowarah_Asia_Sch_PE_Fiber_TASC_O | TASC | AME-862-R | Outdoor |  | 35.9663 | 31.9301 | East Amman | Roof Top | rubin eali muhamad abu arshyd | 0795219121/0788104294 | Pole P6*1+P9*2 | 24 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414565 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | 2G Sector C M-tilt data and image have something wrong Update: As discussed, 2G sector C will be on the same 14-port antenna and the measured 9 degrees are resulted from DP slope not the clamp | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-14 | Yes | W42 |  | 442 | RFI
2102 | 2102-Manara_Tabein_Msq_PE_Fiber_TASC_O | TASC | AME-809-R | Outdoor |  | 35.9639 | 31.9331 | East Amman | Roof Top | salim eiad salim saeadat | 079-6724403/079-5306543 | Pole P9 + P6 | 21 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414566 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved | Double-check the azimuth for all sectors with the optimizer. | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482 | RFI
2131 | 2131-UL_Manara_School_Back_PE_O | TASC | AME-1097-R | Outdoor |  | 35.9593 | 31.9353 | East Amman | Roof Top |  |  | Tower 16 | 25 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414567 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
2108 | 2108-Um_Nowarah_PSD_PE_Fiber_TASC_O | TASC | AME-822-R | Outdoor |  | 35.9597 | 31.9303 | East Amman | Roof Top | mudiriat al amn aleamm |  | Pole P9 X 1 + Wall mount 3m x1 | 13 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414568 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | wrong power solution | Moath & Waed | Approved |  | Omar Sami | Approved | (antenna base from roof top level) does not make sense. As agreed it should measured from top of the antenna. Please check them again update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-10-28 | Yes | W44 | PSD Access - Maram Tasc | 428
2116 | 2116-Wadi_Remam_CPLX_PE_Fiber_TASC_O | TASC | AME-831-R | Outdoor |  | 35.954 | 31.942 | East Amman | Roof Top | lawiy khalil salamih ghaly | 079-88064415/079-5151612 | Tower T 16 | 18 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414569 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-22 | Yes | W34 |  | 495 | RFI
2168 | 2168-Manara_PC_Fiber_TASC | TASC | AME-249-R | Indoor | 276 | 35.9489 | 31.9417 | East Amman | Roof Top | hani salamat sulayman alhayk |  | Tower T 12 | 24 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414570 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-07 | Yes | W41 | Need Access Card | 449
2126 | 2126-Basheer_2_PD_Fiber_TASC | TASC | AME-222-R | Indoor | 42 | 35.9459 | 31.9354 | East Amman | Roof Top | fatimat saeid yusif mhmd | 06/4783416 079-5762172/079-9859881 | Tower T 12 | 21 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414571 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449 | RFI
2130 | 2130-Um_Nowarah_10_Bridge_PF_Fiber_TASC | TASC | AME-746-R | Indoor | 1690 | 35.9551 | 31.9359 | East Amman | Roof Top | mufid husni eabd eubdalilh | 079-9000777 | Pole P6 X 1 + P9 X 1 | 37 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414572 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | Fill all the civil data in the civil table correctly | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-23 | Yes | W43 |  | 433 | RFI
2107 | 2107-Qweismeh_2_PE_Fiber_TASC_O | TASC | AME-638-R | Outdoor |  | 35.9517 | 31.9357 | East Amman | Roof Top | eumar mahmud sulayman dawud | 0777-229821/078-6269522/079-5333565 | Pole P9 X 1 + P9 X 1 | 18 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414573 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Sector names are A, B not A, C Sectors A and B azimuth does not match the view M-tilt Clamp direction (up or down) does not match with the image Need clear image for the m-tilt clamp of sector B Update: sector A azimuth still not matching Same note about m-tilt clamp Update: sector A azimuth still not matching Update: sector A azimuth still not matching | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-12 | Yes | W37 |  | 474 | RFI
2101 | 2101-Qweismeh_PRC_Taghreed_Sch_PE_Fiber_TASC_O | TASC | AME-223-R | Outdoor |  | 35.9489 | 31.9311 | East Amman | Roof Top | mahmud eali eabd alqadir eali salh | 06-4141305 079-5121228 | Pole P9 X 1 + Wallmounted Dp(3m) | 18 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414574 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | Rejected Sector B & C are to close to each other - refer to optimizer first - no change :( | Omar Sami | Approved | 2G is only two sectors (A and B) 3G m-tilt direction does not match the images sector B of the AAU m-tilt is 4 (85.8 ~ 86) update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-21 | Yes | W43 |  | 435
2115 | 2115-Qweismeh_Ind_2_PE_Fiber_TASC | TASC | AME-704-R | Indoor | 1645 | 35.9457 | 31.9286 | East Amman | Roof Top | hamid shahadat hamid abu jnyd | 06-4777144 079-502011/0777-517011 | Tower T 16 | 17 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | NEW | SMP-WO-1414625 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | mismatch between sector A and C new 14-port antenna azimuth and the current azimuth 2G and 4G are on the AAU but there is mismatch in m-tilt values for the same sector Since 3G and 4G have varying azimuths, please label the image to indicate which view corresponds to which technology update: first note still exist, please check the azimuth mismatch in the RF and BTS sheets update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482
2121 | 2121-Qweismeh_Stadium_PC_Fiber_TASC | TASC | AME-218-R | Indoor | 126 | 35.9491 | 31.9268 | East Amman | Roof Top | mahmud eabd hasan muhayze | 06/4126423 | Tower T 16 | 28 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414575 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | wrong 5G Sectors | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-02 | Yes | W40 |  | 454
2117 | 2117-Qweismeh_Market_PE_Fiber_TASC_O | TASC | AME-832-R | Outdoor |  | 35.9515 | 31.9243 | East Amman | Roof Top | warathat almarhum hasan muhamad husayn njibh | 07909052484 / 0799541529 / 0796545427 | Pole P6 X 1 + P9 X 2 | 22 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | NEW | SMP-WO-1414626 | Ecotel |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-08-26 | Yes | W35 |  | 491
2111 | 2111-Qweismeh_Stadium_Top_PE_Fiber_TASC_O | TASC | AME-1011-R | Outdoor |  | 35.9549 | 31.9269 | East Amman | Roof Top | anwar eabd alfattah namuru alshalalifah | 0796732732/0799553395/0796707970 | Tower T 16 | 14 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414576 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | Civil Requirment New no matching with BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-16 | Yes | W42 |  | 440
2138 | 2138-Maadi_2_PE_Fiber_TASC_O | TASC | AME-981-R | Outdoor |  | 35.9607 | 31.9224 | East Amman | Roof Top | walid taemuh iibrahim almujdlawy | 0795783601/0786020852 | Pole P9 + P6 | 18 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414577 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved | Azimuth Separation for Sector C & D , recommended values (190,260) | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-10-21 | Yes | W43 |  | 435
2122 | 2122-Um_Nowarah_Maadi_PE_Fiber_TASC | TASC | AME-732-R | Indoor | 1671 | 35.9657 | 31.9241 | East Amman | Roof Top | warathat almarhum saeid ahmad muhamad aldaeamst | 079-5525731 | Tower T 16 | 21 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414578 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482
2124 | 2124-AbuAlanda_Rufaida_Msq_PE_TASC_O | TASC | AMS-219-R | Outdoor |  | 35.972 | 31.9231 | East Amman | Roof Top |  |  | Pole P6X4 | 6 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414579 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Mismatch between azimuth of sector B 3G and the view 2G sectors are (A,B) not (B,C) 2G and (3G,4G) have different antenna types, so please provided labeled m-tilt clamp images for each update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449
2118 | 2118-Abu_Alanda_Oruba_District | TASC | AMS-346-R | Outdoor |  | 35.9687 | 31.9189 | Amman | Tower | 0 | 0 | RT | RT T 16 | Full Swap | P.O.2 | Group12S | Cluster-21 |  | Traditional | SMP-WO-1414646 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-07 | Yes | W41 |  |  | RFI
5455 | 5455-Ashrafyeh_Musdar_PD_Fiber_TASC_O | TASC | AME-960-R | Outdoor |  | 35.9309 | 31.9407 | East Amman | Roof Top | hanna eisaa sulayman abu alzlf | 05/3243477 0777471500/0779623692 | Pole P9*2+P6*1 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426889 | Ecotel | Ecotel | Requested1 | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | Use same DP for 5G +TDD | Moath & Waed | Approved | Sector D Azimuth is wrong double check | Omar Sami | Approved | Sector D Azimuth does not match the view update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449
5430 | 5430-Arman_CRL_PD_Fiber_TASC | TASC | AME-724-R | Indoor | 1668 | 35.9323 | 31.9384 | East Amman | Roof Top | khalayl saeid husayn sluw | 079-5489087 | Pole P6 X 2 | 15 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426890 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-28 | Yes | W35 |  | 489
5413 | 5413-Ashrafyeh_PC_Fiber_Manage | ZAIN/M | AME-376-R | Indoor | 397 | 35.9381 | 31.936 | East Amman | Roof Top | nakhlat matri salamat ghanim | 06-4772379 0795505020/0795528213/0795656237 | Pole P6 X 4 + P9 X 1 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426891 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Proposed Solution should follow 4G Azimuth not 2G/3G | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-01 | Yes | W36 |  | 485 | RFI
5408 | 5408-Basheer_Ent_PC_Fiber_TASC | TASC | AME-686-R | Indoor | 177 | 35.9381 | 31.9394 | East Amman | Roof Top | ahmad hasan fathi alshanawy | 079-5055951/079-5111258 | Pole P6 X 3 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426892 | Ecotel | Ecotel | Requested1 | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | photos and details for the 5 MASTS and where is the 20m tower? Location of each Antenna on the masts | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482
5405 | 5405-Ashrafyeh_1_PE_Fiber_TASC_O | TASC | AME-328-R | Outdoor |  | 35.9391 | 31.9427 | East Amman | Roof Top | yaequb eabd almajid aleashi | 06/4615942 079-5521115 | Pole WallMount3m*1+P6*1 | 12 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426893 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved | no 5g solution is suggested | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482
5424 | 5424-P_Ashrafyeh_Top_PF_Fiber | ZAIN | AME-793-P | Electricity Pole |  | 35.9429 | 31.9446 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1475040 | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-18 | Yes | W34 |  | 499
5409 | 5409-Gofeh_Top_PE_Fiber_TASC_O | TASC | AME-712-R | Outdoor |  | 35.9399 | 31.9459 | East Amman | Roof Top | ealia jasir eabd almahdi alharasis | 077-5690341/079-99025908 | Tower T 16 +P6#1 | 15 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426894 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482 | RFI
5439 | 5439-Gofeh_Camp_PE_Fiber_TASC_O | TASC | AME-337-R | Outdoor |  | 35.9376 | 31.9467 | East Amman | Roof Top | iibrahim eisaa muhamad khatab |  | Pole WallMount 6m*1+ WallMount 3m*1 | 15 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426895 | Ecotel | Ecotel | Requested1 | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | We need to add concrete instead of RFU cabinet./need to new pole | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | Fill all the data in Civil table, and make sure regarding the Requested Dp's length since one of the wall mounts already 3m Specify each sector on which pole/ wall mount | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | B | Approved | Approved | 2024-11-03 | Yes | W45 |  | 422
5422 | 5422-Arman_3_PD_Fiber_TASC | TASC | AME-764-R | Indoor | 1738 | 35.9363 | 31.9435 | East Amman | Roof Top | iibrahim ahmad musaa dawd | 079-7222211 | Pole P6 X 1 + P9 X 2 | 21 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426896 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482
5453 | 5453-Gofeh_Saowdah_Sch_PE_Fiber_TASC_O | TASC | AME-953-R | Outdoor |  | 35.9322 | 31.9425 | East Amman | Roof Top | warathat mahmud khalil iibrahim ased | 0795135138/0798616181/0792811482 | Pole P9 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426897 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Sector is symbol is B not A, for all sectors. what about 6-port antenna ? will it be disconnected ? update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482 | RFI
5416 | 5416-Hay_Arman_PD_Fiber_TASC | TASC | AME-502-R | Indoor | 434 | 35.9335 | 31.9402 | East Amman | Roof Top | nadiana jamil mufdi alsafdi | 06/4771677 079/6770052 | Tower T 12 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426898 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 2 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | Sector names are B, C not A, B Wrong m-tilt value for sector A 4G (AAU) Modify antenna base from roof top level values update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-10-06 | Yes | W41 |  | 450
5419 | 5419-Ashrafyeh_Mada_PE_Fiber_TASC_O | TASC | AME-898-R | Outdoor |  | 35.9358 | 31.9409 | East Amman | Roof Top | mahmud muhamad ahmad alhars | 795542905 | Tower T 12 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426899 | Ecotel | Ecotel | Requested1 | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-29 | Yes | W35 |  | 488 | RFI
5458 | 5458-Hay_Arman_1_PF_M | ZAIN | AME-371-R | Micro Cell |  | 35.935 | 31.9424 | Amman | Pole | 0 | 0 | RT | RT P 3 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1439885 | Al-Lewan | Ecotel>> Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | determine the location of the needed CT on the civil requirements new | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-11-10 | Yes | W46
5445 | 5445-Arman_2_PE_Fiber_TASC_O | TASC | AME-361-R | Outdoor |  | 35.936 | 31.9422 | East Amman | Roof Top | eali muhamad mahmud abu su | 06/4778831 077/488328 - 079/5537438 | Pole P6+P3 | 14 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1426900 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | Masts details & current antennas in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-04 | Yes | W36 |  | 482 | RFI
5414 | 5414-Basheer_Hospital_PE_Manage_O | ZAIN/M | AME-848-R | Outdoor |  | 35.9413 | 31.9396 | East Amman | Roof Top | maeali wazir almaliat bial iidafat liwazifatih | 799050499 | Pole P4 X 3 + Wallmounted dp 1m x 3 | 20 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427320 | Al-Lewan | Ecotel>> Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved | Bore sector B & C are close refer to optimization | Omar Sami | Approved |  | Rabie Otoum | Approved | Civil Requirment New no matching with BTS Location of each Antenna on the masts // update the masts height to 4m not 3m | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-11-16 | Yes | W46 | Need Access leter from health ministry | 409
5404 | 5404-Hay_Um_Teneh_PD_Fiber_TASC | TASC | AME-685-R | Indoor | 113 | 35.9435 | 31.9387 | East Amman | Roof Top | yusuf iibrahim yunis abu wardh | 079-5850835/079-5671636 | Pole P6 X 3 | 21 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427321 | Al-Lewan | Ecotel>> Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved | Masts details & current antennas in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-11-10 | Yes | W46 |  | 415 | RFI
5417 | 5417-Um_Tineh_Mada_PE_Fiber_TASC_O | TASC | AME-888-R | Outdoor |  | 35.9452 | 31.941 | East Amman | Roof Top | riad ahmad eabd alqadir eulyan | 797135781 | Pole P6*2 | 19 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427322 | Ecotel | Ecotel | Requested1 | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | modify 4G3G Mechanical tilting Photo sector C label | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468
5415 | 5415-Blood_Bank_PE_Fiber_TASC | TASC | AME-481-R | Indoor | 408 | 35.9436 | 31.9432 | East Amman | Roof Top | yusuf ealia eudtallh alsawfany | 06-4390884 079-5934550 | Pole P6 X 3 + P8 X 1 | 21 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427323 | Al-Lewan | Ecotel>> Al-Lewan | Requested1 | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved | sector B 2G m-tilt data and image does not make sense update: same issue still exist Update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-11-16 | Yes | W46 |  | 409
5440 | 5440-UL_Taj_PSD_West_PE_Fiber_TASC_O | TASC | AME-1075-R | Outdoor |  | 35.9489 | 31.9454 | East Amman | Roof Top | farhan rezq allah | 02/6236321 - 02/6236323 | Tower T 20 | 30 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427324 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
5450 | 5450-Taj_Hayooz_Ave_PE_Fiber_TASC_O | TASC | AME-931-R | Outdoor |  | 35.9531 | 31.9484 | East Amman | Roof Top | muhamad ghalib :mhmd mahmud maraei | 786498946 | Pole P9 + P6 | 14 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427325 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
5410 | 5410-Taj_2_PC_Fiber_TASC | TASC | AME-210-R | Indoor | 12 | 35.955 | 31.9503 | East Amman | Roof Top | jamil eabd aleaziz eabd alhalim eamru | 06/4770978 | Pole P6 X 2 + P9 X 1 | 15 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427326 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Moath & Waed | Approved |  | Baher Obaidat | Approved | Mismatch between azimuth of sector B 3G and the view 2G sectors are (A,B) not (B,C) 2G and (3G,4G) have different antenna types, so please provided labeled m-tilt clamp images for each update: issues were tackled | Qais Malkawi & Baker Asaad | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449 | RFI
5456 | 5456-Taj_Sch_PF_TASC_O | TASC | AME-991-R | Outdoor |  | 35.9589 | 31.9525 | East Amman | Roof Top | kawkab zael eabd khalf alharasisa | 0799555230/0777723649 | Pole P9#2 | 14 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427327 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
5411 | 5411-Nasha_PD_TASC | TASC | AME-102-R | Indoor | 298 | 35.9592 | 31.9582 | East Amman | Roof Top | eadil muhamad dhiban albaysani | 06/4774335 | Tower T 10 | 19 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427328 | Al-Lewan | Ecotel>> Al-Lewan | Requested1 | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | SC Solution is Wrong , SD is 2G only |  | Approved |  |  | Approved | 4G sectors are (A, B, and C) not (A, B, and D) update: issue was tackled |  | Approved | Tower details in civil sheet! |  | Approved |  | Yes |  | A | Approved | Approved | 2024-11-10 | Yes | W46 |  | 415
5454 | 5454-Taj_Rising_PE_Fiber_TASC_O | TASC | AME-959-R | Outdoor |  | 35.9585 | 31.9568 | East Amman | Roof Top | majid iibrahim muhamad almjdlany | 786495230 | Pole P9 | 15 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427329 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 2 |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  |  | A | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
5423 | 5423-Taj_PC_Fiber_TASC | TASC | AME-219-R | Indoor | 48 | 35.9589 | 31.9552 | East Amman | Roof Top | faysal adyb muhamad mustaghaa |  | Pole P6 X 3 + Wallmounting Dp x 1 | 12 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427330 | Ecotel | Ecotel | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-11-10 | Yes | W46 |  | 415 | RFI
5441 | 5441-Taj_3_PC_Fiber | TASC | AME-234-R | Indoor | 368 | 35.9549 | 31.9534 | East Amman | Roof Top | fathi husayn yusif rabieat | 06/4782197 079/5602383 | Pole P6 X 4 + P9 X 1 | 19 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427331 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | photos and details for the 5 MASTS and where is the 20m tower? Location of each Antenna on the masts | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-11-16 | Yes | W46 |  | 409
5403 | 5403-Hay_Tafaileh_PE_Fiber_TASC_O | TASC | AME-623-R | Outdoor | 135 | 35.9492 | 31.9516 | East Amman | Roof Top | mahdi eizat muhamad alaghbr | 796373109 | Pole P6 X 3 | 15 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427332 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily | Yes | 5 |  | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449
5402 | 5402-Tafaileh_2_PE_Fiber_TASC_O | TASC | AME-327-R | Outdoor |  | 35.9507 | 31.951 | East Amman | Roof Top | mahir ahmad eisaa aleulwan | 079-7261345 | Pole P9*1+Tripod 6m *1 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427333 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-09-18 | Yes | W38 |  | 468 | RFI
5452 | 5452-P_Taj_Darak_St_PF | ZAIN | AME-1001-P | Electricity Pole |  | 35.9501 | 31.9495 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  |  | ElecticityPole | Electicity Pole | Not Requested | Done |  |  |  | RAN Only | 1 | [6 empty] | Murad Al-khalily |  |  | Murad Al-khalily |  |  | Murad Al-khalily |  |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 1 |  | Approved | Approved | 2024-08-18 | Yes | W34 |  | 499
5407 | 5407-Taj_St_PC_Fiber_TASC | TASC | AME-618-R | Indoor | 1549 | 35.9468 | 31.9466 | East Amman | Roof Top | khalid ahmad samarayn bisifatih wakilana ean samarina | 06-4775986 079-9320584 | Pole P6 X 2 + P9 X 2 | 18 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427334 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | 4G sector B (AAU) m-tilt is 3.4 which is better to approximate it to 3 not 4 update: issue was tackled | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-10-06 | Yes | W41 |  | 450
5425 | 5425-Hay_Tafaileh_CTR_PE_Fiber_TASC_O | TASC | AME-1034-R | Outdoor |  | 35.9466 | 31.948 | East Amman | Roof Top |  |  | Pole P9#2 | 22 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427335 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily | Yes | 5 |  | Approved | Approved | 2024-09-22 | Yes | W39 |  | 464
5418 | 5418-Tafaileh_Ave_PF_TASC_O | TASC | AME-341-R | Outdoor |  | 35.9441 | 31.95 | East Amman | Roof Top | maryam mahmud iibrahim eubd | 06/4774094 | Pole P6*2 | 13 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427336 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Sector is symbol is B not A, for all sectors. what about 6-port antenna ? will it be disconnected ? update: issues were tackled | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-10-07 | Yes | W41 |  | 449 | RFI
5421 | 5421-Gofeh_PE_Fiber_TASC | TASC | AME-344-R | Indoor | 1509 | 35.9437 | 31.9479 | East Amman | Roof Top | wayil majid khalil erft |  | Pole P6 x 3 + P8 X 1 | 15 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427337 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 2 |  | Yes |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Sector names are B, C not A, B Wrong m-tilt value for sector A 4G (AAU) Modify antenna base from roof top level values update: issues were tackled | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 | A | Approved | Approved | 2024-10-08 | Yes | W41 |  | 448
5451 | 5451-Gofeh_Rising_PE_Fiber_TASC_O | TASC | AME-943-R | Outdoor |  | 35.9415 | 31.9477 | East Amman | Roof Top | eadil salim eabdalilah aleibdalata | 0795521263/0772041344 | Pole P9#2 | 21 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427338 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-09-18 |  | W38 |  | 468 | RFI
5406 | 5406-Royal_Court_PF_O | ZAIN | AME-633-R | Outdoor |  | 35.9485 | 31.9575 | East Amman | Roof Top | aldiywan almulkiu aleamiru qasr raghdan aleamr | 0777-660666 | Pole 6 | 6 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427339 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Masts details & current antennas in civil sheet No 5G ? OR with // and where to be installed since only 4 DP available | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-11-16 |  | W46 |  | 409
5401 | 5401-Royal_Court_2_PF_O | ZAIN | AME-819-R | Outdoor |  | 35.9479 | 31.9553 | East Amman | Roof Top | Royal court |  | Pole 6 | 6 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427340 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Masts details & current antennas in civil sheet | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-11-10 |  | W46 |  | 415
5457 | 5457-Royal_Court_3_PE_Fiber_TASC_Relo_O | TASC | AME-1033-R | Outdoor |  | 35.9442 | 31.9573 | East Amman | Roof Top |  |  | Tower T 16 | 16 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427341 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Civil Requirment New no matching with BTS | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-11-16 |  | W46 |  | 409
5459 | 5459-U_Royal_Court_Offices_Club_M | ZAIN | AME-1095-R | Micro Cell |  | 35.9481 | 31.9587 | Amman | Pole | 0 | 0 | RT | RT P 9 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1419181 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Masts details & current antennas in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 |  | Approved | Approved | 2024-11-03 |  | W45 |  |  | RFI
5420 | 5420-South_Hashmi_2_PE_EBand_TASC | TASC | AME-111-R | Indoor | 305 | 35.9547 | 31.9608 | East Amman | Roof Top | euthman muhamad shahadat hajajan | 06/4913287 | Pole P6 X 3 + P4 X 1 | 21 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427342 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved | modify 4G3G Mechanical tilting Photo sector C label |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 |  | Approved | Approved | 2024-09-15 |  | W38 |  | 471 | RFI
5412 | 5412-UL_Raghadan_Mahatta_Complex_PF_O | ZAIN | AME-1102-R | Outdoor |  | 35.9619 | 31.9647 | East Amman | Roof Top |  |  | Pole 9 * 3 | 9 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427343 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 |  | Approved | Approved | 2024-10-15 |  | W42 |  | 441
5443 | 5443-Nasser_PC_Fiber_TASC | TASC | AME-122-R | Indoor | 299 | 35.964 | 31.9639 | East Amman | Roof Top | eayid muhidiun khalf rashid aleabdalilaat | 06-5065371 079-9913137 | Tower T 12 | 22 | Full Swap | P.O.2 | Group13S | Cluster-54 |  |  | SMP-WO-1427344 | Al-Lewan | Al-Lewan | Requested1 | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | Yes | 5 |  | Approved | Approved | 2024-10-14 |  | W42 |  | 442
1708 | 1708-UL_JKB_Bank_PF_O | ZAIN | AME-1068-R | IBS |  | 35.9151 | 31.963 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 | Abdali & Jabal Husein | Traditional | SMP-WO-1414628 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 1 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2024-11-13 |  | W46 |  | 412
3921 | 3921-Hikma_Company_HQ_Building_PE_IBS | ZAIN | AMS-245-R | IBS |  | 35.8502 | 31.9495 | Amman | IBS | aidwiat alhikma | 06-5811692- 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-39 |  |  | SMP-WO-1486592 | IBS | IBS | Not Requested | Done |  |  |  | RAN Only | 2 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2024-11-13 |  | W46 |  | 412
5427 | 5427-Basheer_Hospital_PF_IBS_O | ZAIN | AME-1069-R | IBS |  | 35.9417 | 31.9389 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-54 |  |  | SMP-WO-1419179 | Al-Lewan |  | Not Requested | Done |  |  |  | RAN Only | 4 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2024-11-13 |  | W46
120 | 120-Galleria_Mall_PE_Fiber_IBS_Zain_Manage | ZAIN/M | AMW-795-R | IBS | 1719 | 35.8623 | 31.9594 | Amman | IBS |  |  |  |  | Full Swap | P.O.2 | IBS | Cluster-1 |  |  | SMP-WO-1486590 | SMART |  |  | Done |  |  |  | RAN Only |  | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved
3508 | 3508-Four_Seasons_PF_IBS_O | ZAIN | AMW-70-R | IBS |  | 35.881 | 31.9621 | Amman | IBS |  |  |  |  | Full Swap | P.O.2 | IBS | Cluster-35 |  |  | SMP-WO-1486591 | SMART | [6 empty] | RAN Only |  | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS
1704 | 1704-UL_Abdali_Boulevard_PD_Org | ZAIN | AME-857-R | IBS |  | 35.9068 | 31.9645 | East Amman | IBS | aleabdaliu bwlyfard |  | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 | Abdali & Jabal Husein |  |  | IBS | IBS | Not Requested |  |  |  |  | RAN Only | 5 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18 |  | W34 |  | 499
1748 | 1748-DAMAC_Tower_PF_IBS_Org | ZAIN | AME-999-R | IBS |  | 35.9097 | 31.9631 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419184 |  |  | Not Requested |  |  |  |  | RAN Only | 2 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1707 | 1707-Rotana_Tower_PF_IBS_Org | ZAIN | AME-893-R | IBS |  | 35.9031 | 31.965 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419185 |  |  | Not Requested |  |  |  |  | RAN Only | 3 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1739 | 1739-W_Hotel_Abdali_PF_IBS_Org | ZAIN | AMW-919-R | IBS |  | 35.9029 | 31.9641 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419186 |  |  | Not Requested |  |  |  |  | 5G | 5 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1740 | 1740-Rotana_Arjan_Hotel_1_PF_IBS_Org | ZAIN | AME-906-R | IBS |  | 35.907 | 31.9643 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419187 |  |  | Not Requested |  |  |  |  | 5G | 5 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1736 | 1736-Abdali_Boulevard_2_PF_IBS_Org | ZAIN | AME-901-R | IBS |  | 35.9052 | 31.9645 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419188 |  |  | Not Requested |  |  |  |  | 5G | 5 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1741 | 1741-Rotana_Arjan_Hotel_PF_IBS_Org | ZAIN | AME-907-R | IBS |  | 35.9039 | 31.9645 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419189 |  |  | Not Requested |  |  |  |  | 5G | 5 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1742 | 1742-Abdali_Commercial_Bldg_1_PF_IBS_Org | ZAIN | AME-908-R | IBS |  | 35.9059 | 31.9631 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419191 |  |  | Not Requested | Done |  |  |  | 5G | 6 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2024-08-18
1726 | 1726-Abdali_Mall_PF_IBS_Zain_Manage | ZAIN/M | AME-834-R | IBS |  | 35.9083 | 31.9636 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419192 | SMART |  | Not Requested |  |  |  |  | RAN Only | 6 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-11-13 |  | W46
1744 | 1744-Siraj_Tower_PF_IBS_Org | ZAIN | AME-915-R | IBS |  | 35.9086 | 31.9623 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419194 |  |  | Not Requested |  |  |  |  | 5G | 3 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1728 | 1728-AMC_Hospital_Abdali_PF_IBS_Org | ZAIN | AME-1031-R | IBS |  | 35.9102 | 31.9638 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419195 |  |  | Not Requested |  |  |  |  | RAN Only | 6 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1729 | 1729-UL_Kawar_Group_HQ_building_PF_IBS | ZAIN | AME-1091-R | IBS |  | 35.9028 | 31.9647 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419196 |  |  | Not Requested |  |  |  |  | RAN Only | 1 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | IBS | 2024-08-18
1710 | 1710-Abdali_Views_IBS | ZAIN | AME-1171-R | IBS |  | 35.9095 | 31.9625 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-17 |  |  | SMP-WO-1419197 |  |  | Not Requested |  |  |  |  | RAN Only | 3 | IBS | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x1 | Micro_X1 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x2 | Micro_X2 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x3 | Micro_X3 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x4 | Micro_X4 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x4 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x5 | Micro_X5 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x5 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x6 | Micro_X6 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x6 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x7 | Micro_X7 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x7 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x8 | Micro_X8 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x8 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x9 | Micro_X9 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x9 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x10 | Micro_X10 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x11 | Micro_X11 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x12 | Micro_X12 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x13 | Micro_X13 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x14 | Micro_X14 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x15 | Micro_X15 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x16 | Micro_X16 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [15 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site ID not Identified | 2024-08-18
x17 | Micro_X17 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | no 5G to be added, TSSR is Wrong | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x18 | Micro_X18 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x19 | Micro_X19 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x1 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x20 | Micro_X20 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | wrong power solution &no need to add new DP for sector A& Need to add clear pic for the empty Cabinet | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x21 | Micro_X21 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved | AAU Labels and Azimuth Pictures not shown. ( 4G azimuth pictures represented are a copy of 3G and not seperate) Mechanical tilts pictures should contain the position of the clips to show type of tilt | Malek | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x22 | Micro_X22 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Check with Dabbagh before installtions | Waed & Moath | Approved |  | M. Amro | Approved | Will request access for site audit, this can be postponed | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x23 | Micro_X23 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x24 | Micro_X24 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Not sufficient power information/solved | Obieda | Approved |  | Baher Obaidat | Approved | update tilt (Mech) up and down on the right field (Done) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x25 | Micro_X25 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Wrong power solution./solved | Obieda | Approved |  | Baher Obaidat | Approved | There is confusion in panorama images (azimuth shift) (for example view of azimuth 210) Naming need to be modified (A, B, C) instead of (A, C, D) Update: view of sector C does NOT match with azimuth specify the m-tilt clamp position or the m-tilt direction: up or down update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Site ID not Identified | 2024-08-18
x26 | Micro_X26 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Where is the 3G RRU connection located?/solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x27 | Micro_X27 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | Note: TDD Sectors are (A, B and C) not (A, B and D) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x28 | Micro_X28 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x29 | Micro_X29 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x2 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [5 empty] | Need to check the power solution sheet | Obieda |  |  | Baher Obaidat |  | Actual view of sec-c is 280 degrees, not 230 Bore of B-3G is 150 and it should be 110 Mechanical tilt of sec-C should be (-3) not (3) Update: Notes above were handled, but 2G sector names are A,B,C NOT A,C,D Update2: For our reference and convenient data, please reflect the new 2G sectors naming on the while RF sheet update3: issues were tackled | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  |  | Site ID not Identified | 2024-08-18
x30 | Micro_X30 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 | [5 empty] | Not sufficient power information./solved The site photos show that the TDD DCDU is not the same as the one mentioned for TDD RRUs./solved | Obieda |  |  | Baher Obaidat |  | Site naming not following Zain naming (View of existing sector-A should be for sector-C), and existing sector-B should be sector-A, and existing sector-C should be sector-A) Update: m-tilt of 2G/3G antennas looks (down) but they are submitted (up) in the table Update: issues tackled | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  |  | Site ID not Identified | 2024-08-18
x31 | Micro_X31 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | There isn't enough space between the two BTS cabinets to install the NOKIA cabinet. Please consider dismantling one of the cabinets instead./solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x32 | Micro_X32 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x33 | Micro_X33 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | Please reconsider the solution of Sec-B 5G antenna, current solution might lead to AAU being blocked by 5G antenna and 5G antenna being blocked by new 10-port antenna | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x34 | Micro_X34 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | install the NOKIA cabinet on the right of the existing cabinet./solved Wrong power solution. We cannot use the BLVD circuit breakers for RRUs. ¦¦ please to cascade the 3G DCDU with 2G DCDU on the same CB or relocate the 2G power sources to 3G DCDU./solved | Obieda | Approved |  | Baher Obaidat | Approved | Sec-B 4G azimuth should be 110 instead of 150 Sec-C 4G, mech tilt should be 0 instead of 1 | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Site ID not Identified | 2024-08-18
x35 | Micro_X35 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Incorrect power solution./solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x36 | Micro_X36 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Site ID not Identified | 2024-08-18
x37 | Micro_X37 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested |  |  |  |  | RAN Only | 1 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Site ID not Identified | 2024-08-18
x38 | Micro_X38 |  |  | Site ID not Identify | [9 empty] | Full Swap | P.O.2 | X | Cluster-x3 | [5 empty] | Not Requested | Done |  |  |  | RAN Only | 1 |  |  |  |  | Approved | Need power distrubtion/solved | Obieda | Approved |  | Baher Obaidat | Approved | As Agreed, the height should be measured from top of the antenna Sector B antenna is on 7m height (from the bottom of the antenna as you provided) why to be installed on 4m ?! Update: issues tackled | Rabie Otoum | Approved | wrong data for 10port dimention and AQQY // same rejection reason 19/03 same rejection 24/03 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-08-18
2606 | 2606-MOI_PE_TASC |  | AMW-610-R | Indoor | 1551 | 35.9075 | 31.9788 | West Amman | Roof Top | khayriat muradi eabd alrawuwf saliman | 06-5665771 079-5527201 | Tower T 12 | 26 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355223 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-13 | Yes | W24 |  | 565 | RFI | Under Zain Validation | Approved
2611 | 2611-UL_Shmeisani_PSD_PF_O |  | AMW-818-R | Outdoor |  | 35.9014 | 31.9752 | West Amman | Roof Top | mudiriat al amn aleamm |  | Pole P9 + P6 | 13 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355225 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | Wrong Antenna solution / need to replace the TDD antenna with 3 DP/solved | Obieda | Approved |  | Baher Obaidat | Approved | photos for sector-C view are not in agreement with measured azimuth (290) for both 2G/3G & 4G (Done) both mech tilt of sec-D 2G/3G and sec-A AAU are not reflected on table as actually measured (Done) Tilt (mech.) tilting UP or down is not mentioned (Done) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-13 | Yes | W24 |  | 565 | RFI | Under Zain Validation | Approved
5607 | 5607-Prince_Faisal_Palace_Rising_PF_TASC_O |  | AMW-838-R | Outdoor |  | 35.8353 | 32.0251 | West Amman | Roof Top | muhamad ahmad alhaji murad sakw | 06-5354127 0777-592591/077-2472516 | Pole P9#2 | 10 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355272 | Al-Lewan | khalil Al Omari>> Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-29 | Yes | W22 |  | 580 | RFI |  | Approved
5629 | 5629-Sweileh_PSD_PF_O |  | AMW-828-R | Outdoor |  | 35.8383 | 32.0176 | West Amman | Roof Top | mudiriat al amn aleamm |  | Tower 20 | 20 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355281 | Cellcom | Cellcom | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | No tower height in civil sheet! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-07-22 | Yes | W30 |  | 526 | RFI | Access Issue / Under proccess | Approved
5631 | 5631-Sweileh_Hay_Maysaloon_PB_Fiber_TASC |  | AMW-314-G | Indoor | 173 | 35.8324 | 32.0224 | West Amman | Green Field | alkhasat almalakiat |  | Tower T 18 | 25 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355282 | Cellcom | Cellcom | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | number of free deport arm need to be written even if it is Zero | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-10 | Yes | W11 |  | 660 | RFI | TSSR Under preperation | Approved
5640 | 5640-Royal_Group_PF_Org_O |  | AMW_924_R | Outdoor |  | 35.8273 | 32.0158 | West Amman | Roof Top | royal group org |  | Pole 6 | 6 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355288 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | Will request access for site audit, this can be postponed | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-06-06 | Yes | W23 |  | 572 |  |  | Approved
2562 | 2562-UL_Safoot_Talab_Alola_Sch_PF_TASC_O |  | AMW-1109-R | Outdoor |  | 35.8369 | 32.0336 | West Amman | Roof Top |  |  | Pole P9#2 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355206 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Install the AQQY antennas directly on the masts./solved | Obieda | Approved |  | Baher Obaidat | Approved | based on the picture provided, the provided azimuth value for Sector A (330) does not match with actual azimuth value of the picture view (0), please see the attached image.(Corrected from Nokia Side_ Approved) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-06 | Yes | W23 |  | 572 | RFI |  | Approved
5205 | 5205-Tareq_4_PD_Fiber_TASC |  | AME-690-R | Indoor | 203 | 35.938 | 32.0052 | East Amman | Roof Top | hasan eumar alhaj salih alzibn | 078-087149/079-6343820 | Tower T 12 | 22 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355324 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-12-04 | Yes | W49 | Shelter Key Problem | 391 | RFI |  | Approved |  |  |  |  | Downloaded
5207 | 5207-Tareq_PA_Fiber_TASC |  | AME-262-R | Indoor | 180 | 35.945 | 31.9993 | East Amman | Roof Top | haydar rashid iibrahim qart |  | Tower T 16 | 28 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355325 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved | no tssr is attached | Baher Obaidat | Approved |  | Rabie Otoum | Approved | Worng data for Antennas dimensions | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-12-04 | Yes | W49 |  | 391 | RFI |  | Approved |  |  |  |  | Downloaded
5209 | 5209-Lada_Company_PC_Fiber |  | AME-591-R | Indoor | 1517 | 35.9408 | 31.9952 | East Amman | Roof Top | fathi eabd rbh husayn badran washarkawaha | 0777/308856 | Tower T 12 | 22 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355326 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Not sufficient power information/solved | Obieda | Approved |  | Baher Obaidat | Approved | Please to modify the syntax of Tilt(mech.) in upcoming TSSRs. bear in mind to keep the clarification (Up or Down) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-12-04 | Yes | W49 |  | 391 | RFI |  | Approved |  |  |  |  | Downloaded
5228 | 5228-Tareq_Fardous_Msq_PD_Fiber_O |  | AME-804-R | Outdoor |  | 35.9421 | 32.0082 | East Amman | Roof Top | mahmud salamat arhyl alhtamlt | 077-9862976/078-5370599 | Tower T 16 | 22 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355342 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved | need to adjust the old DPs so the new antenna becomes beside the old one not behand it | Baher Obaidat | Approved | Photo Showing the Azimuth of North Direction is wrong. Sec-D mechanical tilt should be 2 instead of 4 (Up) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-12-04 | Yes | W49 |  | 391 | RFI |  | Approved
5235 | 5235-UL_Faisal_College_AbuAlia_2_O |  | AME-1127-R | Outdoor |  | 35.951 | 32.0016 | East Amman | [5 empty] | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355345 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | Table shows sector-D is 2G/3G, while it should be 2G/3G/4G "we will Dismanteld exsisting 8 port antenna for (2G/3G/4G) S.A and install new antenna 10-port at height ( 5.8m) from the heigh on mast-C , (AZ=290 ) ", this sentence is wrong, this should be for sec-D not A. If mast A may be overloaded, we recommend to deploy new mast if applicable. | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-12-04 | Yes | W49 |  | 391 | RFI |  | Approved
5212 | 5212-Tabarbour_2_PC_Fiber_TASC |  | AME-261-R | Indoor | 190 | 35.9644 | 31.9892 | East Amman | Roof Top | akrm eabd alrawuwf zakariaaan ghwsht | 06-5065072/0796630017 | Pole P6 X 5 | 15 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355328 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved | no tssr is attached | Baher Obaidat | Approved | Missing TSSR .xlsx file new 10-port antenna azimuth of sector C should be kept as the existing Update: issue tackled | Rabie Otoum | Approved | NO TSSR founded Wrong Data in the provided civil table, the dismantled and new equipment's shall be cleared and distributed over the existing masts same note 17/04 same note 21/04 Mast 1 overloaded & TASC will ask to install a new pole | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-28 07:32 | Yes | W13 |  | 641.6859 | RFI |  | Approved |  |  |  |  | Downloaded
5240 | 5240-AbuAlia_PC_Fiber_TASC |  | AME-279-R | Indoor | 29 | 35.9632 | 32.0013 | East Amman | Roof Top | talaq muhamad mutlaq alhbahbh | 06/5051030 077/415752 | Tower T 12 | 25 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355346 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-31 10:10 | Yes | W14 |  | 638.5764 | RFI |  | Approved
5248 | 5248-SOS_Amman_PD_Fiber_TASC |  | AME-598-R | Indoor | 1524 | 35.951 | 31.997 | East Amman | Roof Top | muhamad eabd alfattah ahmad abu twq | 079/6574442 | Tower T 12 | 28 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355347 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | "Existing 4G Antenna Azimuth for sector D" Column name need to be added | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-31 10:11 | Yes | W14 | Shelter Key Problem | 638.5754 | RFI |  | Approved
5271 | 5271-UL_Tareq_Wafa_Garden_O |  | AME-1145-R | Outdoor |  | 35.9575 | 32.0018 | Amman | [5 empty] | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1376030 | Al-Lewan | Khalil>>Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | It is not mentioned that we will dismantle the 6-ports antennas!/solved The mast heights are 6m, not 9m as mentioned in the civil sheet./solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 | Yes | W16 |  | 622 | RFI |  | Approved
5206 | 5206-Tabarbour_Iskan_Dobat_PF_EBand_TASC |  | AME-695-R | Indoor | 431 | 35.9594 | 31.9961 | East Amman | Roof Top | fahami mahmud eabd alruhmin alnamrawi | 06-5052800 079-5331555/079-9408344 | Pole P6*2 | 18 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355244 | SMART |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | Let the New 10-port antenna of sector A be on azimuth 30 degrees instead of 10. | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-13 10:29 | Yes | W11 |  | 656.5635 | RFI |  | Approved |  |  |  |  | Downloaded
5203 | 5203-AbuAlia_2_PC_EBand_TASC |  | AME-570-R | Indoor | 1534 | 35.9776 | 31.9994 | East Amman | Roof Top | nabih muhamad ahmad alkhtyb | 777806005 | Tower T 16 | 28 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355323 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved | Civil table / BTS sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-17 13:24 | Yes | W12 |  | 652.4417 | RFI |  | Approved
5214 | 5214-Tareq_3_PC_Fiber_TASC |  | AME-505-R | Indoor | 449 | 35.9497 | 32.0107 | East Amman | Roof Top | eayishat ealia yusif jadalulah | 06/505273 | Tower T 12 | 18 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355329 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | View sector A does not match with the view update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-07 | Yes | W19 |  | 602 | RFI |  | Approved |  |  |  |  | Downloaded
2308 | 2308-UL_Tarkhees_Marka_Back_PE_TASC_O |  | AME-1052-R | Outdoor |  | 35.9982 | 31.9934 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355263 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Add 2 PDU and 2 FPFH./solved | Obieda | Approved |  | M. Amro | Approved | mechanical tilt values on table, not matching the provided photos. | Akram Abdelrahim &Karam Jaber | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-28 12:31 | Yes | W13 |  | 641.4781 | RFI |  | Approved |  |  |  |  | Downloaded
5219 | 5219-Tabarbour_SOS_PF_TASC |  | AME-693-R | Indoor | 393 | 35.9514 | 31.9929 | East Amman | Roof Top | eatuh muhamad kusab aldaejih | 079-6471831/079-7357286 | Tower T 20 | 16 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355336 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-14 07:15 | Yes | W11 |  | 655.698 | RFI |  | Approved
5274 | 5274-Tareq_Military_Telecom_PF_TASC_O |  | AME-971-R | Outdoor |  | 35.9613 | 32.004 | East Amman | Roof Top | bilal eabd allatif amin eyd | 0799059878/0777665406 | Pole P9#2 | 18 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355356 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Amro | Approved |  | Akram Abdelrahim &Karam Jaber | Approved | civil requirements new not matched with the BTS sheet (cabinet concrete base for nokia cabinet!!!) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-26 10:03 | Yes | W13 |  | 643.5816 | RFI |  | Approved
2341 | 2341-UL_Tarkhees_Marka_TL_PC_Fiber_TASC |  | ZRQ-141-R | Indoor |  | 36.0027 | 31.9912 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355309 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | wrong data in civil table / BTS sheet / and civil sheet not as the standard // New DP 1.5m not 3m as TI requested | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-28 07:15 | Yes | W13 |  | 641.6981 | RFI |  | Approved
5232 | 5232-AbuAlia_CTR_PE_TASC_O |  | AME-904-R | Outdoor |  | 35.9696 | 32.0022 | East Amman | Roof Top | haytham jadin alhaq | 0798681557/0795600744 | Pole P9#2 | 20 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355344 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | 4G on Power sheet is missing. | Zaid | Approved | TSSR file does not exist | Baher Obaidat | Approved | Missing TSSR excel file update: 4G sector A M-tilt should be down following 3G/2G as it is 6-ports antenna updates: issues were tackled | Rabie Otoum | Approved | NO TSSR founded | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-01 12:54 | Yes | W14 |  | 637.4628 | RFI |  | Approved
5221 | 5221-Military_CMD_Tabarbour_PD_EBand_TASC |  | AME-707-R | Indoor | 1629 | 35.9584 | 32.0084 | East Amman | Roof Top | bahiat zakayin yahyaa eubud | 06-5064898 079-5805244 | Pole P9 X 3 | 21 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355338 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved | Existing Antenna Type (Band / No. of Ports) & Antenna Brand Name / Model Not provided for Sec-B 4G (Done) Mech. tilt photos of tilt meter are not clear for Sec-A & Sec-B (Done) Antenna Clamp is not mentioned in Mech Tilt value (UP , Down) (Done) | Rabie Otoum | Approved | civil requirement new need update to match the BTS (2 new DP's or 3?) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-14 10:34 | Yes | W11 |  | 655.5601 | RFI |  | Approved |  |  |  |  | Downloaded
5210 | 5210-Tareq_Alhoury_Bakery_PE_UMN_O |  | AME-799-R | Outdoor |  | 35.9415 | 32.0021 | East Amman | Roof Top | Tareq Relo. |  | Tower 16 | 21 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355339 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | M-tilts of sectors A,B and C seems to be down NOT up from the images while sector D is up Provide clear images for the m-tilt clamps showing the whole antenna to recognize the clamp's position Update: issues tackled | Rabie Otoum | Approved | civil reqirments new not matched with the BTS sheet new DP's is needed or not?? | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-19 10:32 | Yes | W12 |  | 650.5613 | RFI |  | Approved
5217 | 5217-UL_Prince_Hassan_Forest_East_PF_TASC_O |  | AME-1064-R | Outdoor |  | 35.9717 | 31.9846 | East Amman | Roof Top |  |  | Tower T 20 | 24 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355340 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-03-14 09:38 | Yes | W11 |  | 655.5987 | RFI |  | Approved |  |  |  |  | Downloaded
2317 | 2317-ULT_Marka_PB_Fiber_TASC |  | AME-265-R | Indoor |  | 35.9887 | 31.9848 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355266 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Azimuth angles for Sector B&C doesn't match the theoretical angles for Sector B (90-180) & C (180-270) | Zaid | Approved |  | Baher Obaidat | Approved | M-tilts seems to be down NOT up from the images Provide clear images for the m-tilt clamps showing the whole antenna to recognize the clamp's position Update: even though you did not provide clear images for the m-tilt clamps, it will be approved as the value on the table corrected | Rabie Otoum | Approved | BTS sheet (New DP's or not) if yes update the civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-03-20 07:40 | Yes | W12 |  | 649.6809 | RFI |  | Approved |  |  |  |  | Downloaded
5249 | 5249-AbuAlia_4_PD_Fiber_TASC |  | AME-752-R | Indoor | 1717 | 35.9675 | 31.9974 | East Amman | Roof Top | yusuf mahmud iibrahim aleurb | 078-5005040 | Pole P6 x 2 + P9X 1 | 20 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355348 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | 4G AHEB should be only for 3 sectors, Recheck power on all sheets. | Zaid | Approved |  | Baher Obaidat | Approved | need to reconfigure sectors A, and C as we found CPRI swap and naming should be interchanged. | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-18 08:52 | Yes | W12 |  | 651.6306 | RFI |  | Approved
5250 | 5250-Tabarbour_MGS_PF_TASC_O |  | AME-785-R | Outdoor |  | 35.9367 | 31.9923 | East Amman | Roof Top | Manaseer | 06-5734070 | Pole P9*1+WallMount 4m*1+WallMount6m*1 | 15 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355350 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | MAST A & B not specified on BTS sheet. No details for power consumption | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-01 10:41 | Yes | W14 |  | 637.5546 | RFI |  | Approved
5265 | 5265-Faisal_College_AbuAlia_PF_TASC_O |  | AME-924-R | Outdoor |  | 35.9547 | 32.0033 | East Amman | Roof Top | eabd alhamid eabd almuneim eabd alkarim almaeayith | 06/5063395 0797839808/0797085045 | Tower T 16 | 12 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355351 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | 2G/3G Sectors A,B, and C m-tilt looks up not down Sector A 2G/G azimuth is wrong provided clearer view image for sector B, showing more landmarks Note not related to rejection: new sector A need to be installed on azimuth 30 ,B on azimuth 220, and sector C on 320 note: rejected based on request note: rejected as agreed to update the new azimuth update: modified to the new azimuth A: 30, B: 220, C: 330 update: modified to the new azimuth A: 30, B: 220, C: 330 | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-03-19 10:24 | Yes | W12 |  | 650.5669 | RFI |  | Approved
5268 | 5268-AbuAlia_Army_HSG_PF_TASC_O |  | AME-961-R | Outdoor |  | 35.9557 | 31.998 | East Amman | Roof Top | ahlam saeid eali mdll | 0797730178/0798962501 | Pole P9#2 | 24 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355352 | khalilAlOmari |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved | DIM in civil table!!!! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-18 11:08 | Yes | W12 |  | 651.5359 | RFI |  | Approved
5269 | 5269-Tabarbour_Amman_Municipality_PE_Fiber_TASC_O |  | AME-958-R | Outdoor |  | 35.9457 | 31.9968 | East Amman | Roof Top | ayuwb eabd alfattah jameah shariyf | 0786597433/0795182795/0779134642 | Pole P9 + P6 | 19 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355353 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Amro | Approved | mechanical tilt values on table, not matching the provided photos. BTS suggestions (S.B After swap 2 port ANT install 5G Ant AQQY AT H :5m ,AZ =220 ¦¦ S.C After swap 2 port ANT install 5G Ant AQQY AT H :5.50m ,AZ =320) not matched suggestions provided on photos bear in mind the points in the remark are the correct one. | Akram Abdelrahim &Karam Jaber | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-19 10:30 | Yes | W12 |  | 650.5627 | RFI |  | Approved
5239 | 5239-Tabarbour_PD_Fiber_TASC_Relo_O |  | AME-1060-R | Outdoor |  | 35.9551 | 31.9898 | East Amman | Roof Top | jamal jamil falayh aleabdalulat | 0799818871/0796320302 | Pole P9 + P6X2 | 27 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355349 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-14 09:32 | Yes | W11 |  | 655.6028 | RFI |  | Approved
5272 | 5272-Billeh_Tareq_PE_Fiber_TASC_O |  | AME-951-R | Outdoor |  | 35.9327 | 31.998 | East Amman | Roof Top | wizarat al awqaf | 06/5066626 795200019 | Pole P9#2 | 21 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355355 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | need to dismantle one of BTS cabinet/done incorrect antenna solution/solved wrong power solution/solved | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | Civil Requirements New not clear (needed 5 new DP) new Antennas 3 and free DP's is 1 The civil sheet does not match with the BTS sheet no TSSR found | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-24 13:53 | Yes | W17 |  | 614.4215 | RFI |  | Approved
2307 | 2307-UL_Ain_Ghazal_Bridge_PC_EBand_TASC |  | AME-257-R | Indoor |  | 35.974 | 31.9877 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355262 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Dismantle Cabinet was chosen for AMIA installation. | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-24 13:35 | Yes | W13 |  | 645.4338 | RFI |  | Approved |  |  |  |  | Downloaded
5275 | 5275-Tareq_Khalil_Rahman_Msq_PF_TASC_O |  | AME-975-R | Outdoor |  | 35.9727 | 31.9982 | East Amman | Roof Top | tariq eabd alkarim | 06/5052846 0785155825/0797083056/ | Pole P9+P6X2 | 18 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355357 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | Change 2G sector Name from B to C has been requested from our side. | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-12 13:36 | Yes | W11 |  | 657.4334 | RFI |  | Approved
5276 | 5276-Military_CMD_West_PE_Fiber_TASC_O |  | AME-976-R | Outdoor |  | 35.9496 | 32.0067 | East Amman | Roof Top | mustafaa ealia mustafaa shueban | 06/5159349 796500647 | Pole P9#2 | 18 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355358 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved | for sector D, please swap the locations of the antennas (6ports and 4 ports) , then install the 5G DB to the left of the new location of the 4 ports antenna // please check the attachment | Baher Obaidat | Approved |  | Rabie Otoum | Approved | missing tower height in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-18 11:07 | Yes | W12 |  | 651.5367 | RFI |  | Approved
5277 | 5277-Faisal_College_PE_Fiber_TASC_O |  | AME-977-R | Outdoor |  | 35.9476 | 32.0023 | East Amman | Roof Top | asead jbr hasan abu labdh | 0790872918/0795014080 | Tower T 16 | 30 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355359 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved | for sector C, install the new AQQY just above the AAU without installing new DB | Baher Obaidat | Approved | specify the m-tilt clamp position (or m-tilt direction: up or down) Provide clear images for the m-tilt clamps showing the whole antenna to recognize the clamp's position update: issues were tackled | Rabie Otoum | Approved | Antennas heights in civil sheet to be checked | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-18 11:09 | Yes | W12 |  | 651.5353 | RFI |  | Approved
2760 | 2760-Qalaa_2_PE_Fiber_TASC_O |  | AME-713-R | Outdoor |  | 35.9361 | 31.9569 | East Amman | Roof Top | eadili eabd alrahmn shukri juri wakilana ean jari | 079-9331608/077-6597891 | Pole P9 + P6 | 15 | ThinLayer | RO2 | Group4T | Cluster-27 | Wast Al-Balad | Traditional | SMP-WO-1355321 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | New antennas azimuth should match with the current. specify the azimuth of the antenna (not the mast) Update: Azimuth was modified on BTS sheet | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-25 10:38 | Yes | W17 |  | 613.5567 | RFI |  | Approved |  |  |  |  | Downloaded
2312 | 2312-UL_Wannanat_Ave_PC_Fiber_TASC |  | AME-658-R | Indoor |  | 35.9804 | 31.9871 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355265 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 | Yes | W16 | Shelter Key Problem | 622 | RFI |  | Approved |  |  |  |  | Downloaded
3136 | 3136-U_Zarqa_Highway_MGS_PF_TASC_O |  | ZRQ-247-R | Outdoor |  | 36.0154 | 31.9958 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-31 | Marka | Traditional | SMP-WO-1355330 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | We need to know what is connected specifically on LLVD side, if we have Transmission modules, we should move them to BLVD side instead of BBU. If we got 3 free C.B on LLVD side, power solution will be (2*63 -> FPFH1:(ACOC+2AQQY+1AHEB) + 1*63-> FPFH2) Power solution: one of BBU power cables will be disconnected, then the other cable will be connected on (3G+L900) DCDU. So, we will get 3 free 63A C.B (2*63 -> FPFH1:(ACOC+2AQQY+1AHEB) + 1*63-> FPFH2). Power solution Need to fixed on all sheets. | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 | Yes | W16 |  | 622 | RFI |  | Approved |  |  |  |  | Downloaded
1320 | 1320-UL_South_Marka_PD_Fiber_TASC |  | AME-110-R | Indoor |  | 35.9815 | 31.9595 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355242 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved | Tilt (mech.) need to indicate Up or Down (Done) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-24 09:37 | Yes | W17 |  | 614.5992 | RFI |  | Approved |  |  |  |  | Downloaded
3135 | 3135-UL_Development_HSG_PF_O |  | ZRQ-230-R | Outdoor |  | 36.0177 | 31.9885 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-31 | Marka | Traditional | SMP-WO-1355327 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-24 13:39 | Yes | W13 |  | 645.4314 | RFI |  | Approved |  |  |  |  | Downloaded
2306 | 2306-UL_Abdullat_Ave_CTR_PF_Fiber_TASC_O |  | AME-1054-R | Outdoor |  | 35.9922 | 31.9782 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355261 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-28 07:18 | Yes | W13 |  | 641.6957 | RFI |  | Approved |  |  |  |  | Downloaded
2311 | 2311-UL_North_Marka_Hamzeh_Msq_PF_TASC_O |  | AME-1005-R | Outdoor |  | 35.9762 | 31.9775 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355264 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | correct the antennas dimensions | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-03-27 13:29 | Yes | W13 |  | 642.4384 | RFI |  | Approved |  |  |  |  | Downloaded
5231 | 5231-Souq_Tabarbour_PF_TASC_O |  | AME-890-R | Outdoor |  | 35.9448 | 31.9927 | East Amman | Roof Top | muhamad jamil musaa alfawaqh | 0795129295/0796448614 | Tower T 16 | 27 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355343 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-01 12:46 | Yes | W14 |  | 637.4684 | RFI |  | Approved
2319 | 2319-UL_Marka_TL_Back_PE_TASC_O |  | AME-1021-R | Outdoor |  | 36.0031 | 31.9882 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355268 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | LLVD & BLVD should be specified clearly also need to be revised. | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved | correct the antennas dimensions | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-24 13:29 | Yes | W13 |  | 645.4382 | RFI |  | Approved |  |  |  |  | Downloaded
2318 | 2318-UL_Marka_Skrab_CTR_PF_Fiber_TASC_O |  | ZRQ-420-R | Outdoor |  | 36.0029 | 31.9967 | Zarqa | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355267 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | On S.A 5G there is no matching between BTS sheet and remarks on both (BTS+site preparation) Sheets | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-20 13:01 | Yes | W12 |  | 649.4574 | RFI |  | Approved |  |  |  |  | Downloaded
2325 | 2325-UL_Marka_2_PE_TASC |  | AME-272-R | Indoor |  | 35.9965 | 31.9866 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355270 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Power solution should be (free 2*63 LLVD C.B for FPFH 2 + Adding new 63 A C.B for FPFH 1) | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-25 13:04 | Yes | W13 |  | 644.4557 | RFI |  | Approved |  |  |  |  | Downloaded
2320 | 2320-UL_Mowasah_Hospital_PF_DIBS_Manage |  | AME-268-R | Indoor |  | 35.9778 | 31.9796 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355269 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 | IBS-D |  |  |  | Approved | RHH & Antenna height need to be fixed on all sheets. LLVD and BLVD not clear enough to judge. Dismantle old cabinet is chosen. | Zaid | Approved | move the free db of sector D above the 6 ports antenna, height become approximately at 10m | M. Amro | Approved |  | Rabie Otoum | Approved | correct the antennas dimensions | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-16 10:58 | Yes | W16 |  | 622.5433 | RFI |  | Approved |  |  |  |  | Downloaded
2354 | 2354-UL_Souq_Marka_CTR_PE_TASC_O |  | AME-973-R | Outdoor |  | 35.9873 | 31.9814 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355314 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | We need to know what is connected specifically on LLVD side, if we have Transmission modules, we should move them to BLVD side. If we have BBU on LLVD we can move it to AAU DCDU. Adding DP is chosen. / Please mention that the DP will carry both TDD and AQQY. | Zaid | Approved | And please don't use this solution (((Another solution for 5G Antenna: we can use this FREE Mast for all New 5G Antennas with all same azimuth and Elevations mentioned above))) | M. Amro | Approved | keep this TSSR Released at your side until a physical action by Zain Team to be conducted on the overlapped 2G/3G sectors B & C (Azimuth change from 210 & 260 --> 180 & 275 to follow 4G), then we set together and update the existing TSSR with new values and pictures to approve. thanks waiting for Zain technicians feedback, request has been submitted through Oddo system (will be done by Zain) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-24 13:28 | Yes | W13 |  | 645.4392 | RFI |  | Approved |  |  |  |  | Downloaded
2330 | 2330-U_AbuAlia_Taqwa_Ave_PF_TASC |  | AME-723-R | Indoor |  | 35.9751 | 31.9934 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355302 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Masts A,B&C need to be revised well to be matched on all sheets, because it seems difficult to understand them. How much LLVD C.B we have and what is connected on each one of them. Connection of TDD DCDU is missed. Masts and sectors should be matched on all sheets. | Zaid | Approved |  | M. Amro | Approved | Dears Nokia Team, Just change Azimuth value for Sector B from 80 to 115 and upload the TSSR again to approve (Done) we requested Azimuth change from 80 to 115 to solve overlap issue between SB & SA (Done) New Note: correct the technology name from 3G to 2G on kathrien antenna for Sector C, also from 2G4G to 3G4G on 4 port antenna of sector C ,(Done) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-08 10:37 | Yes | W15 |  | 630.5578 | RFI |  | Approved |  |  |  |  | Downloaded
1313 | 1313-UL_Marqab_3_PE_EBand_TASC_O |  | AME-671-R | Outdoor |  | 35.9859 | 31.9524 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355252 | Al-Lewan | Khalil>>Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-25 10:41 | Yes | W17 |  | 613.5546 | RFI |  | Approved |  |  |  |  | Downloaded
3120 | 3120-UL_Polytechnic_PF_TASC_O |  | ZRQ-121-R | Outdoor |  | 36.0196 | 31.9916 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-31 | Marka | Traditional | SMP-WO-1355322 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-26 12:51 | Yes | W13 |  | 643.4647 | RFI |  | Approved |  |  |  |  | Downloaded
5222 | 5222-Tabarbour_Carrefour_PD_Fiber_TASC_O |  | AME-818-R | Outdoor |  | 35.9348 | 32.0021 | East Amman | Roof Top | sharikat al ahwar | 079-6529191 | Tower T 12 | 23 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355341 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | BBU connection is missing. You should mention that we need to shift ATN from LLVD to BLVD./New Power solution will be sent offline | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-17 07:44 | Yes | W12 | Access Granted | 652.6779 | RFI |  | Approved
5220 | 5220-Tareq_5_PE_Fiber_TASC |  | AME-705-R | Indoor | 1623 | 35.9377 | 31.9989 | East Amman | Roof Top | eabd alqadir ltfy eabd alqadir zayn aldyn | 798-55076094/0777-806589 | Tower T 12 | 21 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355337 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | No need for DP on sector B & C. | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-01 12:44 | Yes | W14 |  | 637.4695 | RFI |  | Approved |  |  |  |  | Downloaded
1301 | 1301-ULT_Hamlan_2_PE_Fiber_TASC |  | AME-93-R | Indoor |  | 35.9715 | 31.9607 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355175 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | No need for DP on Sector A On sector D if 4 port installed on DP there is no need for DP to install AQQY | Zaid | Approved |  | M. Amro | Approved | sectors B and C azimuth values do NOT match with the view update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-31 10:08 | Yes | W14 |  | 638.5776 | RFI |  | Approved |  |  |  |  | Downloaded
2332 | 2332-ULT_Wannanat_2_PD_Fiber_TASC |  | AME-280-R | Indoor |  | 35.9813 | 31.9814 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355304 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | New Rectifier should be MTS. Insert MTS power solution is needed. | Zaid | Approved |  | M. Amro | Approved | Azimuth values for 2G sectors B & D are wrong compared with what mesured by compass (Done) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-28 10:37 | Yes | W13 |  | 641.5575 | RFI |  | Approved
2333 | 2333-ULT_Wannanat_CTR_PD_Fiber_TASC_Relo_O |  | AME-1032-R | Outdoor |  | 35.9825 | 31.9861 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355305 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | SectorC-new 5G Antenna location on BTS sheet should be for sector C on description. | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-20 12:59 | Yes | W12 |  | 649.459 | RFI |  | Approved
2331 | 2331-ULT_Abdullat_Ave_PC_Fiber_TASC |  | AME-277-R | Indoor |  | 35.9917 | 31.9799 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355303 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved | Sectors View does not match with azimuth Still views have large difference azimuth with the data in the table. even the 360 photos have mismatches views note was tackled new 10-port antenna sector D installation height mismatch (should be on 6.25 instead of 5.25 in BTS sheet) update: issues were tackled | Rabie Otoum | Approved | civil table / BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-03-28 07:21 | Yes | W13 |  | 641.6936 | RFI |  | Approved
2334 | 2334-UL_Deir_Latin_Marka_PE_Fiber_TASC_O |  | AME-772-R | Outdoor |  | 35.9868 | 31.9792 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355306 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved | Dears Nokia team, from your side Please just change 2G Sector name from A to B and upload the new TSSR to Approve (Done) we requested from our database team to Change 2G Sector Name from 1330-Aden_Rising_PF_TASC_O-A to 1330-Aden_Rising_PF_TASC_O-B (Done) the TSSR shows that the feeders are connected to antenna directed toward sector B direction (140) instead of Sector A direction (80). | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-19 10:22 | Yes | W12 |  | 650.5681 | RFI |  | Approved
2351 | 2351-ULT_Marka_AlKhansa_Hospital_PE_Fiber_TASC_O |  | AME-966-R | Outdoor |  | 35.9891 | 31.9878 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355312 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | RHH & Antenna height need to be fixed on all sheets. TDD missed in all sheets except on power sheet. AQQY on Sec A. can be installed directly on mast. On Sec B. we can install AQQY on free DP with taking into consideration adjusting DP arms to avoid Blockage issues. What do you mean by Outdoor PDU? | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-19 10:08 | Yes | W12 |  | 650.5781 | RFI |  | Approved |  |  |  |  | Downloaded
2337 | 2337-UL_Marka_Aydi_Ave_PF_EBand_BTS_O |  | AME-1087-R | Outdoor |  | 36.0018 | 31.9813 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355308 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | RHH & Antenna height need to be fixed on all sheets. LLVD & BLVD not specified on Plugs, or we can distribute them on free fuses of DCDUs. If you are sure from BLVD and LLVD then we cannot connect our modules as is. AAU not clarified on power sheet. | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-07 11:27 | Yes | W15 |  | 631.5227 | RFI |  | Approved |  |  |  |  | Downloaded
2342 | 2342-UL_Flour_Mill_PD_Fiber_Manage |  | ZRQ-220-R | Indoor |  | 36.0086 | 31.9912 | Zarqa | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355310 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Reuse the free DP on Mast A S.B for S.C on Mast B. Mentioning that we need to adjust the DP arms to make all antennas on same row is needed. | Zaid | Approved |  | M. Amro | Approved | Sector A azimuth is shifted (not matching with the view) Sector B m-tilt image does not match with data in the table update: First note about sector A view still the same update: azimuth of sector A accepted with tolerance | Rabie Otoum | Approved | location of Antennas not in civil table wrong data provided in the civil table wrong data provided in the civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-01 10:40 | Yes | W14 |  | 637.5554 | RFI |  | Approved |  |  |  |  | Downloaded
2350 | 2350-UL_Hamzeh_Marka_PE_Fiber_TASC_O |  | AME-955-R | Outdoor |  | 35.9843 | 31.9837 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355311 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Replace old TDD DP on Sector B & C with 3m DP to carry both AQQY&TDD. Mentioning that we need to adjust the DP arms to make all antennas on same row is needed. | Zaid | Approved |  | M. Amro | Approved | Antennas height must be measured from the top. update: issue was tackled | Rabie Otoum | Approved | civil table not clear regarding the location of the Antennas | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-19 10:06 | Yes | W12 |  | 650.5789 | RFI |  | Approved
2352 | 2352-UL_Souq_Marka_TL_PD_Fiber_TASC_O |  | AME-972-R | Outdoor |  | 35.9925 | 31.9827 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355313 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-19 10:21 | Yes | W12 |  | 650.5689 | RFI |  | Approved |  |  |  |  | Downloaded
2304 | 2304-UL_Marka_That_Netaqin_Scl_O |  | AME-1144-R | Outdoor |  | 35.9892 | 31.9911 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | Power cable length issue | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | RHH & Antenna height need to be fixed on all sheets. PDU connections not clear enough to judge where the PDU feeds?. What do you mean with LLVD1 & LLVD2. | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-28 07:16 | Yes | W13 |  | 641.6969 | RFI |  | Approved |  |  |  |  | Downloaded
5218 | 5218-Prince_Hassan_Forest_PF_TASC |  | AME-681-R | Indoor | 70 | 35.9613 | 31.986 | East Amman | Roof Top | hani salah ahmad slah | 079-6300508/079-57302116 | Pole P6*3 | 16 | ThinLayer | RO2 | Group1T | Cluster-52 | Tabarbour | Traditional | SMP-WO-1355332 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Zaid | Approved |  | M. Amro | Approved | All the existing antennas are install on 9m height. Why the new 10-ports antenna will be installed on different heights ? update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-28 10:44 | Yes | W13 | Access Granted | 641.5529 | RFI |  | Approved |  |  |  |  | Downloaded
2315 | 2315-UL_Hay_Hamzeh_Marka_PE_Fiber_TASC |  | AME-682-R | Indoor |  | 35.9854 | 31.9897 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355333 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Amro | Approved | update: issue was tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-31 12:54 | Yes | W14 |  | 638.4623 | RFI |  | Approved |  |  |  |  | Downloaded
2309 | 2309-UL_Marka_Airport_CRL_PF_EBand_TASC |  | AME-651-R | Indoor |  | 35.9778 | 31.9765 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355335 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved | Not sufficient power information/solved | Obieda | Approved | Please modify the shifting for all TDD antennas from downward to upward ( install new Dps for TDD antennas upward of existing ) | M. Amro | Approved | Site naming is wrong (A,B,D), and it should be (A,B,C) Please to verify If 4G sec-A - 6 ports antenna is on 60 degrees ? Update: issues tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-01 10:39 | Yes | W14 |  | 637.5563 | RFI |  | Approved |  |  |  |  | Downloaded
1344 | 1344-UL_Nadi_Sebaq_PC_Fiber_TASC |  | AME-117-R | Indoor |  | 35.9774 | 31.9638 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355255 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Matching the masts name between civil sheet and BTS sheet is needed. On Existing AC Power Equipment table on Define the CB to connect Nokia Equipment cell change it to new solution | Zaid | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-31 11:44 | Yes | W14 |  | 638.5109 | RFI |  | Approved |  |  |  |  | Downloaded
1304 | 1304-UL_Hizam_Rd_2_PD_Fiber_TASC |  | AME-408-R | Indoor |  | 35.9847 | 31.9584 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355176 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | AQQY should be on the same height with 10 Port Ant. on Sec B & C (Switching between TDD and 10 Port is needed after Optimization approval). Unrealistic height for AQQY on sector B & C. | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-07 12:41 | Yes | W15 |  | 631.4712 | RFI |  | Approved |  |  |  |  | Downloaded
1308 | 1308-ULT_Marka_Airport_Back_PC_Fiber_TASC_O |  | AME-648-R | Outdoor |  | 35.9832 | 31.9652 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355177 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Incorrect power solution./solved | Obieda | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-16 06:49 | Yes | W16 |  | 622.7161 | RFI |  | Approved |  |  |  |  | Downloaded
1305 | 1305-ULT_Alia_Nasser_PC_Fiber_TASC |  | AME-550-R | Indoor |  | 35.9643 | 31.9536 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355179 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | incorrect antenna solution/solved Incorrect Power Solution./solved | Obieda | Approved |  | M. Amro | Approved | Azimuth sector.B 90 not zero update: tackled | Rabie Otoum | Approved | Wrong data in the civil sheet and not matching with pictures and provided civil table Same note 21/04 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-16 06:51 | Yes | W16 |  | 622.7145 | RFI |  | Approved |  |  |  |  | Downloaded
1312 | 1312-UL_Marqab_Middle_PE_Fiber_TASC_O |  | AME-829-R | Outdoor |  | 35.9881 | 31.9462 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355234 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-31 11:46 | Yes | W14 |  | 638.5098 | RFI |  | Approved |  |  |  |  | Downloaded
1310 | 1310-ULT_Hizam_PA_Fiber_TASC |  | AME-101-G | Indoor |  | 36.0031 | 31.9424 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355235 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Amro | Approved | 4G mechanical tilt mismatch ( up or down) Need clear images for the m-tilt clamp Update: still inconsistence in m-tilt data TDD antennas height decreased rejected as it most likely would be blocked update: issues were tackled | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-14 12:29 | Yes | W16 |  | 624.4799 | RFI |  | Approved |  |  |  |  | Downloaded
1316 | 1316-UL_Marqab_Back_PE_Fiber_TASC_O |  | AME-1128-R | Outdoor |  | 35.9834 | 31.9475 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355236 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Obieda | Approved |  | M. Amro | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-07 10:25 | Yes | W15 |  | 631.566 | RFI |  | Approved |  |  |  |  | Downloaded
1321 | 1321-UL_Marqab_2_PE_Fiber_TASC_O |  | AME-773-R | Outdoor |  | 35.9905 | 31.9522 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355237 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-31 11:48 | Yes | W14 |  | 638.5087 | RFI |  | Approved |  |  |  |  | Downloaded
1314 | 1314-UL_Marqab_PD_Fiber_TASC |  | AME-673-R | Indoor |  | 35.9922 | 31.9427 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355238 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-08 10:52 | Yes | W15 |  | 630.547 | RFI |  | Approved |  |  |  |  | Downloaded
1324 | 1324-UL_Abrar_Msq_Marka_PE_Fiber_TASC_O |  | AME-849-R | Outdoor |  | 35.9767 | 31.9618 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355239 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | 2G should be OFF Power solution not clear | Zaid | Approved | for sector A and C , the old DB position has to be adjusted ,so when installing the new DB , the new antenna becomes beside the old one not behind it. | Baher Obaidat | Approved | overlap in Azimuth for 3 sectors, please implement Azimuth values as the following , A=15 , B=80 , C=145 (request has been sent to Zain Riggers to implement these Azimuth values) | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-15 09:58 | Yes | W16 |  | 623.5846 | RFI |  | Approved |  |  |  |  | Downloaded
1326 | 1326-UL_Aden_Ave_PF_TASC_O |  | AME-1041-R | Outdoor |  | 35.971 | 31.9542 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355241 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | need to update the power soluation as the new power sheet | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved | update civil table as the standard // determine each Antenna location & height & match it with BTS sheet updated and approved from the past batch!! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-31 10:07 | Yes | W14 |  | 638.5784 | RFI |  | Approved |  |  |  |  | Downloaded
1351 | 1351-UL_South_Marka_Harsha_PE_Fiber_TASC_O |  | AME-1013-R | Outdoor |  | 35.9835 | 31.9506 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355253 | Al-Lewan | Khalil>>Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved | Missing the number of existing DP's in the civil & tower height foot print updated and approved from the past batch!! | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved |  |  |  |  | Downloaded
1330 | 1330-UL_Aden_Rising_PF_TASC_O |  | AME-645-R | Outdoor |  | 35.9703 | 31.9508 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355243 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-01 10:24 | Yes | W14 |  | 637.567 | RFI |  | Approved |  |  |  |  | Downloaded
1322 | 1322-ULT_Hamlan_PD_Fiber_TASC |  | AME-112-R | Indoor |  | 35.9755 | 31.9583 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355245 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | check available 100 PDU to be free to reuse it from your side | Waed & Moath | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-07 10:24 | Yes | W15 |  | 631.5667 | RFI |  | Approved
1331 | 1331-UL_Nasser_Sch_Aden_PF_TASC_O |  | AME-841-R | Outdoor |  | 35.9774 | 31.9492 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355246 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | AQQY for SA & SB can be installed direct on Mast Antenna and RRH height should be changed. Power Solution should be changed. | Zaid | Approved |  | Baher Obaidat | Approved | North view is shifted Sectors A and C view are wrong sector B view photo is not clear Antenna height should be measured from top of the antenna update: notes were tackled. height of antennas measured from top of the antenna as stated by NOKIA | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-08 09:45 | Yes | W15 |  | 630.5936 | RFI |  | Approved |  |  |  |  | Downloaded
1333 | 1333-UL_Aden_CTR_PE_Fiber_TASC_O |  | AME-938-R | Outdoor |  | 35.9738 | 31.9473 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355247 | Ecotel |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved | set the height of sector A at 12 | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 12:49 | Yes | W16 |  | 621.4658 | RFI |  | Approved
1335 | 1335-ULT_Marqab_Hizam_Rd_PD_Fiber_TASC_O |  | AME-939-R | Outdoor |  | 35.9961 | 31.9467 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355248 | Ecotel |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | FPFH C.B not clear | Zaid | Approved |  | Baher Obaidat | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-08 09:50 | Yes | W15 |  | 630.5903 | RFI |  | Approved |  |  |  |  | Downloaded
1336 | 1336-UL_Naser_Camp_West_PE_EBand_TASC_O |  | AME-1049-R | Outdoor |  | 35.9709 | 31.9566 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355249 | Ecotel |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 07:08 | Yes | W16 |  | 621.7031 | RFI |  | Approved |  |  |  |  | Downloaded
1338 | 1338-UL_Nadi_Sebaq_Ave_PE_Fiber_TASC_O |  | AME-926-R | Outdoor |  | 35.981 | 31.9621 | Amman | [5 empty] | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355250 | Ecotel |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved | no 5g solution is suggested | Baher Obaidat | Approved |  | Malek | Approved | What is the need for the new DP | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-08 09:49 | Yes | W15 |  | 630.5912 | RFI |  | Approved
1339 | 1339-ULT_Laila_Ghfarie_Sch_Marka_PE_Fiber_TASC_O |  | AME-950-R | Outdoor |  | 35.981 | 31.9549 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355251 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-31 13:17 | Yes | W14 |  | 638.4467 | RFI |  | Approved |  |  |  |  | Downloaded
2756 | 2756-Qalaa_Hill_PC_Fiber_TASC |  | AME-370-R | Indoor | 66 | 35.9405 | 31.9544 | East Amman | Roof Top | hayat shaeban yusif maeafan | 06/4659509 | Tower T 10 | 34 | ThinLayer | RO2 | Group4T | Cluster-27 | Wast Al-Balad | Traditional | SMPWO1375143 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 | Yes | W16 |  | 622 | RFI |  | Approved |  |  |  |  | Downloaded
2702 | 2702-Raghadan_CPLX_PC_Fiber_TASC |  | AME-612-R | Indoor | 1547 | 35.9448 | 31.9516 | East Amman | Roof Top | lwiy muhamad muruh alseud |  | Tower T 16 | 13 | ThinLayer | RO2 | Group4T | Cluster-27 | Wast Al-Balad | Traditional | SMP-WO-1375141 | PIS |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Rect Pics not attached | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | Approved | Yes | #VALUE! |  | #VALUE! | RFI |  | Approved |  |  |  |  | Downloaded
1319 | 1319-ULT_Harsha_1_PD_Fiber_TASC |  | AME-109-R | Indoor |  | 35.9776 | 31.954 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group3T | Cluster-13 | Marka | Traditional | SMP-WO-1355331 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Baher Obaidat | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-03-31 13:03 | Yes | W14 |  | 638.456 | RFI |  | Approved |  |  |  |  | Downloaded
2302 | 2302-ULT_Abdullat_Ave_2_PD_Fiber_TASC |  | AME-251-R | Indoor |  | 35.9893 | 31.9764 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355258 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | civil sheet not as the standard | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-08 09:44 | Yes | W15 |  | 630.5945 | RFI |  | Approved |  |  |  |  | Downloaded
2738 | 2738-Wadi_Hadaddeh_1_PD_Fiber_TASC |  | AME-354-R | Indoor | 308 | 35.9393 | 31.9559 | East Amman | Roof Top | jamal wayusif ahmad muhamad dawaly | 06/4611071 - 06/4621782 | Pole P6 X 3 | 15 | ThinLayer | RO2 | Group4T | Cluster-27 | Wast Al-Balad | Traditional | SMP-WO-1355319 | PIS | PIS | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | BTS sheet !! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
2706 | 2706-Qalaa_Hill_Rising_PF_TASC_O |  | AME-812-R | Outdoor |  | 35.9425 | 31.9549 | East Amman | Roof Top | faraj alkurdi | 078-5327992/078-7425555 | Pole P6X2 | 18 | ThinLayer | RO2 | Group4T | Cluster-27 | Wast Al-Balad | Traditional | SMP-WO-1355320 | SMART |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-29 | Yes | W18 |  | 610 | RFI |  | Approved
2710 | 2710-Raghadan_PC_Fiber_TASC |  | AME-334-R | Indoor | 117 | 35.9397 | 31.9505 | East Amman | Roof Top | ahmad salamat muslah abu shamalh |  | Tower T 6 | 13 | ThinLayer | RO2 | Group4T | Cluster-27 | Wast Al-Balad | Traditional | SMP-WO-1355316 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | civil table & MW details | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-16 | Yes | W20 |  | 593 | RFI |  | Approved |  |  |  |  | Downloaded
2715 | 2715-Baqaei_PD_Fiber_TASC |  | AME-348-R | Indoor | 1530 | 35.9348 | 31.9489 | East Amman | Roof Top | muhamad eali fathi albqaey |  | Pole P9 X 4 | 18 | ThinLayer | RO2 | Group4T | Cluster-27 | Albalad | Traditional | SMP-WO-1355317 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-03 | Yes | W23 |  | 575 | RFI |  | Approved
2727 | 2727-Sagf_Sail_PD_Fiber_TASC |  | AME-349-R | Indoor | 137 | 35.9318 | 31.946 | East Amman | Roof Top | mahmud ahmad maeruf washaraka ah | 06/4611103 | Pole P6 X 5 | 15 | ThinLayer | RO2 | Group4T | Cluster-27 | Albalad | Traditional | SMP-WO-1355318 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-16 | Yes | W20 |  | 593 | RFI |  | Approved |  |  |  |  | Downloaded
2610 | 2610-Sham_Hotel_Shmeisani_PF_EBand_TASC |  | AMW-745-R | Indoor | 1704 | 35.8955 | 31.9746 | West Amman | Roof Top | hisham mustafaa eabbas muhyar | 06-5666656 079-6646557 | Pole P6*4 | 21 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355224 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-25 | Yes | W17 |  | 614 | RFI |  | Approved
2565 | 2565-UL_Marine_Academy_East_PF_EBand_BTS_O |  | AMW-1136-R | Outdoor |  | 35.8915 | 32.0688 | West Amman | Roof Top |  |  | Tower 16 | 24 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355207 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-14 | Yes | W20 |  | 595 | RFI |  | Approved |  |  |  |  | Downloaded
2336 | 2336-UL_Wananat_Tareq_Bin_Zeyad_Sch_PE_Fiber_BTS_O |  | AME-1083-R | Outdoor |  | 35.9798 | 31.9831 | Amman | [5 empty] | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355307 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | civil table file extension // does not open | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | C | Approved | Approved | 2024-04-02 | Yes | W14 |  | 637 | RFI |  | Approved
1660 | 1660-RSS_PE_Fiber_TASC_O |  | AMW-920-R | Outdoor |  | 35.8832 | 32.0172 | West Amman | Roof Top | ahmad eubayd khadir alsuwilmiiyn | 0795540307/0795380090 | Pole P6 X2 + P9 X 1 | 30 | Full Swap | RO2 | Group1S | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266805 | khalilAlOmari |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | MW details on the civil table!! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-29 | Yes | W22 |  | 580 | RFI |  | Approved
1644 | 1644-Eng_HSG_Jordan_St_PF_TASC |  | AMW-711-R | Indoor | 327 | 35.9043 | 32.0104 | West Amman | Roof Top | saeid husayn saeid mustafaa | 078-5222555/079-9989296 | Tower T 12 | 18 | Full Swap | RO2 | Group1S | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266802 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Please modify the power solution so that it becomes as follows:FPFH1(C.B1*100):2AQQY+AHGEF+AHDA/FPFH2(C.B1*100):AHGEF+2AHEB+AHDA+ACOC | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2601 | 2601-Water_Authority_Shmeisani_PF_TASC |  | AMW-384-R | Indoor | 409 | 35.9047 | 31.9747 | West Amman | Roof Top | eatif muhamad ahmad yasin w musaa muhamad ahmad yasyn | 06-5686862 077-391491 | Pole P4#1 + P6#1 + P9#1 | 18 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355221 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | MW details on the civil table!! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-06-13 | Yes | W24 |  | 565 | RFI | Under Zain Validation | Approved
2614 | 2614-Shmeisani_Qadsieh_College_Back_PF_TASC_O |  | AMW-1012-R | Outdoor |  | 35.9018 | 31.97 | West Amman | Roof Top | muhamad amin ahmad hasan hamadh | 0777222002/0796498474 | Pole P9#2 | 21 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355227 | SMART |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-25 | Yes | W17 |  | 614 | RFI |  | Approved
2305 | 2305-UL_Jarwan_PD_Fiber_Org_TASC |  | AME-662-R | Indoor |  | 35.9973 | 31.9825 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355260 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-03-31 12:53 | Yes | W14 |  | 638.4633 | RFI |  | Approved |  |  |  |  | Downloaded
2613 | 2613-MOI_Mada_PF_TASC_O |  | AME-894-R | Outdoor |  | 35.9114 | 31.9732 | West Amman | Roof Top | asma kamil hasan eisaa | 0799008112/0799279029 | Tower T 12 | 30 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355226 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | please edit the notes on the power sheet | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | wrong data in civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
2327 | 2327-UL_Orchida_Hall_PF_TASC |  | AME-747-R | Indoor |  | 35.9913 | 31.9931 | Amman |  | Najjar |  |  |  | ThinLayer | RO2 | Group2T | Cluster-23 | Marka-North | Traditional | SMP-WO-1355334 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-02 | Yes | W14 |  | 637 | RFI |  | Approved |  |  |  |  | Downloaded
2603 | 2603-Meridian_Back_PE_EBand_TASC |  | AMW-568-R | Indoor | 1531 | 35.906 | 31.972 | West Amman | Roof Top | rami rasmi muhamad alghwl | 079-5049252 | Tower T 16 + P9 | 30 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355222 | SMART |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | The AMIA will be installed in place of the existing cabinet | Waed & Moath | Approved | NO 5G solution | M. Amro | Approved |  | Malek | Approved | civil requirement new not matching with civil sheet. Same note | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 | Yes | W16 |  | 622 | RFI |  | Approved
2621 | 2621-Arjan_PC_Fiber_TASC |  | AME-300-R | Indoor | 386 | 35.9129 | 31.9755 | West Amman | Roof Top | mahmud eabd alkarim khalil aldysi | 079/5503646 | Pole P6 X 3 | 16 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355229 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | AMIA Location is Rejected | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-12 | Yes | W20 |  | 597 | RFI |  | Approved |  |  |  |  | Downloaded
2622 | 2622-Dar_Hotel_PF_TASC_O |  | AME-301-R | Outdoor |  | 35.8904 | 31.9731 | West Amman | Roof Top | nizar mahmud aleabdi | 06/5622200 079-5550766 | Pole P6*2 | 20 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355230 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
2631 | 2631-MOC_PE_EBand_TASC |  | AME-309-R | Indoor | 359 | 35.905 | 31.9683 | West Amman | Roof Top | ahmad eiwad sulayman alsalahat | 06/5694811 079/5528552/079-5822220 | Pole P6X3+Wall Mounting (3m)+Wall Mounting | 21 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355231 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved | NO 5G solution | M. Amro | Approved | Kindly confirm that RRH install will not be back to back of antenna for ease of movement in the future. | Malek | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-29 | Yes | W18 |  | 610 | RFI |  | Approved
2640 | 2640-Birds_Gardens_PC_TASC |  | AME-317-R | Indoor | 372 | 35.8936 | 31.9713 | West Amman | Roof Top | bisam samih earafat eabd alruhmin abu khalaf | 077/232464 | Pole P6 X 2 + P9 X 1 + Wall mounted 3m Dp X 2 | 22 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355232 | SMART |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Please provide me power solution for (no 5g)/Modified the TSSR will not be installed 5G | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | The civil sheet does not match with the provided civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-17 | Yes | W16 |  | 622 | RFI |  | Approved
2619 | 2619-Sight_And_Sound_PB_TASC |  | AME-296-R | Indoor | 125 | 35.8976 | 31.9725 | West Amman | Roof Top | sharikat alsawt walsuwrih al urduniyat | 06/5661136 | Pole P6*4+P9*1 | 17 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355228 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
5606 | 5606-East_Sweileh_PD_EBand_TASC |  | AMW-305-R | Indoor | 160 | 35.8439 | 32.0275 | West Amman | Roof Top | hayjar yusif musaa alduws | 06/5331562 079-6818185/0777-319149 | Pole P6 X 4 | 22 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355271 | khalilAlOmari |  | Requested | Done |  |  |  | RAN Only | 4 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | wrong data provided in the civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved
5608 | 5608-Kamalieh_2_PE_Fiber_TASC |  | AMW-300-R | Indoor | 228 | 35.8294 | 32.0309 | West Amman | Roof Top | husayn yahyaa eadil bilatawy | 079/5527152 | Pole P9+P6X3 | 20 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355273 | Al-Tawseaa |  | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-29 | Yes | W22 |  | 580 | RFI |  | Approved
5613 | 5613-Sweileh_Civil_Defence_PF_EBand_TASC |  | AMW-304-R | Indoor | 176 | 35.8401 | 32.0197 | West Amman | Roof Top | Jordanian Electricity Company | 06/5340341- 078-5190846 | Pole WallMounting3#3 + P3#3 + P6#2 | 25 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355274 | Al-Tawseaa |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved | Approved after physical changes | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-13 | Yes | W24 |  | 565 | RFI | Under Zain Validation | Approved
5616 | 5616-Kamalieh_CRL_PC_Fiber |  | AMW-789-R | Indoor | 1729 | 35.8265 | 32.0292 | West Amman | Roof Top | shakir salamat muflah alzabydi | 079-7679400 | Tower T 16 | 13 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355275 | khalilAlOmari |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | M. Amro | Approved |  | Malek | Approved | Tower height !! // civil table !! // why H frame not normal DP? | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved
5617 | 5617-Kamalieh_3_PF_TASC_O |  | AMW-857-R | Outdoor |  | 35.814 | 32.0342 | West Amman | Roof Top | eabd yaequb saeid alkaluti | 06-5340409 079-5076223/ | Tower T 16 | 15 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355276 | khalilAlOmari |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | The SA is shifted to the mast3 without shifting SA(5G) ,but the SD(5G) is shifted on the mast 3 ,Please check again about sectors distribution.//power table is wrong. You did not add the 5g antenna to the sub sheet (planned site configuration )/Did you get approval to place the SD on two different poles, from the planning and optimization teams? wrong power solution /SD:As in the attached pictures, we have an empty DP. I think we don't need to add a new one?! | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table not matched with the BTS // The new installation or reuse in the table // sector height 7.5 meters on a 6 meters pole // number of existing DP on each Mast 30/10 reduce the load on Mast2 to Mast 3 by relocate new sector on it same note 1-11 relocate TDD antenna from Mast 1 to Mast 3 before proceeding with the installation from the past batch!! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-08 | Yes | W15 |  | 631 | RFI |  | Approved
5618 | 5618-Police_Patrol_3_PD_TASC |  | AMW-418-R | Indoor | 446 | 35.8492 | 32.0241 | West Amman | Roof Top | warathat ghalib iibrahim ahmad iibrahim eabd rizq | 06-5350587 079-5912807/079-7334810 | Pole P6X3+P9 | 22 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355277 | Al-Tawseaa |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-13 | Yes | W20 |  | 596 | RFI |  | Approved
5626 | 5626-Kamalieh_West_PC_Fiber_TASC |  | AMW-501-R | Indoor | 1503 | 35.8119 | 32.0288 | West Amman | Roof Top | rafat mustafaa ahmad salh |  | Tower T 12 | 27 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355278 | Cellcom | Cellcom | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | sdfreqgwhtrddsfsf | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved
5627 | 5627-Kamalieh_End_2_PF_TASC_O |  | AMW-855-R | Outdoor |  | 35.8205 | 32.0333 | West Amman | Roof Top | warathat eabd rbh ealia muflih alzabidi | 077-5506121/077-6933217 | Pole P9 | 15 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355279 | Cellcom | Cellcom | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | correct the antennas dimensions, fill all the data in the civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
5628 | 5628-Sweileh_Ind_TL_PE_GPON_TASC_O |  | AMW-861-R | Outdoor |  | 35.8457 | 32.0165 | West Amman | Roof Top | fayiz musaa ahmad alhuluw | 079-5872548/079-5300312 | Pole P9#2 | 24 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355280 | khalilAlOmari |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | power sheet: wrong power solution we need to CB 100 for FBFH 3 not 63 | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table & the whole sheet not as the standard | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-17 | Yes | W16 |  | 622 | RFI |  | Approved
5632 | 5632-Souq_Sweileh_PE_Zain_TASC |  | AMW-383-R | Indoor | 401 | 35.8413 | 32.0241 | West Amman | Roof Top | mamun muhamad dhib marza alshiyshani | 077/462165 | Pole P6*6 | 21 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355283 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved | /replace type of sector to(A/B/C/D)NOT (1/2/3/4) | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved
5633 | 5633-Rahmanieh_Sweileh_PE_GPON_TASC_O |  | AMW-877-R | Outdoor |  | 35.8359 | 32.0154 | West Amman | Roof Top | zahir muhamad ahmad alkhtyb | 06 5359096 065347492 795542188 | Pole P9 | 14 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355284 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-25 10:45 | Yes | W17 |  | 613.5522 | RFI |  | Approved
5635 | 5635-Sweileh_Ind_PA_Fiber_TASC |  | AMW-318-G | Indoor | 174 | 35.8494 | 32.0198 | West Amman | Green Field | safiat bymrza alshiyshani |  | Tower T 30 | 20 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355285 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved | (SD&SC)as TSSR same picture/replace type of sector to(A/B/C/D)NOT (1/2/3/4)/The AMIA will be installed in place of the existing cabinet | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-06-04 | Yes | W23 |  | 574 | RFI |  | Approved
5636 | 5636-Kamalieh_Safoot_PF_EBand_TASC |  | AMW-689-R | Indoor | 1610 | 35.8365 | 32.0305 | West Amman | Roof Top | zaynab eubdallah ahmad jbr | 079-5699477 | Pole P9 + P6 | 18 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355286 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-29 | Yes | W18 |  | 610 | RFI |  | Approved
5637 | 5637-Kamalieh_PA_Fiber_TASC |  | AMW-319-R | Indoor | 175 | 35.8222 | 32.0302 | West Amman | Roof Top | eisam yaequb musaa qamawat | 06/5412553 | Tower T 6 | 21 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355287 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-29 | Yes | W18 |  | 610 | RFI |  | Approved
5641 | 5641-Police_Patrol_TL_PD_Fiber_TASC |  | AMW-701-R | Indoor | 183 | 35.8566 | 32.0249 | West Amman | Roof Top | sharikat alsuws washarakaha | 079-7436611/079-5592401/079-5791166 | Pole P6 X 2 + P9 X 1 | 26 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355289 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved
5645 | 5645-Higher_Education_2_PE_Fiber_TASC_O |  | AMW-1070-R | Outdoor |  | 35.8664 | 32.0278 | West Amman | Roof Top | dif allah faris yusif alluwzi | 797480809 | Tower T 16 | 21 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355290 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-24 07:34 | Yes | W17 |  | 614.6847 | RFI |  | Approved
5646 | 5646-Police_Patrol_2_PD_EBand_TASC |  | AMW-435-R | Indoor | 479 | 35.853 | 32.028 | West Amman | Roof Top | ratib saeid hasan hanawy | 06-534537 079-5518857 | Pole P6#2 + P9#1 | 18 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355291 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 3 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-09 | Yes | W19 |  | 600 | RFI |  | Approved
5647 | 5647-Prince_Faisal_Palace_PE_Fiber_TASC |  | AMW-706-R | Indoor | 461 | 35.8358 | 32.0229 | West Amman | Roof Top | jamil ealia ewad alruhahlat | 077-9429645 | Pole P6X3 | 21 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355292 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | I need a clear picture of the entire rectifier | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-21 | Yes | W21 |  | 588 | RFI |  | Approved
5649 | 5649-Sweileh_Market_PF_TASC_O |  | AMW-868-R | Outdoor |  | 35.8357 | 32.0282 | West Amman | Roof Top | muhamad kamal mustafaa altrk | 079-5729000/079-7990900 | Pole P6*2+P9*1 | 24 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355293 | Al-Tawseaa | Tawseaa | Requested | Done |  |  |  | 5G | 5 |  |  |  |  | Approved | AMIA will be installed in place of the existing cabinet | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
5651 | 5651-Sweileh_CRL_PF_TASC_O |  | AMW-979-R | Outdoor |  | 35.8452 | 32.0225 | West Amman | Roof Top | akram ahmad khalf darabukah | 0799758404/0775715248 | Pole P9#2 | 24 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355294 | khalilAlOmari |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | we need to Clear pictures identify each BLVD&LLVD Please specify the C.Bs that will be replaced in the LLVD | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-09 | Yes | W19 |  | 600 | RFI |  | Approved
5652 | 5652-Sweileh_East_Mid_PE_TASC_O |  | AMW-1055-R | Outdoor |  | 35.8474 | 32.0281 | West Amman | Roof Top | sham eabd alqadir 'ahmad alhadidaa | 795668870/0796849393 | Pole P9#2 | 9 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355295 | Al-Tawseaa | Tawseaa | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | approved with note (Please specify another location for the ACOC as we agreed with mufeed/ we will used for all sectors 10 ports antenna not 14 ports antenna ) | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | Civil sheet does not match with BTS sheet same note 21-04 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
5653 | 5653-Jubaiha_Manhal_InterX_PE_Fiber_TASC_O |  | AMW-1003-R | Outdoor |  | 35.8714 | 32.0282 | West Amman | Roof Top | walid mustafaa ahmad shawish | 786189128 | Pole P9#2 | 23 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355296 | Al-Tawseaa | Tawseaa | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved | Align heights of AAU with 6port antenna | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
5654 | 5654-East_Sweileh_UmKather_PE_EBand_TASC_O |  | AMW-995-R | Outdoor |  | 35.8469 | 32.0262 | West Amman | Roof Top | sami muhamad fiad aldargham | 05/3557077 796504158 | Pole P9#2 | 21 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355297 | Al-Tawseaa | Tawseaa | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved | Solved\ Sector A azimuth=95, sector B=125, sector C=2245 and sector D=320 | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved
5657 | 5657-Police_Patrol_4_PE_TASC_O |  | AMW-997-R | Outdoor |  | 35.852 | 32.0267 | West Amman | Roof Top | eatif muhamad raghib shumwt | 0795873779/0795698690/0788720410 | Pole P6+P9 | 21 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355298 | Al-Tawseaa | Tawseaa | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved | Install a new 9m pole for Sector C & D | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-21 | Yes | W21 |  | 588 | RFI |  | Approved
5659 | 5659-Sweileh_Market_2_PF_TASC_O |  | AMW-1013-R | Outdoor |  | 35.8376 | 32.0261 | West Amman | Roof Top | euthman khalid ahmad alzaebi | 0792540223/079254221 | Pole P9 + P6 | 24 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355299 | Al-Tawseaa | Tawseaa | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-07 | Yes | W19 |  | 602 | RFI | Hold by Zain Optimization due proposed Azimuth plan | Approved
5661 | 5661-UL_Safoot_Kamalieh_Mid_O |  | AMW-1146-R | Outdoor |  | 35.8257 | 32.032 | West Amman | Roof Top |  |  | Tower 16 | 25 | Full Swap | RO2 | Group2S | Cluster-56 | Swieleh | Traditional | SMP-WO-1355300 | Al-Tawseaa | Tawseaa | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table Same note | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-09 | Yes | W19 |  | 600 | RFI |  | Approved
2542 | 2542-Rasheed_End_2_PE_Fiber_TASC_O |  | AMW-816-R | Outdoor |  | 35.8863 | 32.0173 | West Amman | Roof Top | hasan kamil hasan eisaa | 079-6356063/079-5450014 | Pole P6*3 | 21 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1266855 | khalilAlOmari |  | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | 5G to be ABD / TSSR BCD which is Wrong | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-24 | Yes | W21 |  | 585 | RFI |  | Approved
2501 | 2501-Jubaiha_PA_Fiber_TASC |  | AMW-249-G | Indoor | 67 | 35.861 | 32.0369 | West Amman | Green Field | eabd alkarim eyd alluwzi |  | Tower T 45 | 20 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1349049 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved | Solved\ Sectors azimuths are 60, 150 and 250 | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2502 | 2502-Manhal_CRL_PE_Fiber_TASC |  | AMW-645-R | Indoor | 1565 | 35.8692 | 32.0342 | West Amman | Roof Top | jamil khalid ealia sawaydat | 07777-87239/079-5602447 | Tower T 12 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1349050 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 2 |  |  |  |  | Approved | modify the power solution so that it becomes as follows:FPFH1(100):1AQQY + AHGEF + 3*AHEB+AHGEF+AHDA//FPFH2(100):AQQY + AHGEF + AHEB + 2*AHDA//(1*30):ACOC | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-14 | Yes | W20 |  | 595 | RFI |  | Approved |  |  |  |  | Downloaded
2503 | 2503-Jubaiha_3_PE_TASC |  | AMW-651-R | Indoor | 1569 | 35.8806 | 32.048 | West Amman | Roof Top | muhamad mahmud saeid aleajluni | 06-5105168 0777-410921 | Tower T 12 | 23 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355162 | Powergate | Powergate | Requested | Done |  |  |  | RAN Only | 4 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-29 | Yes | W22 |  | 580 | RFI |  | Approved
2504 | 2504-Higher_Education_3_PC_Fiber_TASC |  | AMW-335-R | Indoor | 491 | 35.8794 | 32.0328 | West Amman | Roof Top | ghaliatan muhamad ashq alnazr | 06-5348835 079-5228022 | Tower T 16 | 19 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355163 | Powergate | Powergate | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | civil requirment sheet:no need to install DP (AS LLD NO 5G sites ) | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved
2506 | 2506-Imam_Ghazali_PE_Fiber_TASC_O |  | AMW-617-R | Outdoor |  | 35.8524 | 32.0338 | West Amman | Roof Top | naji bayir sulayman albtaynat | 078-6392072 | Pole P6*1+P9*2 | 14 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355164 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-21 | Yes | W21 |  | 588 | RFI |  | Approved |  |  |  |  | Downloaded
2507 | 2507-Kamalieh_End_PF_TASC_O |  | AMW-628-R | Outdoor |  | 35.8207 | 32.0383 | West Amman | Roof Top | eaziz salih eabdalilah eabydallh | 079-5681244/0776988983 abu elias | Pole P6 X 2 + P9 X 1 | 15 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355165 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-09 | Yes | W19 |  | 600 | RFI |  | Approved |  |  |  |  | Downloaded
2508 | 2508-Khadra_Ave_PC_EBand_TASC |  | AMW-257-R | Indoor | 179 | 35.8986 | 32.0311 | West Amman | Roof Top | wahib mahmud khalyl salim abu altyn | 06/5234653 079-7336694 | Pole P6 X 4 | 26 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355166 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved | Solved\ Sector A azimuth is 50 | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2510 | 2510-AbuNusair_4_PE_Fiber_TASC |  | AMW-684-R | Indoor | 1599 | 35.8773 | 32.0594 | West Amman | Roof Top | muhamad fuad hasan khalf | 0777-88858/079-5134242 | Tower T 12 | 22 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355167 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2511 | 2511-Rasheed_Jordan_St_PE_TASC |  | AMW-685-R | Indoor | 1603 | 35.8919 | 32.0214 | West Amman | Roof Top | juzif khadir nuqulana habash | 06-5236369 079-5132612 | Tower T 12 | 23 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355168 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | RAN Only | 4 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-29 | Yes | W22 |  | 580 | RFI |  | Approved
2512 | 2512-Jordan_St_4_PC_Fiber_TASC |  | AMW-502-R | Indoor | 60 | 35.8693 | 32.0674 | Balqa | Roof Top | sakar ahmad eiad alsukr | 06-5370007 079-5538436 | Tower T 16 | 22 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355169 | Al-Lewan | Al-Lewan | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved |  |  |  |  | Downloaded
2516 | 2516-AbuNusair_3_PD_Fiber_TASC |  | AMW-265-R | Indoor | 7 | 35.8724 | 32.0605 | West Amman | Roof Top | eatij bashir manahi aleadwan |  | Pole P6 X 2 + P9 X 2 + P4 X 1 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355170 | Powergate | Powergate | Requested | Done |  |  |  | RAN Only | 2 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved | Solved\ 4G sector D azimuth value is wrong | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2517 | 2517-Hay_Dyaa_AbuNusair_PF_Zain_TASC |  | AMW-736-R | Indoor | 1643 | 35.883 | 32.0729 | West Amman | Roof Top | seadimustafaa rshiyd alghazw | 0777-400266/079-6140085 | Tower T 12 | 21 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355171 | Powergate | Powergate | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-31 | Yes | W22 |  | 578 | RFI |  | Approved
2519 | 2519-Safoot_PE_Fiber_TASC |  | AMW-268-R | Indoor | 166 | 35.8332 | 32.0391 | Balqa | Roof Top | eabd alkarim iismaeil ahmad hmydt | 06/5335209 079/5782455 | Tower T 12 | 26 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355172 | Al-Tawseaa | Al-Tawseaa | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved | Solved\ antennas on same sector has the same azimuth Solved\ provided azimuths are wrong and doesn't match with the 360 photos | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-03 | Yes | W14 |  | 636 | RFI |  | Approved |  |  |  |  | Downloaded
2520 | 2520-Wasieh_CRL_Tab_Kraa_PD_Fiber_TASC |  | AMW-765-R | Indoor | 1675 | 35.8911 | 32.0563 | West Amman | Roof Top | nasir ahmad fayad alwrikat | 079-7702202 | Tower T 12 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355173 | Al-Tawseaa | Al-Tawseaa | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved | Solved\ Sectors are A,b and c | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-14 | Yes | W20 |  | 595 | RFI |  | Approved |  |  |  |  | Downloaded
2521 | 2521-AbuNusair_PA_Fiber_TASC |  | AMW-270-G | Indoor | 5 | 35.8786 | 32.0554 | West Amman | Green Field | almuasasat aleamat lilaskan w altatwir alhadri |  | Tower T 30 | 30 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355174 | Al-Tawseaa | Al-Tawseaa | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved |  | Waed & Moath | Approved | no the 5g solution is not suggested | Baher Obaidat | Approved | Approved after physical changes | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-09 | Yes | W19 |  | 600 | RFI |  | Approved |  |  |  |  | Downloaded
2525 | 2525-Shafa_Badran_Itifaq_Sch_PE_Fiber_TASC_O |  | AMW-1092-R | Outdoor |  | 35.8948 | 32.0481 | West Amman | Roof Top |  |  | Pole P9#2 | 27 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355180 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-25 10:54 | Yes | W17 |  | 613.5459 | RFI |  | Approved |  |  |  |  | Downloaded
2528 | 2528-Higher_Education_PE_O |  | AMW-277-R | Outdoor | 49 | 35.876 | 32.0311 | West Amman | Roof Top | nasir sadqi munib shumut | 06/5341334 - 06/5341359 | Pole P9 x 3 | 19 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355181 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-06-04 | Yes | W23 |  | 574 | RFI |  | Approved
2530 | 2530-Zaytouneh_2_PD_Fiber_TASC |  | AMW-761-R | Indoor | 1679 | 35.8891 | 32.0341 | West Amman | Roof Top | hazim nsar hanna aldababnat | 06-5333775 079-9043619 | Tower T 18 | 14 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355182 | Al-Tawseaa | Al-Tawseaa | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | wrong power solution /and re -check power sheet | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-15 | Yes | W20 |  | 594 | RFI |  | Approved |  |  |  |  | Downloaded
2533 | 2533-AbuNusair_Market_PD_Fiber_TASC |  | AMW-671-R | Indoor | 1590 | 35.8755 | 32.05 | West Amman | Roof Top | mashhur mahmud jarid aledwan | 06-5231100 079-5755128 | Pole P6 X 3 | 27 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355184 | Powergate | Powergate | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | no 5g site | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-24 | Yes | W17 |  | 615 | RFI |  | Approved |  |  |  |  | Downloaded
2534 | 2534-Tab_Kraa_PD_Fiber_TASC_O |  | AMW-283-R | Outdoor | 161 | 35.886 | 32.0534 | West Amman | Roof Top | eabd alhamid shakir khalifat aleadwan | 06/5236705 079/5506422 | Pole P6 X 2+ P9 X 2 | 21 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355185 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  | Yes |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-24 | Yes | W21 |  | 585 | RFI |  | Approved
2536 | 2536-Safeway_Jubaiha_Back_PE_O |  | AMW-874-R | Outdoor |  | 35.8558 | 32.0293 | West Amman | Roof Top | hajar yusif sulayman alluwzi | 0798301010 / 0798167858 | Pole P9#2 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355186 | Al-Lewan | Al Lewan | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | note RF sheet: separate each service | Waed & Moath | Approved |  | Omar Sami | Approved | Sector A is 40 degrees, not 70. | Mo'taz Al-Khateeb | Approved | civil table not as the standard // location of each Anntena on which Mast not sector // | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-29 | Yes | W22 |  | 580 | RFI |  | Approved
2537 | 2537-Jubaiha_Rayyan_Ave_PE |  | AMW-754-R | Indoor | 1737 | 35.868 | 32.0308 | West Amman | Roof Top | ghazi tahir muhamad hunuwn | 06-5353227 0777-288228 | Tower T 16 | 16 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355187 | Powergate | Powergate | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-13 | Yes | W24 |  | 565 | RFI | Under Zain Validation | Approved
2538 | 2538-Jubaiha_Rayyan_Ave_2_PD |  | AMW-774-R | Indoor | 1730 | 35.8652 | 32.0352 | West Amman | Roof Top | samirat eabdallah muhi aldiyn eawatilh | 079-6064707/079-5666789 | Tower T 16 | 16 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355188 | Sigma | Sigma | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-06 | Yes | W23 |  | 572 | RFI |  | Approved
2539 | 2539-Bunat_Ghad_Sch_PE_Fiber_TASC_O |  | AMW-800-R | Outdoor |  | 35.8446 | 32.0371 | West Amman | Roof Top | mahir nishan mazid jarisat | 079-9070990 | Pole P9#2 | 11 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355189 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-19 | Yes | W21 |  | 590 | RFI |  | Approved |  |  |  |  | Downloaded
2540 | 2540-Jubaiha_2_PE_EBand_TASC |  | AMW-288-R | Indoor | 371 | 35.8717 | 32.0426 | West Amman | Roof Top | bashirat tawfiq shakir eulush | 079/5221817 | Tower T 12 | 36 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355190 | SMART | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-05-12 | Yes | W20 |  | 597 | RFI |  | Approved
2543 | 2543-Jubaiha_Tunnel_PF_TASC_O |  | AMW-836-R | Outdoor |  | 35.878 | 32.0406 | West Amman | Roof Top | amin muhamad jaefar eabd alrahim alemd | 06-5348161 079-5996670 | Tower T 12 | 22 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355191 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved | Site will be Relocated in 18/5 , Please to make the TSSR again | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil table Same note | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | B | Approved | Approved | 2024-04-04 | Yes | W14 |  | 635 | RFI |  | Approved |  |  |  |  | Downloaded
2545 | 2545-Rasheed_End_PE |  | AMW-796-R | Indoor | 1728 | 35.8817 | 32.0278 | West Amman | Roof Top | iibrahim eabd aljabir eabd alqadir jamus | 079-9601013/079-6206233 | Pole P9#2 | 14 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355192 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Please re-check all the TSSR(RF sheet: we need separat each(2g/3g/4g)//no need to instaal DPs........) | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-12 | Yes | W20 |  | 597 | RFI |  | Approved
2546 | 2546-Shafa_Badran_CRL_PE_Fiber_TASC_Relo_O |  | AMW-1108-R | Outdoor |  | 35.8918 | 32.0481 | West Amman | Roof Top | iibrahim musaa alshaykh abu qbe | 079-5523992/079-8781983 | Tower T 16 | 33 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355193 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved | Solved\ Sectors are A, C and D | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-09 | Yes | W19 |  | 600 | RFI |  | Approved |  |  |  |  | Downloaded
2547 | 2547-Shafa_Badran_Thehiebeh_PE_Fiber_TASC_O |  | AMW-878-R | Outdoor |  | 35.8865 | 32.0446 | West Amman | Roof Top | muhamad eabdallah khalil hasayn | 795635839 | Pole P6*3 | 21 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355196 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  | Waed & Moath | Approved | increase all the sectors on the top of the pole ( 1-2 m increase) | Omar Sami | Approved | Solved\ Sector A azimuth 20 | Mo'taz Al-Khateeb | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-01 | Yes | W18 |  | 608 | RFI |  | Approved |  |  |  |  | Downloaded
2549 | 2549-Lamerada_Hotel_Jordan_Uni_PE_Fiber_TASC |  | AMW-755-R | Indoor | 1677 | 35.8778 | 32.0281 | West Amman | Roof Top | mustafaa ealia muhamad alkhtib | 079-5603661/079-5070826 | Pole P6X3 | 21 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355197 | SMART | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Mo'taz Al-Khateeb | Approved | civil SHEET | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-13 | Yes | W20 |  | 596 | RFI |  | Approved
2550 | 2550-Jubaiha_5_PD |  | AMW-786-R | Indoor | 1743 | 35.8782 | 32.0354 | West Amman | Roof Top | eabd alkarim iibrahim eabd alruhmin alsamak | 079-8734085/079-8924740 | Tower T 20 | 29 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355198 | SMART | Powergate | Requested | Done |  |  |  | RAN Only | 3 |  |  |  |  | Approved |  | Waed & Moath | Approved |  | Omar Sami | Approved |  | Malek | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-04 | Yes | W23 |  | 574 | RFI |  | Approved
2553 | 2553-Zaytouneh_Ave_PE |  | AMW-723-R | Indoor | 1667 | 35.8846 | 32.0337 | West Amman | Roof Top | fayiz eata allah eabdalalah alkhalayfata | 079-5204622/0777-6510 | Pole P6*2+P9*1 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355199 | Powergate | SMART | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  | Moath & Waed | Approved |  | Omar Sami | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 |  | Approved | Approved | 2024-05-22 |  | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2554 | 2554-Jubaiha_Sweileh_PE_Fiber_TASC |  | AMW-787-R | Indoor | 1739 | 35.8611 | 32.0318 | West Amman | Roof Top | muhamad hasan muhamad alsayfi | 079-6692065 | Tower T 20 | 26 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355200 | Powergate | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved |  | Murad Al-khalily | Approved | Murad Al-khalily |  | 5 |  | Approved | Approved | 2024-05-21 | Yes | W21 |  | 588 | RFI |  | Approved |  |  |  |  | Downloaded
2555 | 2555-Princess_Bassma_Palace_Back_PF_TASC_O |  | AMW-1099-R | Outdoor |  | 35.856 | 32.0385 | Balqa | Roof Top | sharikat al ahli liltaajir altamwilii | 06-534606446 079-6850789/ | Pole P9 | 15 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355201 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 2 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | 5 |  | Approved | Approved | 2024-05-09 |  | W19 |  | 600 | RFI |  | Approved |  |  |  |  | Downloaded
2556 | 2556-Marine_Academy_PE_Fiber_TASC_O |  | AMW-856-R | Outdoor |  | 35.8882 | 32.0647 | West Amman | Roof Top | fayzt ahmad hasan yasin | 06-5231806 0777-490966 | Pole P9#2 | 12 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355202 | Al-Lewan |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-15 | Yes | W20 |  | 594 | RFI |  | Approved |  |  |  |  | Downloaded
2557 | 2557-Tab_Kraa_2_PD_O |  | AMW-858-R | Outdoor |  | 35.8967 | 32.0629 | West Amman | Roof Top | khamis tawfiq ahmad alfalah | 0777-490966/078-6455135/179-6846847 | Tower T 12 | 19 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355203 | Al-Lewan |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-01 | Yes | W18 |  | 608 | RFI |  | Approved |  |  |  |  | Downloaded
2641 | 2641-Dakhelieh_PE_TASC |  | AME-324-R | Indoor | 387 | 35.9104 | 31.9713 | West Amman | Roof Top | mahmud hamadat mahmud eatyt | 079-5869531 | Pole P6 X 5 | 20 | Full Swap | RO2 | Group1S | Cluster-26 | Shmisani | Traditional | SMP-WO-1355233 | SMART |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-04-25 | Yes | W17 |  | 614 | RFI | Hold by Zain Optimization due proposed Azimuth plan | Approved
2558 | 2558-Rasheed_Hospital_Back_PF_BTS_Relo_O |  | AMW-1110-R | Outdoor |  | 35.862 | 32.058 | West Amman | Roof Top | ahmad eabd allatif tawfiq abu sae | 0795942258/0788635569 | Pole 9 * 2 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355204 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Change the formula to become( We will reuse two PDU(100A) and add a new PDU(100A)) |  | Approved | set azimuth of sector A to 50 at leg 4 , and C to 165 at leg 2, and D to 265 at leg 3 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-12 | Yes | W20 |  | 597 | RFI |  | Approved |  |  |  |  | Downloaded
2559 | 2559-Safoot_East_PF_TASC_O |  | AMW-996-R | Outdoor |  | 35.8263 | 32.0366 | Balqa | Roof Top | muhamad ahmad eabd alkhaliq dawud | 079582231/0799270869 | Pole P9#2 | 20 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355205 | Cellcom |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2566 | 2566-UL_Rasheed_Rital_Academy_Back_PF_BTS_O |  | AMW-1138-R | Outdoor |  | 35.8905 | 32.0257 | West Amman | Roof Top |  |  | Tower 20 | 35 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355208 | Cellcom |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved |  |  |  |  | Downloaded
2569 | 2569-UL_Shafa_Badran_UmHjair_PF_TASC_O |  | AMW-1134-R | Outdoor |  | 35.893 | 32.0444 | West Amman | Roof Top |  |  | Tower T 20 | 29 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355209 | Cellcom |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  |  | Approved | Sectors Naming is wrong (should be A,C,D) |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-19 | Yes | W21 |  | 590 | RFI |  | Approved |  |  |  |  | Downloaded
2571 | 2571-Shafa_Badran_CTR_PE_Fiber_TASC_O |  | AMW-969-R | Outdoor |  | 35.8944 | 32.054 | West Amman | Roof Top | ahmad yusif muhamad aleadwan | 0780800182/0777782618 | Tower T 20 | 26 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355210 | Ecotel |  | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  |  | Approved | set azimuth of sector A to 20 , azimuth of B to120 and sector of C to 240//still h |  | Approved |  |  | Approved | check dimension and height of existing M.w and Antennas. The antenna dimension in civil sheet are not matched with provided table in the same sheet. The pictures for masts are not showing the full of masts and details // Need extra Mast//reject again 6-7 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-12 | Yes | W20 |  | 597 | RFI |  | Approved
2572 | 2572-Sahara_Mall_Jordan_St_PE_Fiber_TASC_O |  | AMW-970-R | Outdoor |  | 35.8712 | 32.0572 | West Amman | Roof Top | husayn ahmad farij alrawashdh | 0772178709/0772178674 | Pole P9#2 | 23 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355211 | Ecotel |  | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  |  | Approved | set the azimuth of sector C to 270, install the new DP at leg D to the left on 4G antenna |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-06 | Yes | W19 |  | 603 | RFI |  | Approved
2573 | 2573-Jubaiha_UmHjair_PF_TASC_O |  | AMW-974-R | Outdoor |  | 35.8935 | 32.0401 | West Amman | Roof Top | farial mahmud eubayd salayman | 0799341818/0790453889 | Tower T 20 | 32 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355212 | Al-Lewan | Al-Lewan>>GSM | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-03 | Yes | W23 |  | 575 | RFI |  | Approved
2574 | 2574-Sideeq_Ave_Back_PD_EBand_TASC_O |  | AMW-980-R | Outdoor |  | 35.8996 | 32.0241 | West Amman | Roof Top | eumar sayir mahmud knakryh | 06/5343021 778537099 | Pole P9#2 | 18 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355213 | PIS | PIS | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  |  | Approved | set sector A to 20 , sector B to 160 , sector C to 260 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-24 | Yes | W21 |  | 585 | RFI |  | Approved
2578 | 2578-Iskan_AbuNusair_North_PE_Fiber_TASC_O |  | AMW-990-R | Outdoor |  | 35.8836 | 32.0627 | West Amman | Roof Top | ashraf ealia hasan eabdalrahman | 777888999 | Tower T 16 | 21 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355214 | PIS | PIS | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-29 | Yes | W22 |  | 580 | RFI |  | Approved
2579 | 2579-Zaytouneh_3_PE_Fiber_TASC_O |  | AMW-998-R | Outdoor |  | 35.8895 | 32.0302 | West Amman | Roof Top | iibrahim khalil milad aljamalih | 0798972153/0798667403/0798567982 | Pole P9#2 | 9 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355215 | Powergate | SMART | Requested | Done |  |  |  | RAN Only | 4 |  |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-22 | Yes | W21 |  | 587 | RFI |  | Approved |  |  |  |  | Downloaded
2580 | 2580-AbuNusair_2_PE_EBand_O |  | AMW-935-R | Outdoor |  | 35.8802 | 32.0661 | West Amman | Roof Top | ahmad muhamad qasim alelawnt | 0795752129/0776408649 | Pole P9 X2 | 20 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355216 | Powergate | SMART | Requested | Done |  |  |  | 5G | 3 |  | Yes |  |  | Approved | Bad Pictures , Sectors Location not clear , 5G sector B C D not A B D |  | Approved | set azimuth of sector A to 5 on relative mast , and sector B to 95 on relative mast and sector C to 225 on relative mast |  | Approved | Azimuth Views are not aligned with panorama view(needs correction) |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-13 | Yes | W24 |  | 565 | RFI | Under Zain Validation | Approved
2582 | 2582-AbuNusair_Farouq_Msq_PE_Fiber_TASC_O |  | AMW-961-R | Outdoor |  | 35.8864 | 32.0564 | West Amman | Roof Top |  |  | Tower T 16 | 15 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355217 | Powergate | SMART | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved | Already Swapped |  | Approved | pictures not clear |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-16 | Yes | W20 |  | 593 | RFI |  | Approved |  |  |  |  | Downloaded
2587 | 2587-Safoot_End_PE_Fiber_TASC_O |  | AMW-1017-R | Outdoor |  | 35.8408 | 32.0418 | Balqa | Roof Top | eadnan eatayh muhamad muhisun | 0795599072/0799419260 | Pole P9 + P6 | 21 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355218 | PIS | PIS | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved | Already Swapped |  | Approved | increase height of sector C & D |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-06 | Yes | W23 |  | 572 | RFI |  | Approved
2588 | 2588-Rasheed_Hospital_PE_DIBS_Manage_O |  | AMW-1036-R | Outdoor |  | 35.868 | 32.0636 | Balqa | Roof Top | markaz mustashfaa alrashid |  | Pole P6+P9 | 19 | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355219 | PIS | PIS | Requested | Done |  |  |  | 5G | 5 | IBS-D |  |  |  | Approved |  |  | Approved | Needs verification from civil on the DP instalation feasibility |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-06-06 | Yes | W23 |  | 572 | RFI |  | Approved
2593 | 2593-UL_TabKraa_AbuNseir_O |  | AMW-1180-R | Outdoor |  | 35.8825 | 32.0509 | Amman | [5 empty] | Full Swap | RO2 | Group3S | Cluster-25 | Jubeiha | Traditional | SMP-WO-1355220 | Sigma | Sigma | Requested | Done |  |  |  | 5G | 4 |  |  |  |  | Approved |  |  | Approved | sector A to 75 and install the new antenna at the free DP of sector B , sector B at 170 and install the new antenna at the free DP of sector C , sector C at 325 and install the new antenna at the free DP of sector D |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-31 | Yes | W22 |  | 578 | RFI |  | Approved
6143 | 6143-UL_Safoot_Center_O |  | AMW-1195-R | Outdoor |  | 35.8525 | 32.0557 | Amman | [5 empty] | Full Swap | RO2 | Group3S | Cluster-61 | Safoot | Traditional | SMP-WO-1355301 | PIS |  | Requested | Done |  |  |  | 5G | 3 |  |  |  |  | Approved |  |  | Approved | set azimuth of sector B to 230 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-05-31 | Yes | W22 |  | 578 | RFI |  | Approved
5426 | Royal_Court_AlBait_PF_IBS_M | ZAIN | AME-1059-R | IBS |  | 35.9471 | 31.9585 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-54 |  |  | SMP-WO-1419180 |  |  | Not Requested |  |  |  |  | RAN Only | 1 | IBS |  |  |  | Approved |  |  | Approved | set sector A to 80, sector B to 190 , sector C to 285 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | IBS | 2024-08-18 | Yes
2615 | 2615-Corp_Hotel_PF_IBS_M | ZAIN | AMW-1083-R | IBS |  | 35.9055 | 31.9761 | Amman | IBS | 0 | 0 | IBS | IBS | Full Swap | P.O.2 | IBS | Cluster-26 |  |  | SMP-WO-1419183 |  |  | Not Requested |  |  |  |  | RAN Only | 1 | IBS |  |  |  | Approved | Only we will work on the 4 Outdoor Sectors , to contact Dabbagh from Zain to work on it |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved |  | 2024-11-10
5045 | 5045-UL_Nazzal_Hunain_Sch_O | [22 empty] | Done | [9 empty] | Approved | Already Approved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  |  | W0 |  | 46021
3604 | 3604-TV_HSG_PB_Fiber_TASC |  | AME-62-R | Indoor | 361 | 35.9243 | 31.9141 | South Amman | Roof Top | aminih muhamad yusif khalyl | 06/4783200 079/5528690 | Pole P9 X 1 + P6 X 4 + D3 X 1 | 10 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1216978 | UTC |  | 47733528 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | Already Approved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3611 | 3611-Haj_Hassan_PE_EBand_TASC_O |  | AMS-202-R | Outdoor |  | 35.9306 | 31.9108 | South Amman | Roof Top | abd al hakeem al3egel | 799815755 | Tower T 20 | 21 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1216979 | UTC |  | 47733535 | Done |  |  |  | 5G | [5 empty] | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3612 | 3612-Mugabalein_Ind_Jwico_Factory_PF_O |  | AMS-308-R | Outdoor |  | 35.8978 | 31.9087 | South Amman | Roof Top | Mugablein INd jwico factory |  | Tower 12 | 9 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219427 | UTC |  | 47733537 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
150 | 150-Abdoun_Osra_Rest_Back_PE_GPON_TASC_O |  | AMS-167-R | Outdoor |  | 35.877 | 31.9531 | South Amman | Roof Top | muhamad hashim muhamad eali aldhnus | 0797481200/0799442828/0799190926 | Tower T 16 | 22 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216966 | R&D |  | 47759359 | Done |  |  |  | 5G | [5 empty] | Approved | please to follow 3G/4G AZ for 5G & for 2G will check again |  | Approved |  |  | Approved |  |  | Approved | Approved Zain equipment's | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-20 | Yes | W34 |  | 863 |  |  | Approved
3614 | 3614-Yasmeen_Subhi_Msq_PF_TASC_O |  | AMS-51-R | Outdoor |  | 35.8935 | 31.9152 | South Amman | Roof Top | mahir barakat | 0798242660- 078-5527744 | Tower T 16 | 26 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1217278 | UTC |  | 47733542 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | 2G Sector C Azimuth not correct, Kindly check |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
3619 | 3619-Quds_St_PD_EBand_TASC |  | AME-77-R | Indoor | 365 | 35.8947 | 31.9139 | South Amman | Roof Top | muhamad dawud eubayd allah alatrsh | 06/4161572/06/4206152 079/5549968 | Pole P6 X 3 + P9 X 3 | 21 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219428 | TAWSEAA |  | 47734288 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved | baher, for 5 G solution , set the azimuth of sector A to 0 on mast A set the azimuth of sector B to 120 at mast B. set the azimuth of sector C to 210 at mast C.//// notes have been modified on TSSR sheet |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3624 | 3624-ARAMEX_Quds_St_PF_Manage_O |  | AME-774-R | Outdoor |  | 35.9024 | 31.9136 | South Amman | Roof Top | sharikat aramkis al urdun almhdudat |  | Pole Mast 6m#2 | 12 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1216980 | UTC |  | 47733546 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved - 5G Cancelled from this site |  | Approved | set azimuth to 55/130/240 |  | Approved |  |  | Approved | mismatch TSSR and solution (No 5G) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-05-24 | Yes | W21 |  | 951 |  |  | Approved |  |  |  |  | Downloaded
3211 | 3211-English_Sch_PC_EBand_TASC |  | AMW-375-R | Indoor | 1513 | 35.844 | 31.9872 | West Amman | Roof Top | rayid iilyas hanna eaways | 079-5609817/0777384567/0795609817 | Pole P6 X 3 | 23 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1235943 | Al-Lewan |  | 48358860 | Done |  |  |  | 5G | [5 empty] | Approved | new attachment uploaded |  | Approved | baher, for 5G solution , use sector A and C and D |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-03 | Yes | W31 |  | 880 |  |  | Approved
3629 | 3629-UL_Haj_Hassan_Ave_North_PE_Fiber_TASC_O |  | AMS-269-R | Outdoor |  | 35.9348 | 31.9167 | South Amman | Roof Top |  |  | Tower T 16 | 25 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219429 | UTC |  | 47733550 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3636 | 3636-Mugabalein_Jwaied_Ave_PB_Fiber_TASC |  | AME-717-R | Indoor | 1660 | 35.8991 | 31.9046 | South Amman | Roof Top | warathat shaeban alashqir | 079-6991821 | Pole P9 X 2 + P6 X 2 | 18 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219430 | UTC |  | 47733553 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
3637 | 3637-Haj_Hassan_Manar_Sch_PE_Fiber_TASC_O |  | AMS-112-R | Outdoor |  | 35.936 | 31.9129 | South Amman | Roof Top | khilfat muhamad harb alhadiyd | 0799116728/0790284545/0795980192 | Tower T 16 | 24 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1217280 | UTC |  | 47733554 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved |  | Approved | set azimuth od sector A to 60 , set azimuth od sector C to 185 ,ad move the antenna to the very left DP of the frame, set azimuth of sector D to 300 and swap the locations between 10porths and new AQQL |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3638 | 3638-Jabal_Hadeed_CRL_PE_Fiber_TASC_O |  | AMS-124-R | Outdoor |  | 35.9455 | 31.9083 | South Amman | Roof Top | khalid falh eayid aldabubi | 0795915911/0797784575/0976404090 | Pole P9 + P6 | 18 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1216981 | UTC |  | 47733555 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | for 5G solution . set azimuth of sector B to 180 and add new DP at leg C , set azimuth of sector C to 300 at leg D |  | Approved |  |  | Approved | The civil requirements in civil sheet are not matched with BTS one // approved after the update 26-06 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
3639 | 3639-Mugabalein_South_Amman_PSD_PF_TASC_O |  | AME-777-R | Outdoor |  | 35.9198 | 31.9054 | South Amman | Roof Top | mudiriat al amn aleamm |  | Pole Mast 9m#2+Mast 6m#1 | 14 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1216982 | UTC |  | 47733556 | Done |  |  |  | 5G | [5 empty] | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3217 | 3217-Radwan_Sch_PD_Fiber_Relo_O |  | AMW-653-R | Outdoor | 1582 | 35.8418 | 31.9993 | West Amman | Roof Top | ahmad eabdallah mafdi kharisat | 06-5336974 079-5007734/079-5901667 | Pole 9 * 2 | 27 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1235945 | Al-Lewan |  | 48358869 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved |  | Approved | set azimuth of sector B to 260 and keep the rest as mentioned |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-03 | Yes | W31 |  | 880 |  |  | Approved
3643 | 3643-Mugabalein_Ind_PC_EBand_TASC |  | AME-86-R | Indoor | 275 | 35.9044 | 31.9118 | South Amman | Roof Top | saedi hasan saeid altamymi | 06/5667685 | Pole P6 X4 + P4 X1 | 11 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1216983 | UTC |  | 47733560 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Needs to modify the Azimuth of the sectors will provide you with the update soon |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
3644 | 3644-Haj_Hassan_Ave_CTR_PE_Fiber_TASC_O |  | AME-929-R | Outdoor |  | 35.9285 | 31.9119 | South Amman | Roof Top | iibrahim ahmad eali shnywr | 0795402881/07891780051/0785353842 | Pole P9#2 | 21 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219432 | UTC |  | 47733562 | Done |  |  |  | 5G | [5 empty] | Approved | The site consists of 4 sectors, not 3 sectors ///the site as shown on sheet RF Sector D (two antennas2G/3G)NOT(only one antenna(2g) |  | Approved | solution suggested in conclusion is different from what is suggested beside each picture, and the measured azimuth in RF sheet is wrong and different from the suggested solution |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
3645 | 3645-Mugabalein_Mansour_Sch_PE_GPON_TASC_O |  | AMS-134-R | Outdoor |  | 35.895 | 31.8997 | South Amman | Roof Top | sharikat al ahliat lilaistithmar | 06/5561204 0777566420/0790262814 | Tower T 16 | 24 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1217281 | UTC |  | 47733564 | Done |  |  |  | 5G | [5 empty] | Approved | The PICs in the sectors(A&B) are similar//according to the power study that was sent from Nokia, needs to be changed for the rectifier. |  | Approved | solution suggested in conclusion is different from what is suggested beside each picture, and the measured azimuth in RF sheet is wrong and different from the suggested solution...... set azimuth of sector A to 5, and B to 175 and C to 265 |  | Approved | Update the azimuth values with the provided one from ourside |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-05-24 | Yes | W21 |  | 951 |  |  | Approved |  |  |  |  | Downloaded
3646 | 3646-Mugabalein_Huffath_Sch_PE_GPON_TASC_O |  | AMS-143-R | Outdoor |  | 35.9034 | 31.8985 | South Amman | Roof Top | muhanad iibrahim eabd alfattah aleasy | 0791431773/0788104448/0796686642 | Pole P9#2 | 21 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219433 | UTC |  | 47733565 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3648 | 3648-Souq_Mugabalein_4_PE_TASC_O |  | AMS-175-R | Outdoor |  | 35.9151 | 31.9066 | South Amman | Roof Top | muhamad nawaf hasan almasaeidih | 0795504467/0799056304 | Pole P9X2+P6 | 18 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1217282 | UTC |  | 47733567 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | set azimuth of sector A to 30 , and sector B to 100 and sector C to 280 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3649 | 3649-UL_Mugabalein_Oqab_CRL_PF_TASC_O |  | AMS-256-R | Outdoor |  | 35.9119 | 31.9114 | South Amman | Roof Top |  |  | Tower T 12 | 24 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219434 | TAWSEAA |  | 47734295 | Done |  |  |  | 5G | [5 empty] | Approved | Sectors as sent from the planning(A/C), please adhere to this on all sheet///We don't need to Concert Foundation as on (remark /BTS sheet) |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3242 | 3242-City_Mall_PD |  | AMW-545-R-CO | Indoor |  | 35.8372 | 31.9802 | West Amman | Roof Top | sharikat alkhayr lilaistithmarat aleaqariat | 06/5560893 | Pole 9 | 33 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221064 | Al-Lewan |  | 48095341 | Done |  |  |  | 5G | [5 empty] | Approved | (SA&SB) are same pictures |  | Approved | set azimuth of secto A to 40 at leg 1-2 , set azimuth of sector B to 165 at leg 2-3, set azimuth of sector c to 300 at leg3-1 |  | Approved | Please to update the new provided Azimuth for all sectors not only 4G |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-03 | Yes | W27 |  | 911 |  |  | Approved
3502 | 3502-Wadi_Abdoun_PD_TASC |  | AME-157-R | Indoor | 316 | 35.9017 | 31.9519 | West Amman | Roof Top | mahmud yusif abu khazant | 079-6220856 | Tower T 12 | 25 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216968 | UTC |  | 47733503 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved |  |  |  |  | Downloaded
3503 | 3503-Aytam_Bldg_PF_TASC_O |  | AMW-99-R | Outdoor |  | 35.8808 | 31.9573 | West Amman | Roof Top | muasasat tanmiat amwal alaytam | 06/5934310 | Pole P6X2 | 20 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216969 | UTC |  | 47733505 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | set azimuths to 0/100/260 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved |  |  |  |  | Downloaded
3506 | 3506-Abdoun_Bridge_PE_GPON |  | AMW-778-R | Indoor | 1709 | 35.8927 | 31.9531 | West Amman | Roof Top | suead nasri jurj almahashi | 06-5930518 078-8888809/078-8739999 | Pole P9 X2 | 18 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1217274 | UTC |  | 47733507 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-30 | Yes | W31 |  | 884 |  |  | Approved |  |  |  |  | Downloaded
3507 | 3507-Ammoun_Hotel_PD_Fiber_TASC |  | AMW-78-R | Indoor | 379 | 35.8842 | 31.9587 | West Amman | Roof Top | mnirt muhamad eali zakariaaan tahabusm | 06/5931941 079/5678869 | Pole P6 X5 + P9 X 1 | 21 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216970 | UTC |  | 47733509 | Done |  |  |  | 5G | [5 empty] | Approved | it must be modified on all page(need DP or free dp/power solution)///The tower information must be pole not wall mount //all information on the remark (BTS SHEET)is wrong |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved |  |  |  |  | Downloaded
3250 | 3250-Howara_Rest_PC_Fiber_Zain_TASC |  | AMW-757-R | Indoor | 1710 | 35.8303 | 32.0028 | West Amman | Roof Top | ewny trky salim mhmd | 079-5576911 | Tower T 12 | 19 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221970 | Al-Lewan |  | 48095342 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-22 | Yes | W25 |  | 922 |  |  | Approved
3517 | 3517-Abdoun_CRL_PF_TASC |  | AMW-16-R | Indoor | 104 | 35.8901 | 31.9465 | West Amman | Roof Top | ghazwat muhiu aldiyn khayru alsaeudi | 06/5934225 | Pole P9 | 16 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216972 | UTC |  | 47733517 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved |  | Approved | set azimuth to 10 / 120/280(mast A) |  | Approved | Please Add pictures of electrical tilt device used/ readings per sector |  | Approved | already approved 06/06/2023 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-20 | Yes | W34 |  | 863 |  |  | Approved |  |  |  |  | Downloaded
3254 | 3254-Khalda_Bridge_PD_GPON_TASC_O |  | AMW-1054-R | Outdoor |  | 35.8308 | 31.9971 | West Amman | Roof Top | abd alsalam abu dalhoum | 0796092122/0795819803 | Pole P9 x 3 | 27 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221065 | SMART |  | 47734529 | Done |  |  |  | 5G | [5 empty] | Approved | Please add(we will swap RRUs on the IBS sectors) |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-19 | Yes | W25 |  | 925 |  |  | Approved
3524 | 3524-FreeZone_Century_PF_FiberNode_O |  | AMW-1022-R | Outdoor |  | 35.8862 | 31.9597 | West Amman | Roof Top | alsharikat al urduniyat liltaelim alfundaqii walsiyahi | 0797333373 - | Pole 9 | 24 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216974 | AL-DAR |  | 48358850 | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | the provided azimuth not updated |  | Approved | The data provided in civil sheet and 5G solution is not matched with other sheets such as BTS. please re-check and provide one accurate data and requirements. | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-20 | Yes | W34 |  | 863 |  |  | Approved |  |  |  |  | Downloaded
3255 | 3255-Khalda_Bridge_Tche_Tche_PD_GPON_TASC_O |  | AMW-1056-R | Outdoor |  | 35.8395 | 31.9962 | West Amman | Roof Top | smir fuhayd iibrahim jarisat | 797976666/0777772888/0797607179/0777900850 | Pole P9X2+P6 | 32 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221066 | SMART |  | 47734533 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved |  | Approved |  |  | Approved |  |  | Approved | match the civil sheet table with the BTS | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-03 | Yes | W31 |  | 880 |  |  | Approved
3529 | 3529-Heena_CTR_PC_Fiber_TASC |  | AMW-373-R | Indoor | 415 | 35.8972 | 31.9452 | West Amman | Roof Top | nawaf ahmad iislam hayana | 06/5932099 079/5091258 | Pole P6 X 2 + P9 X 1 | 17 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1219425 | TAWSEAA |  | 47734277 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Coverage View Photo with bad Quality |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved
3552 | 3552-4th_CRL_PD_TASC |  | AME-152-R | Indoor | 102 | 35.8936 | 31.9563 | West Amman | Roof Top | muhamad zaki hasan jabarat |  | Pole P6 X5 | 15 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216975 | UTC |  | 47733521 | Done |  |  |  | 5G | [5 empty] | Approved | Already Swapped |  | Approved | consider ACD instead of ABC |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-20 | Yes | W34 |  | 863 |  |  | Approved |  |  |  |  | Downloaded
3553 | 3553-Muhtaseb_CPLX_Abdoun_PD_GPON_TASC |  | AMW-735-R | Indoor | 1649 | 35.8839 | 31.9531 | West Amman | Roof Top | eisaa iilia amin amsyh | 079-5934924 | Tower T 18 | 17 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216976 | UTC |  | 47733522 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | The Site has (A,B, and C) sectors not (B,C, & D) needs to update the data filling |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-04 | Yes | W27 |  | 910 |  |  | Approved |  |  |  |  | Downloaded
3257 | 3257-Asriyya_Sch_Front_PE_GPON_TASC_O |  | AMW-978-R | Outdoor |  | 35.8389 | 32.0017 | West Amman | Roof Top | rafiq muhamad khadir abu salman | 0787221112/0785389905 | Tower T 16 | 32 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1219422 | Al-Lewan |  | 48095343 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | The photos of RF tab with bad quality |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-06 | Yes | W27 |  | 908 |  |  | Approved
3509 | 3509-Prime_Ministry_PF_Zain_O |  | AMW-633-R | Outdoor |  | 35.8962 | 31.9586 | West Amman | Roof Top | riasat alwazara |  | Pole 6 | 6 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216971 | UTC |  | 47733511 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Will Updated you with the new azimuth values soon |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-30 | Yes | W31 |  | 884 |  |  | Approved |  |  |  |  | Downloaded
3566 | 3566-UL_Kabarity_PB_Fiber_TASC |  | AMW-52-R | Indoor | 218 | 35.8894 | 31.9549 | West Amman | Roof Top | yasir faysal madhkur alkibariti | 079/5530710 | Pole P6 X 1 + P5 X 1 + P4 X 1 | 20 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1219426 | TAWSEAA |  | 47734279 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Need to modify the azimuth will provide it soon also to update the site location |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-05-31 | Yes | W22 |  | 944 |  |  | Approved
101 | 101-Sweifieh_Olympia_PE_GPON_TASC |  | AMW-719-R | Indoor | 1611 | 35.875 | 31.9498 | South Amman | Roof Top | faridat yaequb salim aldik | 06-5929747 079-5521604/079-6058577 | Tower T 16 | 24 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216955 | R&D |  | 47759338 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved
106 | 106-Sweifieh_2_PA_Fiber_TASC |  | AMW-481-R | Indoor | 481 | 35.8757 | 31.9551 | South Amman | Roof Top | ghazi mahmud muhamad alzghlwl | 06-5932804/06-4780860 079-5535614/079-5529424 | Tower T 18 + P9 X 1 +P6 X 5 | 21 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216959 | R&D |  | 47759343 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | install 5G antenna at the top heights for sectors A |  | Approved |  |  | Approved | The site delivered to me on Ndpd 14-06-2023 & 09-07-2023 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved
114 | 114-Avenue_Mall_PE_EBand_EFIBS_Manage |  | AMW-588-R | Indoor | 1555 | 35.8692 | 31.9571 | South Amman | Roof Top | khalil muhamad iibrahim qutus | 65833197 | Pole P6 X4 + P9 X 1 + Wall Mount 1m | IBS | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216962 | R&D |  | 47759350 | Done |  |  |  | 5G |  | IBS-E |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved
102 | 102-Mango_Sweifieh_PD_Fiber_TASC |  | AMW-331-R | Indoor | 454 | 35.8611 | 31.956 | South Amman | Roof Top | sayibat jaefar saeid tahqakhah | 077/318382 | Pole P9X2+P6X2+Wall Mounting 3m | 24 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216957 | R&D |  | 47759339 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | re-check the type of existing antenna at sectorA Mast2 in civil sheet, since it's not matched with BTS sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved
103 | 103-Geneva_Hotel_PE_Fiber_BIBS_O |  | AMW-1072-R | Outdoor |  | 35.8567 | 31.9636 | South Amman | Roof Top | Genval Hotel |  | Pole 6 | 6 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1219398 | R&D |  | 47759340 | Done |  |  |  | 5G |  | IBS-B |  |  |  | Approved | (site preparation sheet )we will swaps to 10 ports antenna not 6 ports |  | Approved |  |  | Approved | The photos of RF tab with bad quality |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-06 | Yes | W23 |  | 938 |  |  | Approved
105 | 105-Wakalat_St_PE_Fiber_TASC_O |  | AMW-575-R | Outdoor |  | 35.8605 | 31.9582 | South Amman | Roof Top | eabd alsalam muhamad asead eabd alsalam aljabali | 079-5506579 | Pole P9+P6X2+Wall Mounting 3m | 21 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216958 | R&D |  | 47759342 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-06 | Yes | W23 |  | 938 |  |  | Approved
109 | 109-American_Sch_PE_GPON |  | AMW-9-R | Indoor | 253 | 35.8621 | 31.9522 | South Amman | Roof Top | nabil nasir aldiyn abu znad |  | Tower T 12 | 28 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216960 | R&D |  | 47759346 | Done |  |  |  | 5G | [5 empty] | Approved | Already Approved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-26 | Yes | W30 |  | 888 |  |  | Approved
113 | 113-Hamra_St_PE_TASC_O |  | AMW-570-R | Outdoor |  | 35.8663 | 31.9562 | South Amman | Roof Top | muhamad eumar sadqi hilmi aladhm |  | Pole P6X2+P9 | 13 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216961 | R&D |  | 47759349 | Done |  |  |  | 5G | [5 empty] | Approved | please we need to add ladder 1m//modify comment (dismantle RRU(4G))to be (dismantle RRUs(2g/3g/4g) dismantle all RRUs //Determine that we needs two PDU(100A) and reuse existing PDU(100 A) |  | Approved |  |  | Approved |  |  | Approved | Match the antenna dimension with the provided table in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-06 | Yes | W23 |  | 938 |  |  | Approved
117 | 117-Sweifieh_3_PC_Fiber_TASC |  | AMW-556-R | Indoor | 1528 | 35.8658 | 31.9577 | South Amman | Roof Top | ahmad salih mahmud alqrywti | 079/6380312 | Pole P6 X 2 + P9 X 2 | 20 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216963 | R&D |  | 47759351 | Done |  |  |  | 5G | [5 empty] | Approved | please modify azimuth to be 345 not 340 |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-10 | Yes | W23 |  | 934 |  |  | Approved
131 | 131-UL_Skatting_Palace_PE_GPON_TASC |  | AMW-26-R | Indoor | 216 | 35.8668 | 31.9509 | South Amman | Roof Top | sahil kazim salim ahmd | 06/5528042 - 06/5581008 | Pole P6X4 | 14 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216964 | R&D |  | 47759357 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Correct the Mast number & correct the required 5G sectors in each mast in civil sheet to be cleared and matched with all provided data and sheets | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-11 | Yes | W28 |  | 903 |  |  | Approved
139 | 139-Amman_Family_Protection_Back_PE_GPON_AIBS_O |  | AMS-184-R | Outdoor |  | 35.8526 | 31.952 | South Amman | Roof Top | alghabia lilasikan walmujamaeat altijariat |  | Pole 9 | IBS | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1219399 | R&D |  | 47759358 | Done |  |  |  | 5G |  | IBS-A |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved
141 | 141-Firas_CPLX_PC_Fiber_TASC |  | AMW-36-R | Indoor | 247 | 35.8719 | 31.9512 | South Amman | Roof Top | tamari muhamad eabd alrahmin euql | 06/5923430 079/5592394/079-7611110 | Pole P9 X 2 + P6 X 1+ Wall mount Dp(3m) | 18 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1221960 | Al-Lewan |  | 47759332 | Done |  |  |  | 5G | [5 empty] | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved | new pole needed | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved |  |  |  |  | Downloaded
3511 | 3511-Enviroment_Police_Abdoun_PE_GPON_TASC_O |  | AMW-932-R | Outdoor |  | 35.8944 | 31.9415 | West Amman | Roof Top | talal muhamad musaa asmaeyl | 0777630040/0777497754 | Pole P9#2 | 18 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1219423 | UTC |  | 47733513 | Done |  |  |  | 5G | [5 empty] | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
155 | 155-UL_Sweifieh_Paris_St_PE_GPON_TASC_O |  | AMS-15-R | Outdoor |  | 35.8594 | 31.9568 | South Amman | Roof Top | amal muhamad mtr khdr | 0796278564/0795667403 | Pole P6*2 | 17 | Part of 134 | Phase-1 | Batch_3 | Cluster-1 |  | Traditional | SMP-WO-1216967 | R&D |  | 47759361 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Will check the azimuth values and update you accordingly |  | Approved | already approved 8-06-2023 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-06 | Yes | W23 |  | 938 |  |  | Approved
5906 | 5906-Abdoun_Mall_PF_BIBS_Manage |  | AMW-6-R | Indoor | 1525 | 35.8805 | 31.9413 | South Amman | Roof Top | sharikat al aswaq alealamiat almutatawirat lltjart | 06-5527946 | Pole wall mount pole 6m #2+wall mount dp 1m#1 | 9 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221974 | UTC |  | 47733588 | Done |  |  |  | 5G |  | IBS-B |  |  |  | Approved |  |  | Approved | No Comments |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3519 | 3519-Marwan_Khair_PE_TASC |  | AMW-820-R | Indoor | 1726 | 35.878 | 31.9614 | West Amman | Roof Top | rbye eabd almajid eubdallah aleashy | 079-7488619/079-5095577 | Pole P9*2+P6*1+WallMount6m*1 | 39 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216973 | UTC |  | 47733519 | Done |  |  |  | 5G | [5 empty] | Approved | Already Swapped |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-15 | Yes | W28 |  | 899 |  |  | Approved |  |  |  |  | Downloaded
5936 | 5936-Second_Cup_Abdoun_PE_GPON_TASC_O |  | AMW-776-R | Outdoor |  | 35.8778 | 31.9467 | South Amman | Roof Top | amjad musaa nakhu salih aslanik | 079-6208208 | Pole P9#2 | 25 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221980 | UTC |  | 47733608 | Done |  |  |  | 5G | [5 empty] | Approved | Check uploaded sheet |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3528 | 3528-Abdoun_Bridge_CRL_PE_GPON_TASC_O |  | AMW-1058-R | Outdoor |  | 35.8931 | 31.9489 | West Amman | Roof Top | wael briwish | 0795115255/0799696244 | Pole P6#1 + P9#2 | 27 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1217275 | UTC |  | 47733520 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Coverage View Of Sector B not Clear |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-20 | Yes | W34 |  | 863 |  |  | Approved |  |  |  |  | Downloaded
5909 | 5909-Deir_Ghbar_3_PE_Fiber_TASC |  | AMS-283-R | Indoor | 1771 | 35.8639 | 31.9409 | South Amman | Roof Top | fatimat muhamad jylany bwab | 06-5864806/06-5856812/06-5817383 779556608 | Tower T 20 | 27 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221975 | UTC |  | 47733589 | Done |  |  |  | 5G | [5 empty] | Approved | Need 1*DP for 5G SEC A INSIDE TOWER BODY (Need to shift existing bracing to install the new DP at same azimuth for SEC A 90 |  | Approved | No Comments |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-09 | Yes | W28 |  | 905 |  |  | Approved |  |  |  |  | Downloaded
5911 | 5911-Deir_Ghbar_2_PE_GPON_TASC_O |  | AMW-943-R | Outdoor |  | 35.8662 | 31.9428 | South Amman | Roof Top | zayd mutlaq eabd aljalil alsharayeh | 0796826154/0795522167 | Pole P9 x 3 | 18 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1216985 | UTC |  | 47733590 | Done |  |  |  | 5G | [5 empty] | Approved | USE existing 2*CB 125A and 2*CB 64A for 2*FPFH & 1*CB 32A for ACOC |  | Approved | No Comments |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-09 | Yes | W28 |  | 905 |  |  | Approved |  |  |  |  | Downloaded
5930 | 5930-BlueFig_PE_TASC |  | AMW-380-R | Indoor | 414 | 35.8849 | 31.9422 | South Amman | Roof Top | shakir muhamad kayid alriyalat | 079-5361060 | Tower T 12 | 21 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1219444 | UTC |  | 47733606 | Done |  |  |  | 5G | [5 empty] | Approved | Check uploaded sheet |  | Approved | If Civil load approved |  | Approved |  |  | Approved | Use the free wall mount, and or install a new wall mount to carry out 2 AQQL on Mast 1 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-17 | Yes | W29 |  | 897 |  |  | Approved |  |  |  |  | Downloaded
5954 | 5954-American_Embassy_Traffic_PC_Fiber_TASC |  | AMW-44-R | Indoor | 14 | 35.8814 | 31.948 | South Amman | Roof Top | saed eumar eabd alefwalealwl | 079/5524482 | Tower T 16 | 32 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221984 | UTC |  | 47733617 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-10 | Yes | W28 |  | 904 |  |  | Approved |  |  |  |  | Downloaded
5969 | 5969-Owaileh_PE_TASC_O |  | AME-532-R | Outdoor |  | 35.8466 | 31.9247 | South Amman | Roof Top | eisaa ealia iibrahim alnaeimi | 077786896/079-7791212 | Pole P6+P9 | 15 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1219450 | UTC |  | 47733623 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-10 | Yes | W28 |  | 904 |  |  | Approved |  |  |  |  | Downloaded
5970 | 5970-Youbil_PB_Fiber_TASC |  | AMW-11-R | Indoor | 325 | 35.8964 | 31.9395 | South Amman | Roof Top | muhamad mustafaa hamdan alnajar | 06/5823926 | Tower T 12 | 20 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1216994 | UTC |  | 47733624 | Done |  |  |  | 5G | [5 empty] | Approved | Use existing 2*125 A and 2*63A for FPFH and 1*32A CB for ACOC // You need to arrange with site owner before come to the site |  | Approved | No Comments |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-16 | Yes | W29 |  | 898 |  |  | Approved |  |  |  |  | Downloaded
5924 | 5924-Taj_Mall_3_PF_FiberNode_O |  | AMW-691-R | Outdoor |  | 35.8873 | 31.9408 | South Amman | Roof Top | Taj Mall 4 |  | Pole 9 | 28 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1216988 | UTC |  | 47733596 | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved | No Comments |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-17 | Yes | W29 |  | 897 |  |  | Approved |  |  |  |  | Downloaded
5922 | 5922-American_Embassy_PD_Fiber_TASC |  | AMW-20-R | Indoor | 133 | 35.8788 | 31.9434 | South Amman | Roof Top | ahmad eabd alrazq eabd alrahmn khalyfat | 06/5501087 | Pole P6 X 4 + P9 X 1 | 21 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221977 | UTC |  | 47733595 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
5925 | 5925-Duhair_North_PF_TASC_O |  | AMS-42-R | Outdoor |  | 35.8545 | 31.9286 | South Amman | Roof Top | muhamad eabd alkarim mahmud haja ealy | 0777490419/0791366460 | Pole P9 + P6 | 17 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221978 | UTC |  | 47733599 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | No Comments |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
5928 | 5928-Qaser_Snober_PF_EBand_TASC_O |  | AMW-831-R | Outdoor |  | 35.8606 | 31.9298 | South Amman | Roof Top | dunya fuad dawud hnbly | 079-9203127/078-5900902 | Tower T 12 | 13 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221979 | UTC |  | 47733603 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3555 | 3555-Orthodoxy_Club_PE_GPON_Manage_O |  | AMW-784-R | Outdoor |  | 35.8961 | 31.9479 | West Amman | Roof Top | Orthodoxy club |  | Pole P9 + P6 | 16 | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1217276 | UTC |  | 47733525 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | The photos of RF tab with bad quality |  | Approved | The provided table in civil sheet/ location for required 10port and 5G antennas is not correct in comparison with BTS sheet. | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved |  |  |  |  | Downloaded
5948 | 5948-Sweifieh_American_Sch_Back_PE_GPON_TASC_O |  | AMS-241-R | Outdoor |  | 35.8612 | 31.9486 | South Amman | Roof Top |  |  | Pole P9#2 | 21 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1216991 | R&D |  | 47759365 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Needs to modify the Azimuth of the sectors will provide you with the update soon |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-14 | Yes | W24 |  | 930 |  |  | Approved
5953 | 5953-Rujm_Nawabelseh_PE_TASC_O |  | AMW-43-R | Outdoor |  | 35.8618 | 31.9314 | South Amman | Roof Top | ziad ahmad kamil almaghribi | 06-573152 079-9773152 | Pole P9 + P6 | 6 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221983 | UTC |  | 47733616 | Done |  |  |  | 5G | [5 empty] | Approved | There is a fifth sector E(2g&3g)that nothing was mentioned about/there are 2 solution about space(ACOC)we will take (dismantle TMC &RFC cabinet) |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
5959 | 5959-Arab_Bank_Airport_Rd_PF_TASC |  | AMW-724-R | Indoor | 1653 | 35.8551 | 31.9318 | South Amman | Roof Top | musaa saeid eiad alnaeimat | 06-571362 0777-500219 | Pole P9 + P6 | 11 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221985 | UTC |  | 47733618 | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
5963 | 5963-Osra_Rest_PF_TASC_O |  | AMS-216-R | Outdoor |  | 35.8833 | 31.9496 | South Amman | Roof Top | mhmd kamal trky mhmd | 795576911/0797019069 | Pole P9 x 3 | 25 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1216993 | UTC |  | 47733621 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | The photos of RF tab with bad quality |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3557 | 3557-4th_CRL_Etihad_CPLX_PF_DIBS_O |  | AMW-984-R | Outdoor |  | 35.8975 | 31.9544 | West Amman | Roof Top | aitihad almustasharin | 4612377- 0 | Pole 9 | IBS | Part of 134 | Phase-1 | Batch_2 | Cluster-35 |  | Traditional | SMP-WO-1216977 | UTC |  | 47733527 | Done |  |  |  | RAN Only |  | IBS-D |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | approved after reducing the load | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-20 | Yes | W34 |  | 863 |  |  | Approved |  |  |  |  | Downloaded
3613 | 3613-Dokanji_Mugabalein_PE_Fiber_O |  | AME-880-R | Outdoor |  | 35.8889 | 31.9027 | South Amman | Roof Top | musaa muhamad khamis alshanawy | 0786448061/0790301430 | Pole P9X4+Wall Mounting (3m)+Wall Mounting (4m) | 21 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1217277 | UTC |  | 47733540 | Done |  |  |  | 5G | [5 empty] | Approved | For new location of ACOC (CAB) need to make sure the bracing will not close the door of new CAB or not |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
3902 | 3902-Wadi_Seer_Ind_2_PF_TASC |  | AMW-112-R | Indoor | 314 | 35.848 | 31.9448 | South Amman | Roof Top | eisam ahmad muhamad hjyj | 06-5822341/06-5926599 079/5546125 | Pole P9#2 + P6#2 + P5#1 | 23 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221085 | TAWSEAA |  | 47734297 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Modify the needed DP in civil requirement sheet to 1.5m instead of 2m. | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-23 | Yes | W30 |  | 891 |  |  | Approved
3628 | 3628-Mugabalein_Huffath_North_PE_GPON_TASC_O |  | AMS-234-R | Outdoor |  | 35.907 | 31.9009 | South Amman | Roof Top |  |  | Tower T 16 | 28 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1217279 | UTC |  | 47733549 | Done |  |  |  | 5G | [5 empty] | Approved | Install Nokia Cabinet (ACOC) on tower base BACK TO BACK WITH EXISTING CABs |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-05-24 | Yes | W21 |  | 951 |  |  | Approved |  |  |  |  | Downloaded
3642 | 3642-South_CPLX_West_PE_GPON_TASC_O |  | AME-932-R | Outdoor |  | 35.9266 | 31.9163 | South Amman | Roof Top | muetazu mahmud eabdallah alnhway | 0795133885/0785133885 | Pole P9#2 | 18 | Part of 134 | Phase-1 | Batch_1 | Cluster-36 |  | Traditional | SMP-WO-1219431 | UTC |  | 47733559 | Done |  |  |  | 5G | [5 empty] | Approved | Need to make sure the length of existing DPs for existing 5G Huawei ANTs enough to reuse for Nokia 5G ANT |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | No Excel file | 5 | A | Approved | Approved | 2023-08-18 | Yes | W33 |  | 865 |  |  | Approved |  |  |  |  | Downloaded
3911 | 3911-UL_Wadi_Seer_Bus_St_PF_O |  | AMS-18-R | Outdoor |  | 35.8166 | 31.9468 | South Amman | Roof Top | badieat yunis eabd rbh abu dari |  | Pole P9 X 2 | 21 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221091 | TAWSEAA |  | 47734315 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-11 | Yes | W28 |  | 903 |  |  | Approved
3916 | 3916-Public_Works_Ministry_PE_EBand_TASC |  | AMW-124-R | Indoor | 389 | 35.8506 | 31.9523 | South Amman | Roof Top | iibrahim wakym dawud bashwty |  | Pole P6 X 4 + P9 X 1 | 18 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221094 | TAWSEAA |  | 47734326 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | wrong azimuth sector C/ approved |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-02 | Yes | W31 |  | 881 |  |  | Approved
3906 | 3906-Bayader_Ahli_Club_PF_TASC_O |  | AMW-860-R | Outdoor |  | 35.8492 | 31.9486 | South Amman | Roof Top | alnnadi al ahlii alriyadiu eamman wayumthiluhum saeid shqm | 06-5823126 079-6666248 | Tower T 12 | 12 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1219435 | UTC |  | 47733570 | Done |  |  |  | 5G | [5 empty] | Approved | Change RECTIFIER |  | Approved |  |  | Approved |  |  | Approved | already approved 08/06/2023 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved
3922 | 3922-UL_AbuAlSous_Cliff_PF_TASC_O |  | AMS-270-R | Outdoor |  | 35.8188 | 31.9414 | South Amman | Roof Top |  |  | Tower T 20 | 31 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221097 | TAWSEAA |  | 47734329 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved
3943 | 3943-Bayader_Hello_Jordan_PF_EBand_TASC_O |  | AMS-132-R | Outdoor |  | 35.8444 | 31.9455 | South Amman | Roof Top | samiruh eadnan fahim halawh | 06/5289400 079585000/0777998000/0797768242 | Pole P9*1+WallMounting6*1 | 24 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221972 | UTC |  | 47733581 | Done |  |  |  | 5G | [5 empty] | Approved | Site have 2 PDUs so need 1 PDU 100A and Connect ACOC on Plug 32A / No changes in PWR solution (PLEASE DO NOT SEND TSARS IF NOT MODIFIED) |  | Approved |  |  | Approved |  |  | Approved | check the availability to reduce the antenna's height on Mast A and avoid TASC rejection. | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-22 | Yes | W25 |  | 922 |  |  | Approved |  |  |  |  | Downloaded
3945 | 3945-Bayader_AbuAlSous_PE_GPON_TASC_O |  | AMS-158-R | Outdoor |  | 35.8248 | 31.9478 | South Amman | Roof Top | fuzi saeid eabd alrahim alslaj | 0795422127/0795280365/0796706090 | Pole P9#2 | 21 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221973 | UTC |  | 47733583 | Done |  |  |  | 5G | [5 empty] | Approved | Use free (2X 100A)(2X 63A) C.B for 2*FPFH // 1X 32A C.B ACOC |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-15 | Yes | W33 |  | 868 |  |  | Approved |  |  |  |  | Downloaded
3947 | 3947-Bayader_Ind_East_PE_Fiber_TASC_O |  | AMS-163-R | Outdoor |  | 35.839 | 31.9421 | South Amman | Roof Top | tariq alkurdi | 0796407878/0797560849 | Pole P9 + P6 | 15 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221103 | UTC |  | 47733584 | Done |  |  |  | 5G | [5 empty] | Approved | 1-Taken PICs just for ANTs & RRH sides, need full picture for all pole including the solutions (BTS Sheet) // 2-5G ANTs proposal spaces for SECs 3&4 not clear (FREE DPs) |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-11 | Yes | W28 |  | 903 |  |  | Approved |  |  |  |  | Downloaded
3907 | 3907-Bayader_TL_PE_O |  | AMS-14-R | Outdoor |  | 35.8306 | 31.9542 | South Amman | Roof Top | hind yasin eumar kawksh |  | Tower T 12 | 18 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221971 | UTC |  | 47733572 | Done |  |  |  | 5G | [5 empty] | Approved | No Need to take any swap for SD / For PWR solution use the existing 2*CBs (capacity for each one 100A labeled 2G&3G) and add new CB 100A also connect the indoor CAB to one from free CBs 32A |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-11 | Yes | W28 |  | 903 |  |  | Approved
3948 | 3948-Bayader_Qoblan_Bakery_PE_GPON_TASC_O |  | AMW-1080-R | Outdoor |  | 35.8408 | 31.9511 | South Amman | Roof Top |  |  | Tower T 16 | 21 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1221104 | UTC |  | 47733585 | Done |  |  |  | 5G | [5 empty] | Approved | 1-Change the comments to (Need to change the rectifier) for PWR solution in all sheets in the TSSR |  | Approved |  |  | Approved |  |  | Approved | if we may relocate the existing 2*MW 0.3 from Mast B to Mast A to reduce the load from Mast B | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-10 | Yes | W28 |  | 904 |  |  | Approved |  |  |  |  | Downloaded
3918 | 3918-Ole_Jordan_PF_BIBS_O |  | AMW-497-R | Outdoor |  | 35.8467 | 31.9408 | South Amman | Roof Top |  |  | Pole 9 | 20 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1219437 | UTC |  | 47733576 | Done |  |  |  | RAN Only |  | IBS-B |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | extra bracing needed // new DP's needed must be #3 (not clear on civil requirement sheet) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-09 | Yes | W28 |  | 905 |  |  | Approved |  |  |  |  | Downloaded
3942 | 3942-Wadi_Seer_16_St_PE_Fiber_TASC_O |  | AMS-114-R | Outdoor |  | 35.8233 | 31.9512 | South Amman | Roof Top | mansur eabd alrahmn muhamad abu basilat |  | Tower T 12 | 26 | Part of 134 | Phase-1 | Batch_5 | Cluster-39 |  | Traditional | SMP-WO-1219438 | TAWSEAA |  | 47734349 | Done |  |  |  | 5G | [5 empty] | Approved | Use the existing 4G CB 100A for FPFH / use the existing 3G CB 80A for AMIA /Need new 2X100A C.B for 2 FPFH |  | Approved | No excel file/Approved |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved
915 | 915-Music_Box_PC_GPON_TASC |  | AMW-390-R | Indoor | 441 | 35.8529 | 31.9654 | South Amman | Roof Top | nzar iismaeil mustafaa alqaryuti | 06-5825757 079/5526016/0795518666/0795511224 | Tower T 16 | 24 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221961 | UTC |  | 47733625 | Done |  |  |  | 5G | [5 empty] | Approved | Antenna type not correct , Please to check again per sector with more pictures |  | Approved |  |  | Approved | the site has 3 sectors on 3G, only sector A has data |  | Approved | no photos in the civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-02 | Yes | W31 |  | 881 |  |  | Approved
5919 | 5919-Deir_Ghbar_Traffic_PE_Fiber_TASC |  | AMW-18-R | Indoor | 15 | 35.8723 | 31.9471 | South Amman | Roof Top | alsharikat al urduniyat alsewdyt likhadamat altaeam | 079-5587344 | Pole P6X4 + P4.5 | 20 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221976 | UTC |  | 47733592 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | need to verify the azimuths, its different from zain data/Approved |  | Approved | Military Area |  | Approved | reduce the load from mast B to avoid TASC rejection | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
5947 | 5947-Deir_Ghbar_Shamsi_CRL_PF_TASC_O |  | AMS-126-R | Outdoor |  | 35.8684 | 31.9372 | South Amman | Roof Top | mahmud eabd alghaniu eabd allatif mashael | 06/5862933 0798183790/0798312557 | Pole P9*2+ WallMount6m*1 | 21 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221982 | UTC |  | 47733614 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Kindly have a seperate azimuth picture for each antenna serving its own technology (2G alone 3G,4G alone) |  | Approved | reduce the load from mast 1 by moving 1 (10 port antenna) to mast 2 to avoid TASC rejection | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
5938 | 5938-Airport_Rd_MGS_PE_TASC_O |  | AMW-824-R | Outdoor |  | 35.8604 | 31.9194 | South Amman | Roof Top | Manaseer | 06-5734070 | Pole P6X2 + P9 | 15 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221981 | UTC |  | 47733609 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Need to reduce one sector on MAST1 to 3m and/or new MAST | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
5968 | 5968-UL_Abdoun_Cozmo_PE_O |  | AMS-33-R | Outdoor |  | 35.8782 | 31.9486 | South Amman | Roof Top | sharikat qustandiun naql ayumathiluha qstandiun nql | 0795522329/0799991543 | Pole P9 + P6 | 30 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221987 | TAWSEAA |  | 47734351 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-15 | Yes | W24 |  | 929 |  |  | Approved
934 | 934-UL_Jandaweel_1_PE_GPON_TASC_Relo_O |  | AMW-1123-R | Outdoor |  | 35.8367 | 31.9659 | South Amman | Roof Top |  |  | Tower T 16 | 28 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1219407 | UTC |  | 47733627 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-05 | Yes | W27 |  | 909 |  |  | Approved
5962 | 5962-Abdel_Hameed_Sharaf_Sch_PE_GPON_CIBS_O |  | AMS-183-R | Outdoor |  | 35.8718 | 31.9432 | South Amman | Roof Top | alghabia lilasikan walmujamaeat altijariat |  | Pole 9 | 25 | Part of 134 | Phase-1 | Batch_4 | Cluster-59 |  | Traditional | SMP-WO-1221986 | UTC |  | 47733620 | Done |  |  |  | 5G |  | IBS-C |  |  |  | Approved |  |  | Approved | for 5G , set azimuth of sector C to 295, move the 10 ports antenna to the new DP and install the AAQ where the old antenna was installed . |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-13 | Yes | W28 |  | 901 |  |  | Approved |  |  |  |  | Downloaded
957 | 957-Kursy_CTR_PE_GPON_TASC_O |  | AMS-238-R | Outdoor |  | 35.8251 | 31.9638 | South Amman | Roof Top |  |  | Pole P9#2 | 21 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221046 | TAWSEAA |  | 47734375 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | for 5G solution ; for sector A, set the azimuth to 5 , and swap the locations between the 5G antenna and 6 ports antenna. , for sector B , set the azimuth to 75 ; for sector C , set the azimuth to 135 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-04 | Yes | W27 |  | 910 |  |  | Approved
961 | 961-UL_KHBP_Bldng_10_PF_O |  | AMW-1151-R | Outdoor |  | 35.8344 | 31.9727 | South Amman | Roof Top |  |  | Pole 9 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221048 | TAWSEAA |  | 47734383 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-11 | Yes | W24 |  | 933 |  |  | Approved
962 | 962-UL_KHBP_Bldng_19_PF_O |  | AMW-1152-R | Outdoor |  | 35.8333 | 31.9722 | South Amman | Roof Top |  |  | Pole 9 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221049 | TAWSEAA |  | 47734388 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | for 5G solution, set azimuth of sector A to 10, set azimuth of sector C to 170 and move the antenna to the right leg of the H frame. |  | Approved | will be reviewed when approval for taking photos is granted |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-12 | Yes | W24 |  | 932 |  |  | Approved
963 | 963-UL_KHBP_Bldng_7_PF_O |  | AMW-1153-R | Outdoor |  | 35.8351 | 31.9714 | South Amman | Roof Top |  |  | Pole 9 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221050 | TAWSEAA |  | 47734391 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Add extra bracing to mast 1 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-11 | Yes | W28 |  | 903 |  |  | Approved
902 | 902-U_Jandaweel_3_PE_GPON_TASC_O |  | AMW-661-R | Outdoor | 1594 | 35.8403 | 31.9648 | South Amman | Roof Top | ahmad muhamad tawfiq albarqawi | 077-6048114/077-9382827 | Pole P9#2 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1219400 | Al-Lewan |  | 48095336 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | for 5G solution, set azimuth of sector B to 125 instead of 105 |  | Approved | Comments solved o files found |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-02 | Yes | W31 |  | 881 |  |  | Approved
936 | 936-Jaber_Rawabi_PC_GPON_TASC_O |  | AMW-451-R | Outdoor | 471 | 35.8489 | 31.9713 | South Amman | Roof Top | eibdalrahmin hashim eabd alkarim abu nawar | 079/5543548 | Tower T 16 | 22 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221041 | UTC |  | 47733628 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | set sector B azimuth to 140 |  | Approved | Comments Solved \Sec C mech tilt photos are in very low quality |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-09 | Yes | W28 |  | 905 |  |  | Approved
901 | 901-Manaseer_HQ_PF_O |  | AMW-853-R | Outdoor |  | 35.844 | 31.9628 | South Amman | Roof Top | majmueat almanasiyr |  | Pole 9 | 9 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221033 | Al-Lewan |  | 47759330 | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Double check if the site needs Dp's for 5G or not, as the swap solution and antenna that will be dismantled not clear enough for me | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-17 | Yes | W29 |  | 897 |  |  | Approved
928 | 928-UL_Kursy_1_PE |  | AMW-1130-R | Indoor |  | 35.8279 | 31.9653 | South Amman | Roof Top | sayid eabd alwahhab salim alqutawnat washarkawh | 07777/46300 | Tower 12 | 21 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1219406 | R&D |  | 47759368 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | for 5G solution, wrong data are taken for sectors , azimuth of A is 0, azimuth of B is 120 , azimuth of C is 270 , |  | Approved |  |  | Approved | already approved 18/06/2023 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-13 | Yes | W28 |  | 901 |  |  | Approved
956 | 956-Qaisieh_Nbr_Hood_PF_TASC_O |  | AMS-162-R | Outdoor |  | 35.8136 | 31.9628 | South Amman | Roof Top | eawdat alqysy wayumthiluh muhamad eawdat muhamad alqysy | 0795533492/0790771512 | Pole P9 + P6 | 21 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221045 | Al-Lewan |  | 47759334 | Done |  |  |  | 5G | [5 empty] | Approved | need Civil works from Zain |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-10 | Yes | W28 |  | 904 |  |  | Approved |  |  |  |  | Downloaded
919 | 919-UL_Prince_Rashid_Ave_PE_TASC |  | AMW-782-R | Indoor | 1721 | 35.8494 | 31.9679 | South Amman | Roof Top | shahir eali fadil alnaeimat | 079-5951314 | Tower T 20 | 26 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221964 | Al-Lewan |  | 48095339 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | need to rename sectors to , ABD, 60/140/0 |  | Approved | Comments not solved \All cells uses RET (Check) |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-23 | Yes | W30 |  | 891 |  |  | Approved
958 | 958-Jandaweel_End_PE_GPON_TASC_O |  | AMW-1086-R | Outdoor |  | 35.8372 | 31.9582 | South Amman | Roof Top |  |  | Pole P9#2 | 9 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221047 | TAWSEAA |  | 47734380 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Sector C azimuth photo is the same for all technologies although the antenna is different |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-11 | Yes | W24 |  | 933 |  |  | Approved
921 | 921-Jandaweel_2_PE |  | AMW-370-R | Indoor | 488 | 35.8383 | 31.9602 | South Amman | Roof Top | majid rashid iibrahim aljuyusi | 06-5811508 | Pole P6X3 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221037 | TAWSEAA |  | 47734356 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | RET is used on sector C for 3G & 4G. |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved
925 | 925-Aswaq_AlSalam_PF_EBand_TASC_O |  | AMW-814-R | Outdoor |  | 35.833 | 31.9682 | South Amman | Roof Top | ramzi eabd alruhmin wayumthiluh yasir eabd alrahmin | 079-6670883 | Pole P9 + P6 | 21 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1219405 | R&D |  | 47759366 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | RCU label photo is uploaded instead of the antenna label for Sectors A & B for 2G |  | Approved | Please use new 10port antenna with dimension 1999mm x 349mm and modify the civil sheet based on that | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-13 | Yes | W33 |  | 870 |  |  | Approved
955 | 955-Prince_Rashid_Ave_CRL_PE_GPON_TASC_O |  | AMS-136-R | Outdoor |  | 35.8463 | 31.9685 | South Amman | Roof Top | nasir eumar iibrahim almubidiun |  | Pole P9#2 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1235942 | Al-Lewan |  | 48358875 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-02 | Yes | W31 |  | 881 |  |  | Approved
911 | 911-Zain_Top_PF_FiberNode |  | AMW-120-R | Indoor | 478 | 35.8447 | 31.9636 | South Amman | Roof Top | zain top WMX |  | Pole 9 | 20 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221036 | TAWSEAA |  | 48358854 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-02 | Yes | W31 |  | 881 |  |  | Approved
3212 | 3212-International_Sch_PF_Manage_O |  | AMW-626-R | Outdoor |  | 35.8241 | 31.9806 | West Amman | Roof Top | alakadyamiat alduwaliat | 06-5502055 0777-503072 | Pole Wall mount dp 3m #3, Wall mount pole #2(3m&6m) | 12 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1235944 | Al-Lewan |  | 48358865 | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | The same azimuth photo is used for different antennas |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-24 | Yes | W30 |  | 890 |  |  | Approved
3220 | 3220-Medical_City_Princess_Eman_PF_TASC_O |  | AMW-589-R | Outdoor |  | 35.8306 | 31.9794 | West Amman | Roof Top | alqiadat aleamat lilquwwat almusalahat alardinit |  | Pole 6 | 6 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221058 | Al-Lewan |  | 48358904 | Done |  |  |  | 5G | [5 empty] | Approved | Site have 2 PDUs so need 1 PDU 100A and Connect ACOC on Plug 32A |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-03 | Yes | W31 |  | 880 |  |  | Approved
3235 | 3235-Asriyya_Sch_Back_PE_GPON_TASC |  | AMW-731-R | Indoor | 1617 | 35.8503 | 31.9996 | West Amman | Roof Top | muhamad faris eabd alghani almusaa | 079-7000123/079-5522089 | Pole P6#2 + P9#1 | 24 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1235947 | Al-Lewan |  | 48358905 | Done |  |  |  | 5G | [5 empty] | Approved | The capacity of existing PDUs not clear /If Site have one PDU 100a so need 2 PDU 100A and Connect ACOC on Plug 32A /No Need to swap the existing ANTs SEC A-The swap should be just for RRUs (Please mention that in the TSSR) |  | Approved |  |  | Approved |  |  | Approved | Add tower height to civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-13 | Yes | W28 |  | 901 |  |  | Approved
3248 | 3248-Sands_Sch_Back_PE_GPON_O |  | AMW-946-R | Outdoor |  | 35.8452 | 32.0023 | West Amman | Roof Top | basam alramhy | 799511920 | Pole P6+P3 | 18 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1235948 | Al-Lewan |  | 48358883 | Done |  |  |  | 5G | [5 empty] | Approved | 1-Install new ACOC cabinet back to back old cabinets // 2- CAB have one PDU so need 2 PDUs 100A and Connect ACOC on Plug 32A |  | Approved |  |  | Approved | Coverage view photo need to be clear |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-26 | Yes | W30 |  | 888 |  |  | Approved
920 | 920-Kursy_Ave_Back_PF_O |  | AMW-733-R | Outdoor | 1703 | 35.8254 | 31.9679 | South Amman | Roof Top | eadil jamil tanus hadad | 079-5888187 | Pole P9 x 3 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221965 | Al-Lewan |  | 47759331 | Done |  |  |  | 5G | [5 empty] | Approved | Check the installation steps with Ahmad Aldabagh |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-02 | Yes | W31 |  | 881 |  |  | Approved
3218 | 3218-Midas_Khalda_PE_GPON_Manage_O |  | AMW-670-R | Outdoor |  | 35.8539 | 31.9969 | West Amman | Roof Top | eabdallah ahmad aleubdialilih aleasafa | 079-6771350/079-5112445/079-5663093 | Tower T 12 | 20 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1235946 | Al-Lewan |  | 48358879 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-09 | Yes | W32 |  | 874 |  |  | Approved
3202 | 3202-New_Khalda_PE_TASC |  | AMW-295-R | Indoor | 89 | 35.8426 | 31.9955 | West Amman | Roof Top | eali iibrahim muhamad hamaadat |  | Tower T 6 + P4 X 1 | 21 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1219411 | SMART |  | 47734471 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved
3203 | 3203-Dabouq_2_PB_Fiber_TASC |  | AMW-644-R | Indoor | 1567 | 35.8231 | 32.0008 | West Amman | Roof Top | eahad yaequb eabdalilah maedi | 06-5411242 077-9573538 | Tower T 16 | 12 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1219412 | SMART |  | 47734477 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-03 | Yes | W27 |  | 911 |  |  | Approved
3221 | 3221-Midas_Back_PD_GPON_Org_O |  | AMW-673-R | Outdoor |  | 35.8527 | 31.9908 | West Amman | Roof Top | eabd alruwuwf tawfiq alshaykh sharif saed aldyn | 079-5034133 | Pole P9*2+P6*1 | 18 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221967 | UTC |  | 47733498 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-19 | Yes | W25 |  | 925 |  |  | Approved
3222 | 3222-Dabouq_PB_Fiber_Zain_TASC |  | AMW-309-G | Indoor | 91 | 35.819 | 32.0003 | West Amman | Green Field | eabd alhafiz muhamad hamd shanaq | 06-411976 079-6612111 | Tower T 30 | 25 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1219415 | SMART |  | 47734483 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  | Laith | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-14 | Yes | W24 |  | 930 |  |  | Approved
3226 | 3226-Amman_Academy_Back_PD_Fiber_TASC |  | AMW-718-R | Indoor | 1608 | 35.834 | 32.0016 | West Amman | Roof Top | muhamad khayr ahmad khalid khlf | 0777-403335/079-5552398 | Pole P9 X 2 | 21 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1219417 | UTC |  | 47733501 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  | Laith | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-15 | Yes | W24 |  | 929 |  |  | Approved
3227 | 3227-King_Hussein_Msq_PE_GPON_TASC_Relo_O |  | AMW-1059-R | Outdoor |  | 35.8178 | 31.9902 | West Amman | Roof Top | muhamad dayf allah eabd alghanii aldawayakata | 0776506595/0795646615 | Pole P9 X 1 + P6 X 3 | 15 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221059 | Al-Lewan |  | 47759336 | Done |  |  |  | 5G | [5 empty] | Approved | Need 63CB or 2*32CBs for 5G FBFH |  | Approved |  | Laith | Approved |  |  | Approved | civil reqirments new not matched with the BTS sheet // civil table Mast C D 3 4 ??? // existing deport arms for all Masts and the free DP's updated and approved // only the tower for Zain's // update the tower details and remove the Masts Dismantle or reuse in civil table!!! update the tower details and the existing DP's and the free DP's// | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-22 | Yes | W25 |  | 922 |  |  | Approved |  |  |  |  | Downloaded
3228 | 3228-Khalda_Halls_PD_GPON_O |  | AMW-844-R | Outdoor |  | 35.8476 | 31.9942 | West Amman | Roof Top | fwzi abu jabir | 079-9915339/079-6663634 | Tower T 12 | 24 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1217267 | SMART |  | 47734496 | Done |  |  |  | 5G | [5 empty] | Approved | connect on the free 2*50CBs for 5G FBFH |  | Approved |  | Laith | Approved |  |  | Approved | reduce the load from Mast A to Mast B if TASC rejected the site | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-22 | Yes | W25 |  | 922 |  |  | Approved
3230 | 3230-Dokan_Dabouq_PE_GPON_TASC_O |  | AMW-854-R | Outdoor |  | 35.8217 | 31.9982 | West Amman | Roof Top | munaa shahir tahir aleatum | 079-9771952 | Pole Wall Mounting 9mX2 | 18 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1217268 | SMART |  | 47734502 | Done |  |  |  | 5G | [5 empty] | Approved | connect on the free 2*50CBs for 5G FBFH |  | Approved |  | Laith | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-15 | Yes | W24 |  | 929 |  |  | Approved
3238 | 3238-Dabouq_Sweileh_1_PE_O |  | AMW-783-R | Outdoor |  | 35.8331 | 32.0086 | West Amman | Roof Top | sharikat almarkaz aleararabii | 06-5810259 079-9322262 | Tower T 16 | 24 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1217271 | SMART |  | 47734516 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-07-04 | Yes | W27 |  | 910 |  |  | Approved
3239 | 3239-King_Hussein_Gardens_Events_PF_O |  | AMW-563-R | Outdoor |  | 35.8303 | 31.9857 | West Amman | Green Field | king hussein gardens events |  | Pole 9 | 7 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1219418 | Al-Lewan |  | 48095348 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-02 | Yes | W27 |  | 912 |  |  | Approved |  |  |  |  | Downloaded
3252 | 3252-Khalda_Pioneer_Sch_Back_PF_TASC_O |  | AMW-1034-R | Outdoor |  | 35.8364 | 31.9916 | West Amman | Roof Top | Belal hader | 0796660622/0797992999 | Pole P6X2 | 21 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1217273 | SMART |  | 47734525 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-06-20 | Yes | W25 |  | 924 |  |  | Approved
3223 | 3223-Khalda_Market_PD_GPON_O |  | AMW-846-R | Outdoor |  | 35.8474 | 31.9818 | West Amman | Roof Top | khamis yasin sulayman hubul | 079-5865555 | Pole P9 + P6 | 19 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1219416 | SMART |  | 47734486 | Done |  |  |  | 5G | [5 empty] | Approved | Add the layout to the TSSR |  | Approved |  |  | Approved |  |  | Approved | Conditionally approved after correcting the dimensions of 10ports antenna | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-07-11 | Yes | W28 |  | 903 |  |  | Approved
3225 | 3225-Dabouq_TL_PF_TASC_O |  | AMW-667-R | Outdoor | 6 | 35.8234 | 31.9927 | West Amman | Roof Top | mufid shahir eabd alrahim alhndi | 06-5412805 079-5315837 | Pole P6+P9 | 14 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1217266 | SMART |  | 47734493 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil sheet not matched with the BTS sheet Approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-06 | Yes | W27 |  | 908 |  |  | Approved
3237 | 3237-Khalda_East_PE_GPON_TASC_O |  | AMW-859-R | Outdoor |  | 35.833 | 31.9921 | West Amman | Roof Top | eabd alkarim yusif eabd alhalim kalbunat | 079-6502222/079-5355777 | Pole P9#2 | 15 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1217270 | SMART |  | 47734512 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-03 | Yes | W31 |  | 880 |  |  | Approved
3240 | 3240-Hamsharie_Msq_PE_GPON_TASC_O |  | AMW-790-R | Outdoor | 1733 | 35.8362 | 31.9885 | West Amman | Roof Top | eala eizat euthman mahmudan | 079-9766531 | Tower T 20 | 26 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1221968 | UTC |  | 47733502 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | We need to install 5G on A/B/C but in remarks you add sector D .... So please commit with A/B/C |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-06-19 | Yes | W25 |  | 925 |  |  | Approved |  |  |  |  | Downloaded
930 | 930-U_RACJ_PE_PF_EBand_O |  | AMS-56-R | Outdoor |  | 35.8492 | 31.963 | South Amman | Roof Top | RACJ_O |  | Pole 6 | 12 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221039 | TAWSEAA |  | 47734362 | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Mast 3 overloaded // new mast needed and/or reduce one sector to 3m // update civil requirement sheet // validate the antennas dimension especially the 10 ports. antennas dimension the 10 &8 ports still the same approved on new mast | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-07-09 | Yes | W28 |  | 905 |  |  | Approved
3244 | 3244-Salheen_Khalda_PE_GPON_O |  | AMW-873-R | Outdoor |  | 35.8517 | 31.9925 | West Amman | Roof Top | muhamad sulayman musaa alskr | 0795901901 / 0772345357 | Pole P6X2 | 18 | Part of 134 | Phase-1 | Batch_7 | Cluster-32 |  | Traditional | SMP-WO-1217272 | SMART |  | 47734521 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Reduce antennas height on Mast 1 6.7 since the mast only 6m // and the other 2 antennas to 3 meters to reduce the load on the mast Civil table antennas Hight approved. and recheck with planning. | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-06-22 | Yes | W25 |  | 922 |  |  | Approved
954 | 954-Northern_Rabahia_PE_TASC_O |  | AMW-981-R | Outdoor |  | 35.8147 | 31.9723 | South Amman | Roof Top | rasmiat khalf aleariq alfalah | 0772523658/0778892030/0772312068 | Tower T 16 | 22 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1219409 | TAWSEAA |  | 48358857 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | approved using the free Mast NOT UPDATED | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-07-05 | Yes | W27 |  | 909 |  |  | Approved
966 | 966-Prince_Rashid_Ave_2_PE_GPON_TASC_O |  | AMS-37-R | Outdoor |  | 35.8441 | 31.9724 | South Amman | Roof Top | muhamad taysir qasim alhaj muhamad qasm | 079-5794447 | Tower T 20 | 20 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221051 | Al-Lewan |  | 47759335 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | The solution does not match with the provided data and pictures, also the double check the 10ports antenna dimension. updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-11 | Yes | W28 |  | 903 |  |  | Approved |  |  |  |  | Downloaded
918 | 918-Abdullah_Ghosheh_MGS_Back_PE_GPON_TASC_O |  | AMS-246-R | Outdoor |  | 35.8522 | 31.9727 | South Amman | Roof Top |  |  | Pole P9#2 | 18 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1221962 | Al-Lewan |  | 48095338 | Done |  |  |  | 5G | [5 empty] | Approved | Need photo to show all CBs with good resolution |  | Approved |  |  | Approved |  |  | Approved | The civil work sheet does not match with BTS// double check the M.W dimensions and add them to the civil table// Conditionally approved noting that the previous comments not modified. and shall be corrected. Also, correct the 10 ports antenna dimensions. | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-05 | Yes | W27 |  | 909 |  |  | Approved
937 | 937-Shaab_St_PF_O |  | AMW-135-R | Outdoor |  | 35.8244 | 31.9746 | South Amman | Roof Top | dayirat almukhabarat aleamat |  | Pole Tripod 2m + Wall mounted Dp 3m | 9 | Part of 134 | Phase-1 | Batch_6 | Cluster-9 |  | Traditional | SMP-WO-1219408 | UTC |  | 47733629 | Done |  |  |  | 5G | [5 empty] | Approved | Change the PWR solution to (Need to add 3*pdu 100A and use 1*PDU 100 A for FPFH and reuse 1*plugs 32A for AMIA) |  | Approved |  |  | Approved |  |  | Approved | check if we can move one sector to MAST 3 from mast 1 or reduce the height of 2 Antennas to 6 meters instead of 9 meters on Mast 1 to reduce the load | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-08-02 | Yes | W31 |  | 881 |  |  | Approved
3827 | 3827-QAIA_Ext_PF_IBS_Zain |  | MAD-246-R | IBS |  | 35.997 | 31.7208 | Airport | IBS | [5 empty] | Phase-2 | Airport | Cluster-38 |  | Traditional | SMP-SMP-1308642 | TAWSEAA |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Conditionally approved after correcting the dimensions of 10ports antenna | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-15 | Yes | W46 |  | 776 |  |  | Approved
3821 | 3821-QAIA_South_Bldg_PF_Zain |  | MAD-215-R | IBS |  | 35.997 | 31.7208 | Airport | IBS | [5 empty] | Phase-2 | Airport | Cluster-38 |  | Traditional | SMP-SMP-1308641 | TAWSEAA |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | The civil table is missed ( please add the civil table ) | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-15 | Yes | W46 |  | 776 |  |  | Approved
3822 | 3822-QAIA_North_Bldg_PF_Zain |  | MAD-213-R | IBS |  | 35.997 | 31.7208 | Airport | IBS | [5 empty] | Phase-2 | Airport | Cluster-38 |  | Traditional | SMP-WO-1308639 | TAWSEAA |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | no need for cable tray as the TSSR | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-15 | Yes | W46 |  | 776 |  |  | Approved
3820 | 3820-QAIA_Main_Bldg_PF_IBS_Zain |  | MAD-214-R | IBS |  | 35.997 | 31.7208 | Airport | IBS | [5 empty] | Phase-2 | Airport | Cluster-38 |  | Traditional | SMP-SMP-1308638 | TAWSEAA |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved | Please avoid use the CBs which dedicated for TDD |  | Approved | make sure to install the 5G antenna infront of the steel fence, so the fence becomes behind the antenna |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-15 | Yes | W46 |  | 776 |  |  | Approved
1207 | 1207-UL-Rimal-Ave-Market-PE-Fiber-TASC-O |  | AQB-235-R | IBS |  | 35.0041 | 29.5564 | Aqaba | IBS | [5 empty] | Phase-2 | AQABA | Cluster-12 |  | Traditional | SMP-WO-1308017 | TAWSEAA |  |  | Done |  |  |  | 5G | [5 empty] | Approved | need to check SE , IBS to check the 2G/3G/4G needed - Contact Ahmad Dabagh |  | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-19 | Yes | W47 |  | 772 |  |  | Approved
1213 | 1213-UL-Shamieh-Aqaba-PE-TASC-O |  | AQB-169-G | IBS |  | 35.0666 | 29.5925 | Aqaba | IBS | [5 empty] | Phase-2 | AQABA | Cluster-12 |  | Traditional | SMP-WO-1308021 | TAWSEAA |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-19 | Yes | W47 |  | 772 |  |  | Approved
1236 | 1236-UL-Charity-Assoc-PA-Fiber-TASC |  | AQB-142-R | Outdoor |  | 35.0079 | 29.5469 | Aqaba | Green Field | [5 empty] | Phase-2 | AQABA | Cluster-12 |  | Traditional | SMP-WO-1308019 | TAWSEAA |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | No excel sheet | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 5 | A | Approved | Approved | 2023-11-19 | Yes | W47 |  | 772 |  |  | Approved
1244 | 1244-UL-Aqaba-6th-Ave-North-PE-Fiber-TASC-O |  | AQB-208-R | IBS |  | 35.0117 | 29.5537 | Aqaba | IBS | [5 empty] | Phase-2 | AQABA | Cluster-12 |  | Traditional | SMP-WO-1308020 | TAWSEAA |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved | check the data to be only for GF tower not RT on the TSSR xls// use the free DP instead of the new // civil table for the 8 port new installation or reuse!! | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-19 | Yes | W47 |  | 772 |  |  | Approved
1295 | 1295-UL-Shamieh-Aqaba-PE-TASC-Relo-O |  | AQB-256-R | IBS |  | 35.0661 | 29.5881 | Aqaba | IBS | [5 empty] | Phase-2 | AQABA | Cluster-12 |  | Traditional | SMP-WO-1308022 | TAWSEAA |  |  | Done |  |  |  | 5G | [5 empty] | Approved | need DC Power study , 4 FPFH |  | Approved | We need add 5G on sector A/B/C but the solution in remarks provided for all sectors ... so please the 5G just on A/B/C | Laith | Approved |  | Hosni Olayan & Mohammad Abujrai | Approved | 5G solution in civil sheet 4 AQQL and in BTS 3 AQQL | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-19 | Yes | W47 |  | 772 |  |  | Approved
2201 | 2201-Usama_Alrawabi_PE_GPON_TASC |  | AMW-215-R | Indoor | 9 | 35.8522 | 31.9692 | West Amman | Roof Top | eadil muhamad asead hnyh | 799620788 | Tower T 12 | 22 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1281289 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved | Please recheck the RF sheet (where is the 4G ANTs) |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-11 | Yes | W41 |  | 811 |  |  | Approved
220 | 220-Khawam_Hotel_Abdali_PE_GPON_BIBS_O |  | AME-1010-R | Outdoor |  | 35.8936 | 31.9678 | West Amman | Roof Top | Sharekat al bakheet | 06/5680045 | Pole 9 | 9 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266767 | khalilAlOmari |  |  | Done |  |  |  | 5G |  | IBS-B |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | fill the Masts details // height// bracings // DP's // update the civil table with MAST2 not pole // same note but the site online (no civil action required ) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
2214 | 2214-UL_Souq_Khalda_Back_PE_GPON_O |  | AMW-840-R | Outdoor |  | 35.8509 | 31.9828 | West Amman | Roof Top | sami khalil eabd alkarim aldysy | 078-8974791 | Tower T 12 | 25 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266844 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
2210 | 2210-Maaref_Sch_PD_Fiber_TASC |  | AMW-306-R | Indoor | 284 | 35.8431 | 31.9804 | West Amman | Roof Top | hasan farhan mutlaq alnaeimat | 079/5867976 | Tower T 16 | 23 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266841 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved | adding new Mast |  | Approved | 5G service will be installed on 3 sectors , and the solution for 4 sectors |  | Approved |  |  | Approved | Need new Mast | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2217 | 2217-UL_Rawabi_East_PE_O |  | AMW-1139-R | Outdoor |  | 35.8581 | 31.9684 | West Amman | Roof Top |  |  | Tower 16 | 28 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266846 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | we have in the mast (1) 3 sector not 2 sector and there isn't match BTS sheet with civil 1 sheet / power solution & power table are wrong |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2234 | 2234-Holiday_Inn_Back_PE_GPON_TASC |  | AMW-510-R | Indoor | 1500 | 35.8572 | 31.9872 | West Amman | Roof Top | muhmadebayd mazin aleasaf | 078/8541998/0795224296 | Tower T 12 + P9#2 | 21 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266850 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2220 | 2220-Holiday_Inn_PE_GPON_TASC |  | AMW-681-R | Indoor | 1600 | 35.8649 | 31.9799 | West Amman | Roof Top | majid rashid eubdallah alzaml | 079-5569016 | Pole P6 X 5 | 25 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266847 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Azimuth values mismatch with pictures for sector A and B should be down not up |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2209 | 2209-City_Mall_Back_PE_GPON_TASC |  | AMW-752-R | Indoor | 1678 | 35.8438 | 31.9823 | West Amman | Roof Top | madad alnaeimat | 079-6877756 | Pole P9 x 3 | 21 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266840 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Need to reduce one of the two sectors on mast 1. An email has been sent internally to determine the solution |  | Approved |  |  | Approved |  |  | Approved | civil table not as the standard // determine the new installation on each pole and height number of existing DP's not matching with the site photos & the needed DP's shall be 1 not 3 Approved after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-28 | Yes | W39 |  | 824 |  |  | Approved
2223 | 2223-Rabieh_Itisalat_Mada_PD_GPON_O |  | AMW-936-R | Outdoor |  | 35.8686 | 31.9803 | West Amman | Roof Top | amiyh ahmad rashid alrashid | 06-5528282 0797210666/ | Pole P6 X1 + P9 X 1 | 15 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266848 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil table and BTS summery mismatch data | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2224 | 2224-Salheen_PB_Fiber_TASC |  | AMW-427-R | Indoor | 464 | 35.8513 | 31.9792 | West Amman | Roof Top | nasif iilyas eawdat qamuatan | 079/5516912 | Pole P9 X 1 + P6 X 3 | 24 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266849 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
2211 | 2211-NISC_PB_Fiber_TASC |  | AMW-223-R | Indoor | 296 | 35.8703 | 31.9771 | West Amman | Roof Top | eunud matrad alsamiyr |  | Pole P9 X 3 + P6 X 1 + P3 X 1 | 20 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266842 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2213 | 2213-Auhod_Msq_PB_Fiber_TASC |  | AMW-225-R | Indoor | 367 | 35.856 | 31.9713 | West Amman | Roof Top | ayman muhamad tahir rashid fydy | 06/5331888 | Pole P9 X 3 + P6 X 3 | 17 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266843 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved | SD only 2G need check , Maybe will Dismantle it |  | Approved |  |  | Approved | Kindly redo TSSR data since it is not filled correctly |  | Approved | add the DP's numbers the free and the reuse // 3 new DP in the civil requirements new & reuse the existing ones in the BTS // check the antennas name & dimensions in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2206 | 2206-Old_Khalda_PD_GPON_O |  | AMW-302-R | Outdoor | 373 | 35.8526 | 31.9849 | West Amman | Roof Top | muhamad mustafaa iismaeil mustafaa | 079/6616373 | Pole P9X2+P6 | 20 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1232294 | AL-DAR | AL-DAR | 47741500 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | Reuse the existing CBs in the LLVD & and avoid the BLLVD CBs |  | Approved | increase height for sector A & B |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-01 | Yes | W40 |  | 821 |  |  | Approved
2207 | 2207-Abdallah_Ghosheh_PC_GPON_TASC_O |  | AMW-227-R | Outdoor |  | 35.8537 | 31.9753 | West Amman | Roof Top | faras sabhi eabd alfattah alghnmt | 06/5531016 795677678 | Pole P6 X 3 | 18 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266838 | R&D |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Use the concrete foundation to the left of the Huawei cabinets./solved |  | Approved |  |  | Approved | Solved\ Azimuths are wrong |  | Approved | Missing Tower Height // Foot print of Tower // tower foundation// number of existing & free DP'S photos in civil sheet updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2208 | 2208-Ward_Rest_PD_GPON_TASC |  | AMW-693-R | Indoor | 114 | 35.8612 | 31.9869 | West Amman | Roof Top | samir nuqula jaris aldyr | 079-5616627/079-5793366 | Tower T 12 | 25 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266839 | R&D |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Validated by Zain supervisor (Ahmad Dabbagh) and approved by E-mail from IBS manager (Murad Khalili) |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2202 | 2202-Ayass_Hotel_PE_Fiber_AIBS_O |  | AMW-679-R | Outdoor |  | 35.8643 | 31.9823 | West Amman | Roof Top | sharikat alrakayiz lilaistithmar |  | --- --- | 20 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1281290 | Cellcom |  |  | Done |  |  |  | 5G |  | IBS-A |  |  |  | Approved | Wrong power solution - Changed the proposal for the power solution to 'need new rectifier/solved |  | Approved |  |  | Approved |  |  | Approved | Missing site layout | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor | 5 | A | Approved | Approved | 2023-10-10 | Yes | W41 |  | 812 |  |  | Approved
2215 | 2215-Mecca_St_PC_Fiber_TASC |  | AMW-635-R | Indoor | 1572 | 35.856 | 31.977 | West Amman | Roof Top | eabd alsalam mathari salamat alnaeimat | 06-5517726 079-9090906 | Pole P6 X 4 + P3(Wallmounted) x 1 | 27 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266845 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong Antenna Soluation./solved need to upgrade the AC meter/solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-11 | Yes | W41 |  | 811 |  |  | Approved
208 | 208-Tyche_Hotel_PE_GPON_EIBS_TASC_O |  | AMW-1094-R | Outdoor |  | 35.8917 | 31.963 | West Amman | Roof Top |  |  | Pole P6X3 | 6 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1291427 | Cellcom |  |  | Done |  |  |  | 5G |  | IBS-E |  |  |  | Approved | meter is single 30 Amper |  | Approved |  |  | Approved |  |  | Approved | Reduce the load from Mast A by reducing the Antennas height or relocate one or 2 Antenna to Mast B | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-05 | Yes | W45 |  | 786 |  |  | Approved
904 | 904-Medical_City_Farah_PE_EFIBS_Manage |  | AMW-590-R | Indoor | 1543 | 35.8328 | 31.9773 | South Amman | Roof Top | alqiadat aleamat lilquwwat almusalahat alardinit |  | Pole 9 | 21 | Part of 63 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1281291 | Al-Lewan |  |  | Done |  |  |  | 5G |  | IBS-E/F |  |  |  | Approved | wrong power solution! / Third time!!/solved Need to reduce one of the two sectors on mast 1. An email has been sent internally to determine the solution/solved |  | Approved |  |  | Approved |  |  | Approved | need to reduce the load by reducing the height of new installation Antennas to 6 meters instead of top (8 Port Antennas dimension need update in civil sheet) | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-12 | Yes | W41 |  | 810 |  |  | Approved
909 | 909-Mecca_CRL_PC_TASC |  | AMW-669-R | Indoor | 1588 | 35.8397 | 31.9705 | South Amman | Roof Top | musaa eabd alruhmin musaa mahmud | 079-6213235/0795562206 | Tower T 12 | 20 | Part of 63 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1221035 | AL-DAR | AL-DAR |  | Done |  |  |  | 5G | [5 empty] | Approved | redistribute the antenna locations on the masts./solved please follow the new power distubtion soluation. |  | Approved |  |  | Approved | Solved\ Mech tilts are down not up |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
926 | 926-Kursy_2_PD_GPON |  | AMW-526-G | Indoor | 1516 | 35.8278 | 31.9599 | South Amman | Green Field | musaa hasan alraja albakhit | 0777/771282 | Tower T 30 | 20 | Part of 63 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1221038 | TAWSEAA | TWASEAA | 47734359 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | no need to install DP in the SA &SC we have civil//SB (we will install all antennas at the same high=7.89)/as power consumption solution we need to install 3* FPFH not 2&add power solution table |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
935 | 935-Daewoo_Mecca_PE_GPON_TASC_O |  | AMS-191-R | Outdoor |  | 35.8446 | 31.976 | South Amman | Roof Top | eabd alrazzaq hani daruzh | 06/5515347 079/5811116 | Tower T 12 | 25 | Part of 63 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1221040 | TAWSEAA | TWASEAA | 47734368 | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution/solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
940 | 940-Bayader_2_PE_GPON |  | AMW-746-R | Indoor | 1688 | 35.8339 | 31.9614 | South Amman | Roof Top | mahmud eisaa ahmad shnyur | 07777-49074 | Tower T 16 | 20 | Part of 63 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1221042 | UTC | UTC | 47733630 | Done |  |  |  | 5G | [5 empty] | Approved | The rectifier will be changed soon. |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
946 | 946-Shaab_St_Khazan_PF_M |  | AMW-138-R | Micro Cell |  | 35.8241 | 31.973 | Amman | Pole | dayirat almukhabarat aleamat |  | Microcell | 12 | Part of P1 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1285742 | khalilAlOmari | Cellcom>>Desert |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | solved\ mech tilt data doesn't match the photos |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-16 | Yes | W46 |  | 775 |  |  | Approved
949 | 949-8th_CRL_PA_Fiber_TASC |  | AMW-140-R | Indoor | 33 | 35.8527 | 31.9582 | South Amman | Roof Top | ahmad eisaa muhamad abu dhyab | 06/5813708 079/5899100/0795036140/ | Tower T 16 + D3 X 2 | 28 | Part of 63 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1221043 | AL-DAR | AL-DAR |  | Done |  |  |  | 5G | [5 empty] | Approved | Use the existing CBs for FPFHs / AND CONNECT THE AMIA TO BLVD IF NO AVILABLE CBs |  | Approved |  |  | Approved | Solved\ 4G Sector C data are missing |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
953 | 953-Abdeen_CPLX_7th_CRL_PE_GPON_TASC_O |  | AMS-123-R | Outdoor |  | 35.8544 | 31.9566 | South Amman | Roof Top | muetaz iibrahim fhmy eabidin | 06/5862315 0777770071/0777991599 | Pole P6X2 | 24 | Part of 63 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1221044 | TAWSEAA | TWASEAA | 47734370 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5901 | 5901-Deir_Ghbar_1_PC_Fiber_TASC |  | AMW-479-R | Indoor | 475 | 35.8666 | 31.9394 | South Amman | Roof Top | eabdallah eabd al ilh eabdalalah shakiran | 06/5820054/06-58509936 079-5820054 | Pole P6 X 3 | 23 | Part of P1 | Phase-2 | Batch_12 | Cluster-59 |  | Traditional | SMP-WO-1221105 | UTC | UTC | 47733587 | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution/solved need to upgrade the AC meter./solved Need to reduce one of the two sectors on mast 1. An email has been sent internally to determine the solution./solved |  | Approved |  |  | Approved | Solved\ Sectors are B,C and D. not A, B and C. Solved\ 3G Tilts are 1, 3 and 4 degrees for the sectors b, C and D respectively. |  | Approved | Mast B overloaded // need a new Mast or to reduce the load by canceling one sector 6 Antennas on Mast B 7.5 meters the Max | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
3233 | 3233-King_Hussein_Gardens_PC_Fiber_TASC |  | AMW-316-R | Indoor | 80 | 35.8336 | 31.9853 | West Amman | Roof Top | sharifat ahmad murad alkardi | 06/5539910 | Tower T 12 | 18 | Part of P1 | Phase-2 | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1299140 | Cellcom | AL-DAR>> Cellcom |  | Done |  |  |  | 5G | [5 empty] | Approved | Need to update the power solution as the new power sheet. |  | Approved |  |  | Approved | Solved\ Sector A azimuth picture is reused for different antennas. Solved\ Some of the compass pictures are not readable (pixilated). Sector A 4G mech tilt inclinometer display is not readable. |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-11 | Yes | W45 |  | 780 |  |  | Approved
5944 | 5944-Philadelphia_Sch_Back_PE_GPON_TASC_O |  | AMS-52-R | Outdoor |  | 35.8519 | 31.9426 | South Amman | Roof Top | warathat biaismih iismaeil mustafaa alqaryuti | 0799000019/0795556466 | Tower T 16 | 32 | Part of P1 | Phase-2 | Batch_12 | Cluster-59 |  | Traditional | SMP-WO-1221108 | UTC | UTC | 47733610 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-10 | Yes | W41 |  | 812 |  |  | Approved
2001 | 2001-Nishan_CRL_North_PB_Fiber_TASC |  | AMW-1096-R | Indoor |  | 35.8654 | 31.9997 | West Amman | Roof Top | ahmad eubayd mukid aleasaf |  | Pole P9 X 2 | 21 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266806 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | panaroma pictures need to be updated |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
3513 | 3513-Music_CTR_PC_Fiber_TASC |  | AME-292-R | Indoor | 350 | 35.8934 | 31.9589 | West Amman | Roof Top | eayishat eabd alrahim alfirj aleutayat | 06/5674973 079/5504772 | Pole P9 X 1+ P6 X4 | 14 | Part of 63 | Phase-2 | Batch_13 | Cluster-35 |  | Traditional | SMP-WO-1221067 | UTC | UTC | 47733514 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Update the civil table Qty's not// needed DP's in the civil requirements new check the availability to reduce one sector height from Mast B to 6 meters // before sending the site to TASC | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
3229 | 3229-Asriyya_Sch_PC_Fiber_TASC |  | AMW-313-R | Indoor | 252 | 35.8491 | 31.9971 | West Amman | Roof Top | eabd almatlab muhamad asead aljabalay | 06/5357838 079-5849283/079-9888577 | Tower T 16 | 32 | Part of P1 | Phase-2 | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1221060 | Al-Lewan |  | 47759337 | Done |  |  |  | 5G | [5 empty] | Approved | 5G civil not clear , please to resubmit it |  | Approved |  |  | Approved | Retake all azimuth pictures for sectors ( NO RETAKE TOOK PLACE IN TSSR) |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
4026 | 4026-Sport_City_2_PC_Fiber_TASC |  | AME-304-R | Indoor | 255 | 35.9045 | 31.9878 | West Amman | Roof Top | kamal hamid mahmadalzayd | 06/5150902 079/5698052 | Pole P6 X 3 + P9 X 1 | 27 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281080 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-30 | Yes | W44 |  | 792 |  |  | Approved
3236 | 3236-New_English_CRL_PB_Fiber_TASC |  | AMW-540-R | Indoor | 1515 | 35.8494 | 31.9898 | West Amman | Roof Top | madihat muhamad alzzahir washurakayuha | 0777/695176 | Tower T 16 | 26 | Part of P1 | Phase-2 | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1291428 | Cellcom | AL-DAR>> Cellcom |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil sheet / table not as the standard // check each antenna location & Qty's & dimension // approved after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-07 | Yes | W45 |  | 784 |  |  | Approved
3919 | 3919-Bayader_Ind_PD_Fiber_TASC |  | AMW-722-R | Indoor | 1622 | 35.8339 | 31.9447 | South Amman | Roof Top | ewny muhamad muhamad aleitar wayumthiluh eabd almajid aletar | 079-7814285/0777-228698 | Tower T 12 | 14 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221095 | UTC | UTC | 47733578 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | Need clear photo for Rectifier, and more details about the LLVD and BLVD CBs/solved |  | Approved |  |  | Approved |  |  | Approved | Missing Tower details in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-21 | Yes | W42 |  | 801 |  |  | Approved |  |  |  |  | Downloaded
1617 | 1617-Jordan_Uni_East_Gate_PE_EBand_TASC_O |  | AMW-1043-R | Outdoor | 1747 | 35.8807 | 32.007 | West Amman | Roof Top | muhamad qasim yasin asead | 0777767734/0790308237/00966569569771 | Tower T 24 | 42 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266787 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
3243 | 3243-City_Mall_1_PD_Fiber_IBS_Manage |  | AMW-545-R | IBS |  | 35.8359 | 31.9809 | Amman | IBS |  |  | IBS (Indoor) |  | Part of P1 | Phase-2 | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1285733 | Al-Lewan |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved | Wrong power solution ,The AC meter reads 63, not 16!/solved.. please follow the updated sheet for power distribution. |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-16 | Yes | W46 |  | 775 |  |  | Approved
2003 | 2003-Cambridge_Sch_PE_GPON_TASC |  | AMW-330-R | Indoor | 421 | 35.8804 | 31.9799 | West Amman | Roof Top | zahdi musaa shryth eali yaequb | 971506537406 079-5538771/077-227227 | Tower T12 + P6 | 21 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266807 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | need new TSSR/Solved |  | Approved | noted to aysar will be clarified more |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-31 | Yes | W44 |  | 791 |  |  | Approved
2031 | 2031-Iskan_Ibin_Sina_2_PE_GPON_TASC_O |  | AMW-623-R | Outdoor |  | 35.8554 | 32.0059 | West Amman | Roof Top | khalid eawdat musaa zaydan | 079-5678882 | Pole P6X3 | 18 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266828 | PIS |  |  | Done |  |  |  | 5G | [5 empty] | Approved | the 5G DP must be 3m instead of 1.5m. |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
3232 | 3232-Khalda_Sweileh_PF_TASC |  | AMW-770-R | Indoor | 1720 | 35.8484 | 32.0103 | West Amman | Roof Top | jamil eabd alrahmin jbr ahmidan | 06-5333922 079-8706683 | Pole P9 + P6 | 15 | Part of P1 | Phase-2 | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1217269 | SMART | SMART | 47734506 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ North direction picture is blocked Solved\ Sector A views are different with the same azimuth value Solved\ Sectors naming is shifted, Sector A azimuth is 130 and sector B is 350. Solved\ mech tilt data doesn't match with the table |  | Approved | civil sheet not as the standard | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
1616 | 1616-Uni_Bridge_InterX_PD_GPON_TASC_O |  | AMW-954-R | Outdoor |  | 35.8731 | 32.0047 | West Amman | Roof Top | muhamad fakhari muhamad hasan abu shrkh | 0795838151/0799114255/0799962828 | Pole P9 + P6 | 26 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266786 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
1606 | 1606-Girls_Dorm_PA_Fiber_TASC |  | AMW-148-R | Indoor | 138 | 35.8847 | 32.0077 | West Amman | Roof Top | eumar mahmud musaa abu shaykhuh w namuru salim namuru jalaad | 06/524431 077-9107174 | Tower T 16 + P4 X 2 | 30 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266779 | Al-Lewan |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | There is an antenna(2g) in sector A that is not mentioned//we need to install every sector at the same high //I need you to show me and specify with pictures BLVD&LLVD |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-11 | Yes | W45 |  | 780 |  |  | Approved
108 | 108-C_Town_7th_CRL_PE_EBand_TASC |  | AMW-8-R | Indoor | 143 | 35.8615 | 31.9607 | South Amman | Roof Top | khadir mahmud eali alhmshry |  | Tower T 12 | 28 | Part of P1 | Phase-2 | Batch_15 | Cluster-1 |  | Traditional | SMP-WO-1221026 | R&D | R&D | 47759345 | Done |  |  |  | 5G | [5 empty] | Approved | find the uploaded file for the power distribution solution. no need to upgrade the IBS sector! |  | Approved | Need more clarification & pictures for 5G installation solution |  | Approved |  |  | Approved | BTS Summary missing | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-17 | Yes | W42 |  | 805 |  |  | Approved
1610 | 1610-Manhal_Sch_PE_Fiber_TASC |  | AMW-436-R | Indoor | 485 | 35.8861 | 32.0139 | West Amman | Roof Top | nawal bidawiin haj husayn badway | 06-5160078 079-5670984 | Pole P9*1+P6*3 | 21 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266781 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution/ Solved change the number of sectors on BTS sheet to 3 sectors instead of 4 sectors/ Solved the 5G DP must be 3m instead of 1.5m/solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-21 | Yes | W42 |  | 801 |  |  | Approved
3609 | 3609-Sahaba_CRL_PD_Fiber_TASC |  | AME-193-R | Indoor | 362 | 35.9206 | 31.9249 | South Amman | Roof Top | salih ahmad yusif alkhatib | 06/4399873 079-5129029/079-6029777/00971506233363 | Pole P9 X4 | 9 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221072 | UTC | UTC | 47733534 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | The photos of the rectifier are not clear./solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-15 | Yes | W42 |  | 807 |  |  | Approved
5609 | 5609-Jordan_Uni_Seveen_PE_Fiber_TASC |  | AMW-637-R | Indoor | 1561 | 35.8697 | 32.0207 | West Amman | Roof Top | muhamad amin ebdallh amin alkhdra | 06-5822170 079-5581111 | Tower T 12 | 24 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281095 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong Antenna Solution./solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-19 | Yes | W42 |  | 803 |  |  | Approved
5610 | 5610-Jordan_Uni_Macdonalds_PC_Fiber_TASC |  | AMW-636-R | Indoor | 1560 | 35.8681 | 32.0147 | West Amman | Roof Top | usamat rashad eabd alrazzaq barakat | 06-5336049/06-5347312 079-5542245/078-8436123 | Pole P9 X 1 + P6 X 2 | 24 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281096 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | The rectifier and power solution are not clear/Solved The solution for antennas is not clear./Solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-19 | Yes | W42 |  | 803 |  |  | Approved
147 | 147-Kalha_PE_TASC |  | AMW-40-R | Indoor | 35 | 35.8665 | 31.9589 | South Amman | Roof Top | musaa eabd alfattah eabd alruhmin abu ghwsh | 06/5853737 079/5604347 | Pole P9#1 + P5#1 + WallMounting3#3 + P2#1 + P6#1 | 19 | Part of P1 | Phase-2 | Batch_15 | Cluster-1 |  | Traditional | SMP-WO-1221032 | Al-Lewan |  | 47759333 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil sheet data missing // provide the data for each pole as the standard approved but missing the poles heights in the civil sheet (not as the standard ) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
1605 | 1605-Nivin_Rising_2_PD_O |  | AMW-948-R | Outdoor |  | 35.8622 | 32.0169 | West Amman | Roof Top | salah aldiyn mustafaa ahmad shawish | 0798797900/0786797900 | Pole P9#2 | 23 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266778 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-02 | Yes | W44 |  | 789 |  |  | Approved
1626 | 1626-Uni_Dr_HSG_PC_Fiber_TASC_Relo_O |  | AMW-1084-R | Outdoor |  | 35.8782 | 32.0143 | West Amman | Roof Top | hasan husni muhamad albayjawy | 06/5667019 - 06/4727491 079/5520289 | Tower T 20 | 19 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266792 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | update 8-port Antenna dim in civil table | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
5656 | 5656-Jordan_Uni_Computer_CTR_PF_TASC_O |  | AMW-888-R | Outdoor |  | 35.8752 | 32.0142 | West Amman | Roof Top | aljamieat al urduniyat | 06-5355000 | Pole P9 x 3 | 15 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281109 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved | the 5G DP must be 3m instead of 1.5m |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-30 | Yes | W44 |  | 792 |  |  | Approved
3940 | 3940-MOICT_8th_CRL_PD_GPON_TASC |  | AMW-747-R | Indoor | 1661 | 35.8466 | 31.9587 | South Amman | Roof Top | khadijat eumar mahmud yusuf | 0777-529329 | Tower T 16 | 29 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221102 | TAWSEAA | TWASEAA | 47734345 | Done |  |  |  | 5G | [5 empty] | Approved | The rectifier will be changed soon. |  | Approved |  |  | Approved | Kindly redo azimuth pictures as they are not clear for all tech |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-17 | Yes | W42 |  | 805 |  |  | Approved
5658 | 5658-Sweileh_Fadhila_Ave_PE_GPON_TASC_O |  | AMW-1001-R | Outdoor |  | 35.8546 | 32.0172 | West Amman | Roof Top | lilayum li iidarat alfanadiq wayumthiluha salim aleabdallaat |  | Pole P9#2 | 27 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281110 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved | NEED mast extend to 9m to Relocate SB |  | Approved |  |  | Approved |  |  | Approved | Relocate one sector from MAST 1 to MAST 2 or reduce 2 sectors height to 6 meters // Missing poles details (bracings // DP's// Pole height) // Missing MW details updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-02 | Yes | W44 |  | 789 |  |  | Approved
3215 | 3215-Sands_Sch_PD_GPON_TASC |  | AMW-631-R | Indoor | 1564 | 35.8447 | 32.0056 | West Amman | Roof Top | muhamad eabd alghaniu saeid blbybsy | 06-5356192 079-7029387 | Tower T 16 | 13 | Part of P1 | Phase-2 | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1291773 | Cellcom | AL-DAR>> Cellcom |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-09 | Yes | W45 |  | 782 |  |  | Approved
5615 | 5615-Tourism_Police_Station_PD_Fiber_TASC |  | AMW-788-R | Indoor | 1736 | 35.873 | 32.0248 | West Amman | Roof Top | eadnan alealii wayumthiluhum zahir ahmad iibrahim malahm | 079-5767076 | Tower T 20 | 31 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281100 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-04 | Yes | W44 |  | 787 |  |  | Approved
111 | 111-Ramada_Hotel_PE_GPON_TASC |  | AMW-130-R | Indoor | 205 | 35.8574 | 31.9616 | South Amman | Roof Top | eabdalsalam asead eabd alsalam aljabali | 06-4161383 079-5506579 | Pole P9X2+P6X4 | 21 | Part of P1 | Phase-2 | Batch_15 | Cluster-1 |  | Traditional | SMP-WO-1221028 | R&D | R&D | 47759348 | Done |  |  |  | 5G | [5 empty] | Approved | incorrect site name/Solved wrong power solution/Solved |  | Approved |  |  | Approved | the site name is 1619-UL_Rasheed_Jordan_St_2_PE_TASC_O |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
2007 | 2007-Ibin_AlHaitham_Back_PD_Fiber_TASC |  | AMW-652-R | Indoor | 1584 | 35.8766 | 31.9947 | West Amman | Roof Top | mazin mustafaa muhamad alhsn | 079-5893391 | Tower T 16 | 31 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1281063 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Need to transfer SC From Mast 2 to the new location of Sector C (MAST 3) to avoid the overload / Need double check from planning & optimization teams Use the existing CBs in the existing rectifier |  | Approved |  |  | Approved |  |  | Approved | reduce the load from MAST 2 to MAST 1 or MAST 3 by shifting one sector // determine each MAST number on each photo // update the BTS summery with the masts number for each sector updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
3912 | 3912-UmAlSous_PC_Fiber_TASC |  | AMW-327-R | Indoor | 406 | 35.8217 | 31.9465 | South Amman | Roof Top | saeid ahmad eabd alhamid qatnani | 06-5864622/06-5818106 079-9007999/079-6666069 | Pole P6 X 3 + P9 X 1 | 15 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221092 | TAWSEAA | TWASEAA | 47734318 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | no DPs needed for 5G |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-05-14 | Yes | W20 |  | 961 |  |  | Approved
3615 | 3615-Souq_Mugabalein_2_PF_TASC |  | AME-749-R | Indoor | 1713 | 35.912 | 31.9065 | South Amman | Roof Top | ltfy nayif hasan almasaeidah | 079-5203134 | Tower T 12 | 21 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221074 | UTC | UTC | 47733543 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil table not as the standard// determine each Antenna new installation or reuse or dismantle // Antenna height & location // number of existing DP // any wall mount or DP on wall // shall match with the BTS updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved |  |  |  |  | Downloaded
3601 | 3601-Hitteen_PD_EBand_TASC |  | AME-499-R | Indoor | 450 | 35.9366 | 31.9097 | South Amman | Roof Top | harb eabidarbih eubdallah rajban | 06/4786782 079/5690769 | Tower T 12 | 24 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221068 | TAWSEAA | TWASEAA | 47734283 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | 5g sectors (A/C/D)not((A/B/D)///modify power solution &Add power table |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
3626 | 3626-Mugabalein_Safeway_PD_Fiber |  | AME-716-R | Indoor | 1683 | 35.9127 | 31.9156 | South Amman | Roof Top | sayid husayn dahabur dahbur | 079-6612121/079-5545878 | Pole P9 X2 | 24 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221079 | UTC | UTC | 47733548 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved |  |  |  |  | Downloaded
1631 | 1631-Tlaa_AlAli_PE_GPON_TASC_O |  | AMW-169-R | Outdoor |  | 35.87 | 32.0024 | West Amman | Roof Top | muhsin nasr ramadan dawd | 079-5177500 | Pole P6+P3X2 | 21 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266796 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution/solved Need more details about the ACOC location and whether we can replace one of the fiber boxes with an ACOC/solved Wrong antenna information/solved |  | Approved |  |  | Approved | Site Location needs correction. |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
4070 | 4070-Mukhtar_Sport_City_Back_PE_GPON_TASC_O |  | AMW-930-R | Outdoor |  | 35.9002 | 31.9896 | West Amman | Roof Top | yusuf salih eisaa batarish | 0799043040/0795333217 | Tower T 20 | 27 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281089 | R&D | R&D |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution. The photos are not clear enough to determine if the ACOC location is correct. |  | Approved |  |  | Approved |  |  | Approved | location of Antennas in civil table only on the existing MASTS // need to update the solution and locate the materials on the new proposed MASTS // and propse the location for the new MASTS civil table still not updated and has a blank fields Approved after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-05 | Yes | W45 |  | 786 |  |  | Approved
110 | 110-Cozmo_7th_CRL_PC_EBand_TASC |  | AMW-598-R | Indoor | 1553 | 35.8568 | 31.9541 | South Amman | Roof Top | tarah saed salamat halsat | 079-6686632 | Tower T 16 | 17 | Part of P1 | Phase-2 | Batch_15 | Cluster-1 |  | Traditional | SMP-WO-1221027 | R&D | R&D | 47759347 | Done |  |  |  | 5G | [5 empty] | Approved | The rectifier will be changed soon. |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
2014 | 2014-Gardens_Hospital_PF_AIBS_Manage |  | AMW-807-R | Indoor | 1727 | 35.878 | 31.9856 | West Amman | Roof Top | mustashfaa aljardunz | 06-5544205 | Pole P 4 | 26 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1281067 | Cellcom |  |  | Done |  |  |  | 5G |  | IBS-A |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-31 | Yes | W44 |  | 791 |  |  | Approved
2018 | 2018-Waha_CRL_PD_EBand_TASC |  | AMW-203-R | Indoor | 107 | 35.8715 | 31.9898 | West Amman | Roof Top | tawfiq eabd salman farhanan | 079-5254748/079-5357626 | Pole P6 x 4 | 25 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266818 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-21 | Yes | W42 |  | 801 |  |  | Approved
1620 | 1620-Souq_Sultan_PE_GPON_TASC |  | AMW-763-R | Indoor | 1682 | 35.8712 | 31.9999 | West Amman | Roof Top | eabdallah mahmud ahmad alhaj ahmad | 077-9733944/079-6771119 | Pole P9 x 3 | 21 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266790 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | The ACOC location will be blocked by other cabinets, we need to add a concrete foundation on the lift the existing cabinets./solved Need to reduce one of the two sectors on mast 1. An email has been sent internally to determine the solution./solved |  | Approved |  |  | Approved |  |  | Approved | determine what is the new installation / dismantle / reuse /Antennas location on Masts" civil table" // bracings numbers in civil sheet updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-21 | Yes | W42 |  | 801 |  |  | Approved
3621 | 3621-Um_AlHeiran_PE_TASC |  | AME-216-R | Indoor | 20 | 35.9394 | 31.9151 | South Amman | Roof Top | ltfy mahmud hasnin |  | Tower T 12 | 19 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221075 | TAWSEAA | TWASEAA | 47734290 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | Wrong power solution/solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-16 | Yes | W46 |  | 775 |  |  | Approved
1627 | 1627-Uni_Main_Gate_PB_Fiber_TASC |  | AMW-165-R | Indoor | 57 | 35.8707 | 32.0102 | West Amman | Roof Top | zahdi khamis muhamad hasawat | 06-5851468 079-5024855 | Pole P9 X 1 + P6 X 4 | 23 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266793 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved | The rectifier will be changed soon. |  | Approved | No files |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-22 | Yes | W43 |  | 800 |  |  | Approved
4033 | 4033-Hadath_PF_TASC |  | AMW-171-R | Indoor | 32 | 35.8943 | 31.987 | West Amman | Roof Top | eisaa muhamad khalil aljylani | 06/5676088 079/5747754 | Pole P6X2+P9 | 20 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281084 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | The rectifier will be changed soon. |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
1643 | 1643-Rasheed_Back_PE_TASC_O |  | AMW-180-R | Outdoor | 374 | 35.888 | 32.0023 | West Amman | Roof Top | hilal muhamad asead alsharif | 06/5150180 0790985885/ | Tower T 12 | 19 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266801 | Cellcom |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | need to updgrade the AC meter |  | Approved |  |  | Approved |  |  | Approved | Needed DP's 2 not 3 | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-23 | Yes | W43 |  | 799 |  |  | Approved
3647 | 3647-Zohour_PC_Fiber_O |  | AME-954-R | Outdoor |  | 35.915 | 31.9183 | South Amman | Roof Top | khalil yusif ahmad salm | 0796276937/0795515986 | Tower T 12 | 27 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221082 | UTC | UTC | 47733566 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | Need to update the power solution as the new power sheet. |  | Approved |  |  | Approved |  |  | Approved | check the civil table '// reused & new & dismantle // match with the BTS // update the location filed and match all with the BTS updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
2017 | 2017-Omar_Mukhtar_PC_Fiber_TASC |  | AMW-485-R | Indoor | 123 | 35.8673 | 31.9879 | West Amman | Roof Top | muhamad jumeat iibrahim alkhazindar | 06/4653245 795570881 | Pole P9 X 1 + P6 X 5 | 27 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266817 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-22 | Yes | W43 |  | 800 |  |  | Approved
2023 | 2023-Rabieh_Itisalat_PD_GPON_TASC |  | AMW-767-R | Indoor | 1734 | 35.8731 | 31.9807 | West Amman | Roof Top | samir alghafaar wakilana ean muhamad nyrwkh | 079-5888280 | Tower T 16 | 19 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266822 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | Install a new 9m pole for Sector A |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-17 | Yes | W42 |  | 805 |  |  | Approved
4035 | 4035-Takhasosi_Hospital_2_PE_Fiber_TASC |  | AMW-740-R | Indoor | 1651 | 35.9017 | 31.9786 | West Amman | Roof Top | majdulin eabd alrazzaq saed | 079-9073587 | Pole P6+P9 | 21 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281085 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-12 | Yes | W46 |  | 779 |  |  | Approved
2008 | 2008-Rabieh_Tlaa_AlAli_PD_Fiber_TASC |  | AMW-742-R | Indoor | 1702 | 35.8715 | 31.9855 | West Amman | Roof Top | khalid hasan iibrahim kharis wakila | 06-5530707 079-7122217 | Pole P9 X 1 + P6 X 2 | 17 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1281064 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | increase sector C to the top ( 12m) |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
1648 | 1648-Uni_Dr_HSG_END_PE_Fiber_TASC_O |  | AMW-1090-R | Outdoor |  | 35.8762 | 32.0201 | West Amman | Roof Top |  |  | Tower T 12 | 27 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266803 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | For the planned data Keep 5G SA Same as 4G @90 Degrees For the planned data Keep 5G SB Same as 4G @175 Degrees |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
1619 | 1619-Rasheed_Jordan_St_2_PE_TASC_O |  | AMW-785-R | Outdoor |  | 35.8849 | 32.0238 | West Amman | Roof Top | yusraa ahmad husayn mudahat | 079-7375555 | Pole P9#2 | 17 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266789 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | SA SC AAU & need 5G , SB 2G 3G only no 5G on it , SD 2G 3G IBS |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
5614 | 5614-North_Amman_Court_PE_Fiber_TASC |  | AMW-334-R | Indoor | 426 | 35.8633 | 32.0219 | West Amman | Roof Top | sayf aldiyn muhamad hamid salamt | 06-5333981 079-5522748/079-7246111/079-7300889 | Pole P6 X 4 | 20 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281099 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-08 | Yes | W45 |  | 783 |  |  | Approved
4080 | 4080-Rasheed_Customs_PE_GPON_TASC_O |  | AMW-901-R | Outdoor |  | 35.9022 | 31.9988 | West Amman | Roof Top | ahmad muhamad ahmad alrwashdt | 796767770 | Pole P6+Wall mount 6mX1 | 18 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281090 | R&D | R&D |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution - connected on BLVD! / solved |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-02 | Yes | W44 |  | 789 |  |  | Approved
2034 | 2034-Ibin_AlHaitham_Hospital_PF_Fiber_CDIBS_O |  | AMW-1103-R | Outdoor |  | 35.8732 | 31.997 | West Amman | Roof Top |  |  | Pole 6 | 24 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266829 | khalilAlOmari |  |  | Done |  |  |  | 5G |  | IBS-D/C |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
126 | 126-AlMadinah_AlMonawara_PD_Fiber_O |  | AMW-23-R | Outdoor | 256 | 35.8644 | 31.964 | South Amman | Roof Top | eabd aleaziz mubarak eabd alqadir almjaly | 06/5814810 077-2053366/079-5444061 | Tower T 16 | 18 | Part of P1 | Phase-2 | Batch_15 | Cluster-1 |  | Traditional | SMP-WO-1221031 | R&D | R&D | 47759356 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
2015 | 2015-Ibin_AlHaitham_PC_Fiber_TASC |  | AMW-201-R | Indoor | 1 | 35.8762 | 31.9922 | West Amman | Roof Top | yusuf eisaa samiyr | 06/5601030 - 06/4645885 | Pole P6 X 2 + P5 X 1 | 16 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1281068 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | ,Please modify the solution power and add new table |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-31 | Yes | W44 |  | 791 |  |  | Approved
2010 | 2010-Waha_CRL_2_PE_O |  | AMW-864-R | Outdoor |  | 35.8691 | 31.9906 | West Amman | Roof Top | ahmad aleanzii | 06-5537107 0777-661022 | Pole Wall Mounting 6m + P6 | 29 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266811 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved | SD to be Dismantle ( Kathrin Antenna) AZ 280 |  | Approved |  |  | Approved | Keep Planned installation Sector A @ 55, Sector B @185, Sector C @210 |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-31 | Yes | W44 |  | 791 |  |  | Approved
2016 | 2016-Bashiti_TL_PD_GPON_TASC_O |  | AMW-953-R | Outdoor |  | 35.8576 | 31.9946 | West Amman | Roof Top | sami salim salim hbsh | 06-5535322 0795566441/ | Pole P9#2 | 30 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266816 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved | capacity sectors (A/B/C) NOT (A/C/D)/5G SECTOR (A/B/C) and pictures not match |  | Approved |  |  | Approved | Please review BTS remarks for sector C |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
2039 | 2039-Tlaa_AlAli_Sch_PE_GPON_TASC_O |  | AMW-975-R | Outdoor |  | 35.8639 | 31.9959 | West Amman | Roof Top | eimad fawaz husayn alnaeimat | 0796005949/0799711110 | Tower T 20 | 34 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266830 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-17 | Yes | W42 |  | 805 |  |  | Approved
2019 | 2019-North_NISC_PE_TASC |  | AMW-204-R | Indoor | 297 | 35.8742 | 31.9826 | West Amman | Roof Top | eabd alruwuwf muhamad mustafaa alhasan | 06/5522643 | Tower T 16 | 12 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266819 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | Approved increase all sectors(change structure) |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-20 | Yes | W42 |  | 802 |  |  | Approved
2012 | 2012-Reef_CTR_PB_Fiber_TASC |  | AMW-198-R | Indoor | 121 | 35.8626 | 31.9932 | West Amman | Roof Top | muhamad eali muhamad abu eyash | 06-5411302 079-5522943 | Pole P9 X 1 + P6 X 5 + P3 X 1 | 14 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1281066 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | reduce the AQQL Antenna on Mast2 to 6 meters as the 10 port & cancel the new Mast proposal | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
2040 | 2040-Iskan_Ibin_Sina_CTR_PE_GPON_TASC_O |  | AMW-992-R | Outdoor |  | 35.8586 | 32.0051 | West Amman | Roof Top | ahmad saqr karim aleasaf | 0795555968/0796041500 | Pole P9#2 | 16 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266831 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Approved but new solution Sector C new antenna should both be 280 4G and 3G |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
2022 | 2022-Assaf_Msq_PF_EBand_TASC_O |  | AMW-914-R | Outdoor |  | 35.8577 | 31.9918 | West Amman | Roof Top | muasasat al amirat taghrid litanmiat alfunun walharf | 06-5377314 0797633350/ | Tower T 20 | 21 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266821 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
2028 | 2028-Iskan_Ibin_Sina_PE_GPON_TASC |  | AMW-419-R | Indoor | 435 | 35.8628 | 32.0051 | West Amman | Roof Top | fuzi ahmad eabd almajid alzabdiyat | 079-5027506/0795027506 | Tower T 16 | 22 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266827 | PIS |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | match 5G sector C height with 3G/4G Antenna |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
2021 | 2021-Alfieh_Gardens_PE |  | AMW-725-R | Indoor | 1715 | 35.879 | 31.9927 | West Amman | Roof Top | sharikat al iiman lilaistisharat | 079-319505/079-5202223 | Tower T 12 | 22 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266820 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved | wrong power solution - please to use the LLVD CBs!/solved |  | Approved |  |  | Approved | Approved after antenna redesign and plan with Aysar |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
1615 | 1615-Rasheed_Civil_Defence_PE_GPON_TASC_O |  | AMW-1027-R | Outdoor |  | 35.8804 | 32.0052 | West Amman | Roof Top | rida salim salim alayubi | 06/5155218 0799892325/0786084854 | Tower T 20 | 29 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266785 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | SA to install new 5G above TDD Antenna |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
2027 | 2027-Middle_Gardens_PF_Fiber_TASC |  | AMW-211-R | Indoor | 326 | 35.8812 | 31.987 | West Amman | Roof Top | mahmud falah salim aleasaf | 06/5676123 079-5135523 | Pole WallMount 9#2 + P6#1 + P3#1 | 18 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266826 | SMART |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | the existing sectors(B/C/D) not (A/B/C) |  | Approved | the new pole has to be 9m pol and install the new 5G antenna at the top |  | Approved |  |  | Approved | civil table not as the standard "the data not matched with the photos" // update the civil table and match with the BTS sheet (the existing and the proposed ) // beside the civil requirements new not match with the BTS // updated approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
2032 | 2032-Khalda_2_PE_GPON_TASC |  | AMW-700-R | Indoor | 1609 | 35.855 | 32.0015 | West Amman | Roof Top | munir fawzi khalil eala aldin | 079-5449123/079-5944123 | Tower T 18 | 28 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1232293 | AL-DAR | AL-DAR | 47741499 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
2203 | 2203-Auhod_Back_PE_GPON_TASC_O |  | AMW-444-R | Outdoor |  | 35.8582 | 31.9739 | West Amman | Roof Top | wafa hani ahmad alruwsan | 079-9669555 | Pole P6X2+P9 | 18 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266836 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
2204 | 2204-Dur_Manthour_PF_TASC_O |  | AMW-945-R | Outdoor |  | 35.8597 | 31.9821 | West Amman | Roof Top | nasir iismaeil husayn abu khdra | 0797777155/0796289067 | Pole P9X4 | 21 | Part of 63 | Phase-2 | Batch_10 | Cluster-22 |  | Traditional | SMP-WO-1266837 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Kindly change planned Sector A from 30 to 50 for both 2G3G4G and 5G antennas |  | Approved | you may relocate DP from Mast2 to Mast 1 | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
4008 | 4008-Dentist_HSG_PD_Fiber_TASC |  | AMW-150-R | Indoor | 79 | 35.8839 | 31.9937 | West Amman | Roof Top | ahmad sulayman alkayid alealy | 079-6680933 | Tower T 12 | 15 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1295719 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | Use the second solution for the ACOC location! |  | Approved |  |  | Approved |  |  | Approved | use the existing 6DP (relocate them were you need ) and add 1 extra DP "in the civil requirements" since the proposed # of Antennas is 7 | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-05 | Yes | W45 |  | 786 |  |  | Approved
4024 | 4024-Arabian_College_PD_Fiber_TASC |  | AMW-333-R | Indoor | 443 | 35.8875 | 31.9857 | West Amman | Roof Top | fatimatan walid allaham | 06-5601824 079/5775118 | Tower T 16 | 25 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281078 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution/solved wrong antenna solution/solved |  | Approved |  |  | Approved | Solved\ 3G/4G sectors are A,B,C not A,C,D Solved\ 360 photos are shifted |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-02 | Yes | W44 |  | 789 |  |  | Approved
4025 | 4025-Dawahi_Hotel_PE_DIBS_Manage |  | AMW-414-R | Indoor | 474 | 35.8866 | 31.9985 | West Amman | Roof Top | sharikat alshshati aldhahabii lilaistithmar | 06/5159314 079/5583058 | Pole P6X2+P9 | 26 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281079 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G |  | IBS-D |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
4045 | 4045-Arjan_Civil_Defence_PF_TASC |  | AMW-716-R | Indoor | 1633 | 35.911 | 31.9848 | West Amman | Roof Top | niqabat ashab mahattat a/ fahd hakim alfayz | 06-5661702/06-5661701 079-5133001/079-5776323 | Tower T 16 | 19 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281087 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil sheet not matched with the BTS and not as the standard updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
2024 | 2024-Ibin_Sina_HSG_Tlaa_AlAli_PE_GPON |  | AMW-753-R | Indoor | 1731 | 35.8622 | 32.0111 | West Amman | Roof Top | farial hasan eabd alwahhab alhilwani | 06-5335614 078-5440447/079-5449833 | Pole P9+P6X2 | 12 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266823 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
4002 | 4002-Rawda_Sahafa_Tunnel_PE_EBand_TASC |  | AMW-144-R | Indoor | 120 | 35.8892 | 31.9928 | West Amman | Roof Top | hasan husni muhamad albayjawy |  | Tower T12+P9 | 29 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266872 | PIS |  |  | Done |  |  |  | 5G | [5 empty] | Approved | meter is single 30 Amper |  | Approved |  |  | Approved |  |  | Approved | civil table not matched with the BTS sheet and not as the standard updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
4021 | 4021-Dahiet_Rasheed_Rawda_PE_GPON_TASC_O |  | AMW-994-R | Outdoor |  | 35.8893 | 31.9973 | West Amman | Roof Top | sami mahmud ahmad smarh | 06/5158021 0799222546/0788358584/ | Pole P9 + P6 | 21 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266887 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution/solved not clear antenna soluation/solved Need to change the ACOC location to the other side of the CT on the same concrete./solved |  | Approved | We will proceed as Sectors A & B just ... no need for c as indoor solution |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
5912 | 5912-Tche_Tche_Sweifieh_PD_Fiber_TASC |  | AMW-629-R | Indoor | 201 | 35.8655 | 31.9487 | South Amman | Roof Top | eali ahmad ayuwb rjb | 079-5103301 | Tower T 16 | 28 | Part of P1 | Phase-2 | Batch_12 | Cluster-59 |  | Traditional | SMP-WO-1221106 | R&D | R&D | 47759364 | Done |  |  |  | 5G | [5 empty] | Approved | Wrong power solution - Changed the proposal for the power solution to 'need new rectifier./solved |  | Approved |  |  | Approved | solved\ mech tilt data doesn't match the photos |  | Approved | civil table not as the standard // determine the new installation on each pole location, Qty's and height updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
3210 | 3210-Sweileh_PA_Fiber_TASC |  | AMW-325-G | Indoor | 388 | 35.8418 | 32.0056 | West Amman | Green Field | eabd aljalil fahd alkayid alsalamat alskr | 06/5341143 079/6981400 | Tower T 60 | 21 | Part of P1 | Phase-2 | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1221052 | R&D | R&D | 47759362 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved | Wrong power solution/solved need to updgrade the AC meter |  | Approved |  |  | Approved |  |  | Approved | BTS Summary missing | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-04 | Yes | W44 |  | 787 |  |  | Approved
122 | 122-Cozmo_Back_PSD_PF_TASC_O |  | AMW-817-R | Outdoor |  | 35.8535 | 31.9503 | South Amman | Roof Top | mudiriat al amn aleamm |  | Tower T 12 | 22 | Part of P1 | Phase-2 | Batch_15 | Cluster-1 |  | Traditional | SMP-WO-1221030 | R&D | R&D | 47759355 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ Sector B & C azimuth is wrong |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
4010 | 4010-Comodore_PE_TASC |  | AME-289-R | Indoor | 226 | 35.8947 | 31.9791 | West Amman | Roof Top | muhamad rady eabd alfattah albshtawy | 06/5510903 | Pole P6*4+Tripod 2.5m*1 | 22 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1295734 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved | need to updgrade the AC meter |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
4028 | 4028-Rasheed_4_PB_Fiber |  | AMW-819-R | Indoor | 1732 | 35.8943 | 31.9975 | West Amman | Roof Top | faris alzubaydi | 079-5189922/079-9882074 | Pole P9 X 2 + P6 X 2 | 15 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1295753 | Al-Lewan | Desert |  | Done |  |  |  | 5G | [5 empty] | Approved | Not Modified !! (Still with the same notes ) // No need 5G solution for SEC A / Need clear general photos for the rectifier and CBs capacity to definite the BLLVD & LLVD and use the available CB accordingly |  | Approved | bore sector A is close from B , also increase sector c height |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
4029 | 4029-Hadath_Back_Market_PE_Fiber_TASC_O |  | AMW-1016-R | Outdoor |  | 35.8932 | 31.9864 | West Amman | Roof Top | farahan khalid muhamad mahmud | 0795579692/0792573321 | Pole P9#2 | 24 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1295768 | Al-Lewan | Desert |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | pictures for sector B & C not clear |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-09 | Yes | W45 |  | 782 |  |  | Approved
4007 | 4007-Amman_Stadium_PC_Fiber_TASC |  | AMW-426-R | Indoor | 465 | 35.8981 | 31.9863 | West Amman | Roof Top | eabdallah hasan iibrahim alluwzi |  | Pole P6 X 3 | 19 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266876 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
4006 | 4006-Rabieh_PA_Fiber_TASC |  | AMW-468-R | Indoor | 111 | 35.8866 | 31.9801 | West Amman | Roof Top | eabd alfattah eabd alghaniu tablt |  | Tower T 16 | 17 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266875 | SMART |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | number of DP's all zeros'!! in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
3622 | 3622-Iskan_AbuRagheb_PE_TASC |  | AME-677-R | Indoor | 1602 | 35.9196 | 31.8995 | South Amman | Roof Top | ahmad muhamad saeid husayn salh | 078-8738993/079-9701553 | Tower T 12 | 28 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221076 | TAWSEAA | TWASEAA | 47734292 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-16 | Yes | W46 |  | 775 |  |  | Approved
2026 | 2026-Banafsaj_Hall_PB_Fiber_TASC |  | AMW-168-R | Indoor | 347 | 35.8601 | 31.9997 | West Amman | Roof Top | muhamad husayn eali bani hani | 06/5353530 079/6792555/079-7412887/078-555122 | Tower T 12 + P6 X 1 | 27 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266825 | SMART |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-30 | Yes | W44 |  | 792 |  |  | Approved
4004 | 4004-Safeway_TL_PD_GPON_TASC |  | AME-288-R | Indoor | 34 | 35.8929 | 31.9826 | West Amman | Roof Top | iismaeil eiash ahmad yusf | 06/5523520 079/5521768 | Pole P6 X 3 + P4 X1 + P3(Wall mounted) X 1 | 25 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281074 | SMART | SMART |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-05 | Yes | W45 |  | 786 |  |  | Approved
119 | 119-Barakah_Mall_1_PF_Manage_O |  | AMW-566-R | Outdoor |  | 35.866 | 31.9552 | South Amman | Roof Top | sharikat albarkat lilaistithmar waltijarat aleamat | 06-5808888 | Pole P6 X 2 | 24 | Part of P1 | Phase-2 | Batch_15 | Cluster-1 |  | Traditional | SMP-WO-1221029 | R&D | R&D | 47759353 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
4018 | 4018-Takhasosi_Hospital_PE_TASC |  | AME-297-R | Indoor | 264 | 35.8983 | 31.9792 | West Amman | Roof Top | eisam eabd allatif hasan hawash | 06/5662285 079/5467417 - 0 79/5403341 | Pole P6 X 6 | 22 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266885 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | in bts sector D antenna should not be swapped as it only has 2G , no need to swap to 10 port antenna |  | Approved | missing tower details in the civil sheet !!!! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
1601 | 1601-RSS_2_PE_Fiber_TASC |  | AMW-381-R | Indoor | 497 | 35.8809 | 32.0221 | West Amman | Roof Top | ziad fathi muhamad abu krsh | 0777-554423 | Pole P9X2+P6X2 | 16 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1281060 | R&D | R&D |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-09 | Yes | W45 |  | 782 |  |  | Approved
4022 | 4022-Sport_City_End_PE_Fiber_TASC_O |  | AMW-1015-R | Outdoor |  | 35.9033 | 31.9933 | West Amman | Roof Top | husni husayn | 0798052732/0795842298 | Pole P9#2 | 21 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281076 | SMART | SMART |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Mast 1 overloaded // need a new Mast to separate the proposed load // civil requirement new still need update (no need for DP's on Mast 1) 29/10 // 08 //11 no need for DP's on MAST1 //9/11 BTS summery not updated | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
1621 | 1621-Souq_Sultan_Auhod_St_PD_GPON_TASC_O |  | AMW-967-R | Outdoor |  | 35.8686 | 31.9993 | West Amman | Roof Top | sultan dayf allah muhamad alshuwbiki |  | Tower T 16 | 34 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266791 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
1636 | 1636-Arena_PF_TASC |  | AMW-174-R | Indoor | 8 | 35.8771 | 32.0005 | West Amman | Roof Top | sharikat alaryna lilaistithmarat alfunduqiat alsiyahiat |  | Pole Mast 6m#5+Mast 9m#1 | 23 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266800 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil sheet table not as the standard // determined the dismantle // new // reuse // each location +++ 29/10 civil table still not as the standard and not matched with the BTS sheet // updated 8/11 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-12 | Yes | W46 |  | 779 |  |  | Approved
1612 | 1612-Islamic_College_Rasheed_PF_TASC_O |  | AMW-647-R | Outdoor | 1576 | 35.8948 | 32.0126 | West Amman | Roof Top | kamal eabd alrahim eatana hykl | 079-5595552/079-9701593 | Pole P9 x 3 | 21 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266783 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | The BTS sheet does not match the civil sheet updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
4012 | 4012-UL_Sameh_Mall_Tawfiq_Bldg_PE_GPON_TASC_O |  | AMW-1105-R | Outdoor |  | 35.8843 | 31.9847 | West Amman | Roof Top |  |  | Pole P9#2 | 20 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266881 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
4014 | 4014-Safeway_Gardens_PF_EBand_TASC_O |  | AMW-611-R | Outdoor |  | 35.8953 | 31.9823 | West Amman | Roof Top | yusuf eabd alhamid muhamad alnasur | 079-9668448 | Pole P6X3 | 20 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266882 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
4017 | 4017-UL_Gardens_Souq_Shaker_Back_PF_EBand_TASC_O |  | AMW-1132-R | Outdoor |  | 35.8845 | 31.9911 | West Amman | Roof Top |  |  | Pole P9#2 | 21 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266884 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
2025 | 2025-Otoum_Complex_Gardens_St_PE_Fiber_CIBS_O |  | AMW-1048-R | Outdoor |  | 35.8787 | 31.9867 | West Amman | Roof Top | zayd muhamad tawfiq aleatuwm | 0795350150/0777747739 | Pole 9 | 24 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1266824 | SMART |  |  | Done |  |  |  | 5G |  | IBS-C |  |  |  | Approved |  |  | Approved | no excel sheet available |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-31 | Yes | W44 |  | 791 |  |  | Approved
1611 | 1611-Tlaa_AlAli_Shamali_PC_Fiber_TASC |  | AMW-153-R | Indoor | 52 | 35.8707 | 31.9958 | West Amman | Roof Top | eabd allah ealan mutlaq aleimayirat | 06/5522947/06-5516578 079-5522905/ | Pole P6 X 5 + P9 X 1 | 19 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266782 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-07 | Yes | W45 |  | 784 |  |  | Approved
1635 | 1635-Dahiet_Rasheed_5_PD_Fiber_TASC |  | AMW-739-R | Indoor | 1706 | 35.885 | 32.0032 | West Amman | Roof Top | sayid jarar bisifatih walia ealaa abnayih alqusr | 079-5582010 | Pole P6 X 3 | 17 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266799 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
1632 | 1632-Nivin_Rising_PF_EBand_TASC |  | AMW-170-R | Indoor | 187 | 35.8638 | 32.0138 | West Amman | Roof Top | hatim rashid saeid salh | 06/5166561 079/5514758-0797720997-0788842804 | Tower T 12 | 16 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266797 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | in future installation plan, antennas need to keep atleast 60 degrees apart in azimuth Solved\ Sector B 3G azimuth is wrong Solved\ some of azimuth values are wrong Solved\ 3G setor B is missing |  | Approved | new installation for Huawei Antenna !! | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-13 | Yes | W46 |  | 778 |  |  | Approved
1603 | 1603-Abu_AlHaj_PF_EBand_TASC_O |  | AMW-145-R | Outdoor |  | 35.88 | 32.0008 | West Amman | Roof Top | sami mustafaa muhamad mahmud | 06-5150956 079/5230078 | Pole P9 + P6 | 19 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266777 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ Sector A elec tilt photo is missing Solved\ mech tilt values are wrong |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-19 | Yes | W42 |  | 803 |  |  | Approved
3939 | 3939-Wadi_Seer_Back_PC_Fiber_TASC |  | AMW-496-R | Indoor | 1514 | 35.8415 | 31.9402 | South Amman | Roof Top | husam mustafaa eali qadadt | 079/5567837/0797226761 | Tower T 16 | 21 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221101 | TAWSEAA | TWASEAA | 47734341 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-07 | Yes | W45 |  | 784 |  |  | Approved
3909 | 3909-Wadi_Seer_PA_Fiber_TASC |  | AMW-118-G | Indoor | 310 | 35.829 | 31.9513 | South Amman | Green Field | eabd alqadir khalil iibrahim yasyn |  | Tower T 30 | 31 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221089 | TAWSEAA | TWASEAA | 47734310 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-11 | Yes | W45 |  | 780 |  |  | Approved
2011 | 2011-Wifaq_Gardens_PE_Fiber_TASC |  | AMW-332-R | Indoor | 405 | 35.8724 | 31.9928 | West Amman | Roof Top | eisam iibrahim yusif hasanan | 06-4753386/06-4881299 079-5521305 | Pole P5*1+P6*3+P9*1 | 19 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1281065 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ 4G data is not filled in the table Solved\ 4G sectors needs renaming (Sector A azimuth is 310 and B is 80). Correction: SA: 80 , SB: 235 , SC: 310 Solved\ we need the 3G (6port) antennas to match the new 10 port antennas azimuths. SA: 80 , SB: 235 , SC: 310 |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-19 | Yes | W42 |  | 803 |  |  | Approved
3904 | 3904-Wadi_Seer_2_PD_Fiber_TASC |  | AMW-567-R | Indoor | 1526 | 35.8374 | 31.9544 | South Amman | Roof Top | mashhur earif fadil altalafiha | 079-5123383 079-6847683 | Pole P9 X 3 + P6 X 1 | 21 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221086 | TAWSEAA | TWASEAA | 47734303 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved | Keep sector B as a wallmount |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor | 5 | A | Approved | Approved | 2023-11-15 | Yes | W46 |  | 776 |  |  | Approved
2005 | 2005-Tlaa_AlAli_2_PC_GPON_TASC |  | AMW-500-R | Indoor | 116 | 35.8759 | 31.9876 | West Amman | Roof Top | iismaeil eiash ahmad yusf |  | Pole P6 X 3 + P9 X 2 | 26 | Part of P1 | Phase-2 | Batch_18 | Cluster-20 |  | Traditional | SMP-WO-1281062 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-19 | Yes | W42 |  | 803 |  |  | Approved
3905 | 3905-Rawnaq_PD_Fiber_TASC |  | AMW-654-R | Indoor | 1577 | 35.8456 | 31.9509 | South Amman | Roof Top | sulayman mahmud khalil abu faruh | 06-5865442 079-6470717 | Tower T 12 | 24 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221087 | TAWSEAA | TWASEAA | 47734306 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
4046 | 4046-Omarieh_Sch_1_PE_Fiber_TASC |  | AMW-741-R | Indoor | 1699 | 35.8843 | 31.9881 | West Amman | Roof Top | sharikat al ahli liltaajir | 079-7211960/079-5088666 | Pole P6X3+P9 | 24 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281088 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-21 | Yes | W42 |  | 801 |  |  | Approved
1649 | 1649-Islamic_College_Rasheed_HQ_PF_EBand_O |  | AMW-1089-R | Outdoor |  | 35.891 | 32.0169 | West Amman | Roof Top |  |  | Pole P9#2 | 12 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266804 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | solved\ mech tilt data doesn't match the photos |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-19 | Yes | W42 |  | 803 |  |  | Approved
3923 | 3923-Wadi_Seer_Ind_PA_Fiber_TASC |  | AMW-129-R | Indoor | 313 | 35.8404 | 31.9461 | South Amman | Roof Top | mahfuz eabd allah eisaa eabd alkhaliq | 06/5527163 079-5116351 | Tower T 16 + P6 X 3 | 18 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221098 | TAWSEAA | TWASEAA | 47734334 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | missing DP's numbers in civil sheet | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-12 | Yes | W46 |  | 779 |  |  | Approved
1609 | 1609-Rasheed_3_PE_Fiber_TASC |  | AMW-151-R | Indoor | 385 | 35.8834 | 32.0041 | West Amman | Roof Top | may humday tawfiq abu alsamn | 077/490750 | Pole P6X4 + P9 | 16 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266780 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | update the civil requirements new to include the AQQL concrete base | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
3603 | 3603-Hitteen_South_Amman_Court_PE_O |  | AME-794-R | Outdoor |  | 35.9414 | 31.9072 | South Amman | Roof Top | ahmad euthman mustafaa alsharif | 079-5141077 | Pole P9*1+P6*2 | 21 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221069 | TAWSEAA | TWASEAA | 47734285 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ GSM data are missing |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-09 | Yes | W45 |  | 782 |  |  | Approved
3630 | 3630-South_CPLX_PC_Fiber_TASC |  | AME-647-R | Indoor | 1625 | 35.9323 | 31.9156 | South Amman | Roof Top | anwar muhamad iibrahim abu rahamat | 078-8320865 | Tower T 16 | 15 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221080 | UTC | UTC | 47733552 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | update the civil requirements new to include the ACOC concrete base | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-11 | Yes | W45 |  | 780 |  |  | Approved
3929 | 3929-Wadi_Seer_3_PE_Fiber_TASC |  | AMW-433-R | Indoor | 457 | 35.8387 | 31.9498 | South Amman | Roof Top | wasam ealia eabd alrahim abu eadi | 06-5852259 | Pole P6X4 | 21 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221100 | TAWSEAA | TWASEAA | 47734338 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ Sector B LTE is not AAU |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-15 | Yes | W46 |  | 776 |  |  | Approved
5623 | 5623-Uni_Msq_PC_Fiber_TASC |  | AMW-160-R | Indoor | 266 | 35.8672 | 32.0195 | West Amman | Roof Top | razzan ridwan almaeany | 795552550 | Tower T 6 | 28 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281102 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-21 | Yes | W47 |  | 770 |  |  | Approved
4009 | 4009-Gardens_St_PF_Fiber_TASC |  | AMW-196-R | Indoor | 153 | 35.8852 | 31.9854 | West Amman | Roof Top | eabd alhadi bajis eabd alhady |  | Pole P6*3 | 21 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266878 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil table not as the standard | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved
4003 | 4003-Orchida_PC_EBand_TASC |  | AME-283-R | Indoor | 22 | 35.8916 | 31.9781 | West Amman | Roof Top | wilyam iibrahim asead haniyna |  | Tower T 16 | 19 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281073 | SMART | SMART |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | the solution to install Antennas at height 9 meters on a 3 meters Mast C not applicable | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
3610 | 3610-Um_AlHeiran_Post_PD_EBand_TASC |  | AME-68-R | Indoor | 96 | 35.9321 | 31.9071 | South Amman | Roof Top | yusuf mahmud duesan bidawanan | 06/4789313 079-5560058 | Pole P9 X 1 + P6 X 3 | 14 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221073 | TAWSEAA | TWASEAA | 47734287 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | number of free deport arm need to be updated | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
1613 | 1613-Doctors_HSG_2_PD_Fib er_TASC_Relo_O |  | AMW-1081-R | Outdoor |  | 35.8792 | 32.0179 | West Amman | Roof Top | hsin muhamad mustafaa abu farh | 079-9942075/078-5586283 | Tower T 20 | 20 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266784 | Al-Lewan |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-09 | Yes | W45 |  | 782 |  |  | Approved
3908 | 3908-Souq_Bayader_PE_GPON_TASC_O |  | AMW-677-R | Outdoor | 1598 | 35.8332 | 31.9527 | South Amman | Roof Top | amin aljaludi | 06-5810532 079-5539971 | Tower T 12 | 19 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221088 | UTC | UTC | 47733573 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | consider the following azimuths. 0/180/255 |  | Approved |  |  | Approved | check the antennas dimensions in civil sheet and update the BTS summery with Antennas height | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
4020 | 4020-Gardens_Barakeh_PE_Fiber_TASC |  | AMW-760-R | Indoor | 1685 | 35.8887 | 31.9904 | West Amman | Roof Top | ghassan farahan dhyab hadad | 079-6595838 | Pole P9 + P6 | 18 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266886 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | the Mast overloaded // reduce the load by shifting Antennas to the existing tower Approved after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-30 | Yes | W44 |  | 792 |  |  | Approved
1630 | 1630-Dustur_Back_PE |  | AMW-750-R | Indoor | 1689 | 35.8811 | 31.9973 | West Amman | Roof Top | eabd alrahim mahmud fadal eabd alrahim wkyla | 06-5603320 079-9740439 | Pole P9#2 | 21 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266795 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-13 | Yes | W46 |  | 778 |  |  | Approved
1628 | 1628-Uni_Bridge_PC_Fiber_TASC |  | AMW-537-R | Indoor | 1511 | 35.8665 | 32.0071 | West Amman | Roof Top | kamilat fakhri eurufat eabd alrazzaq ahmad shahin | 06/5332677 0777/863062 | Tower T 12 | 30 | Part of P2 | Phase-2 | Batch_20 | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266794 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Conditionally approved, used 1.5 m DP for 5G antenna. and install hexagon #4 for ACOC cabinet | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-11 | Yes | W45 |  | 780 |  |  | Approved
3670 | 3670-Souq_Mugabalein_PE_EBand_TASC_O |  | AMS-229-R | Outdoor |  | 35.9124 | 31.9024 | South Amman | Roof Top | eatifunmukhalideudat eabd rbh falh alduruwe | 06-4204433 079-5847141 | Tower T 20 | 27 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221084 | UTC | UTC | 47733569 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-29 | Yes | W44 |  | 793 |  |  | Approved |  |  |  |  | Downloaded
5638 | 5638-Jordan_Uni_King_Abdullah_College_PF_EBand_TASC_O |  | AMW-887-R | Outdoor |  | 35.8723 | 32.0141 | West Amman | Roof Top | aljamieat al urduniyat | 06-5355000 | Pole P6*3 | 18 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281105 | SMART | SMART |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-01 | Yes | W44 |  | 790 |  |  | Approved
5624 | 5624-North_Uni_Gate_PC_Fiber_TASC |  | AMW-161-R | Indoor | 58 | 35.8736 | 32.0229 | West Amman | Roof Top | hasan waeabd alhalim muhamad ealia alluwzi | 06/5336166 - 06/5344172 | Tower T 12 + P6 | 16 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281103 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Azimuth data is wrong |  | Approved | add civil requirement new sheets | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-12 | Yes | W46 |  | 779 |  |  | Approved
4011 | 4011-Sport_City_PD_Fiber_TASC |  | AME-290-R | Indoor | 254 | 35.9036 | 31.9902 | West Amman | Roof Top | dhib kamil ahmad khamys | 06/4635249 - 06/5151797 079-5314341 | Tower T 10.55 + WallMount 3m | 19 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1266880 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | approved after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
5639 | 5639-Radar_Sweileh_PE_GPON_TASC_O |  | AMW-571-R | Outdoor |  | 35.8537 | 32.013 | West Amman | Roof Top | nahil musaa eabdallah mhamd | 079-5060324 | Pole P6X3 | 6 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281106 | SMART | SMART |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-02 | Yes | W44 |  | 789 |  |  | Approved
5603 | 5603-Jordan_Uni_HQ_PE_EBand_TASC |  | AMW-801-R | Indoor | 402 | 35.8695 | 32.0161 | West Amman | Roof Top | aljamieat alardniat | 06-5355000 | Pole P6*3 | 15 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281094 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Mast 2 not 15 meters | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-21 | Yes | W47 |  | 770 |  |  | Approved
3910 | 3910-Narjes_PD_Fiber_TASC |  | AMW-119-R | Indoor | 288 | 35.8434 | 31.9568 | South Amman | Roof Top | eabdallah eabd al ilh shakiran | 06-5859790 079-5104088 | Tower T 16 | 18 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221090 | UTC | UTC | 47733575 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | Used same 6 port antenna for 2G/3G/4G S.B at height 10m from the Low antenna, and Az=76. & increase mechanical 2 degress in the existing * Add new DP for AQQL Ant (5G) at height 10 m from the Low antenna, and Az=76. |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-11 | Yes | W45 |  | 780 |  |  | Approved
5630 | 5630-Jordan_Uni_Parking_PF_EBand_TASC |  | AMW-802-R | Indoor | 403 | 35.8721 | 32.0197 | West Amman | Roof Top | aljamieat alardniat | 06-5355000 | Pole P6X2+P4+P2 | 21 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281104 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-12 | Yes | W46 |  | 779 |  |  | Approved
4042 | 4042-Rasheed_Link_PC_Fiber_TASC |  | AMW-179-R | Indoor | 346 | 35.8965 | 31.9933 | West Amman | Roof Top | muhamad muhiu aldiyn abu lghd | 0795420528 - 0795524742 | Tower T 12 + P6 X 3 | 23 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281086 | Cellcom |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved | Mech tilt data not filled in the table Azimuths for 2G and 3G are different while they are using the same antenna 3G sector B azimuth pic is blocked by the pole All 360 photos are shifted |  | Approved | Double check the 10ports antenna dimensions | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-25 | Yes | W43 |  | 797 |  |  | Approved
3606 | 3606-Rawdhah_Ras_Ain_PF_TASC_O |  | AMS-122-R | Outdoor |  | 35.916 | 31.9218 | South Amman | Roof Top | mahmud eisaa jabiril abrahim | 0796661902/0795656692 | Tower T 20 | 20 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221070 | UTC | UTC | 47733530 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | increase sector B height |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
5611 | 5611-Nivin_Rising_End_PE_Fiber_TASC |  | AMW-657-R | Indoor | 1583 | 35.8566 | 32.0196 | West Amman | Roof Top | eisam nahad sadiq enbtawy | 06-5359224 079-6645848 | Pole P9*3+P6*1 | 18 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281097 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | we willdismantle exsisting 4 port antenna for (2G/3G/4G) S.B at height 20 m from the heigh instead of 15.5 Sector B Add new AQQL Ant (5G) on same new Dp 3m at height 20 m from the high antenna, and Az= 155 |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
3623 | 3623-Zohour_Crown_Back_PD_Fiber_TASC_O |  | AMS-95-R | Outdoor |  | 35.9195 | 31.9139 | South Amman | Roof Top | samih mustafaa muhamad abu earh | 06/5697867 077767734/ | Tower T 16 | 25 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221077 | UTC | UTC | 47733544 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | Missing remarks about the 5G solution |  | Approved |  |  | Approved | note for RF planning) check the possibility to reduce the height of 2 antennas to 6 meters instead of 7.5 meters to reduce the load and avoid TASC rejection // | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-30 | Yes | W44 |  | 792 |  |  | Approved
5612 | 5612-Jubaiha_Municipality_JU_PD_Fiber_TASC |  | AMW-762-R | Indoor | 1714 | 35.8655 | 32.023 | West Amman | Roof Top | eali eabd alkarim ealia alluwzi | 079-6805533 | Pole P6 X1 + P9 X 3 | 18 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281098 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | increase sector A height to 10 increase sector B height 10 Increase sector C Height 12 |  | Approved | Azimuth data in the table doesn't match with the photos |  | Approved | Civil sheet & civil requirement new & BTS not for the same site // rejected again same note approved 5-10 | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor | 5 | A | Approved | Approved | 2023-10-26 | Yes | W43 |  | 796 |  |  | Approved
2564 | 2564-UL_Princess_Sumaya_Uni_PF_EBand_TASC_O |  | AMW-1122-R | Outdoor |  | 35.876 | 32.0236 | West Amman | Roof Top |  |  | Pole P9#2 | 18 | Part of P2 | Phase-2 | Batch_22 | Cluster-25 |  | Traditional | SMP-WO-1298989 | Cellcom | PIS>>Cellcom |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-11-12 | Yes | W46 |  | 779 |  |  | Approved
3607 | 3607-Mugabalein_Ind_2_PE_TASC |  | AME-418-R | Indoor | 1502 | 35.8886 | 31.9078 | South Amman | Roof Top | muhamad naji muhamad alqaq | 777461343 | Pole P6X5 | 21 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1221071 | UTC | UTC | 47733533 | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved | Azimuth data in the table doesn't match with the compass photos mech tilt data doesn't match with the incline meter photos |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
235 | 235-Wadi_Saqra_Traffic_PB_Fiber_TASC |  | AMW-89-R | Indoor | 17 | 35.8852 | 31.9654 | West Amman | Roof Top | iibrahim ahmad musaa duraghimatan washarkawuh | 06-5603035 | Pole P9 X 1 + P6 X 3 +P2.75 X 1 | 16 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266770 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | Sector B 3G and 4G azimuth should be the same value because it's the same antenna |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
207 | 207-Rahbat_Alwardieh_PE_Fiber_TASC |  | AMW-69-R | Indoor | 122 | 35.8931 | 31.9655 | West Amman | Roof Top | muasasat tanmiat amwal alaytam | 06/5934310 | Pole P9*1+P6*2 | 18 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266764 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | civil table not as the standard // Swap or reuse the Antennas | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
243 | 243-Abilla_PC_Fiber_Zain_TASC |  | AMW-92-R | Indoor | 31 | 35.8978 | 31.963 | West Amman | Roof Top | euday asead eali ased | 06/5924413 - 06/5694181 079/5527449 | Tower T 12 | 32 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266771 | Al-Lewan | SMART>>Al Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Reduce the height of 10port & AQQL antenna on Mast 3 to 6 meters to reduce the load | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
218 | 218-Thaqafa_St_PF_TASC |  | AMW-695-R | Indoor | 169 | 35.9001 | 31.9706 | West Amman | Roof Top | khayriat dawud hasan khawrma | 06-5621857 077-6555001 | Tower T 12 | 22 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266766 | PIS |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | check structure , since 5G solution on 9m & the structure from TSSR is 6m mast |  | Approved | compass photos are pixilated, reupload please. |  | Approved | Why the needs of 2 DP's// please match the BTS sheet with civil table sheet. (no need to fill the tower section since the site is MASTS) approved 5-10 after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-01 | Yes | W40 |  | 821 |  |  | Approved
205 | 205-Shmeisani_PC_TASC |  | AMW-67-R | Indoor | 162 | 35.8981 | 31.9664 | West Amman | Roof Top | rajab hamzat eabbas dakiduk |  | Tower T- 6 + P2 | 20 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266762 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
4027 | 4027-Safeway_Shmeisani_PC_EBand_TASC |  | AME-305-R | Indoor | 144 | 35.899 | 31.9833 | West Amman | Roof Top | rbhy shakir hasan alkhatib | 079-9966124 | Tower T 12 | 12 | Part of P1 | Phase-2 | Batch_19 | Cluster-40 |  | Traditional | SMP-WO-1281081 | khalilAlOmari | Desert |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-24 | Yes | W43 |  | 798 |  |  | Approved
230 | 230-Zalatimo_Shmeisani_PF_Fiber_TASC_O |  | AMW-1040-R | Outdoor |  | 35.8937 | 31.9693 | West Amman | Roof Top | yusuf eawdah hamid eakluk | 0795521621/ | Tower T 16 | 27 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266768 | Cellcom | SMART>>Cellcom |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
201 | 201-Jordan_Hospital_PF_DIBS_Manage |  | AME-487-R | Indoor | 444 | 35.8997 | 31.9606 | West Amman | Roof Top | sharikat mustashfaa al urdun alhadiytha | 06-5620777/ 06-5607550 | Pole P6X3 | 18 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266761 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G |  | IBS-D |  |  |  | Approved |  |  | Approved | increase height of all the sector to the top |  | Approved |  |  | Approved | Need new Mast conditionally approved. the civil sheet shall be updated and matched with BTS one (as no new antennas will be added) | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
206 | 206-Wadi_Saqra_PC_Fiber_TASC |  | AMW-68-R | Indoor | 315 | 35.8896 | 31.9679 | West Amman | Roof Top | mahmud yusif mahmud abu khznt |  | Tower T 6 + P7 X 1 + P4 X 1 | 24 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266763 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | check Sec C azimuth since panorama picture 270 and antenna bore 200, where both have the same view increase height of all sectors to top |  | Approved |  |  | Approved | update the Antenna height on Mast B // insert the MW dim on civil table // | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-01 | Yes | W40 |  | 821 |  |  | Approved
245 | 245-Libyan_Embassy_2_PD_Fiber_TASC |  | AMW-548-R | Indoor | 1519 | 35.8894 | 31.9639 | West Amman | Roof Top | runuh juzif jaris alashrm | 079/6445738 | Pole P9 X 3 | 10 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266772 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
234 | 234-Itihad_Bank_Shmeisani_PF_AIBS_O |  | AMW-907-R | Outdoor |  | 35.9 | 31.9653 | West Amman | Roof Top | bank alatihad |  | Pole 4 | 5 | Part of 63 | Phase-2 | Batch_8 | Cluster-2 |  | Traditional | SMP-WO-1266769 | TAWSEAA | TWASEAA |  | Done |  |  |  | RAN Only |  | IBS-A |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-11 | Yes | W41 |  | 811 |  |  | Approved
3231 | 3231-Royal_Zone6_Prince_PF_M |  | AMW-508-R | Micro Cell | 3231-Royal_Zone6_Prince_PF_M | 35.8233 | 31.9825 | Amman | Pole | Royal_Zone_6_Mini_VIP |  | Unknown yet - TBD | 18 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1285746 | Al-Lewan |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved |  |  | Approved | increase height of all the sector to the top |  | Approved |  |  | Approved | Antennas dim//Check the tower Height// civil sheet does not exist Notes modified. | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-16 | Yes | W46 |  | 775 |  |  | Approved
5501 | 5501-North_King_Abdullah_Gardens_PD_O |  | AMW-867-R | Outdoor |  | 35.8866 | 31.9718 | West Amman | Roof Top | eabd aljabbar muhsin dhiab alkabisi | 06-5659130/06-5659131 079-7210209 | Pole P6+P9 | 21 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266903 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved | increase all sector to top of the mast |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
5502 | 5502-Mawardy_PC_Fiber_TASC |  | AMW-208-R | Indoor | 279 | 35.8828 | 31.9727 | West Amman | Roof Top | iismaeil maseud saqf alhyt |  | Tower T 12 | 29 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266904 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | each mast two poles 9 meters // 4*9 meters poles | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5503 | 5503-Barq_PC_Fiber_TASC |  | AMW-217-R | Indoor | 40 | 35.8814 | 31.9677 | West Amman | Roof Top | ahmad kazim yusif alburqa | 06/5531732 - 06/5534352 - 06/5525831 077/454901 | Pole P6 X 2 + P9 X 1 + Wall mounted 3m Dp | 16 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266905 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved | Sector C azimuth is wrong the table , the right value is 220 |  | Approved | Check the civil table (MW dim) | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5504 | 5504-Rabieh_CRL_PE_GPON_TASC_O |  | AMW-573-R | Outdoor |  | 35.8822 | 31.9741 | West Amman | Roof Top | sharikat badr qutum washarakaha | 079-5615453/079-5600241 | Pole P6*2+P9*1 | 24 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266906 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | Mast A overloaded // redcue one sector height to 6 meters in order to reduce the load updated and approved | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Outdoor | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5508 | 5508-Rabieh_Shmeisani_TL_PD_GPON_TASC |  | AMW-751-R | Indoor | 1694 | 35.8871 | 31.9756 | West Amman | Roof Top | usamat aladrisy wayumthiluh adhum nabih namiq aladrisi | 06-5533939 079-5573434 | Pole P6 X4 | 23 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266907 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved | wrong Antenna dimensions // missing number of existing deport arms & tower foot print // approved after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5510 | 5510-Dahiet_Alhussein_PC_GPON_O |  | AMW-830-R | Outdoor |  | 35.8824 | 31.964 | West Amman | Roof Top | sami salim saeid eamysh | 079-5349595/079-5511170 | Tower T 20 | 24 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266908 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot | New Rect Indoor + Need to Add Batteries | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5512 | 5512-Um_Uthaina_2_PE_GPON_TASC_O |  | AMW-899-R | Outdoor |  | 35.8736 | 31.9704 | West Amman | Roof Top | saeid muhia aldiyn muhamad eisaa | 795349974 | Pole P9#2 | 18 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266909 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5514 | 5514-Chinese_Embassy_PD_GPON_TASC |  | AMW-200-R | Indoor | 134 | 35.8835 | 31.9772 | West Amman | Roof Top | faris sulti mikhayiyl qaqish |  | Tower T 12 | 18 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266910 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5516 | 5516-Kilo_3_PF_Fiber_O |  | AMW-1032-R | Outdoor |  | 35.8609 | 31.9751 | West Amman | Roof Top | eammar farahan hamadi hamady | 0798493566/0779194879 | Pole P9#2 | 32 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266911 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
5517 | 5517-Um_Al_Summaq_CTR_PE_GPON_TASC_O |  | AMW-1047-R | Outdoor |  | 35.8616 | 31.9783 | West Amman | Roof Top | eabd alddayim mthary salamih alnaeimat | 0797333330/0795722800 | Pole P6+P9 | 27 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266912 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5518 | 5518-Khalil_Rahman_PC_GPON_TASC |  | AMW-230-R | Indoor | 90 | 35.8627 | 31.9683 | West Amman | Roof Top | mahir muhamad mahmud zaynh |  | Tower T 12 | 25 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266913 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-15 | Yes | W42 |  | 807 |  |  | Approved
5519 | 5519-Rawabi_PE_GPON_TASC |  | AMW-697-R | Indoor | 155 | 35.8591 | 31.9655 | West Amman | Roof Top | falh khadir eubdallah abu alshyh | 06-5825723 079-5770740 | Pole P6 X 2 + P9 X 1 | 25 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266914 | R&D |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5520 | 5520-Marmara_Hotel_PF_TASC |  | AMW-231-R | Indoor | 207 | 35.8734 | 31.9735 | West Amman | Roof Top | tawfiq eadil tawfiq kanean | 06/5530480 079/5525636 | Pole P9X2+P6 | 24 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266915 | R&D |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved | No Tower with height 9 meters // pole not tower// Anntenas dim//civil table summery for the existing and proposed antennas | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
5522 | 5522-Um_Uthaina_1_PE_GPON_TASC |  | AMW-756-R | Indoor | 1672 | 35.8695 | 31.9711 | West Amman | Roof Top | eadnan kamal trky mhmd | 079-5576911 | Pole P6*2+P9*1 | 23 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266916 | khalilAlOmari |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
5523 | 5523-Mada_Data_CTR_PC_Fiber_TASC |  | AMW-2-R | Indoor | 103 | 35.8679 | 31.9642 | West Amman | Roof Top | eadil ahmad aldajani |  | Tower T 16 | 21 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266917 | khalilAlOmari |  |  | Done |  |  |  | 5G |  |  | Yes |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5530 | 5530-Um_Uthaina_PA_Fiber_TASC |  | AMW-238-R | Indoor | 18 | 35.8737 | 31.9672 | West Amman | Roof Top | ruwhi eabd aljalil ahmad alqtaby | 06/5624281 079-8830025 | Pole P9 X 3 + P6 X 3 + P5 X 1 | 24 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1282975 | khalilAlOmari | PIS>>Desert |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-12 | Yes | W41 |  | 810 |  |  | Approved
5531 | 5531-Baptist_Sch_PE_GPON_TASC_O |  | AMW-239-R | Outdoor | 1687 | 35.8763 | 31.9739 | West Amman | Roof Top | siham rslan hamzat almuadhin | 06/5523032 079-5103030 | Pole P6*1+P9*2 | 24 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1282967 | khalilAlOmari | PIS>>Desert |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-30 | Yes | W39 |  | 822 |  |  | Approved
5542 | 5542-Bristol_PF_CIBS_O |  | AMW-338-R | Outdoor |  | 35.8766 | 31.9587 | West Amman | Roof Top | funduq brystul |  | Pole 6 | 20 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266923 | Al-Lewan |  |  | Done |  |  |  | RAN Only |  | IBS-C |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5533 | 5533-6th_CRL_PF_EBand_TASC |  | AMW-672-R | Indoor | 1587 | 35.871 | 31.9624 | West Amman | Roof Top | nayil jaris eaways msharbsh | 079-5550294 | Pole P9X2+P6X3 | 15 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266920 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5539 | 5539-5th_CRL_PC_Fiber_TASC |  | AMW-242-R | Indoor | 99 | 35.8794 | 31.9633 | West Amman | Roof Top | laylaa muhamad hamdunh | 65516045 | Tower T 12 | 24 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266921 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-30 | Yes | W39 |  | 822 |  |  | Approved
5541 | 5541-Um_Uthaina_Market_End_PE_GPON_O |  | AMW-876-R | Outdoor |  | 35.8765 | 31.9656 | West Amman | Roof Top | bahjat muharib zael alrramih | 0797728540 077555667 | Pole P6X2 | 26 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266922 | Al-Lewan |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5546 | 5546-Fishawi_PB_Fiber_TASC |  | AMW-243-R | Indoor | 210 | 35.8653 | 31.9684 | West Amman | Roof Top | eawdat eabd alfattah eawdat |  | Tower T 16 | 32 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266924 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5552 | 5552-Um_Uthaina_Emar_Back_PE_GPON_TASC_O |  | AMW-999-R | Outdoor |  | 35.8735 | 31.9628 | West Amman | Roof Top | ghassan sharif yusif alqubj | 0796108888/0791738888 | Pole P9#2 | 25 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266927 | TAWSEAA | TWASEAA |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved | Need the diameter of the electrical pole // check the dim of the existing Anntenas //existing Anntenas 1 duplicate // no 5G data | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
5555 | 5555-Kilo_CRL_PE_Fiber_O |  | AMW-1042-R | Outdoor |  | 35.8663 | 31.9742 | West Amman | Roof Top | sharikat alhajar alaswad lilaistithmarat aleaqaria | 0792860026/0799554660 | Pole P9X4 | 28 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266928 | SMART |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
5561 | 5561-Um_Uthaina_TL_PE_GPON_TASC_O |  | AMW-1060-R | Outdoor |  | 35.8781 | 31.9711 | West Amman | Roof Top | halih kamal husayn salamuha |  | Tower T 16 | 12 | Part of 63 | Phase-2 | Batch_9 | Cluster-55 |  | Traditional | SMP-WO-1266929 | R&D |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-02 | Yes | W40 |  | 820 |  |  | Approved
3650 | 3650-Mugabalien_Mansour_Sch_Top_PF_Fiber_TASC_O |  | AMS-259-R |  |  | 35.8891 | 31.8967 | Amman | Mast 9m |  |  | Unknown yet - TBD | 9 | Part of P1 | Phase-2 | Batch_17 | Cluster-36 |  | Traditional | SMP-WO-1285732 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-09 | Yes | W45 |  | 782 |  |  | Approved
3920 | 3920-UmAlSous_2_PD_Fiber_TASC |  | AMW-692-R | Indoor | 172 | 35.8196 | 31.9538 | South Amman | Roof Top | eabd alwahhab sueud falah albadarin | 06-5814501 0777-238021/0777714911 | Tower T 16 | 31 | Part of P1 | Phase-2 | Batch_16 | Cluster-39 |  | Traditional | SMP-WO-1221096 | R&D | R&D | 47759363 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-02 | Yes | W44 |  | 789 |  |  | Approved
5932 | 5932-Philadelphia_Sch_PC_Fiber_TASC |  | AMW-27-R | Indoor | 282 | 35.8577 | 31.9449 | South Amman | Roof Top | mflh muhamad hamid qreumh |  | Tower T 16 | 28 | Part of P1 | Phase-2 | Batch_12 | Cluster-59 |  | Traditional | SMP-WO-1221107 | UTC | UTC | 47733607 | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
3510 | 3510-UL_P_Canadian_Embassy |  | AMW-1171-P | Electricity Pole |  | 35.8882 | 31.9573 | Amman | Pole |  |  | Electicity Pole | 0 | Part of P1 | Phase-2 | Micro Cell | Cluster-35 |  | Traditional | SMP-WO-1285897 | ElecticityPole |  |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved | GF NOT RT // JEPCO POLE diameters // Antenna Dimension (in m)20.570512134!!//civil table summary for the existing and proposed antennas //civil new requirements | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-06 | Yes | W45 |  | 785 |  |  | Approved
3201 | 3201-UL_P_Khalda_Massa_Back_Complex |  | AMW-1167-P | Electricity Pole |  | 35.5069 | 31.5949 | Amman | Mast 9m |  |  | Electicity Pole | 9 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1285744 | ElecticityPole |  |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved | GF NOT RT!! // JEPCO pole diameter!!//Antenna Dimension!!//civil table summary for the existing and proposed antennas //civil new requirements | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-30 | Yes | W44 |  | 792 |  |  | Approved
952 | 952-UL_P_Kursy_Back_PE_GPON |  | AMW-965-P | Electricity Pole |  | 35.8192 | 31.9624 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-9 |  | Traditional | SMP-WO-1266775 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-15 | Yes | W33 |  | 502 |  |  | Approved
3608 | 3608-Nader_Group_PF_M |  | AME-630-P | Micro Cell |  | 35.8993 | 31.9172 | Amman | Mast 9m | Jordanian Electricity Company |  | Electicity Pole | 9 | Part of P1 | Phase-2 | Micro Cell | Cluster-36 |  | Traditional | SMP-WO-1285729 | Al-Lewan | Al-Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
3617 | 3617-UL_P_Benayat_Hasad_Sch_PE_GPON |  | AMS-86-P | Micro Cell |  | 35.8972 | 31.8884 | Amman | Pole | Jordanian Electricity Company |  | Electicity Pole | 12 | Part of P1 | Phase-2 | Micro Cell | Cluster-36 |  | Traditional | SMP-WO-1285730 | Al-Lewan | Al-Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
265 | 265-P_Shmeisani_Pizza_PF |  | AMW-96-P | Electricity Pole |  | 35.9004 | 31.9672 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-2 |  | Traditional | SMP-WO-1265382 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-28 | Yes | W39 |  | 824 |  |  | Approved
905 | 905-P_Manaseer_HQ_Back_PE_GPON |  | AMS-8-P | Electricity Pole |  | 35.8433 | 31.9634 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-9 |  | Traditional | SMP-WO-1266774 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
1618 | 1618-U_P_Rasheed_College_Top_PF_FiberNode |  | AMW-1098-P | Electricity Pole |  | 35.8884 | 32.0164 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P2 | Phase-2 | Micro Cell | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1266788 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-15 | Yes | W33 |  | 502 |  |  | Approved
1633 | 1633-P_Amman_International_Hotel_PE_GPON |  | AMW-885-P | Electricity Pole |  | 35.8678 | 32.0107 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P2 | Phase-2 | Micro Cell | Cluster-16 | Tlaa Al Ali | Traditional | SMP-WO-1281061 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
2013 | 2013-P_Cambridge_Back_PE_GPON |  | AMW-539-P | Electricity Pole |  | 35.885 | 31.9816 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-20 |  | Traditional | SMP-WO-1281069 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
2033 | 2033-UL_P_Nishan_CRL_PE_GPON |  | AME-1055-P | Electricity Pole |  | 35.8653 | 31.9983 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-20 |  | Traditional | SMP-WO-1281070 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
2205 | 2205-P_Dur_Manthour_Back_PE_GPON |  | AMW-596-P | Electricity Pole |  | 35.86 | 31.9848 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-22 |  | Traditional | SMP-WO-1281071 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
2212 | 2212-U_P_Enviroment_Ministry_PE_GPON |  | AMW-696-P | Electricity Pole |  | 35.8701 | 31.9723 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-22 |  | Traditional | SMP-WO-1281072 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
2216 | 2216-UL_P_Khalda_Eng_Sch_Back_PE_GPON |  | AMW-1082-P | Electricity Pole |  | 35.8463 | 31.9851 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-22 |  | Traditional | SMP-WO-1266853 | PIS | PIS |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-22 | Yes | W38 |  | 830 |  |  | Approved
2230 | 2230-UL_P_AlRawabi_Ahoud_PE_GPON |  | AMW-1037-P | Electricity Pole |  | 35.8589 | 31.9676 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-22 |  | Traditional | SMP-WO-1266854 | PIS | PIS |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-21 | Yes | W38 |  | 831 |  |  | Approved
3213 | 3213-P_Howara_Rest_PE_GPON |  | AMW-630-P | Electricity Pole |  | 35.8364 | 32.0051 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266857 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-26 | Yes | W39 |  | 826 |  |  | Approved
3214 | 3214-P_Rabahieh_PE_GPON |  | AMW-939-P | Electricity Pole |  | 35.82 | 31.9803 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266858 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
3219 | 3219-P_Khalda_Sweileh_2_PE_GPON |  | AMW-446-P | Electricity Pole |  | 35.8509 | 32.0059 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266859 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
3224 | 3224-U_P_Howara_Dabouq_2_PE_GPON |  | AMW-546-P | Electricity Pole |  | 35.8262 | 31.9983 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266860 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
3234 | 3234-P_Khalda_WaterTank_PE_GPON |  | AMW-720-P | Electricity Pole |  | 35.852 | 32.0091 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266861 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
3246 | 3246-U_P_Dabouq_Vivid_Back_PE_GPON |  | AMW-928-P | Electricity Pole |  | 35.8269 | 32.0049 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266862 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-28 | Yes | W39 |  | 824 |  |  | Approved
3258 | 3258-P_Dabouq_Elba_House_Back_PE_GPON |  | AMW-1061-P | Electricity Pole |  | 35.8363 | 32.0121 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266863 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-16 | Yes | W42 |  | 806 |  |  | Approved
3259 | 3259-U_P_Dabouq_Mid_PE_GPON |  | AMW-1133-P | Electricity Pole |  | 35.8253 | 32.0052 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266864 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
3260 | 3260-P_Dabouq_Eagle_TL_PE_GPON |  | AMW-1029-P | Electricity Pole |  | 35.8168 | 31.9929 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-32 |  | Traditional | SMP-WO-1266865 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
3518 | 3518-U_P_Orthodoxy_Club_Back_PE_GPON |  | AMW-952-P | Electricity Pole |  | 35.8976 | 31.9493 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-35 |  | Traditional | SMP-WO-1266866 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
3520 | 3520-P_Abdoun_CRL_Back_PE_GPON |  | AMW-1067-R | Electricity Pole |  | 35.8937 | 31.9465 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-35 |  | Traditional | SMP-WO-1266867 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-21 | Yes | W38 |  | 831 |  |  | Approved
3525 | 3525-P_4th_CRL_PF |  | AME-143-P | Electricity Pole |  | 35.8999 | 31.9551 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-35 |  | Traditional | SMP-WO-1266868 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ sector C azimuth value is the same for different view for the antennas Solved\ Sector C mech tilt photo is the same for 3G/4G although antennas are different Solved\ north direction photo shows only the roof Solved\ 360 photos arent clear Solved\ in the BTS sheet, the sectors naming should go A,C and D clockwise with degrees |  | Approved | civil sheet not as the standard // add the existing DP's // what is the need for 3 DP// civil sheet reuse for no existing Antenna // Notes modified 14-11-2023 | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
3616 | 3616-P_Jabal_Hadeed_PE |  | AME-886-R | Electricity Pole |  | 35.9485 | 31.9099 | South Amman | Electricity Pole | jabal al hadded |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-36 |  | Traditional | SMP-WO-1266870 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
4016 | 4016-U_P_Rabieh_Hill_PE_GPON |  | AMW-891-P | Electricity Pole |  | 35.886 | 31.9812 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-40 |  | Traditional | SMP-WO-1281075 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
4023 | 4023-P_Rasheed_WaterTank_PE_GPON |  | AMW-714-P | Electricity Pole |  | 35.891 | 31.999 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-40 |  | Traditional | SMP-WO-1281077 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5509 | 5509-P_Rabieh_PE_GPON |  | AMW-625-P | Electricity Pole |  | 35.8806 | 31.9757 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-55 |  | Traditional | SMP-WO-1266925 | PIS | PIS |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-21 | Yes | W38 |  | 831 |  |  | Approved
5524 | 5524-U_P_Chinese_Embassy_Back_PE_GPON |  | AMW-890-P | Electricity Pole |  | 35.8813 | 31.9767 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-55 |  | Traditional | SMP-WO-1266926 | PIS | PIS |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-23 | Yes | W38 |  | 829 |  |  | Approved
5540 | 5540-U_P_Um_Uthaina_Back_PE_GPON |  | AMW-792-P | Electricity Pole |  | 35.8771 | 31.9637 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-55 |  | Traditional | SMP-WO-1266930 | PIS | PIS |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved | JEPCO Pole diameters // penetrated depth //Antenna Dimension (in m)131132389!!//civil table summary for the existing and proposed antennas //civil new requirements | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-19 | Yes | W38 |  | 833 |  |  | Approved
5547 | 5547-P_Arabic_CTR_PE_GPON |  | AMW-916-P | Electricity Pole |  | 35.8742 | 31.9605 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-55 |  | Traditional | SMP-WO-1281091 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5548 | 5548-P_Arabic_CTR_Back_1_PE_GPON |  | AMW-958-P | Electricity Pole |  | 35.8739 | 31.9593 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-55 |  | Traditional | SMP-WO-1281092 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved | GF NOT RT!! // JEPCO pole diameters!!//Antenna Dimension!!//civil table summary for the existing and proposed antennas //civil new requirements | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5549 | 5549-P_Arabic_CTR_Back_2_PE_GPON |  | AMW-959-P | Electricity Pole |  | 35.8735 | 31.9583 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-55 |  | Traditional | SMP-WO-1281093 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5619 | 5619-P_Sweileh_Fadhila_Ave_PE_GPON |  | AMW-1053-P | Electricity Pole |  | 35.8547 | 32.0173 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P2 | Phase-2 | Micro Cell | Cluster-56 |  | Traditional | SMP-WO-1281101 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5642 | 5642-UL_P_Nivin_Rising_PE_GPON |  | AMW-779-P | Electricity Pole |  | 35.8595 | 32.0182 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P2 | Phase-2 | Micro Cell | Cluster-56 |  | Traditional | SMP-WO-1281107 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5903 | 5903-P_Abdoun_Mall_Back_PE_GPON |  | AMW-827-P | Electricity Pole |  | 35.8793 | 31.9372 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266951 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-21 | Yes | W38 |  | 831 |  |  | Approved
5904 | 5904-P_Syrian_Embassy_PF |  | AMW-595-P | Electricity Pole |  | 35.8853 | 31.9372 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266952 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-21 | Yes | W38 |  | 831 |  |  | Approved
5905 | 5905-P_Rujm_Nawabelseh_PE_GPON |  | AMW-37-P | Electricity Pole |  | 35.8733 | 31.9385 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266953 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-21 | Yes | W38 |  | 831 |  |  | Approved
5908 | 5908-UL_P_Deir_Ghbar_Edge |  | AMS-333-P | Electricity Pole |  | 35.8586 | 31.9401 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266954 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-22 | Yes | W38 |  | 830 |  |  | Approved
5913 | 5913-P_Deir_Ghbar_Back_2_PF |  | AMW-749-P | Electricity Pole |  | 35.8621 | 31.9356 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266955 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-22 | Yes | W38 |  | 830 |  |  | Approved
5915 | 5915-P_Abdoun_End_PE_GPON |  | AME-616-P | Electricity Pole |  | 35.8796 | 31.9359 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266956 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-23 | Yes | W38 |  | 829 |  |  | Approved
5916 | 5916-P_Abdoun_Thraa_PE_GPON |  | AME-164-P | Electricity Pole |  | 35.8918 | 31.9357 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266957 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-22 | Yes | W38 |  | 830 |  |  | Approved
5917 | 5917-P_Deir_Ghbar_End_PF |  | AME-386-P | Electricity Pole |  | 35.8831 | 31.9363 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266958 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-23 | Yes | W38 |  | 829 |  |  | Approved
5918 | 5918-P_Abdoun_Thraa_2_PE_GPON |  | AMW-614-P | Electricity Pole |  | 35.8909 | 31.9352 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266959 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-21 | Yes | W38 |  | 831 |  |  | Approved
5927 | 5927-P_Prince_Hamzeh_Sch_PF |  | AMW-594-P | Electricity Pole |  | 35.8551 | 31.9214 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266960 | SMART | SMART |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | as per the meeting need better viewing system for pictures & data as its not clear, Data is misleading and random |  | Approved | JEPCO pole not Tower!// pole diameter //Antenna Dimension //civil table summary for the existing and proposed antennas //civil new requirements | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-07-03 | Yes | W27 |  | 911 |  |  | Approved
5648 | 5648-UL_Majdi_Mall_PD_GPON_BIBS_O |  | AMW-905-R | Outdoor |  | 35.8631 | 32.0194 | West Amman | Roof Top | sharikat abna majdi eabd alhadi washarakahum | 06-5338570 0795955115/0777660049 | --- --- | 21 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1281108 | khalilAlOmari | Desert |  | Done |  |  |  | 5G |  | IBS-B |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-11-14 | Yes | W46 |  | 777 |  |  | Approved
5929 | 5929-P_Taj_Mall_Bridge_PF |  | AMW-831-P | Electricity Pole |  | 35.8872 | 31.935 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266961 | KhalilAlOmari | Khalil Al Omari |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-26 | Yes | W39 |  | 826 |  |  | Approved
5933 | 5933-P_Malaysian_Embassy_PF |  | AMW-28-P | Electricity Pole |  | 35.8777 | 31.9378 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266962 | KhalilAlOmari | Khalil Al Omari |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-10-04 | Yes | W40 |  | 818 |  |  | Approved
5934 | 5934-P_Abdoun_AU_Embassy_PE_GPON |  | AMW-865-P | Electricity Pole |  | 35.8788 | 31.9332 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266963 | KhalilAlOmari | Khalil Al Omari |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  | Laith | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-26 | Yes | W39 |  | 826 |  |  | Approved
5937 | 5937-P_Abdoun_Thraa_Hananeh_PE_GPON |  | AMS-44-P | Electricity Pole |  | 35.8902 | 31.9339 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266964 | KhalilAlOmari | Khalil Al Omari |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  | Laith | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-26 | Yes | W39 |  | 826 |  |  | Approved
5940 | 5940-P_Duhair_Top_PF |  | AMW-781-P | Electricity Pole |  | 35.8505 | 31.9247 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266966 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-15 | Yes | W33 |  | 502 |  |  | Approved
5942 | 5942-U_P_Deir_Ghbar_SC_2_PE_GPON |  | AMW-941-P | Electricity Pole |  | 35.8668 | 31.9358 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266967 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
5943 | 5943-P_Little_Academy_Sch_PE_GPON |  | AMS-47-P | Electricity Pole |  | 35.8676 | 31.9457 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266968 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved | Solved\ no compass photo found for azimuths |  | Approved | fill all data for all masts 1,2,3,4 match it with civil table and BTS sheet // beside the dismantling & or reuse Need new pole and/or reduce sector A to 4m.. Approved after update | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-15 | Yes | W33 |  | 502 |  |  | Approved
5945 | 5945-UL_P_Sweifieh_PE_GPON |  | AMS-97-P | Electricity Pole |  | 35.869 | 31.947 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266969 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2023-09-29 | Yes | W39 |  | 823 |  |  | Approved
5946 | 5946-U_P_Malaysian_Embassy_Back_PE_GPON |  | AMS-109-P | Electricity Pole |  | 35.8745 | 31.9374 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266970 | Al-Lewan | Al Lewan |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved | 2024-08-15 | Yes | W33 |  | 502 |  |  | Approved
5949 | 5949-P_Everest_Back_PF |  | AME-748-P | Electricity Pole |  | 35.8701 | 31.9177 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281111 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5951 | 5951-U_P_Duhair_Keyali_PF |  | AMS-263-P | Electricity Pole |  | 35.8535 | 31.9223 | South Amman | Electricity Pole | olive tree hotel |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281112 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5952 | 5952-UL_Deir_Ghbar_PE_GPON_Relo_M |  | AMW-1126-P | Electricity Pole |  | 35.8597 | 31.9395 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281113 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5960 | 5960-UL_P_Everest_Back_2_PF |  | AMS-284-P | Electricity Pole |  | 35.8655 | 31.9139 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281114 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5964 | 5964-P_Kurdi_CPLX_PE_GPON |  | AMW-50-P | Electricity Pole |  | 35.875 | 31.9393 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281115 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5966 | 5966-P_Deir_Ghbar_5_PE_GPON |  | AMS-30-P | Electricity Pole |  | 35.8634 | 31.9449 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281116 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5967 | 5967-U_P_Deir_Ghbar_6_PE_GPON |  | AMS-31-P | Electricity Pole |  | 35.8614 | 31.9451 | South Amman | Electricity Pole | lajnat khadamat mukhayam alzarqa | 05/3937224 079/5972616/0795926029 | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281117 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5973 | 5973-U_P_Deir_Ghbar_Olive_Back_1_PE_GPON |  | AMS-278-P | Electricity Pole |  | 35.8582 | 31.9418 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281118 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5974 | 5974-U_P_Deir_Ghbar_Olive_Back_2_PE_GPON |  | AMS-279-P | Electricity Pole |  | 35.8616 | 31.9425 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281119 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [5 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 | A | Approved | Approved |  | Yes | W0 |  | 46021 |  |  | Approved
5975 | 5975-UL_P_Deir_Ghbar_Olive_Back_3_PE_GPON |  | AMS-280-P | Electricity Pole |  | 35.8602 | 31.9413 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281120 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5976 | 5976-U_P_Deir_Ghbar_Sodqi_Msq |  | AMS-306-P | Electricity Pole |  | 35.8621 | 31.9379 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1281121 | ElecticityPole | Electicity Pole |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5939 | 5939-P_Abdoun_Noqul_2_PE_GPON |  | AMW-778-P | Electricity Pole |  | 35.887 | 31.9386 | South Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1266965 | KhalilAlOmari | Khalil Al Omari |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2023-09-29 |  | W39 |  | 823 |  |  | Approved
938 | 938-Future_Home_PA_Fiber_IBS |  | AMW-136-R | IBS |  | 35.8449 | 31.9717 | Amman | IBS |  |  | IBS (Indoor) |  | Part of P1 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1285738 | Al-Lewan | Al-Lewan |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved | [10 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 2 |  | Approved | Approved | 2023-11-22 | Yes | W47 |  | 769 |  |  | Approved
3516 | 3516-Orthodoxy_Back_PF_UMN_M |  | AMW-955-R | Micro Cell |  | 35.9002 | 31.9473 | Amman | Pole | iismaeil muhamad mustafaa rady | 0777824222/0799478203 |  | 12 | Part of P1 | Phase-2 | Micro Cell | Cluster-35 |  | Traditional | SMP-WO-1285896 | Al-Lewan |  |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2023-12-03 |  | W49 |  | 758 |  |  | Approved
5935 | 5935-U_Malaysian_Embassy_2_PF_M |  | AMW-758-R | Micro Cell |  | 35.8767 | 31.9373 | Amman | Pole | alsifarat almaliziat |  | Unknown yet - TBD | 12 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1285895 | Al-Lewan |  |  | Done |  |  |  | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2023-12-03 |  | W49 |  | 758 |  |  | Approved
1257 | 1257-UL_Ayla_Souq_2_PF_Fiber_IBS_O |  |  |  |  | 34.9908 | 29.5449 | Aqaba | [6 empty] | Phase-2 | AQABA | Cluster-12 |  | Traditional | No TSS SMP | TAWSEAA |  |  | Done |  |  |  | 5G |  | IBS | [8 empty] | Laith |  |  | Rabie Otoum |  |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
1270 | 1270-UL_Ayla_Souq_PF_Fiber_IBS_O |  |  |  |  | 34.9908 | 29.5449 | Aqaba | [6 empty] | Phase-2 | AQABA | Cluster-12 |  | Traditional | No TSS SMP | TAWSEAA |  |  | Done |  |  |  | 5G |  | IBS | [8 empty] | Laith |  |  | Rabie Otoum |  |  | Omar Qaqish & Yousef Al-Natour | Approved | Akram Elturk / Ahmad Al-khateeb |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5907 | 5907-Duhair_PF_M |  | AMW-591-R | Micro Cell |  | 35.8531 | 31.9252 | Amman | Tower 16m |  |  | Electicity Pole | 16 | Part of P1 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1285741 | khalilAlOmari | Desert |  | Done |  |  |  | RAN Only | [13 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2023-10-16 |  | W42 |  | 806 |  |  | Approved
5920 | 5920-Taj_Mall_2_PF_Fiber_IBS |  | AMW-690-R | IBS |  | 35.8873 | 31.9408 | Amman | IBS |  |  | IBS (Indoor) |  | Part of P1 | Phase-2 | Batch_12 | Cluster-59 |  | Traditional | SMP-WO-1285739 | khalilAlOmari | Desert |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved | [7 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 2 |  | Approved | Approved | 2023-11-21 | Yes | W47 |  | 770 |  |  | Approved
5643 | 5643-Jordan_Uni_Eng_PF_M |  | AMW-803-R | Micro Cell |  | 35.8755 | 32.0097 | Amman | Pole | aljamieat alardniat | 06-5355000 | Microcell | 12 | Part of P2 | Phase-2 | Batch_21 | Cluster-56 |  | Traditional | SMP-WO-1285737 | Cellcom |  |  | Done |  |  |  | 5G | [5 empty] | Approved |  |  | Approved |  |  | Approved |  | Rabie Otoum | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 |  | Approved | Approved | 2023-11-20 | Yes | W47 |  | 771 |  |  | Approved
5921 | 5921-Taj_Mall_2_PF_Fiber_IBS |  | AMW-639-R | IBS |  | 35.887256 | 31.940791 | Amman | IBS |  |  | IBS (Indoor) |  | Phase-2 | Phase-2 | Micro Cell | Cluster-59 |  | Traditional | SMP-WO-1308653 | khalilAlOmari |  |  | Done | [5 empty] | IBS | [11 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved | 2023-11-22 |  | W47 |  | 769 |  |  | Approved
903 | 903-Zain_3_PC_Fiber_IBS_O |  | AMW-574-R | Outdoor |  | 35.845 | 31.9629 |  |  |  |  | Unknown yet - TBD |  | Part of P1 | Phase-2 | Batch_11 | Cluster-9 |  | Traditional | SMP-WO-1285740 | khalilAlOmari | Desert |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 5 |  | Approved | Approved | 2023-11-20 | Yes | W47 |  | 771 |  |  | Approved
3245 | 3245-Queen_Rania_Office_PF_IBS_O |  | AMW-894-R | IBS |  | 35.8224 | 31.9845 | Amman | IBS |  |  | IBS (Indoor) |  | Part of P1 | Merged | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1285734 | Al-Lewan |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved | [10 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 2 |  | Approved | Approved | 2023-11-16 | Yes | W46 |  | 775 |  |  | Approved
3251 | 3251-Royal_Zone6_King_PF_IBS_O |  | AMW-508-R-CO-2 | IBS |  | 35.8236 | 31.9841 | Amman | IBS |  |  | IBS (Indoor) |  | Part of P1 | Merged | Batch_14 | Cluster-32 |  | Traditional | SMP-WO-1285736 | Al-Lewan |  |  | Done |  |  |  | 5G |  | IBS |  |  |  | Approved | [10 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 2 |  | Approved | Approved | 2023-11-16 | Yes | W46 |  | 775 |  |  | Approved
5102 | 5102-Wihdat_PC_Fiber_TASC |  | AME-202-R | Indoor | 317 | 35.9316 | 31.9291 | East Amman | Roof Top | hatim khalil eabd alfattah aldaghili |  | Tower T 6 | 18 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5103 | 5103-Zohour_Haraj_PE_Fiber_TASC_O |  | AME-789-R | Outdoor |  | 35.9298 | 31.9273 | East Amman | Roof Top | khalil muhamad khalil mtr | 079-5583870/079-7441695 | Tower T 12 | 24 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 | [6 empty] | Done | [20 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021
5122 | 5122-Qweismeh_Ind_PE_Fiber_TASC |  | AME-599-R | Indoor | 1529 | 35.944 | 31.9197 | East Amman | Roof Top | salman jalal salman alqahiwaa | 079/5680139 | Pole P6*4 | 34 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 |  | Traditional | SMP-WO-1342109 | Cellcom |  |  | Done | [20 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5124 | 5124-King_Abdullah_Stadium_PD_Fiber_TASC |  | AME-220-R | Indoor | 127 | 35.9476 | 31.9221 | East Amman | Roof Top | fuzi eabd rbh ahmad alqadirabu alriysh | 06/4751793 079/5216599 | Tower T 12 | 21 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 |  | Traditional | SMP-WO-1342116 | Cellcom |  |  | Done | [20 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021 |  |  | Approved
5125 | 5125-Middle_East_Qweismeh_Ind_PF_EBand_TASC_O |  | AME-1037-R | Outdoor |  | 35.9416 | 31.917 | East Amman | Roof Top |  |  | Pole P9#2 | 24 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 |  | Traditional | SMP-WO-1342117 | Cellcom |  |  | Done | [20 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | TSSR Under Subcon validation |  |  | W0 |  | 46021 |  |  | Approved
5130 | 5130-Dabaibeh_PC_Fiber_TASC |  | AME-226-R | Indoor | 93 | 35.9347 | 31.9251 | East Amman | Roof Top | muhamad sulayman yusif abu qawtah | 06/4781691 079/5924424 | Pole P6 X 3 | 24 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 | [6 empty] | Done | [6 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Approved | Approved |  |  | W0 |  | 46021
5132 | 5132-Jabal_Hadeed_1_PC_Fiber_TASC |  | AME-228-R | Indoor | 30 | 35.9489 | 31.9188 | East Amman | Roof Top | khalil salim ahmad abu nashish | 06/4737415 079/5565491/0798997080 | Pole P3 X 1 + P6 X 4 + Wall mount | 34 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 |  | Traditional | SMP-WO-1342117 | Cellcom |  |  | Done | [6 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | TSSR Under Subcon validation |  |  | W0 |  | 46021 |  |  | Approved
5133 | 5133-Wihdat_Shop_PC_Fiber_TASC |  | AME-229-R | Indoor | 331 | 35.9355 | 31.93 | East Amman | Roof Top | yasir eabd alruhmin musaa alnajar | 079/5660269 | Pole P6 X 6 + P9 X 1 | 18 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-51 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5307 | 5307-Electricity_HSG_Back_PF_O |  | AME-827-R | Outdoor |  | 35.9646 | 31.91 | South Amman | Roof Top | yasin muhamad falah nasr allah alhaniyti | 077-2000195 | Pole P6*1+P9*2 | 12 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-53 | [13 empty] | Yes | [7 empty] | Omar Sami | [5 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5308 | 5308-MSC_3rd_Location_PA_FiberNode |  | AME-575-R | Indoor |  | 35.9688 | 31.9057 | South Amman | Green Field | MSC 3rd location |  | Tower 18 | 30 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-53 | [13 empty] | Yes | [7 empty] | Omar Sami | [5 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5321 | 5321-AbuAlanda_PA_Fiber_TASC |  | AME-78-R | Indoor | 2 | 35.9618 | 31.9019 | South Amman | Green Field | eabd alwahhab iibrahim rashid alhaniti |  | Tower T 30 | 30 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-53 | [13 empty] | Yes | [7 empty] | Omar Sami | [5 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5323 | 5323-AbuAlanda_Gardens_PD_Fiber_TASC_Relo_O |  | AME-1056-R | Outdoor |  | 35.9558 | 31.9081 | South Amman | Roof Top | muhamad khalid muhamad hasan zghlwan | 079-542288-079-5639591 | Pole P9 x 3 | 21 | ThinLayer | Trial Thin Layer | Trial Thin Layer | Cluster-53 | [13 empty] | Yes | [7 empty] | Omar Sami | [5 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
2219 | 2219-UL_Mecca_Mall_PE_Fiber_IBS_Manage |  | AMW-371-R | [10 empty] | ThinLayer | PO.2 | Trial Thin Layer | Cluster-9 |  |  | SMP-WO-1285898 | Lewan | Al-Lewan | [19 empty] | Karam Jaber & Akram Abdelrahim |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | 1 | Waiting Access Letter | 46021
303 | 303-U_P_Turkish_Embassy_PF |  | AME-911-P | Electricity Pole |  | 35.917 | 31.9518 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-3 |  |  |  | ElecticityPole | Electicity Pole | [19 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole | 2024-03-03 04:54 |  | W10 |  | 666.7957
310 | 310-P_Jordan_Hotel_PF |  | AME-545-P | Electricity Pole |  | 35.9137 | 31.9524 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-3 |  |  |  | ElecticityPole | Electicity Pole | [16 empty] | Baher Obaidat |  |  | Thabet Jaradat & Ahmad Hajdawood |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole | 2024-03-03 04:54 |  | W10 |  | 666.7957
316 | 316-P_2nd_CRL_PF_EBand |  | AME-14-P | Electricity Pole |  | 35.9157 | 31.9512 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-3 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole | 2024-03-03 04:54 |  | W10 |  | 666.7957
338 | 338-P_Foreign_Ministry_PF |  | AME-36-P | Electricity Pole |  | 35.9077 | 31.9538 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-3 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
341 | 341-UL_P_Delta_Ind_Comp_PF |  | AME-1093-P | Electricity Pole |  | 35.9085 | 31.956 | East Amman | Electricity Pole |  |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-3 |  |  |  | ElecticityPole | Electicity Pole | [19 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
358 | 358-P_3rd_CRL_PF |  | AME-51-P | Electricity Pole |  | 35.9112 | 31.954 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-3 |  |  |  | ElecticityPole | Electicity Pole | [19 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
502 | 502-P_Dabouq_Top_PF |  | AMW-507-P | Electricity Pole |  | 35.8085 | 31.9935 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [19 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
505 | 505-U_P_Hummar_Fuheis_PF |  | BLQ-126-P | Electricity Pole |  | 35.7906 | 32.0044 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [19 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
510 | 510-P_Mahis_Civil_Defence_PF |  | AMW-1064-P | Electricity Pole |  | 35.7736 | 31.9846 | West Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [19 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
512 | 512-P_Mahis_Palace_PF |  | AMW-634-P | Electricity Pole |  | 35.7779 | 31.9882 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [19 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
513 | 513-U_P_Haddad_Factory_M_PF |  | BLQ-264-P | Electricity Pole |  | 35.7519 | 32.0012 | Balqa | Electricity Pole |  |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
514 | 514-P_Fuheis_Bachaloria_Sch_PF |  | AMW-686-P | Electricity Pole |  | 35.8046 | 32.0048 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
542 | 542-U_P_Fuheis_PF |  | AMW-791-P | Electricity Pole |  | 35.8046 | 32.0059 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
558 | 558-P_Fardous_2_PF |  | AMW-105-P | Electricity Pole |  | 35.8039 | 31.9936 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
559 | 559-UL_P_Fuheis_North_Market_PF_FiberNode |  | BLQ-188-P | Electricity Pole |  | 35.7933 | 32.0022 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
561 | 561-P_Mahis_PF_FiberNode |  | BLQ-55-P | Electricity Pole |  | 35.7702 | 31.9962 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
562 | 562-P_Dar_Barakeh_PF |  | AMW-106-P | Electricity Pole |  | 35.7944 | 31.9923 | Balqa | Electricity Pole |  |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
573 | 573-P_Mahis_Secondary_Sch_PF |  | BLQ-223-P | Electricity Pole |  | 35.7665 | 31.9941 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
579 | 579-U_P_Bachaloria_Sch_Back_PF |  | BLQ-216-P | Electricity Pole |  | 35.8006 | 31.9991 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
582 | 582-P_Fuheis_Royal_Palace_Back_PE |  | BLQ-209-P | Electricity Pole |  | 35.8032 | 32.0087 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
588 | 588-P_Dabouq_Bachaloria_CRL_PF |  | BLQ-241-P | Electricity Pole |  | 35.8087 | 32.0028 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-5 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
681 | 681-U_P_AbuAlanda_Top_PF |  | AMS-243-P | Electricity Pole |  | 35.9688 | 31.9005 | South Amman | Electricity Pole |  |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-6 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
2730 | 2730-P_Rainbow_Fifty_Six_PF |  | AME-756-P | Electricity Pole |  | 35.9294 | 31.9467 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-27 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
3785 | 3785-UL_P_Salt_Um_Naaj_Bridge_PF |  | BLQ-228-P | Electricity Pole |  | 35.7942 | 32.0251 | Balqa | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-37 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole | 2023-07-03 |  | W27 |  | 911
4828 | 4828-P_South_Hashmi_Rising_PF |  | AME-703-P | Electricity Pole |  | 35.9489 | 31.9618 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-48 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
5106 | 5106-P_Qweismeh_Municipality_PF |  | AME-654-P | Electricity Pole |  | 35.9531 | 31.9162 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-51 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
5204 | 5204-P_Lizen_Sch_PF_FiberNode |  | AME-868-P | Electricity Pole |  | 35.9142 | 31.9987 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-52 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
5211 | 5211-P_Queen_Alia_Hospital_PF |  | AME-1030-P | Electricity Pole |  | 35.9182 | 32.0016 | East Amman | Electricity Pole | mudir eami alkhadamat altibiyat almalakiat |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-52 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
5230 | 5230-P_Hay_Qatanah_PF |  | AME-1020-P | Electricity Pole |  | 35.9164 | 31.9988 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-52 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
5234 | 5234-UL_P_Royal_Police_Academy |  | AME-1098-P | Electricity Pole |  | 35.921 | 32.0067 | East Amman | Electricity Pole |  |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-52 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
5251 | 5251-U_P_Tareq_Khazneh_End_PF |  | AME-913-P | Electricity Pole |  | 35.9253 | 32.0048 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-52 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
5262 | 5262-U_P_Military_CMD_Tabarbour_PF |  | AME-919-P | Electricity Pole |  | 35.954 | 32.0011 | East Amman | Electricity Pole | Jordanian Electricity Company |  | Electicity Pole | 6 | Low Priority |  |  | Cluster-52 |  |  |  | ElecticityPole | Electicity Pole | [22 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
3550 | 3550-UL_P_4th_CTR_M |  | AMW-1157-P | Electricity Pole |  | 35.8937 | 31.9565 | West Amman | Electricity Pole |  |  | Electicity Pole | 6 | Part of P1 |  | Batch_2 | Cluster-35 |  |  | SMP-WO-1266869 | ElecticityPole | SMART | [5 empty] | RAN Only | [16 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed | 2023-09-21 |  | W38 |  | 831
209 | 209-Siemens_Abdali_PC_Fiber_TASC |  | AMW-71-R | Indoor | 376 | 35.8994 | 31.9637 | West Amman | Roof Top | nusuh muhamad ridaan mahmud bdyr | 06/5660073-06/5660093 | Pole P9 X 1 + P6 X 2 | 18 | Low Priority |  |  | Cluster-2 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
503 | 503-Princess_Muna_Palace_PF_O |  | AMW-577-R | Outdoor |  | 35.8206 | 32.0169 | West Amman | Roof Top | aldiywan almulkiu alhashimi | 06-4637341 | Pole 6 | 6 | Low Priority |  |  | Cluster-5 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
504 | 504-Fuheis_PA_Fiber |  | BLQ-171-G | Indoor | 1744 | 35.7899 | 31.9964 | Balqa | Green Field | najih birhim khalifat alziyadat | 06-4721809 0799135547/0796603263 | Tower T 60 | 60 | Low Priority |  |  | Cluster-5 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
511 | 511-UL_Mahis_East_PF_EBand_TASC_O |  | BLQ-263-R | Outdoor |  | 35.7727 | 31.9896 | Balqa | Roof Top |  |  | Tower T 16 | 22 | Low Priority |  |  | Cluster-5 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
521 | 521-Um_Ulaya_Monopole_PF_TASC_O |  | AMW-852-G | Outdoor |  | 35.7671 | 32.0068 | Balqa | Green Field | majlis baladiat alfuhays | 06-4729311 | Pole Monopole 24 | 30 | Low Priority |  |  | Cluster-5 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
524 | 524-National_Amman_Sch_PE_TASC |  | AMW-416-R | Indoor | 423 | 35.8089 | 31.9978 | West Amman | Roof Top | eyd shafiq salim sawis |  | Tower T 12 | 15 | Low Priority |  |  | Cluster-5 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
525 | 525-Fuheis_Kamalieh_Rd_PE_TASC |  | AMW-926-R | Indoor |  | 35.802 | 32.0139 | Balqa | Roof Top | shamaa qustandi tuhaymar alsawis | 06-4729354 772265656 | Tower T 16 | 25 | Low Priority |  |  | Cluster-5 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
526 | 526-Fuheis_CRL_PF_UMN_Manage_O |  | AMW-841-R | Outdoor |  | 35.7813 | 32.0039 | Balqa | Roof Top | Fuhais Circle |  | Tower T 12 | 18 | Low Priority |  |  | Cluster-5 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
534 | 534-Fuheis_Horse_CRL_PF_O |  | AMW-851-R | Outdoor |  | 35.7707 | 32.0008 | Balqa | Roof Top | baladiat alfuhays | 06-4729311 | Pole P6*3 | 18 | Low Priority |  |  | Cluster-5 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
544 | 544-Princess_Haya_Ave_Hummar_PF_TASC |  | AMW-771-R | Indoor | 1821 | 35.804 | 32.0249 | West Amman | Roof Top | muhamad yusif alsaayir alrashdan | 078-7464078 | Pole P9 x 3 | 15 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
554 | 554-Saint_Mary_Fuheis_PF_O |  | AMW-903-R | Outdoor |  | 35.778 | 32.0059 | Balqa | Roof Top | wadad farih salim buru | 795548207 | Pole P9 + P6 | 18 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
556 | 556-Fuheis_Mahis_CRL_PE_Fiber_TASC_O |  | AMW-900-R | Outdoor |  | 35.7764 | 32.002 | Balqa | Roof Top | muhamad mafadiy eisaa samawy | 0777960554/0795353663 | Pole P9#2 | 21 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
557 | 557-Fuheis_Rising_PD_Fiber_TASC_O |  | AMW-902-R | Outdoor |  | 35.7897 | 32.0024 | Balqa | Roof Top | walid sulayman yusif eakrush | 0795516000/0777619616 | Pole P6 X1 + P9 X 1 | 24 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
560 | 560-Zuwwadeh_Rest_PE_Fiber_TASC_O |  | BLQ-190-R | Outdoor |  | 35.7972 | 32.0026 | Balqa | Roof Top | sharikat tawfiq | 0798227821/0798530058 | Pole P9 X 1 + P4 X 1 | 19 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
563 | 563-Fuheis_Top_1_PF_Manage_O |  | AMW-107-R | Outdoor |  | 35.7721 | 32.0107 | Balqa | Roof Top | maryam salamat jamil fakhury | 06/4720608 079-6304410 | Pole P6 X 3 | 13 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
566 | 566-Hummar_Palace_Dabouq_PF_TASC_O |  | AMW-579-R | Outdoor |  | 35.8066 | 32.0076 | Balqa | Roof Top | sahaa iibrahim altarafan aldawd | 06-5411736 079-9053990 | Pole P6+P9 | 13 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
568 | 568-Fardous_3_PE_TASC |  | AMW-737-R | Indoor | 1654 | 35.8109 | 31.9869 | West Amman | Roof Top | dayf allah eabd alghanii alrafifat aldawaykata | 079-5795858 | Pole P9 x 3 | 17 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
569 | 569-Fardous_Gate_PF_TASC |  | AMW-730-R | Indoor | 1652 | 35.8024 | 31.9914 | Balqa | Roof Top | nsar faewr iibrahim alhumuwd | 06-5412245 079-6700663 | Pole P9 + P6 | 12 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
571 | 571-Fuheis_City_CTR_PE_Fiber_TASC_O |  | AMW-982-R | Outdoor |  | 35.7868 | 32.0056 | Balqa | Roof Top | saham nawir salim alnubr | 06/5155735 798125155 | Pole P9#2 | 18 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
572 | 572-UL_Fuheis_AbuDeeb_Ave_PE_Fiber_TASC_O |  | AMW-913-R | Outdoor |  | 35.7709 | 32.0076 | Balqa | Roof Top | warathat faris jaris mufdiin suis | 0772359800/0779960702 | Pole P6 | 18 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
575 | 575-Fuheis_Um_Ulayya_PF_O |  | AMW-915-R | Outdoor |  | 35.7665 | 32.003 | Balqa | Roof Top | shadi eawdih fudayan dawdan | 0776827090/079-5547442 | Pole P9 + P6 | 10 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
589 | 589-UL_Fuheis_Rahwa_HSG_PF_TASC_O |  | BLQ-255-R | Outdoor |  | 35.7794 | 32.0125 | Balqa | Roof Top |  |  | Pole P9#2 | 21 | Low Priority |  |  | Cluster-5 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
1702 | 1702-Qusor_Rd_2_PE_Fiber_TASC_O |  | AME-129-R | Outdoor |  | 35.9369 | 31.9634 | East Amman | Roof Top | eabd alhamid muhamad mansur alebadi | 06/4620291 077-9575896 | Pole P6 X 1 | 18 | Low Priority |  |  | Cluster-17 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
1706 | 1706-Nuzha_Oqbah_Jaber_St_PE_Fiber_TASC_O |  | AME-982-R | Outdoor |  | 35.9297 | 31.9676 | East Amman | Roof Top | muhamad th ahmad alsyd ahmd | 0795362131/0797772421/0799639644 | Pole P9#2 | 21 | Low Priority |  |  | Cluster-17 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
1713 | 1713-Jabal_Hussein_Police_PF_Fiber_O |  | AME-507-R | Outdoor | 1521 | 35.9235 | 31.9635 | East Amman | Roof Top | khalid hamid munyazil munyzl | 06-4640593 796971770 | Pole 4 | 11 | Low Priority |  |  | Cluster-17 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
1747 | 1747-Nuzha_AbuThar_Ghefari_PE_Fiber_TASC_O |  | AME-935-R | Outdoor |  | 35.9288 | 31.9653 | East Amman | Roof Top | asead khalil husayn qatnani | 0799251921/0799792729 | Pole P9#2 | 18 | Low Priority |  |  | Cluster-17 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
2714 | 2714-Jabal_Qusor_Core_PC_Fiber_TASC |  | AME-484-R | Indoor | 459 | 35.9397 | 31.9586 | East Amman | Roof Top | hasan khitab | 06-5810486 079-5501624 | Tower T 12 | 18 | Low Priority |  |  | Cluster-27 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
2716 | 2716-Qusor_Owais_Msq_PE_Fiber_TASC_O |  | AME-983-R | Outdoor |  | 35.9409 | 31.9573 | East Amman | Roof Top | sueud mustafaa eabd almajid aleksh | 0796915901/0785125320/0780746406 | Pole P9#2 | 18 | Low Priority |  |  | Cluster-27 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
2718 | 2718-Qusor_Imam_Shafi_Sch_PE_Fiber_TASC_O |  | AME-912-R | Outdoor |  | 35.9377 | 31.9599 | East Amman | Roof Top | eali asead ealia alsahlay | 0795602690/0795717657/0791470513 | Pole P6*3 | 18 | Low Priority |  |  | Cluster-27 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Electricity Pole |  |  | W0 |  | 46021
2762 | 2762-UL_Alweibedeh_Land_Survey_Directorate_M |  | AME-1090-P | Micro Cell |  | 35.9296 | 31.9564 | East Amman | Electricity Pole |  |  | Electicity Pole | 18 | Low Priority |  |  | Cluster-27 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4801 | 4801-Nayfeh_2_PD_Fiber_TASC |  | AME-604-R | Indoor | 1538 | 35.9431 | 31.9804 | East Amman | Roof Top | muhamad shafiq muhamad abu zyd |  | Tower T 12 | 16 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4802 | 4802-Hashmi_1_PA_Fiber_TASC |  | AME-94-R | Indoor | 302 | 35.9584 | 31.9703 | East Amman | Roof Top | majid eabd allah muhamad al amin almawmani | 06/4909099 079/5546932 | Pole P4+P6 X 2+P9 | 20 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4803 | 4803-Nayfeh_PD_Fiber_TASC |  | AME-95-R | Indoor | 285 | 35.9493 | 31.976 | East Amman | Roof Top | lawiyi muhamad yunis eulyan | 06/5518970 079/5515354 | Pole P9 X 3 + P6 X 2 + P3 X1 + P4 X 1 | 14 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4804 | 4804-Hashmi_2_PC_Fiber_TASC |  | AME-253-R | Indoor | 38 | 35.9554 | 31.9829 | East Amman | Roof Top | eadil ealia muhamad khaliyl | 06/5056808 079/5596358 | Pole P6 X 2+ P3 X 2 + P4X 1 | 19 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4805 | 4805-North_Hashmi_2_PC_Fiber_Zain_TASC |  | AME-97-R | Indoor | 301 | 35.968 | 31.9732 | East Amman | Roof Top | hnd muhamad zaki eabd aleal | 06/5058378 079-9373615 | Tower T 12& P6 x1 | 27 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4806 | 4806-Abu_Jassar_PD_Fiber_TASC |  | AME-613-R | Indoor | 1540 | 35.9598 | 31.9785 | East Amman | Roof Top | qahir khalid eabd alruhmn abu hashish | 06-5528807 079-5450300 | Tower T 12 | 18 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4807 | 4807-Istiqlal_St_End_PE_TASC_O |  | AME-788-R | Outdoor |  | 35.9496 | 31.9674 | East Amman | Roof Top | muhamad hasan muhamad shaykhh | 06-4917368 078-5315444/078-5304997 | Tower T 16 | 21 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4808 | 4808-Queen_Nour_Gardens_2_PC_EBand_TASC_O |  | AME-640-R | Outdoor |  | 35.9501 | 31.9648 | East Amman | Roof Top | iismaeil muhamad iibrahim aleimayarat | 06-4912590 079-6999808/0788-257247 | Pole P6 X 3 | 17 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4809 | 4809-Prince_Hamzeh_Hospital_Clinics_PF_EBand_CIBS_Manage |  | AME-657-R | Indoor | 1573 | 35.9376 | 31.9838 | East Amman | Roof Top | musshatfaa al amir hamzat |  | Pole P6 X 3 + Wallmounting 3m*1 | 14 | Low Priority |  |  | Cluster-48 | [12 empty] | IBS-C | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4810 | 4810-Prince_Hamzeh_Hospital_PF_BIBS_O |  | AME-657-R-CO | Outdoor |  | 35.9376 | 31.9836 | East Amman | Roof Top |  |  | Pole 9 | 22 | Low Priority |  |  | Cluster-48 | [12 empty] | IBS-B | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4811 | 4811-Mutawasta_College_PC_Fiber_TASC |  | AME-561-R | Indoor | 1501 | 35.9242 | 31.9918 | East Amman | Roof Top | eabd rawiq mkhaymr | 795677299 | Tower T 12 + P6 X 1 | 27 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4812 | 4812-Nayfeh_Hawouze_PE_O |  | AME-813-R | Outdoor |  | 35.9484 | 31.9788 | East Amman | Roof Top | muhamad eabd alhamid muhamad eali | 06-5053270 079-6285171 | Pole P6*1+P9*1+WallMounting9 | 21 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4813 | 4813-Souq_Hashmi_Istiqlal_PE_Fiber_TASC_O |  | AME-835-R | Outdoor |  | 35.949 | 31.9728 | East Amman | Roof Top | eaziz tamim naji yusf | 0797507771 / 0796666421 | Pole P9+P6X2 | 21 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4815 | 4815-North_Hashmi_Zahraa_PD_Fiber_TASC |  | AME-683-R | Indoor | 192 | 35.957 | 31.9649 | East Amman | Roof Top | warathat khalid sulayman yusif jaradatan | 06-4903756 079-5738837 | Pole P6 X 3 | 18 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4816 | 4816-North_Hashmi_PB_Fiber_TASC |  | AME-106-R | Indoor | 306 | 35.958 | 31.9754 | East Amman | Roof Top | muhamad eyd alfalah aleulyan albrayst | 06-50604334 079-5536564 | Tower T12 + P6 X 1 | 21 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4817 | 4817-North_Hashmi_3_PD_Fiber_TASC |  | AME-534-R | Indoor | 487 | 35.9599 | 31.9726 | East Amman | Roof Top | muhamad hamid muhamad albashyr | 06-4907886 079-5735399 | Tower T 12 | 24 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4818 | 4818-Marbat_Bridge_PE_Fiber_TASC_Relo_O |  | AME-1061-R | Outdoor |  | 35.9574 | 31.9679 | East Amman | Roof Top | sabah shafiq rashid khazaey | 06-4929281 079-6711279 | Tower T 12 | 24 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4819 | 4819-Nayfeh_3_PD_Fiber_TASC |  | AME-680-R | Indoor | 84 | 35.9476 | 31.9836 | East Amman | Roof Top | namuru eisaa namur abu alrb | 079-6389182 | Pole P6 X 3 | 18 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4820 | 4820-Gas_Station_2_PC_Fiber_TASC |  | AME-141-R | Indoor | 349 | 35.9312 | 31.9832 | East Amman | Roof Top | hasan eumar eiwad alramhi | 077/429371 777429371 | Pole P9 X 3 | 20 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4821 | 4821-South_Hashmi_Middle_PF_TASC_O |  | AME-828-R | Outdoor |  | 35.9525 | 31.9622 | East Amman | Roof Top | euthman eabdallah mahmud alearqan | 079-5355016/0788-141746 | Pole P6X2 | 18 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4822 | 4822-Aqsa_Ave_PD_Fiber_TASC |  | AME-691-R | Indoor | 53 | 35.9389 | 31.9745 | East Amman | Roof Top | yunis eisaa ahmad damaty | 06-5059369 079-5116669 | Pole P6 X 2+ P9 X 1 | 21 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4823 | 4823-Aqsa_St_PF_TASC |  | AME-692-R | Indoor | 322 | 35.9333 | 31.9796 | East Amman | Roof Top | najib hasan hamdan almady | 06-5671505 079-9588432/079-5787733 | Pole P6X2+P9 | 18 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4824 | 4824-UL_Tabarbour_PTE_East_PE_Fiber_TASC_O |  | AME-1076-R | Outdoor |  | 35.9382 | 31.9886 | East Amman | Roof Top | Jordanian Electricity Company |  | Tower T 12 | 21 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4825 | 4825-Hashmi_Anabtawi_PF_EBand_TASC |  | AME-711-R | Indoor | 1646 | 35.9531 | 31.9763 | East Amman | Roof Top | eabd alnnasir muhamad ahmad sarhan | 078-5335588/079-6516477 | Pole P6*2 | 17 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4826 | 4826-Hashmi_Zaghateet_PE_Fiber_TASC |  | AME-710-R | Indoor | 1647 | 35.9661 | 31.9766 | East Amman | Roof Top | muhamad eabd alrahmin muhamad eulyan | 079-9424522/078-7531235 | Pole P9 X 1 + P6 X 1 | 18 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4827 | 4827-Istiqlal_St_PC_Fiber_TASC |  | AME-115-R | Indoor | 357 | 35.9421 | 31.9723 | East Amman | Roof Top | muhamad ahmad ealan sarsur | 06/5679028 | Tower T 12 + P9 | 27 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4829 | 4829-Prince_Hamzeh_Back_PD_Fiber_TASC_O |  | AME-860-R | Outdoor |  | 35.9367 | 31.9805 | East Amman | Roof Top | eazizat muhamad hasan muhamd | 06-5652206 0795909903/0795675742 | Pole P9 X 1 + P6 X 1 | 19 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4830 | 4830-Souq_Hashmi_PE_Fiber_TASC_O |  | AME-839-R | Outdoor |  | 35.9535 | 31.9688 | East Amman | Roof Top | muhamad mahmud muhamad duqh | 0777913478/079-1515548 | Pole P9*1+WallMount9*1 | 21 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4831 | 4831-Prince_Hassan_Forest_Back_PF_TASC_O |  | AME-903-R | Outdoor |  | 35.961 | 31.9841 | East Amman | Roof Top | muhamad eiqab mustafaa aljawabirh | 0777102007/0795708687 | Pole P9X2+P6 | 24 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4832 | 4832-Hashmi_HSG_PD_Fiber_TASC_O |  | AME-920-R | Outdoor |  | 35.9626 | 31.9745 | East Amman | Roof Top | mustafaa iibrahim muhamad alnajar | 0795999128/0790778048 | Pole P9#2 | 21 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4833 | 4833-Hashmi_Shamali_PE_Fiber_TASC_O |  | AME-937-R | Outdoor |  | 35.9519 | 31.9714 | East Amman | Roof Top | arij iibrahim manahi albarayish | 796901860 | Pole P9#2 | 18 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4834 | 4834-Hashmi_Mahatta_Market_PE_Fiber_TASC_O |  | AME-949-R | Outdoor |  | 35.9608 | 31.9679 | East Amman | Roof Top | jamal saeid ahmad salh | 0796616673/0786605043/0795378084 | Pole P9#2 | 21 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4835 | 4835-Aqsa_Ave_Tabarbour_PD_Fiber_TASC_O |  | AME-933-R | Outdoor |  | 35.9475 | 31.9856 | East Amman | Roof Top | hisham muhamad ahmad abu bkr | 0799338840/0798773090 | Tower T 16 | 31 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4836 | 4836-Amaneh_Istiqlal_St_PF_TASC_O |  | AME-927-R | Outdoor |  | 35.9448 | 31.9681 | East Amman | Roof Top | amanat eamman alkubraa |  | Pole P9#2 | 18 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4837 | 4837-Aqsa_Ave_CTR_PE_TASC_O |  | AME-989-R | Outdoor |  | 35.9409 | 31.9772 | East Amman | Roof Top | zaki eawduh mahmud altaemury | 077785237/ | Tower T 16 | 27 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4838 | 4838-UL_Nayfeh_Hawouze_South_PE_Fiber_TASC_O |  | AME-1079-R | Outdoor |  | 35.9452 | 31.9765 | East Amman | Roof Top |  |  | Pole P9#2 | 21 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4840 | 4840-Souq_Hashmi_Back_PE_Fiber_TASC_O |  | AME-838-R | Outdoor |  | 35.9547 | 31.9734 | East Amman | Roof Top | husam hamdi eabdallah alejl | 079-5616747/079-5913121 | Pole P9#2 | 21 | Low Priority |  |  | Cluster-48 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4841 | 4841-PTE_PC_Fiber_TASC |  | AME-132-R | Indoor | 37 | 35.9358 | 31.9879 | East Amman | Roof Top | faris iibrahim faris abu rshydt | 06/5056110 079/5513853 | Pole P5 X 1 + P9 X 2 + P6 X 3 | 15 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4843 | 4843-Nayfeh_Tabarbour_PD_Fiber_TASC |  | AME-761-R | Indoor | 1701 | 35.9523 | 31.9812 | East Amman | Roof Top | husayn mahmud alshaykh mustafaa sabrh | 079-5623691 | Pole P9 X 1 + P6 X 1 | 15 | Low Priority |  |  | Cluster-48 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4902 | 4902-Gas_Station_PF_EBand_TASC |  | AME-125-R | Indoor | 248 | 35.9313 | 31.9757 | East Amman | Roof Top | eisaa eaqalah eubdallah alharahishh |  | Tower T 12 | 21 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4903 | 4903-Hussein_Camp_PE_Fiber_TASC_Relo_O |  | AME-1029-R | Outdoor | 250 | 35.923 | 31.9727 | East Amman | Roof Top | hasan mueawad hasan abwakwayk | 06/4626492 078-5017632 | Pole P9#2 | 29 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4904 | 4904-Nuzha_PA_Fiber_TASC |  | AME-127-R | Indoor | 19 | 35.925 | 31.9766 | East Amman | Roof Top | fayiz fahami muhamad askndrany | 795504053 | Tower T12 + D3 X 1 | 26 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4905 | 4905-Prince_Hassan_Ave_2_PD_Fiber_TASC |  | AME-537-R | Indoor | 493 | 35.9245 | 31.9824 | East Amman | Roof Top | ghazi hsin muhamad eanayt | 06/5660912 | Pole P6 X 2 + P9 X 1 | 22 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4907 | 4907-Prince_Hassan_Ave_4_PD_Fiber_O |  | AME-817-R | Outdoor |  | 35.9276 | 31.9817 | East Amman | Roof Top | sadiquh khamis eumar albilabisi | 079-9172640/079-5812747/079-6351207 | Pole P9 X 2 | 18 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4908 | 4908-Nuzha_CRL_PB_Fiber_TASC |  | AME-130-R | Indoor | 105 | 35.9296 | 31.971 | East Amman | Roof Top | muhamad ebdalmtlb eabdallah yaghy | 06/4615142 - 06/4646942 079-5539446/079-6926455 | Pole P9 X 1+ P6 X 4 | 18 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4909 | 4909-Hay_Aljarn_Arab_Academy_PF_EBand_Org_O |  | AME-921-R | Outdoor |  | 35.9258 | 31.9886 | East Amman | Roof Top | Prince_hasan_Avenue_Org |  | Tower 12 | 25 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4910 | 4910-Hay_Dewan_PD_Fiber_TASC |  | AME-144-R | Indoor | 85 | 35.9333 | 31.969 | East Amman | Roof Top | kamil muhamad flyfl | 06/4653772 | Pole P4 X1 + P3 X1 + P6 X1 | 21 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4911 | 4911-RHC_Rayah_PF_CIBS_Org_O |  | AME-879-R | Outdoor |  | 35.9412 | 31.9674 | East Amman | Roof Top | RHC rayah building |  | --- --- | 20 | Low Priority |  |  | Cluster-49 | [12 empty] | IBS-C | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4912 | 4912-Nuzha_CRL_2_PD_Fiber_TASC |  | AME-128-R | Indoor | 106 | 35.9281 | 31.9702 | East Amman | Roof Top | iibrahim eabd alrahmin khalil | 06/4628565 | Pole P6 X 1+ P3 X1 + Wallmounting dp(3m) x 2 | 18 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4913 | 4913-Aqsa_St_PSD_PF_TASC_O |  | AME-776-R | Outdoor |  | 35.931 | 31.9875 | East Amman | Roof Top | mudiriat al amn aleamm |  | Pole P9 + P6 | 16 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4914 | 4914-Jordan_St_2_PB_Fiber_Zain_TASC |  | AME-293-R | Indoor | 151 | 35.9137 | 31.9834 | East Amman | Roof Top | muhamad ealia zariqat | 06-5691091 079-790386 | Tower T 6 + P6 X 1 + P4 X 1 | 13 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4915 | 4915-Prince_Hassan_Ave_3_PF_TASC |  | AME-676-R | Indoor | 221 | 35.9272 | 31.979 | East Amman | Roof Top | eabd alrahim ahmad ealia hasan | 06-5681189 079-55603607 | Pole P6 X 2 | 19 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4916 | 4916-Qusor_Bridge_PD_Fiber_TASC |  | AME-702-R | Indoor | 1626 | 35.9345 | 31.9724 | East Amman | Roof Top | rbhy eabd alfattah musaa hamdan | 079-5556493/07777-67734 | Pole P6 X 3 | 18 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4917 | 4917-Haraj_Tabarbour_PD_Fiber_TASC |  | AME-701-R | Indoor | 1627 | 35.9186 | 31.9911 | East Amman | Roof Top | khalid saeid hasan abu alhija | 078-8346398/079-7940032 | Pole P9 X 1 + P6X2 | 21 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4918 | 4918-Royal_Hospital_PD_GPON_EIBS_O |  | AME-883-R | Outdoor |  | 35.9175 | 31.9892 | East Amman | Roof Top | Royal Hosptial | 06-5009000 | Pole 9 | 21 | Low Priority |  |  | Cluster-49 | [12 empty] | IBS-E | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4920 | 4920-Saraya_Mall_PE_Fiber_EFIBS_Manage_O |  | AME-837-R | Outdoor |  | 35.9235 | 31.9876 | East Amman | Roof Top | eimad tahir eabd alzaebi |  | Pole Wall mount x5+P6X1+P9x1 | IBS | Low Priority |  |  | Cluster-49 | [12 empty] | IBS-E | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4922 | 4922-UL_Arjan_Top_PE_GPON_TASC_O |  | AME-986-R | Outdoor |  | 35.9145 | 31.9869 | East Amman | Roof Top |  |  | Pole P9#2 | 21 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4924 | 4924-Hay_Aljarn_PD_Fiber_TASC |  | AME-269-R | Indoor | 178 | 35.9261 | 31.9853 | East Amman | Roof Top | riad ahmad salim alkuz |  | Pole P6 X 3 | 19 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4928 | 4928-Jordan_St_PC_Fiber_TASC |  | AME-306-R | Indoor | 364 | 35.9205 | 31.9834 | East Amman | Roof Top | muhamad ahmad saeid abu khrub | 079/5135025 | Tower T 12 | 24 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4929 | 4929-Jordan_St_Tunnel_PE_EBand_TASC |  | AME-307-R | Indoor | 381 | 35.9198 | 31.9788 | East Amman | Roof Top | wafa asead muhamad kharuf | 06/5678348 | Tower T 12 + P6 X2 | 24 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4930 | 4930-Nuzha_2_PD_Fiber_TASC |  | AME-147-R | Indoor | 295 | 35.9228 | 31.9758 | East Amman | Roof Top | ltfy eabd allatif khadir abu nahlat | 06/5677604 077/390422 | Pole P3 X 1 + P9 X 1 +P4 X 1 | 19 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4940 | 4940-Prince_Hassan_Hawooz_PE_Fiber_TASC_O |  | AME-947-R | Outdoor |  | 35.9228 | 31.985 | East Amman | Roof Top | warathat shaeban musaa drwaysh alzayn | 0795610857/0795595103/0795707469 | Pole WallMounting6*1+WallMounting9*1 | 18 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4941 | 4941-Mogherah_Msq_Istiqlal_PE_Fiber_TASC_O |  | AME-963-R | Outdoor |  | 35.9235 | 31.98 | East Amman | Roof Top | nabil eabdah iismaeil aleashi | 795803375 | Pole P6*2 | 21 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4942 | 4942-Prince_Hassan_Ave_PE_Fiber_TASC_O |  | AME-965-R | Outdoor |  | 35.9273 | 31.9905 | East Amman | Roof Top | eabd alrahmin eabdallah shakir eawdaha | 0799011613/0797801725/0795451117 | Pole P6#2 | 21 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4943 | 4943-Hay_Aljarn_Alola_Msq_PE_Fiber_TASC_O |  | AME-967-R | Outdoor |  | 35.9288 | 31.9848 | East Amman | Roof Top | nadir ahmad husayn aljaefari | 079880630/0790771978 | Pole P9 + P6 | 18 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4944 | 4944-Hussein_Camp_Nuzha_PE_Fiber_TASC_O |  | AME-968-R | Outdoor |  | 35.9259 | 31.9721 | East Amman | Roof Top | eubayr salim sulayman abu raman | 0795514962/0796669983 | Pole P9 x 3 | 18 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4945 | 4945-Istiqlal_Yarmouk_Club_PE_Fiber_TASC_O |  | AME-970-R | Outdoor |  | 35.9212 | 31.9817 | East Amman | Roof Top | fatimuh muhamad harb tarkhan | 0795704013/0790479072 | Pole P9#2 | 18 | Low Priority |  |  | Cluster-49 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4946 | 4946-Souq_Nuzha_PE_Fiber_TASC_O |  | AME-984-R | Outdoor |  | 35.9262 | 31.9738 | East Amman | Roof Top | mubarak ahmad musaa mnsi | 0797150008/0799689452 | Pole P9 + P6 | 22 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4948 | 4948-Jordan_St_Ifta_Rising_PE_Fiber_TASC_O |  | AME-985-R | Outdoor |  | 35.9227 | 31.9897 | East Amman | Roof Top | zyn muhamad ahmad mustafaa | 0795223322/0775223322/0795223322 | Pole P9 | 22 | Low Priority |  |  | Cluster-49 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
4955 | 4955-Istiklal_Hospital_PF_Fiber_AIBS_O |  | AME-1015-R | Outdoor |  | 35.916 | 31.9794 | East Amman | Roof Top | musshatfaa aunlistqlal | 06-5652600/0 | Pole 9 | 9 | Low Priority |  |  | Cluster-49 | [12 empty] | IBS-A | [14 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5101 | 5101-Middle_East_PB_Fiber_TASC |  | AME-201-R | Indoor | 158 | 35.9413 | 31.9256 | East Amman | Roof Top | fathi naeman eabd alrasul |  | Tower T 12 + P6 X 1 | 18 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5104 | 5104-Souq_Wihdat_PE_Fiber_TASC |  | AME-629-R | Indoor | 1676 | 35.9382 | 31.9328 | East Amman | Roof Top | nidal husayn eata samaratan | 06-4120680 079-6827227 | Pole P9 | 15 | Low Priority |  |  | Cluster-51 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5105 | 5105-Wihdat_Camp_PD_Fiber_TASC_O |  | AME-798-R | Outdoor |  | 35.9392 | 31.929 | East Amman | Roof Top | ahmad muhamad ebdallh hujuj | 079-9717089/079-5326172 | Pole P9 X 2 | 20 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5107 | 5107-Maadi_PE_Fiber_TASC_Relo_O |  | AME-1057-R | Outdoor |  | 35.9602 | 31.9201 | East Amman | Roof Top | bisam eata yusif aljabili | 06-4707064 077-6721818/079-6458042 | Pole P6 X 1 + P9 X 2 | 16 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5108 | 5108-Um_Tineh_CTR_PD_Fiber_TASC_O |  | AME-843-R | Outdoor |  | 35.9433 | 31.9341 | East Amman | Roof Top | wizarat al awqaf | 0796722980/0796999652 | Pole P9 X 1 + P6 X 1 | 21 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5109 | 5109-Jabal_Hadeed_3_PF_TASC_O |  | AME-209-R | Outdoor | 1550 | 35.9493 | 31.9152 | East Amman | Roof Top | iibrahim namuru mahmud alsywry | 06/4755410 | Pole P6*3+P9*1 | 15 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5110 | 5110-Sumaya_St_PE_Fiber_TASC_O |  | AME-664-R | Outdoor |  | 35.942 | 31.9326 | East Amman | Roof Top | ealia mustafaa husayn uyuban | 06-4777973 079-5771750/078-8625509 | Pole P6*2+WallMounting 3*1 | 13 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5111 | 5111-Zohour_HSG_PB_Fiber_TASC |  | AME-687-R | Indoor | 115 | 35.9281 | 31.9221 | East Amman | Roof Top | qamar iibrahim muhamad bani eta | 079-6285656/079-6213235 | Pole P6 X 3 | 22 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5112 | 5112-Aqsa_CPLX_Jabal_Hadeed_PF_TASC_O |  | AME-882-R | Outdoor |  | 35.9577 | 31.9114 | East Amman | Roof Top | muhamad yusif eali alsuwfany | 0796938586/0788010705 | Pole P9 + P6 | 11 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5113 | 5113-Jabal_Hadeed_4_PB_TASC |  | AME-684-R | Indoor | 167 | 35.9461 | 31.9137 | East Amman | Roof Top | muhamad rashid muhamad alhadiyd | 06-4166832 0777-941308 | Pole P6 X 3 | 18 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5114 | 5114-Nahareyeh_Qweismeh_PE_Fiber_TASC |  | AME-697-R | Indoor | 470 | 35.9489 | 31.9222 | East Amman | Roof Top | iibtsam mahmud sulayman abu ewdat | 079-5080076/079-9829473 | Pole P6 X 2 | 30 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5115 | 5115-UL_Jabal_Hadeed_Mada_PE_Fiber_TASC_O |  | AME-897-R | Outdoor |  | 35.9559 | 31.9197 | East Amman | Roof Top | eabd alfattah hasan mahmud alasmr | 079916829/0795699414 | Pole P9#2 | 13 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5116 | 5116-Jabal_Hadeed_5_PE_Fiber_TASC_O |  | AME-1023-R | Outdoor |  | 35.9482 | 31.9117 | East Amman | Roof Top | nbil eadil rashid 'abu alhalaw |  | Pole P9 + P6 | 22 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5117 | 5117-Wihdat_Club_Hikma_St_PE_Fiber_TASC_O |  | AME-869-R | Outdoor |  | 35.9368 | 31.9323 | East Amman | Roof Top | lajnat khadamat Camp alwahadat | 06/4779693 079/5571701/0799234004 | Pole P6 X 1 + P9 X 1 | 23 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5118 | 5118-Middle_East_Bridge_PC_Fiber_TASC |  | AME-1039-R | Indoor |  | 35.9378 | 31.9215 | East Amman | Roof Top | manirat salim khalil mararan |  | Pole P9 X 1 + P6 X 2 | 51 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5119 | 5119-UL_Wihdat_Camp_Middle_PF_EBand_TASC_O |  | AME-1051-R | Outdoor |  | 35.942 | 31.9297 | East Amman | Roof Top |  |  | Pole P9#2 | 22 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5120 | 5120-Zohour_CRL_PD_Fiber_TASC_O |  | AME-979-R | Outdoor |  | 35.9241 | 31.9212 | East Amman | Roof Top | amjad iismaeil eabdallah eawad | 795382625 | Pole P6X2 + P9 | 21 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [10 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5121 | 5121-Um_AlHeiran_Total_Back_PE_GPON_TASC_O |  | AME-974-R | Outdoor |  | 35.9326 | 31.9217 | East Amman | Roof Top | musaa muhamad eabd alrahmn tylkh | 0790890449/0795212176 | Pole P9 + P6 | 18 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5123 | 5123-Wihdat_Camp_Sahaba_Msq_PE_Fiber_TASC_O |  | AME-990-R | Outdoor |  | 35.9433 | 31.9272 | East Amman | Roof Top | mahir muhamad yusif alshaykh yusif | 077785237/ | Pole P6*2 | 20 | Low Priority |  |  | Cluster-51 | [24 empty] | Rabie Otoum |  |  | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5129 | 5129-Jabal_Hadeed_2_PC_Fiber_TASC |  | AME-225-R | Indoor |  | 35.9566 | 31.9171 | East Amman | Roof Top | ainshirah nizami muhamad khalyl | 079-5421272/0799725512 | Pole P6 X 3 + P9 X1 + Wall mounted Dp(3m) | 29 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5131 | 5131-Wihdat_Madaba_St_PE_Fiber_TASC_O |  | AME-783-R | Outdoor |  | 35.9377 | 31.928 | East Amman | Roof Top | khalf eabd rbh falh alduruwe | 079-5637018/0777-341309 | Pole P6X2 | 14 | Low Priority |  |  | Cluster-51 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5134 | 5134-Jabal_Hadeed_Civil_Defence_PD_Fiber_TASC |  | AME-763-R | Indoor | 1723 | 35.9554 | 31.9145 | East Amman | Roof Top | muhamad khayr iismaeil ahmad almisri | 079-5498922 | Pole P9 X 2 + P6 X 1 | 30 | Low Priority |  |  | Cluster-51 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5135 | 5135-UL_Wihdat_Camp_East_PE_O |  | AME-1109-R | Outdoor |  | 35.94 | 31.9342 | East Amman | Roof Top |  |  | Tower 16 | 25 | Low Priority |  |  | Cluster-51 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5177 | 5177-Wihdat_Gas_Station_PE_Org_O |  | AME-861-R | Outdoor |  | 35.9354 | 31.9335 | East Amman | Roof Top | wihdat gas station |  | Pole 9 | 21 | Low Priority |  |  | Cluster-51 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5201 | 5201-Khazneh_Ekhlas_Msq_PC_Fiber_TASC |  | AME-276-R | Indoor | 360 | 35.9236 | 31.9991 | East Amman | Roof Top | saedun jabir allaami |  | Pole P6 X 6 | 18 | Low Priority |  |  | Cluster-52 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5202 | 5202-Billeh_PE_EBand_Manage_O |  | AME-258-R | Outdoor | 45 | 35.9306 | 31.996 | East Amman | Roof Top | iilia taqula alblh |  | Tower T 16+ P6 | 13 | Low Priority |  |  | Cluster-52 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5208 | 5208-Tabarbour_Khazneh_PE_Fiber_TASC |  | AME-656-R | Indoor | 1581 | 35.9323 | 32.001 | East Amman | Roof Top | hasan ahmad salim alqamaza | 06-5055825 077-6883128/079-6883128 | Pole P9 X 2 | 18 | Low Priority |  |  | Cluster-52 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5213 | 5213-Tareq_Khazneh_PF_EBand_UMN_O |  | AME-800-R | Outdoor |  | 35.9247 | 32.0025 | East Amman | Roof Top | poice Acaemy Al khazneh |  | Pole 9 | 16 | Low Priority |  |  | Cluster-52 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5223 | 5223-Tareq_PSD_PE_Manage_O |  | AME-806-R | Outdoor |  | 35.9372 | 32.0129 | East Amman | Roof Top | mudiriat al amn aleamm |  | Pole Mast 6m#1 +Wall mount 3m+Mast 9m#1 | 15 | Low Priority |  |  | Cluster-52 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5224 | 5224-Tabarbour_TL_PD_EBand_TASC |  | AME-864-R | Indoor | 768 | 35.9449 | 31.989 | East Amman | Roof Top | sharikat firj albaydani | 796529191 | Pole P9 x 2 + P6 X 1 | 29 | Low Priority |  |  | Cluster-52 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5225 | 5225-Hashmi_MOH_PE_Fiber_TASC_O |  | AME-811-R | Outdoor |  | 35.9422 | 31.9855 | East Amman | Roof Top | ahmad walid dhiab alrafati | 079-5130937/079-6223068/079-8756830 | Pole P9 x 3 | 18 | Low Priority |  |  | Cluster-52 | [13 empty] | Yes | [13 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5226 | 5226-Tareq_2_PC_Fiber_TASC |  | AME-273-R | Indoor | 377 | 35.9323 | 32.0068 | East Amman | Roof Top | eali jawadt sari alsuwqy | 06/4905220 077/464763 + 0795885541 + 0788692046 | Pole P6 X 3 + P9 X 2 | 18 | Low Priority |  |  | Cluster-52 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  | Waiting Stakeholder FB | Site not surveyed |  |  | W0 |  | 46021
5229 | 5229-AbuAlia_5_PD_EBand_TASC_O |  | AME-810-R | Outdoor |  | 35.9691 | 32.0067 | East Amman | Roof Top | mahmud yaequb mahmud aljalwdy | 078-8280715/078-6107483/078-6764037 | Pole P9 X 3 | 21 | Low Priority |  |  | Cluster-52 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  |  | Site not surveyed |  |  | W0 |  | 46021
5255 | 5255-Haraj_Tabarbour_North_CPLX_PD_Fiber_TASC_O |  | AME-916-R | Outdoor |  | 35.9198 | 31.9966 | East Amman | Roof Top | warathat almarhum muhamad ahmad khalil eamran | 0796102282/07784130870/0795857982/0785886877/079534803 | Tower T 12 | 22 | Low Priority |  |  | Cluster-52 | [27 empty] | Omar Qaqish & Rahhal | Approved | Morad Jankhot |  | 1 |  |  | Site not surveyed |  |  | W0 |  | 46021
5263 | 5263-Military_Tabarbour_PF_EBand_TASC_O |  | AME-914-R | Outdoor |  | 35.9516 | 32.0144 | East Amman | Roof Top | najah eabd alkarim muhamad alhabarinh | 0796931291/0777768827 | Pole P9#2 | 20 | Low Priority |  |  | Cluster-52 | [28 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5264 | 5264-Tareq_Hay_Alghabeh_PF_TASC_O |  | AME-922-R | Outdoor |  | 35.9439 | 32.0131 | East Amman | Roof Top | basil earif asead jearh | 0789792805/0788186115 | Pole P9#2 | 16 | Low Priority |  |  | Cluster-52 | [28 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5266 | 5266-Alia_Taqwa_Ave_2_PF_EBand_TASC_O |  | AME-944-R | Outdoor |  | 35.9793 | 31.9959 | East Amman | Roof Top | dawud sulayman muhamad shukukani | 0796637907/0795993257 | Pole P9 + P6 | 21 | Low Priority |  |  | Cluster-52 | [28 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5267 | 5267-Tabarbour_PSD_Warehouse_PF_TASC_O |  | AME-936-R | Outdoor |  | 35.9266 | 31.9957 | East Amman | Roof Top | mudiriat al amn aleamm |  | Pole P9#2 | 23 | Low Priority |  |  | Cluster-52 | [28 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5270 | 5270-Tabarbour_Kazneh_Top_PE_Fiber_TASC_O |  | AME-964-R | Outdoor |  | 35.9283 | 32.0034 | East Amman | Roof Top | asmahan mustafaa muhamad eabdh | 0795750989/0797555315/0785300029 | Pole P6X2 | 21 | Low Priority |  |  | Cluster-52 | [13 empty] | Yes | [14 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5273 | 5273-AbuAlia_Shneller_Rd_PF_TASC_O |  | AME-962-R | Outdoor |  | 35.9781 | 32.0096 | East Amman | Roof Top | ghassan ealia wasf milkawi | 0799038789/079675761/0787400100 | Tower T 16 | 17 | Low Priority |  |  | Cluster-52 | [28 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5278 | 5278-Force_Army_Hotel_PF_TASC_O |  | AME-980-R | Outdoor |  | 35.9615 | 32.0117 | East Amman | Roof Top | harun jabril eabd alkarim alrafuae | 0772341000/0778608686 | Pole P9#2 | 21 | Low Priority |  |  | Cluster-52 | [28 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5301 | 5301-AbuAlanda_Caragat_PF_TASC |  | AME-423-R | Indoor | 400 | 35.9648 | 31.898 | South Amman | Roof Top | jabir muhamad walid zayid jabr | 06-4162208 | Tower T 16 | 22 | Low Priority |  |  | Cluster-53 | [13 empty] | Yes | [7 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5304 | 5304-AbuAlanda_Ind_PC_EBand_TASC |  | AME-79-R | Indoor | 4 | 35.9472 | 31.9026 | South Amman | Roof Top | earif eyd abu jnyb alfayz | 06/4783577 0777-205328 | Tower T 16 | 22 | Low Priority |  |  | Cluster-53 | [13 empty] | Yes | [7 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5309 | 5309-Electricity_HSG_PB_Fiber_TASC |  | AME-231-R | Indoor | 339 | 35.9702 | 31.9132 | South Amman | Roof Top | muhamad amin subati alhaniti | 06/4165772 | Pole P6 X 4 + P9 X 1 | 13 | Low Priority |  |  | Cluster-53 | [13 empty] | Yes | [7 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5324 | 5324-Customs_CRL_PC_EBand_TASC |  | AME-422-R | Indoor | 463 | 35.9377 | 31.9013 | South Amman | Roof Top | samah asead saeid alntsht | 079-5582700 | Tower T 12 | 18 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5326 | 5326-AbuAlanda_Bridge_PD_Fiber_TASC |  | AME-750-R | Indoor | 1708 | 35.9579 | 31.9004 | South Amman | Roof Top | mundhir muhamad jameah alkardi | 079-8241586 | Pole P9 x 3 | 21 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5331 | 5331-Hurrieh_St_PD_Fiber_TASC_O |  | AME-755-R | Outdoor |  | 35.9256 | 31.8993 | South Amman | Roof Top | amin ealia salman alqatarinat | 077-9643337/079-7757990 | Pole P9 X 2 + P6 X1 | 20 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5335 | 5335-JRTV_Main_Bldg_PF_O |  | AMS-128-R | Outdoor |  | 35.9347 | 31.9035 | South Amman | Roof Top | muasasat al iidhaeat waltilfiziun |  | Pole 6 | 42 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5336 | 5336-AbuAlanda_Hizam_Rd_PD_TASC |  | AME-721-R | Indoor | 1724 | 35.9804 | 31.9114 | South Amman | Roof Top | musaa khalil musaa badran | 079-5708200 | Pole P9 x 3 | 14 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5342 | 5342-UL_Hitten_Court_Middle_PF_EBand_TASC_O |  | AMS-247-R | Outdoor |  | 35.9414 | 31.9042 | South Amman | Roof Top |  |  | Pole P9#2 | 24 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5352 | 5352-AbuAlanda_Disi_Project_PF_EBand_TASC_O |  | AMS-150-R | Outdoor |  | 35.9768 | 31.9019 | South Amman | Roof Top | em rueuduh albakhit alhaniyti | 0799168400/0798544507 | Pole P9 + P6 | 18 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5356 | 5356-AbuAlanda_Gharbieh_PE_TASC_O |  | AMS-155-R | Outdoor |  | 35.9763 | 31.9176 | South Amman | Roof Top | muhamad abu talib | 0795264340/0798490904 | Tower T12 + P9X2 | 15 | Low Priority |  |  | Cluster-53 | [21 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | Site not surveyed |  |  | W0 |  | 46021
5366 | 5366-Hamaydeh_Hospital_PE_DIBS_O |  | AMS-190-R | Outdoor |  | 35.9339 | 31.9013 | South Amman | Roof Top | mustashfaa d. ahmad alhamayidat aleami |  | --- --- | 20 | Low Priority |  |  | Cluster-53 | [12 empty] | IBS-D | [8 empty] | Omar Sami | [6 empty] | Approved | [5 empty] | survey OG |  |  | W0 |  | 46021
3209 | 3209-Prince_Aisha_Carage_PF_M |  | AMW-301-R | Micro Cell |  | 35.8139 | 32.0114 | Amman | Pole | dabouq 1 |  |  | 12 | Part of P1 |  | Micro Cell | Cluster-32 |  |  | SMP-WO-1285743 | Al-Lewan | R&D>>Al Lewan | [5 empty] | RAN Only | [17 empty] | Approved | [5 empty] | survey OG | 2023-11-15 |  | W46 |  | 776
3207 | 3207-Royal_Zone6_Crises_PF_M |  | AMW-508-R-CO | Micro Cell | 3231-Royal_Zone6_Prince_PF_M | 35.8232 | 31.9837 | Amman | Pole | Royal_Zone_6_Mini_VIP |  | Unknown yet - TBD | 12 | Part of P1 |  | Micro Cell | Cluster-32 |  |  | SMP-WO-1285745 | Al-Lewan | R&D>>Al Lewan | [5 empty] | RAN Only | [17 empty] | Approved | [5 empty] | Site not surveyed | 2023-11-15 |  | W46 |  | 776
2222 | 2222-Mecca_Mall_PF_Fiber_IBS_Manage | ZAIN/M | AMW-528-R | 0 | 1507 | 31.9785 | 35.8439 | Amman | 2G 3G 4G | [5 empty] | PO.2 |  |  |  |  | SMP-WO-1291853 | Lewan | Al-Lewan | [7 empty] | IBS | [15 empty] | Approved | [8 empty] | 1 | Waiting Access Letter | 46021
4605 | 4605-Gigeen_PC_Fiber_TASC | TASC | IRB-5-G | Irbid | 631 | 32.5537 | 35.7859 | Irbid | Tower | [36 empty] | Approved
5826 | 5826-Abel_PD_Fiber_TASC | TASC | TAF-19-R | Tafila | 973 | 30.7995 | 35.5966 | Tafila | Tower | [36 empty] | Approved
746 | 746-Maan_West_PE_TASC | TASC | MAN-66-R | Ma'an |  | 30.2039 | 35.7194 | Ma'an | Tower | [36 empty] | Approved
5878 | 5878-Tafilah_Civil_Defence_PE_Fiber_TASC_O | TASC | TAF-29-R | Tafila |  | 30.8403 | 35.6234 | Tafila | Pole | [36 empty] | Approved
701 | 701-Alshamieh_Maan_PA_Fiber | TASC | MAN-1-G | Ma'an | 902 | 30.2001 | 35.7391 | Ma'an | Tower | [36 empty] | Approved
5807 | 5807-Qadesieh_PB_Fiber_Zain_TASC | TASC | TAF-1-G | Tafila | 877 | 30.6643 | 35.6221 | Tafila | Tower | [36 empty] | Approved
1302 | 1302-Hizam_Rd_3_PF_TASC_O | TASC | AME-610-R | Amman |  | 31.9684 | 36.0006 | Amman | Pole | [36 empty] | Approved
4172 | 4172-Baten_AlGhool_PE_Zain_TASC_Solar | TASC | MAN-16-G | Ma'an | 810 | 29.6945 | 35.9066 | Ma'an | Tower | [36 empty] | Approved
725 | 725-Jafer_City_PC_TASC | TASC | MAN-20-G | Ma'an | 815 | 30.3144 | 36.1733 | Ma'an | Tower | [36 empty] | Approved
4144 | 4144-Hmaimeh_Desert_St_PC_Fiber_TASC | TASC | AQB-4-G | Aqaba | 826 | 29.8745 | 35.3825 | Aqaba | Tower | [36 empty] | Approved
741 | 741-BSC_Maan_PA_Fiber_TASC_Relo | TASC | MAN-26-G | Ma'an | 925 | 30.2559 | 35.7427 | Ma'an | Tower | [36 empty] | Approved
5817 | 5817-Beir_Khaddad_PD_Fiber_TASC | TASC | TAF-14-G | Ma'an | 923 | 30.4366 | 35.5454 | Ma'an | Tower | [36 empty] | Approved
1311 | 1311-National_Paints_Hizam_PF_TASC_O | TASC | AME-634-R | Amman |  | 31.9222 | 35.9894 | Amman | Pole | [36 empty] | Approved
1307 | 1307-Salhiet_Abed_PE_EBand_TASC_O | TASC | AME-631-R | Amman |  | 31.9546 | 36.0059 | Amman | Pole | [36 empty] | Approved
757 | 757-Mohammadieh_PF_TASC_O | TASC | MAN-38-G | Ma'an | 930 | 30.4272 | 35.7495 | Ma'an | Tower | [36 empty] | Approved
748 | 748-Manshiet_Maan_PC_Fiber_TASC | TASC | MAN-33-G | Ma'an | 904 | 30.3939 | 35.6098 | Ma'an | Tower | [36 empty] | Approved
736 | 736-Baida_PF_TASC_O | TASC | MAN-78-R | Ma'an |  | 30.3794 | 35.4644 | Ma'an | Pole | [36 empty] | Approved
5877 | 5877-Eima_Tafilah_PF_TASC_O | TASC | TAF-22-G | Tafila |  | 30.8797 | 35.5953 | Tafila | Pole | [36 empty] | Approved
721 | 721-Hussainiah_PB_Fiber_TASC | TASC | MAN-12-G | Ma'an | 825 | 30.6029 | 35.8041 | Ma'an | Tower | [36 empty] | Approved
743 | 743-Qasmieh_PE_EBand_TASC | TASC | MAN-29-G | Ma'an | 928 | 30.0623 | 35.4936 | Ma'an | Tower | [36 empty] | Approved
754 | 754-Queen_Rania_Hospital_Petra_PF_TASC_O | TASC | MAN-90-R | Ma'an |  | 30.2706 | 35.4515 | Ma'an | Tower | [36 empty] | Approved
4171 | 4171-Modawara_PD_Fiber_TASC | TASC | MAN-15-G | Ma'an | 896 | 29.3248 | 36.0253 | Ma'an | Tower | [36 empty] | Approved
1309 | 1309-Harsha_2_PC_Fiber_TASC | TASC | AME-406-R | Amman | 499 | 31.9437 | 35.9756 | Amman | Pole | [36 empty] | Approved
1323 | 1323-Souq_Nasser_PE_Fiber_TASC | TASC | AME-546-R | Amman | 490 | 31.9609 | 35.9657 | Amman | Pole | [36 empty] | Approved
5864 | 5864-Fdan_PD_Fiber_TASC | TASC | TAF-13-G | Aqaba | 912 | 30.61 | 35.2666 | Aqaba | Tower | [36 empty] | Approved
786 | 786-Qrain_Maan_PE_Fiber_TASC_O | TASC | MAN-105-G | Ma'an |  | 30.1054 | 35.4804 | Ma'an | Tower | [36 empty] | Approved
762 | 762-Beir_Abu_Dannah_PE_Fiber_Zain_TASC | TASC | MAN-67-G | Ma'an | 919 | 30.258 | 35.5372 | Ma'an | Tower | [36 empty] | Approved
787 | 787-Sadaqeh_Maan_PE_Fiber_Zain_TASC_O | TASC | MAN-104-G | Ma'an | 990 | 30.1589 | 35.4904 | Ma'an | Tower | [36 empty] | Approved
740 | 740-skan_Bedoul_PD_TASC_O | TASC | MAN-34-R | Ma'an |  | 30.342 | 35.4552 | Ma'an | Pole | [36 empty] | Approved
5845 | 5845-Dhana_PE_Fiber_TASC_O | TASC | TAF-7-G | Tafila |  | 30.6752 | 35.6168 | Tafila | Tower | [36 empty] | Approved
5808 | 5808-Tafilah_3_PE_Fiber_TASC_O | TASC | TAF-20-R | Tafila |  | 30.8354 | 35.6247 | Tafila | Pole | [36 empty] | Approved
715 | 715-Maan_Janet_Petra_PD_Fiber_TASC_O | TASC | MAN-125-R | Ma'an |  | 30.3212 | 35.4756 | Ma'an | Tower | [36 empty] | Approved
749 | 749-Dlaghah_Village_PF_TASC_O | TASC | MAN-85-R | Ma'an |  | 30.1413 | 35.4087 | Ma'an | Tower | [36 empty] | Approved
710 | 710-Mraigha_PB_Fiber_TASC | TASC | MAN-10-G | Ma'an | 997 | 30.0954 | 35.5252 | Ma'an | Tower | [36 empty] | Approved
5850 | 5850-Hasa_Jurf_Daraweish_PE_TASC_Solar | TASC | KRK-50-G | Tafila | 824 | 30.7516 | 35.9434 | Tafila | Tower | [36 empty] | Approved
751 | 751-Beir_Dabaghat_PF_TASC | TASC | MAN-88-G | Ma'an | 965 | 30.3995 | 35.5104 | Ma'an | Tower | [36 empty] | Approved
4635 | 4635-Kufer_Kefia_PB_Fiber_Zain_TASC | TASC | IRB-41-G | Irbid | 695 | 32.5055 | 35.7646 | Irbid | Tower | [36 empty] | Approved
5812 | 5812-Bsaira_Gharandal_PC_Fiber_Zain_TASC | TASC | TAF-15-G | Tafila | 924 | 30.7103 | 35.6376 | Tafila | Tower | [36 empty] | Approved
5840 | 5840-Ain_Albaida_PB_Fiber_TASC | TASC | TAF-6-G | Tafila | 872 | 30.7719 | 35.643 | Tafila | Tower | [36 empty] | Approved
734 | 734-Taybet_Petra_PE_TASC | TASC | MAN-24-R | Ma'an | 942 | 30.238 | 35.46 | Ma'an | Tower | [36 empty] | Approved
5849 | 5849-Tafilah_Jurf_Daraweish_2_PE_TASC | TASC | TAF-8-G | Tafila | 931 | 30.7998 | 35.7007 | Tafila | Tower | [36 empty] | Approved
718 | 718-Hashmia_Desert_Rd_PC_Fiber_Zain_TASC | TASC | MAN-2-G | Ma'an | 905 | 30.5247 | 35.7978 | Ma'an | Tower | [36 empty] | Approved
1334 | 1334-Aden_Engs_HSG_PD_Fiber_TASC_O | TASC | AME-969-R | Amman |  | 31.9369 | 35.9816 | Amman | Pole | [36 empty] | Approved
5802 | 5802-Prince_Zaid_Hospital_Back_PE_Fiber_TASC_O | TASC | TAF-49-R | Tafila |  | 30.824 | 35.5912 | Tafila | Pole | [36 empty] | Approved
5813 | 5813-Qadesieh_Tafilah_PE_Fiber_TASC_O | TASC | TAF-50-R | Tafila |  | 30.6412 | 35.6417 | Tafila | Pole | [36 empty] | Approved
747 | 747-Maan_Ind_PC_TASC | TASC | MAN-87-R | Ma'an |  | 30.1741 | 35.8179 | Ma'an | Pole | [36 empty] | Approved
713 | 713-King_Hussein_Uni_PE_TASC | TASC | MAN-68-G | Ma'an | 935 | 30.2658 | 35.6842 | Ma'an | Tower | [36 empty] | Approved
760 | 760-Agriculture_HSG_Maan_PE_O | TASC | MAN-135-R | Ma'an |  | 30.1893 | 35.7186 | Ma'an | Pole | [36 empty] | Approved
5820 | 5820-Shytham_PC_Fiber_TASC | TASC | MAN-32-G | Tafila | 933 | 30.8742 | 35.6776 | Tafila | Tower | [36 empty] | Approved
723 | 723-Eyle_PC_Fiber_TASC | TASC | MAN-19-G | Ma'an | 806 | 30.2063 | 35.5258 | Ma'an | Tower | [36 empty] | Approved
5804 | 5804-Shobak_PB_Fiber_TASC | TASC | MAN-4-G | Ma'an | 851 | 30.5152 | 35.5403 | Ma'an | Tower | [36 empty] | Approved
5819 | 5819-Ain_Albaida_City_PB_Fiber_TASC | TASC | TAF-5-G | Tafila | 873 | 30.7795 | 35.5954 | Tafila | Tower | [36 empty] | Approved
714 | 714-Prince_Rasheed_Ave_Maan_PE_Fiber_TASC_O | TASC | MAN-143-R | Ma'an |  | 30.2811 | 35.5441 | Ma'an | Pole | [36 empty] | Approved
1317 | 1317-Nasser_2_PC_Fiber_TASC | TASC | AME-107-R | Amman | 300 | 31.9569 | 35.967 | Amman | Pole | [36 empty] | Approved
705 | 705-Ras_Naqab_PB_TASC | TASC | MAN-5-G | Ma'an | 831 | 30.0307 | 35.4514 | Ma'an | Tower | [36 empty] | Approved
777 | 777-Jarba_PF_TASC_O | TASC | MAN-77-R | Ma'an |  | 30.3734 | 35.5991 | Ma'an | Pole | [36 empty] | Approved
791 | 791-Maan_Hospital_PE_TASC | TASC | MAN-107-R | Ma'an | 995 | 30.1896 | 35.726 | Ma'an | Tower | [36 empty] | Approved
4134 | 4134-Rahma_PD_TASC | TASC | AQB-3-G | Aqaba | 832 | 29.9134 | 35.1433 | Aqaba | Tower | [36 empty] | Approved
1303 | 1303-Hizam_Um_Nowarah_TL_PF_TASC_O | TASC | AME-770-R | Amman |  | 31.9294 | 35.9879 | Amman | Pole | [36 empty] | Approved
4620 | 4620-Ham_Natfeh_PF_TASC | TASC | IRB-237-R | Irbid | 2118 | 32.5095 | 35.8154 | Irbid | Pole | [36 empty] | Approved
5806 | 5806-Tafilah_PB_Fiber_Zain_TASC | TASC | TAF-4-G | Tafila | 848 | 30.8672 | 35.6014 | Tafila | Tower | [36 empty] | Approved
5831 | 5831-Shobak_Stadium_PF_TASC_O | TASC | MAN-111-R | Ma'an |  | 30.5179 | 35.557 | Ma'an | Pole | [36 empty] | Approved
769 | 769-Risha_PF_TASC | TASC | AQB-11-G | Aqaba | 807 | 30.257 | 35.2343 | Aqaba | Tower | [36 empty] | Approved
755 | 755-Rajif_PF_TASC | TASC | MAN-37-G | Ma'an | 830 | 30.1601 | 35.4425 | Ma'an | Tower | [36 empty] | Approved
4133 | 4133-Qweirah_Maan_PB_Fiber_TASC | TASC | MAN-43-G | Aqaba | 918 | 29.8083 | 35.31 | Aqaba | Tower | [36 empty] | Approved
793 | 793-Bastah_Maan_PE_Fiber_TASC_O | TASC | MAN-103-G | Ma'an | 992 | 30.2297 | 35.5307 | Ma'an | Tower | [36 empty] | Approved
5801 | 5801-Beir_Mazkour_PD_TASC | TASC | AQB-9-G | Aqaba | 812 | 30.4984 | 35.2872 | Aqaba | Tower | [36 empty] | Approved
775 | 775-Risha_Old_PA_Fiber_TASC | TASC | AQB-6-G | Aqaba | 836 | 30.2292 | 35.2239 | Aqaba | Tower | [36 empty] | Approved
703 | 703-Hussainiah_Bin_Jazi_PF_Fiber_TASC_O | TASC | MAN-164-R | Ma'an |  | 30.5885 | 35.794 | Ma'an | Pole | [36 empty] | Approved
795 | 795-Maan_Ent_PF_TASC_O | TASC | MAN-129-G | Ma'an |  | 30.1894 | 35.6918 | Ma'an | Tower | [36 empty] | Approved
4102 | 4102-Rashedyeh_Aqaba_PE_TASC_O | TASC | AQB-213-R | Aqaba |  | 29.7323 | 35.2794 | Aqaba | Pole | [36 empty] | Approved
4619 | 4619-Kasarat_Ketem_2_PE_TASC | TASC | IRB-232-R | Irbid | 2113 | 32.4602 | 35.8876 | Irbid | Pole | [36 empty] | Approved
4647 | 4647-Ketem_PD_TASC | TASC | IRB-128-R | Irbid | 748 | 32.4367 | 35.8949 | Irbid | Tower | [36 empty] | Approved
4604 | 4604-Samoa_PD_Fiber_TASC | TASC | IRB-199-R | Irbid | 785 | 32.5164 | 35.7382 | Irbid | Tower | [36 empty] | Approved
2412 | 2412-Naseem_CRL_PD_EBand_TASC | TASC | IRB-62-R | Irbid | 608 | 32.5303 | 35.8529 | Irbid | Pole | [36 empty] | Approved
2442 | 2442-Yarmouk_North_Gate_PE_TASC | TASC | IRB-125-R | Irbid | 742 | 32.5419 | 35.8531 | Irbid | Pole | [36 empty] | Approved
4670 | 4670-Ashrafyeh_Irbid_PE_TASC | TASC | IRB-202-R | Irbid | 787 | 32.4672 | 35.7052 | Irbid | Tower | [36 empty] | Approved
1318 | 1318-Nasser_Railway_PE_TASC_O | TASC | AME-765-R | Amman |  | 31.9584 | 35.9631 | Amman | Tower | [36 empty] | Approved
2416 | 2416-Yarmouk_Uni_3_PE_TASC_O | TASC | IRB-245-R | Irbid |  | 32.5372 | 35.848 | Irbid | Pole | [36 empty] | Approved
4614 | 4614-Kufer_Aan_Junction_PE_TASC | TASC | IRB-221-R | Irbid | 637 | 32.5532 | 35.7655 | Irbid | Pole | [36 empty] | Approved
2405 | 2405-Irbid_Doctor_HSG_2_PD_EBand_TASC | TASC | IRB-222-R | Irbid | 718 | 32.5395 | 35.8448 | Irbid | Pole | [36 empty] | Approved
2433 | 2433-Sheikh_Khalil_CPLX_PD_EBand_TASC | TASC | IRB-169-R | Irbid | 747 | 32.5486 | 35.8561 | Irbid | Pole | [36 empty] | Approved
4607 | 4607-Deir_Yousef_PC_Fiber_TASC | TASC | IRB-211-R | Irbid | 797 | 32.4882 | 35.7948 | Irbid | Tower | [36 empty] | Approved
2414 | 2414-Mahakem_CRL_PA_Fiber_TASC | TASC | IRB-236-R | Irbid | 2117 | 32.526 | 35.8461 | Irbid | Pole | [36 empty] | Approved
4606 | 4606-Huson_2_PE_TASC | TASC | IRB-127-R | Irbid | 745 | 32.485 | 35.8875 | Irbid | Pole | [36 empty] | Approved
4649 | 4649-Edoon_CTR_PB_Fiber_TASC | TASC | IRB-224-R | Irbid | 2100 | 32.5155 | 35.857 | Irbid | Pole | [36 empty] | Approved
2420 | 2420-UNRWA_Back_PE_TASC | TASC | IRB-257-R | Irbid | 2145 | 32.5412 | 35.8477 | Irbid | Pole | [36 empty] | Approved
4627 | 4627-West_Irbid_PSD_PE_EBand_TASC_O | TASC | IRB-274-R | Irbid |  | 32.5286 | 35.7581 | Irbid | Pole | [36 empty] | Approved
4674 | 4674-Natfeh_Irbid_PE_TASC_O | TASC | IRB-403-R | Irbid |  | 32.5213 | 35.819 | Irbid | Pole | [36 empty] | Approved
4666 | 4666-Sareeh_Tarkhees_PF_O | TASC | IRB-324-R | Irbid |  | 32.5003 | 35.8989 | Irbid | Pole | [36 empty] | Approved
2419 | 2419-Yarmouk_Shareaa_PF_TASC_O | TASC | IRB-290-R | Irbid |  | 32.5364 | 35.8557 | Irbid | Pole | [36 empty] | Approved
4659 | 4659-Kufer_Awan_CTR_PF_TASC_O | TASC | IRB-413-R | Irbid |  | 32.4254 | 35.6861 | Irbid | Pole | [36 empty] | Approved
4657 | 4657-Taybeh_PE_TASC | TASC | IRB-49-R | Irbid | 687 | 32.5419 | 35.7174 | Irbid | Tower | [36 empty] | Approved
2415 | 2415-Irbid_Queen_Rania_CRL_PE_Fiber_TASC_O | TASC | IRB-417-R | Irbid |  | 32.5311 | 35.8625 | Irbid | Pole | [36 empty] | Approved
4617 | 4617-Samad_PB_Fiber_TASC | TASC | IRB-36-G | Irbid | 679 | 32.4338 | 35.8323 | Irbid | Tower | [36 empty] | Approved
4628 | 4628-Juhfia_PD_EBand_Zain_TASC | TASC | IRB-40-G | Irbid | 732 | 32.4926 | 35.8234 | Irbid | Tower | [36 empty] | Approved
4671 | 4671-Kufer_Rakeb_PC_EBand_TASC | TASC | IRB-35-G | Irbid | 693 | 32.4492 | 35.6891 | Irbid | Tower | [36 empty] | Approved
2426 | 2426-Alia_Tal_Msq_PE_O | TASC | IRB-275-R | Irbid |  | 32.5378 | 35.8466 | Irbid | Pole | [36 empty] | Approved
4654 | 4654-Sareeh_South_PE_EBand_TASC_O | TASC | IRB-323-R | Irbid |  | 32.499 | 35.889 | Irbid | Pole | [36 empty] | Approved
5857 | 5857-Hasa_Tafilah_Rd_PF_Zain_TASC_O | TASC | TAF-28-G | Tafila |  | 30.8237 | 35.7062 | Tafila | Tower | [36 empty] | Approved
4618 | 4618-Petrol_Cross_PF_TASC_O | TASC | IRB-322-R | Irbid |  | 32.4846 | 35.8602 | Irbid | Tower | [36 empty] | Approved
1341 | 1341-Megherat_Ave_PF_TASC_O | TASC | AME-571-R | Amman | 1535 | 31.9674 | 36.0137 | Amman | Tower | [36 empty] | Approved
4661 | 4661-Edoon_Clinics_Ave_East_PF_TASC_O | TASC | IRB-361-R | Irbid |  | 32.5244 | 35.8568 | Irbid | Tower | [36 empty] | Approved
752 | 752-Wadi_Moussa_Baset_PE_Fiber_TASC_O | TASC | MAN-117-R | Ma'an |  | 30.3132 | 35.4777 | Ma'an | Pole | [36 empty] | Approved
5856 | 5856-Tafilah_Alharith_Maqam_PE_Fiber_TASC_O | TASC | TAF-47-R | Tafila |  | 30.7397 | 35.63 | Tafila | Tower | [36 empty] | Approved
4631 | 4631-Huson_TL_PE_TASC_O | TASC | IRB-327-R | Irbid |  | 32.4908 | 35.883 | Irbid | Pole | [36 empty] | Approved
1325 | 1325-Wadi_Osh_Bwaidah_PF_TASC_O | TASC | AME-876-R | Amman |  | 31.9506 | 36.0456 | Amman | Pole | [36 empty] | Approved
4637 | 4637-Deir_Esseneh_2_PE_EBand_TASC_O | TASC | IRB-340-R | Irbid |  | 32.5361 | 35.7462 | Irbid | Tower | [36 empty] | Approved
320 | 320-TCC_PA_Fiber_IBS_TASC_M | TASC | AME-580-R | Amman | 39 | 31.9541 | 35.9146 | Amman | [21 empty] | IBS | [15 empty] | Approved
5827 | 5827-Qadesieh_Tafilah_South_PD_Fiber_TASC_O | TASC | TAF-33-R | Tafila |  | 30.6565 | 35.6351 | Tafila | Pole | [36 empty] | Approved
2440 | 2440-Hay_Tlool_Irbid_PD_O | TASC | IRB-301-R | Irbid |  | 32.5492 | 35.8696 | Irbid | Tower | [36 empty] | Approved
5860 | 5860-Qraiqra_Village_PF_TASC_O | TASC | TAF-37-R | Aqaba | 222 | 30.631 | 35.4017 | Aqaba | Pole | [36 empty] | Approved
4656 | 4656-Qumaim_Back_Irbid_PE_EBand_TASC_O | TASC | IRB-329-R | Irbid |  | 32.558 | 35.7479 | Irbid | Pole | [36 empty] | Approved
744 | 744-Maan_Mraigha_Rd_PF_TASC_Solar | TASC | MAN-30-G | Ma'an | 899 | 30.0969 | 35.5752 | Ma'an | Tower | [36 empty] | Approved
4639 | 4639-Huson_Camp_CTR_PF_EBand_TASC_O | TASC | IRB-363-R | Irbid |  | 32.4732 | 35.9084 | Irbid | Tower | [36 empty] | Approved
761 | 761-Gharandal_Police_Station_PD_Fiber_TASC | TASC | TAF-11-G | Aqaba | 915 | 30.0754 | 35.1817 | Aqaba | Tower | [36 empty] | Approved
5852 | 5852-Tafilah_Market_PD_Fiber_TASC_O | TASC | TAF-35-R | Tafila |  | 30.8276 | 35.5987 | Tafila | Tower | [36 empty] | Approved
4642 | 4642-Edoon_Big_Msq_PF_TASC_O | TASC | IRB-349-R | Irbid |  | 32.5065 | 35.8574 | Irbid | Pole | [36 empty] | Approved
5854 | 5854-East_Hasa_PE_O | TASC | KRK-196-R | Tafila |  | 30.8192 | 35.9756 | Tafila | Pole | [36 empty] | Approved
5841 | 5841-Jurf_Daraweish_PF_TASC | TASC | KRK-41-G | Tafila | 814 | 30.6916 | 35.863 | Tafila | Tower | [36 empty] | Approved
1350 | 1350-Aden_End_PE_Fiber_TASC_O | TASC | AME-878-R | Amman |  | 31.9343 | 35.987 | Amman | Pole | [36 empty] | Approved
4676 | 4676-Zmal_Irbid_PF_TASC_O | TASC | IRB-338-R | Irbid |  | 32.506 | 35.7368 | Irbid | Pole | [36 empty] | Approved
5829 | 5829-Shobak_Court_PF_TASC_O | TASC | MAN-110-R | Ma'an |  | 30.5199 | 35.5747 | Ma'an | Pole | [36 empty] | Approved
782 | 782-Nursing_College_Maan_PF_TASC_O | TASC | MAN-148-R | Ma'an |  | 30.187 | 35.737 | Ma'an | Pole | [36 empty] | Approved
784 | 784-Rajif_Village_PF_TASC_O | TASC | MAN-136-R | Ma'an |  | 30.1893 | 35.4446 | Ma'an | Pole | [36 empty] | Approved
789 | 789-Taibeh_Wadi_Moussa_PE_O | TASC | MAN-116-R | Ma'an |  | 30.2499 | 35.4689 | Ma'an | Pole | [36 empty] | Approved
2909 | 2909-Irbid_Huson_Rd_PE_EBand_TASC_O | TASC | IRB-303-R | Irbid |  | 32.516 | 35.8724 | Irbid | Tower | [36 empty] | Approved
1377 | 1377-Fardous_HSG_Hizam_Rd_PF_TASC_O | TASC | AME-856-R | Amman |  | 31.9569 | 35.992 | Amman | Pole | [36 empty] | Approved
4638 | 4638-Habaka_Irbid_PE_TASC_O | TASC | IRB-335-R | Irbid |  | 32.4782 | 35.8388 | Irbid | Tower | [36 empty] | Approved
2455 | 2455-Edoon_St_PE_EBand_TASC_O | TASC | IRB-308-R | Irbid |  | 32.5505 | 35.8489 | Irbid | Pole | [36 empty] | Approved
5879 | 5879-Rweim_PE_Fiber_TASC_O | TASC | TAF-26-R | Tafila |  | 30.8327 | 35.5764 | Tafila | Pole | [36 empty] | Approved
4658 | 4658-Kufer_Aan_PF_TASC_O | TASC | IRB-330-R | Irbid |  | 32.5488 | 35.7613 | Irbid | Pole | [36 empty] | Approved
2429 | 2429-Yarmouk_Uni_2_PD_EBand_TASC_O | TASC | IRB-299-R | Irbid |  | 32.5332 | 35.8478 | Irbid | Tower | [36 empty] | Approved
794 | 794-Maan_Railway_HSG_PE_EBand_O | TASC | MAN-109-R | Ma'an |  | 30.1943 | 35.7171 | Ma'an | Pole | [36 empty] | Approved
4673 | 4673-Samad_Irbid_PF_TASC_O | TASC | IRB-343-R | Irbid |  | 32.4492 | 35.8282 | Irbid | Pole | [36 empty] | Approved
771 | 771-Fardakh_Maan_PE_Fiber_TASC_O | TASC | MAN-120-R | Ma'an |  | 30.1896 | 35.5088 | Ma'an | Pole | [36 empty] | Approved
4652 | 4652-Jenen_Safa_Irbid_PD_Fiber_TASC_O | TASC | IRB-354-R | Irbid |  | 32.5213 | 35.7069 | Irbid | Tower | [36 empty] | Approved
770 | 770-Othruh_Uni_St_PF_TASC_O | TASC | MAN-123-R | Ma'an |  | 30.3313 | 35.5936 | Ma'an | Tower | [36 empty] | Approved
4675 | 4675-Ketem_North_PE_TASC_O | TASC | IRB-424-R | Irbid |  | 32.4436 | 35.8902 | Irbid | Pole | [36 empty] | Approved
722 | 722-Hussainiah_Maan_PE_Fiber_TASC_O | TASC | MAN-130-R | Ma'an |  | 30.597 | 35.7924 | Ma'an | Tower | [36 empty] | Approved
4630 | 4630-Huson_North_PF_O | TASC | IRB-288-R | Irbid |  | 32.4906 | 35.8905 | Irbid | Pole | [36 empty] | Approved
716 | 716-Dabbet_Hanout_PF_TASC_O | TASC | MAN-158-R | Aqaba |  | 29.9705 | 35.462 | Aqaba | Tower | [36 empty] | Approved
5866 | 5866-Gharandal_Tafilah_PE_TASC_O | TASC | TAF-41-R | Tafila |  | 30.7138 | 35.6553 | Tafila | Tower | [36 empty] | Approved
5868 | 5868-Shobak_Jahir_PF_TASC_O | TASC | MAN-155-R | Ma'an |  | 30.5272 | 35.5166 | Ma'an | Pole | [36 empty] | Approved
1315 | 1315-Salhiet_Abed_Stadium_PF_TASC_O | TASC | AME-892-R | Amman |  | 31.954 | 36.024 | Amman | Pole | [36 empty] | Approved
717 | 717-Maan_Uni_College_PF_TASC_O | TASC | MAN-162-R | Ma'an |  | 30.25 | 35.6952 | Ma'an | Pole | [36 empty] | Approved
5862 | 5862-Faisalieh_Shobak_PF_TASC_O | TASC | MAN-144-R | Ma'an |  | 30.4851 | 35.6318 | Ma'an | Pole | [36 empty] | Approved
4662 | 4662-Tubneh_Irbid_PF_O | TASC | IRB-351-R | Irbid |  | 32.4746 | 35.7328 | Irbid | Tower | [36 empty] | Approved
5870 | 5870-Shobak_Shamakh_PF_TASC_O | TASC | MAN-159-R | Ma'an |  | 30.4919 | 35.5199 | Ma'an | Pole | [36 empty] | Approved
5867 | 5867-Ain_Albaida_Rd_PE_Fiber_O | TASC | TAF-39-R | Tafila |  | 30.7917 | 35.6011 | Tafila | Pole | [36 empty] | Approved
5832 | 5832-Zoubayrieh_Shobak_PF_TASC_O | TASC | MAN-112-G | Ma'an |  | 30.5019 | 35.5587 | Ma'an | Tower | [36 empty] | Approved
4663 | 4663-Huson_Manshieh_Ave_PF_TASC_O | TASC | IRB-472-R | Irbid |  | 32.4783 | 35.878 | Irbid | Pole | [36 empty] | Approved
2467 | 2467-Hay_Rabyeh_Irbid_PE_TASC_O | TASC | IRB-444-R | Irbid |  | 32.5276 | 35.8503 | Irbid | Pole | [36 empty] | Approved
5893 | 5893-Tafilah_Wadi_Zaid_PE_Fiber_TASC_O | TASC | TAF-43-R | Tafila |  | 30.8254 | 35.5804 | Tafila | Pole | [36 empty] | Approved
5865 | 5865-Mansoura_Shobak_PF_TASC_O | TASC | MAN-142-R | Ma'an |  | 30.5719 | 35.5542 | Ma'an | Pole | [36 empty] | Approved
5888 | 5888-Shobak_Hawaleh_PF_TASC_O | TASC | MAN-160-R | Ma'an |  | 30.4697 | 35.517 | Ma'an | Pole | [36 empty] | Approved
3118 | 3118-Hay_Jafer_Tayar_PD_Fiber_TASC | TASC | ZRQ-205-R | Zarqa | 1802 | 32.0257 | 36.0101 | Zarqa | Tower | [36 empty] | Approved
2328 | 2328-Jawad_Bakery_2_PC_EBand_TASC | TASC | AME-274-R | Amman | 366 | 31.9992 | 35.9952 | Amman | Tower | [36 empty] | Approved
2329 | 2329-Souq_Marka_PD_TASC | TASC | AME-275-R | Amman | 239 | 31.9788 | 35.9837 | Amman | Pole | [36 empty] | Approved
3127 | 3127-Jabal_Shamali_Rasheed_PE_TASC_O | TASC | ZRQ-255-R | Zarqa |  | 32.0286 | 36.025 | Zarqa | Pole | [36 empty] | Approved
3102 | 3102-Polytechnic_Jett_PB_Fiber_TASC | TASC | ZRQ-140-G | Amman | 584 | 31.9933 | 36.0242 | Amman | Tower | [36 empty] | Approved
2310 | 2310-Jabal_Faisal_PE_TASC | TASC | AME-483-R | Amman | 570 | 32.0041 | 36.0015 | Amman | Tower | [36 empty] | Approved
3106 | 3106-Pepsi_HSG_PE_TASC | TASC | ZRQ-99-R | Zarqa | 502 | 31.9998 | 36.0226 | Zarqa | Pole | [36 empty] | Approved
3129 | 3129-Khalid_Bin_Waleed_Village_PE_TASC_O | TASC | ZRQ-198-R | Amman | 599 | 31.9826 | 36.0372 | Amman | Tower | [36 empty] | Approved
3103 | 3103-Jreiba_PC_EBand_Zain_TASC | TASC | ZRQ-171-G | Zarqa | 591 | 32.0414 | 35.9841 | Zarqa | Tower | [36 empty] | Approved
1345 | 1345-Tatweer_Hadari_Hizam_PE_TASC | TASC | ZRQ-161-R | Amman | 440 | 31.975 | 36.0066 | Amman | Pole | [36 empty] | Approved
3145 | 3145-Yajouz_Rasheed_PE_O | TASC | ZRQ-361-R | Zarqa |  | 32.0206 | 36.0034 | Zarqa | Pole | [36 empty] | Approved
3143 | 3143-Wadi_ElEsh_1_PF_TASC_O | TASC | ZRQ-211-G | Amman | 1806 | 31.9761 | 36.0955 | Amman | Tower | [36 empty] | Approved
3109 | 3109-Yajouz_PA_Fiber_TASC | TASC | ZRQ-102-G | Zarqa | 553 | 32.023 | 36.0021 | Zarqa | Tower | [36 empty] | Approved
3117 | 3117-Hitteen_Camp_PF_O | TASC | ZRQ-308-R | Zarqa |  | 32.0071 | 36.0116 | Zarqa | Pole | [36 empty] | Approved
3112 | 3112-Yajouz_Rd_PE_TASC | TASC | ZRQ-173-G | Amman | 593 | 32.0205 | 35.9668 | Amman | Tower | [36 empty] | Approved
3115 | 3115-Mshairfe_Russayfah_PF_TASC | TASC | ZRQ-108-R | Zarqa | 557 | 32.0132 | 36.027 | Zarqa | Pole | [36 empty] | Approved
3161 | 3161-Old_Marka_HSG_PF_TASC_O | TASC | ZRQ-347-R | Amman |  | 31.9856 | 36.0264 | Amman | Pole | [36 empty] | Approved
2314 | 2314-Marka_Gardens_PE_Fiber_TASC | TASC | AME-689-R | Amman | 214 | 31.9751 | 35.9875 | Amman | Pole | [36 empty] | Approved
3116 | 3116-Prince_Hashem_HSG_PB_Fiber_TASC | TASC | ZRQ-109-G | Zarqa | 587 | 32.0045 | 36.0297 | Zarqa | Tower | [36 empty] | Approved
3160 | 3160-Jabal_Faisal_End_PE_TASC_O | TASC | ZRQ-233-R | Zarqa |  | 32.0195 | 36.0171 | Zarqa | Pole | [36 empty] | Approved
3128 | 3128-Iskan_Diyar_Hizam_PF_EBand_TASC_O | TASC | ZRQ-195-R | Amman |  | 31.9769 | 36.0208 | Amman | Pole | [36 empty] | Approved
3131 | 3131-Shneller_PE_TASC | TASC | ZRQ-112-R | Zarqa | 532 | 32.0096 | 36.0068 | Zarqa | Tower | [36 empty] | Approved
3126 | 3126-Hujjaj_Msq_Mshairfe_PF_TASC | TASC | ZRQ-154-R | Zarqa | 588 | 32.0121 | 36.0149 | Zarqa | Tower | [36 empty] | Approved
3146 | 3146-Jreiba_CTR_PF_TASC_O | TASC | ZRQ-357-R | Zarqa |  | 32.0375 | 36.0162 | Zarqa | Pole | [36 empty] | Approved
3134 | 3134-Hizam_Rd_Polytechnic_PD_Fiber_TASC | TASC | ZRQ-222-R | Amman | 1811 | 31.9873 | 36.0203 | Amman | Pole | [36 empty] | Approved
3147 | 3147-Jreiba_North_PF_TASC_O | TASC | ZRQ-362-R | Zarqa |  | 32.037 | 36.0087 | Zarqa | Pole | [36 empty] | Approved
2313 | 2313-Marka_Police_Station_PE_Fiber_TASC | TASC | AME-688-R | Amman | 220 | 31.9772 | 35.9962 | Amman | Pole | [36 empty] | Approved
839 | 839-Zahoom_Karak_Top_PF_TASC_O | TASC | KRK-247-R | Karak |  | 31.1745 | 35.7563 | Karak | Tower | [36 empty] | Approved
3337 | 3337-Mutah_PC_EBand_TASC | TASC | KRK-37-R | Karak | 893 | 31.0985 | 35.7176 | Karak | Tower | [36 empty] | Approved
5875 | 5875-Ghor_Mazraah_West_PE_EBand_TASC_O | TASC | KRK-243-R | Karak |  | 31.2637 | 35.5173 | Karak | Tower | [36 empty] | Approved
3361 | 3361-Moaab_Karak_PC_TASC | TASC | KRK-60-G | Karak | 887 | 31.0273 | 35.7168 | Karak | Tower | [36 empty] | Approved
805 | 805-Rakeen_Batter_PE_TASC | TASC | KRK-5-R | Karak | 829 | 31.224 | 35.7064 | Karak | Tower | [36 empty] | Approved
844 | 844-Fagoue_Karak_PD_TASC | TASC | KRK-44-G | Karak | 886 | 31.3658 | 35.7052 | Karak | Tower | [36 empty] | Approved
880 | 880-Wassieh_Karak_PD_Fiber_TASC_O | TASC | KRK-162-R | Karak |  | 31.2248 | 35.7381 | Karak | Tower | [36 empty] | Approved
1034 | 1034-Merheb_PE_TASC | TASC | ZRQ-21-G | Zarqa | 542 | 32.0866 | 36.0071 | Zarqa | Tower | [36 empty] | Approved
810 | 810-Barada_Bathan_Karak_PE_TASC_O | TASC | KRK-141-G | Karak |  | 31.2087 | 35.6781 | Karak | Tower | [36 empty] | Approved
4317 | 4317-AlJundi_PD_EBand_TASC | TASC | ZRQ-110-R | Zarqa | 511 | 32.0208 | 36.0722 | Zarqa | Tower | [36 empty] | Approved
1580 | 1580-New_Shouneh_PE_TASC_O | TASC | MAD-236-R | Balqa |  | 31.9157 | 35.6045 | Balqa | Tower | [36 empty] | Approved
3331 | 3331-Aai_PE_TASC | TASC | KRK-31-G | Karak | 884 | 31.1377 | 35.6329 | Karak | Tower | [36 empty] | Approved
855 | 855-Sad_Waleh_PE_TASC | TASC | MAD-18-G | Madaba | 455 | 31.5504 | 35.7688 | Madaba | Tower | [36 empty] | Approved
3342 | 3342-Um_Hamaat_Karak_PF_TASC_O | TASC | KRK-210-R | Karak |  | 31.0384 | 35.7621 | Karak | Tower | [36 empty] | Approved
3360 | 3360-Medical_CTR_Mazar_Karak_PE_TASC_O | TASC | KRK-214-R | Karak |  | 31.0637 | 35.6875 | Karak | Pole | [36 empty] | Approved
5828 | 5828-Lesan_DeadSea_PE_Zain_TASC | TASC | KRK-135-G | Karak | 975 | 31.3247 | 35.4788 | Karak | Tower | [36 empty] | Approved
1565 | 1565-Ramah_DeadSea_PB_Fiber_Zain_TASC | TASC | MAD-60-G | Balqa | 112 | 31.8159 | 35.6481 | Balqa | Tower | [36 empty] | Approved
840 | 840-Ruba_Karak_PC_Fiber_TASC | TASC | KRK-40-R | Karak | 882 | 31.2711 | 35.7401 | Karak | Tower | [36 empty] | Approved
868 | 868-Ader_City_PD_Fiber_TASC | TASC | KRK-146-R | Karak | 984 | 31.201 | 35.7599 | Karak | Tower | [36 empty] | Approved
1029 | 1029-Zarqa_Uni_Rd_PD_TASC_O | TASC | ZRQ-157-R | Zarqa | 581 | 32.0369 | 36.1022 | Zarqa | Tower | [36 empty] | Approved
1009 | 1009-Hay_Janaa_PE_TASC | TASC | ZRQ-9-R | Zarqa | 514 | 32.0528 | 36.0904 | Zarqa | Pole | [36 empty] | Approved
1005 | 1005-Zarqa_Madina_Monawara_PD_EBand_TASC_O | TASC | ZRQ-172-R | Zarqa | 590 | 32.0474 | 36.0457 | Zarqa | Tower | [36 empty] | Approved
889 | 889-Karak_Shihabieh_Market_PF_EBand_TASC_O | TASC | KRK-192-R | Karak |  | 31.1785 | 35.6881 | Karak | Tower | [36 empty] | Approved
4301 | 4301-Zarqa_Ind_PF_TASC_O | TASC | ZRQ-151-R | Amman |  | 32.0214 | 36.0825 | Amman | Pole | [36 empty] | Approved
3302 | 3302-Mazar_Police_Station_PE_TASC_O | TASC | KRK-56-R | Karak |  | 31.0605 | 35.6981 | Karak | Tower | [36 empty] | Approved
3375 | 3375-That_Ras_PE_TASC_O | TASC | KRK-156-R | Karak | 994 | 30.9965 | 35.7659 | Karak | Tower | [36 empty] | Approved
3385 | 3385-Mutah_Uni_Eng_PF_EBand_TASC_O | TASC | KRK-183-R | Karak |  | 31.0945 | 35.7214 | Karak | Pole | [36 empty] | Approved
3381 | 3381-Taibeh_Ent_PE_TASC_O | TASC | KRK-185-R | Karak |  | 31.0421 | 35.6139 | Karak | Pole | [36 empty] | Approved
3386 | 3386-Karak_Omarieh_PE_EBand_TASC_O | TASC | KRK-190-G | Karak |  | 31.0331 | 35.7279 | Karak | Tower | [36 empty] | Approved
1505 | 1505-Maghtas_PE_TASC | TASC | MAD-43-G | Balqa | 271 | 31.8409 | 35.5578 | Balqa | Tower | [36 empty] | Approved
3317 | 3317-Karak_Desert_St_PE_EBand_TASC | TASC | KRK-17-G | Karak | 889 | 31.205 | 35.8206 | Karak | Pole | [36 empty] | Approved
3378 | 3378-Mutah_Enjasah_PD_Fiber_TASC_O | TASC | KRK-173-R | Karak |  | 31.0859 | 35.7004 | Karak | Tower | [36 empty] | Approved
3329 | 3329-Sool_PE_TASC_O | TASC | KRK-29-G | Karak |  | 31.0615 | 35.7228 | Karak | Tower | [36 empty] | Approved
882 | 882-Marj_Market_PE_Fiber_TASC_O | TASC | KRK-171-R | Karak |  | 31.1778 | 35.7134 | Karak | Tower | [36 empty] | Approved
3364 | 3364-Qatraneh_Repeater_PE_EBand_TASC | TASC | KRK-62-G | Karak | 934 | 31.2184 | 36.0039 | Karak | Tower | [36 empty] | Approved
2821 | 2821-Hashmia_2_PE_EBand_TASC | TASC | ZRQ-174-G | Zarqa | 592 | 32.139 | 36.1045 | Zarqa | Tower | [36 empty] | Approved
878 | 878-Aliah_Madaba_PF_TASC_O | TASC | MAD-255-R | Madaba |  | 31.5272 | 35.7783 | Madaba | Tower | [36 empty] | Approved
5838 | 5838-Hamdieh_Karak_PF_TASC_O | TASC | KRK-246-R | Karak |  | 30.9219 | 35.9032 | Karak | Pole | [36 empty] | Approved
820 | 820-Theeban_PE_TASC | TASC | MAD-196-R | Madaba | 54 | 31.4995 | 35.7799 | Madaba | Tower | [36 empty] | Approved
1563 | 1563-Maeen_2_PE_EBand_Zain_TASC | TASC | MAD-58-G | Madaba | 245 | 31.6221 | 35.6133 | Madaba | Tower | [36 empty] | Approved
3362 | 3362-Mutah_CTR_PC_Fiber_TASC | TASC | KRK-61-R | Karak | 894 | 31.0918 | 35.6962 | Karak | Tower | [36 empty] | Approved
823 | 823-Karak_College_PC_Fiber_TASC | TASC | KRK-26-G | Karak | 908 | 31.1712 | 35.7389 | Karak | Tower | [36 empty] | Approved
3352 | 3352-Shqaira_PE_TASC | TASC | KRK-11-G | Karak | 842 | 30.9809 | 35.7818 | Karak | Tower | [36 empty] | Approved
1037 | 1037-Princess_Haya_Ave_PF_EBand_TASC_O | TASC | ZRQ-232-R | Zarqa |  | 32.0727 | 36.0553 | Zarqa | Pole | [36 empty] | Approved
1527 | 1527-Jofeh_Aghwar_PD_Fiber_TASC_O | TASC | BLQ-148-R | Balqa |  | 31.8564 | 35.6403 | Balqa | Tower | [36 empty] | Approved
1028 | 1028-Military_College_PF_TASC | TASC | ZRQ-18-R | Zarqa | 539 | 32.0304 | 36.0904 | Zarqa | Pole | [36 empty] | Approved
1026 | 1026-Jabal_Tareq_PD_TASC | TASC | ZRQ-17-R | Zarqa | 510 | 32.0452 | 36.0941 | Zarqa | Pole | [36 empty] | Approved
1033 | 1033-Merheb_2_PE_TASC_O | TASC | ZRQ-210-R | Zarqa |  | 32.084 | 36.0252 | Zarqa | Pole | [36 empty] | Approved
1040 | 1040-Makka_Ave_Zarqa_PF | TASC | ZRQ-223-R | Zarqa | 1817 | 32.052 | 36.0612 | Zarqa | Tower | [36 empty] | Approved
1007 | 1007-Falah_Ave_PF_O | TASC | ZRQ-218-R | Zarqa |  | 32.0591 | 36.0622 | Zarqa | Pole | [36 empty] | Approved
1032 | 1032-Teachers_HSG_PB_Fiber_TASC | TASC | ZRQ-20-R | Zarqa | 503 | 32.0683 | 36.0424 | Zarqa | Tower | [36 empty] | Approved
1004 | 1004-Zawahrah_2_PE_EBand_TASC | TASC | ZRQ-4-R | Zarqa | 527 | 32.0681 | 36.0639 | Zarqa | Pole | [36 empty] | Approved
1006 | 1006-Zawahrah_End_PD_Fiber_TASC | TASC | ZRQ-197-R | Zarqa | 600 | 32.0565 | 36.071 | Zarqa | Pole | [36 empty] | Approved
1019 | 1019-Wadi_Hajar_PE_TASC | TASC | ZRQ-15-R | Zarqa | 552 | 32.0434 | 36.0859 | Zarqa | Tower | [36 empty] | Approved
1012 | 1012-Awajan_Civil_Defence_PB_Fiber_TASC | TASC | ZRQ-12-R | Zarqa | 554 | 32.0313 | 36.0828 | Zarqa | Tower | [36 empty] | Approved
1045 | 1045-Jabal_Tareq_End_PE_O | TASC | ZRQ-251-R | Zarqa |  | 32.0348 | 36.0989 | Zarqa | Pole | [36 empty] | Approved
2829 | 2829-Gharesa_Um_Solaih_PE_TASC | TASC | ZRQ-203-G | Zarqa | 1801 | 32.1595 | 36.0847 | Zarqa | Tower | [36 empty] | Approved
1558 | 1558-DeadSea_Navy_PD_Fiber_TASC | TASC | MAD-120-G | Madaba | 410 | 31.5845 | 35.5553 | Madaba | Tower | [36 empty] | Approved
1010 | 1010-Jabal_Zayton_Hospital_PD_EBand_TASC | TASC | ZRQ-10-R | Zarqa | 543 | 32.0388 | 36.0909 | Zarqa | Pole | [36 empty] | Approved
4324 | 4324-Islamic_Bank_Russayfah_PC_Fiber_TASC | TASC | ZRQ-155-R | Zarqa | 578 | 32.0175 | 36.0428 | Zarqa | Tower | [36 empty] | Approved
4313 | 4313-Awajan_PC_Fiber_TASC | TASC | ZRQ-13-R | Zarqa | 535 | 32.0266 | 36.0513 | Zarqa | Tower | [36 empty] | Approved
1008 | 1008-Zawahrah_CRL_PC_Fiber_TASC_O | TASC | ZRQ-271-R | Zarqa |  | 32.0682 | 36.0699 | Zarqa | Tower | [36 empty] | Approved
1046 | 1046-Jabal_Tareq_CTR_PE_O | TASC | ZRQ-250-R | Zarqa |  | 32.0393 | 36.0984 | Zarqa | Pole | [36 empty] | Approved
1036 | 1036-Zawahrah_3_PE | TASC | ZRQ-216-R | Zarqa | 1810 | 32.0661 | 36.0582 | Zarqa | Pole | [36 empty] | Approved
2804 | 2804-Delail_Ind_PC_Fiber_Zain_TASC | TASC | ZRQ-71-G | Zarqa | 561 | 32.1124 | 36.2969 | Zarqa | Tower | [36 empty] | Approved
802 | 802-Jada_PA_Fiber_TASC | TASC | KRK-2-G | Karak | 813 | 31.3816 | 35.7511 | Karak | Tower | [36 empty] | Approved
811 | 811-Sarfa_PD_EBand_TASC | TASC | KRK-125-G | Karak | 938 | 31.3544 | 35.682 | Karak | Tower | [36 empty] | Approved
887 | 887-Karak_Yarout_PE_TASC_O | TASC | KRK-181-R | Karak |  | 31.2952 | 35.725 | Karak | Tower | [36 empty] | Approved
1540 | 1540-Adassiyah_PC_Fiber_TASC | TASC | MAD-39-G | Amman | 189 | 31.8415 | 35.6945 | Amman | Tower | [36 empty] | Approved
827 | 827-Karak_City_PE_Fiber_TASC_Relo_O | TASC | KRK-261-R | Karak | 998 | 31.1835 | 35.7034 | Karak | Tower | [36 empty] | Approved
1022 | 1022-Hay_Janaa_2_PC_EBand_TASC | TASC | ZRQ-160-R | Zarqa | 567 | 32.0483 | 36.0889 | Zarqa | Tower | [36 empty] | Approved
866 | 866-Karak_Shop_PE_Fiber_TASC_Relo_O | TASC | KRK-263-R | Karak |  | 31.1861 | 35.7026 | Karak | Tower | [36 empty] | Approved
3309 | 3309-Mahmoudeh_Karak_PD_Fiber_TASC_O | TASC | KRK-167-R | Karak |  | 31.1199 | 35.6963 | Karak | Tower | [36 empty] | Approved
3359 | 3359-Abiad_City_PA_Fiber_TASC | TASC | KRK-47-G | Karak | 802 | 30.9706 | 36.0098 | Karak | Tower | [36 empty] | Approved
1920 | 1920-Zarqa_Jadedah_3_PE_EBand_TASC | TASC | ZRQ-74-R | Zarqa | 525 | 32.0882 | 36.0965 | Zarqa | Pole | [36 empty] | Approved
3114 | 3114-Jabal_Shamali_Hay_Shaheed_PE_TASC_O | TASC | ZRQ-257-R | Zarqa |  | 32.0271 | 36.0336 | Zarqa | Tower | [36 empty] | Approved
3348 | 3348-Qatraneh_North_PD_Fiber_TASC_O | TASC | KRK-240-R | Karak |  | 31.2547 | 36.0498 | Karak | Tower | [36 empty] | Approved
4304 | 4304-Zarqa_Ind_2_PE_Zain_TASC | TASC | ZRQ-207-G | Amman | 1803 | 32.0119 | 36.0874 | Amman | Tower | [36 empty] | Approved
3313 | 3313-Um_Rasas_Ent_PC_Fiber_TASC | TASC | KRK-13-G | Amman | 804 | 31.4928 | 36.0602 | Amman | Tower | [36 empty] | Approved
2805 | 2805-Delail_PC_Fiber_TASC | TASC | ZRQ-72-G | Zarqa | 533 | 32.1331 | 36.2718 | Zarqa | Tower | [36 empty] | Approved
4319 | 4319-Zarqa_Qadesieh_PF_TASC_O | TASC | ZRQ-201-R | Zarqa |  | 32.0367 | 36.0264 | Zarqa | Pole | [36 empty] | Approved
836 | 836-Bateer_KaraK_PE_TASC_O | TASC | KRK-236-R | Karak |  | 31.2619 | 35.7024 | Karak | Tower | [36 empty] | Approved
1020 | 1020-Hay_Nuzha_2_PC_Fiber_TASC | TASC | ZRQ-144-R | Zarqa | 576 | 32.052 | 36.0723 | Zarqa | Pole | [36 empty] | Approved
3305 | 3305-Ghwair_PE_TASC | TASC | KRK-145-R | Karak | 978 | 31.1431 | 35.7496 | Karak | Tower | [36 empty] | Approved
4214 | 4214-Jawad_Bakery_Zarqa_PD_Fiber_TASC | TASC | ZRQ-44-R | Zarqa | 540 | 32.0684 | 36.0902 | Zarqa | Pole | [36 empty] | Approved
4350 | 4350-Jabal_Shamali_Qadesieh_PE | TASC | ZRQ-221-R | Zarqa | 1815 | 32.0402 | 36.0445 | Zarqa | Pole | [36 empty] | Approved
3372 | 3372-Talbieh_Karak_PE_EBand_TASC | TASC | KRK-70-G | Karak | 922 | 31.0352 | 35.6409 | Karak | Tower | [36 empty] | Approved
1582 | 1582-King_Hussein_Bridge_PB_Fiber_TASC | TASC | MAD-42-G | Balqa | 163 | 31.8908 | 35.5778 | Balqa | Tower | [36 empty] | Approved
3351 | 3351-Wadi_Abiad_PC_EBand_Zain_TASC | TASC | KRK-9-G | Karak | 801 | 31.0166 | 36.0314 | Karak | Tower | [36 empty] | Approved
4312 | 4312-Russayfah_Zoo_PB_Fiber_TASC | TASC | ZRQ-104-G | Zarqa | 521 | 32.0111 | 36.0473 | Zarqa | Tower | [36 empty] | Approved
5848 | 5848-Ghor_Safi_North_PE_Fiber_TASC_O | TASC | KRK-241-R | Karak |  | 31.0413 | 35.49 | Karak | Tower | [36 empty] | Approved
4360 | 4360-Jabal_Shamali_Tariq_Sch_PE_TASC_O | TASC | ZRQ-258-R | Zarqa |  | 32.0321 | 36.0319 | Zarqa | Tower | [36 empty] | Approved
3345 | 3345-Karak_Mazar_Mutah_West_PD_Fiber_TASC_O | TASC | KRK-222-R | Karak |  | 31.0779 | 35.6918 | Karak | Tower | [36 empty] | Approved
830 | 830-Masaar_Karak_PE_TASC_O | TASC | KRK-226-R | Karak |  | 31.4039 | 35.7523 | Karak | Tower | [36 empty] | Approved
4303 | 4303-Russayfah_2_PB_Fiber_TASC | TASC | ZRQ-96-R | Zarqa | 520 | 32.0214 | 36.0473 | Zarqa | Pole | [36 empty] | Approved
5809 | 5809-Tafilah_Alfares_Hotel_PF_TASC_O | TASC | TAF-48-R | Tafila |  | 30.8403 | 35.6511 | Tafila | Pole | [36 empty] | Approved
4343 | 4343-Russayfah_Aratfeh_PE_EBand_TASC_O | TASC | ZRQ-269-R | Zarqa |  | 32.0162 | 36.054 | Zarqa | Tower | [36 empty] | Approved
1044 | 1044-Jabal_Abiyad_PE_EBand_TASC_O | TASC | ZRQ-239-R | Zarqa |  | 32.0503 | 36.0824 | Zarqa | Pole | [36 empty] | Approved
860 | 860-Msherfet_Um_Rsas_PE_TASC | TASC | KRK-59-G | Amman | 901 | 31.491 | 35.8686 | Amman | Tower | [36 empty] | Approved
3370 | 3370-Hashmia_Karak_CTR_PF_EBand_TASC_O | TASC | KRK-260-R | Karak |  | 31.0135 | 35.7109 | Karak | Tower | [36 empty] | Approved
3391 | 3391-Madian_Karak_PF_TASC_O | TASC | KRK-239-R | Karak |  | 31.1207 | 35.7219 | Karak | Pole | [36 empty] | Approved
852 | 852-Karak_Marj_HSG_PC_Fiber_TASC | TASC | KRK-52-R | Karak | 911 | 31.1748 | 35.7095 | Karak | Tower | [36 empty] | Approved
1546 | 1546-Kafrain_PE_Zain_TASC | TASC | MAD-45-G | Balqa | 222 | 31.8512 | 35.6605 | Balqa | Tower | [36 empty] | Approved
2833 | 2833-Hashmia_Balaama_Rd_PE_TASC | TASC | ZRQ-26-G | Mafraq | 619 | 32.1723 | 36.1118 | Mafraq | Tower | [36 empty] | Approved
3312 | 3312-Karak_Qatraneh_Rd_PF_TASC | TASC | KRK-12-G | Karak | 929 | 31.2204 | 35.9211 | Karak | Tower | [36 empty] | Approved
1519 | 1519-Jawasreh_PC_Fiber_Zain_TASC | TASC | MAD-187-G | Balqa | 68 | 31.8673 | 35.6375 | Balqa | Tower | [36 empty] | Approved
831 | 831-Ader_Karak_PF_TASC_O | TASC | KRK-229-R | Karak |  | 31.2089 | 35.755 | Karak | Pole | [36 empty] | Approved
806 | 806-Fagoue_Market_PF_EBand_TASC_O | TASC | KRK-200-R | Karak |  | 31.3689 | 35.7009 | Karak | Tower | [36 empty] | Approved
3383 | 3383-Mutah_West_PD_Fiber_TASC_O | TASC | KRK-187-R | Karak |  | 31.0884 | 35.6913 | Karak | Tower | [36 empty] | Approved
4330 | 4330-Sanabel_Factory_PE_TASC_O | TASC | ZRQ-19-R | Zarqa | 529 | 32.0291 | 36.0742 | Zarqa | Pole | [36 empty] | Approved
3346 | 3346-Damkhi_PD_Fiber_TASC | TASC | KRK-46-G | Amman | 827 | 31.3409 | 36.0769 | Amman | Tower | [36 empty] | Approved
5898 | 5898-Ibin_Hammad_Dam_PF_TASC_O | TASC | KRK-216-R | Karak |  | 31.2945 | 35.5606 | Karak | Pole | [36 empty] | Approved
5851 | 5851-Fifa_North_PB_Fiber_TASC | TASC | KRK-51-G | Karak | 876 | 31.0384 | 35.4458 | Karak | Tower | [36 empty] | Approved
884 | 884-Karak_Rawda_PD_Fiber_TASC_O | TASC | KRK-195-R | Karak |  | 31.2521 | 35.7385 | Karak | Pole | [36 empty] | Approved
3384 | 3384-Mutah_Uni_Main_PF_EBand_TASC_O | TASC | KRK-182-R | Karak |  | 31.0954 | 35.7174 | Karak | Pole | [36 empty] | Approved
837 | 837-Joza_North_Karak_PF_TASC_O | TASC | KRK-248-R | Karak |  | 31.1608 | 35.6459 | Karak | Pole | [36 empty] | Approved
5846 | 5846-Naqiaa_Ghor_Safi_PE_Fiber_TASC_O | TASC | KRK-242-R | Karak |  | 31.0227 | 35.4793 | Karak | Pole | [36 empty] | Approved
3363 | 3363-Khaldieh_Karak_PE_TASC_O | TASC | KRK-158-R | Karak |  | 31.0305 | 35.7372 | Karak | Tower | [36 empty] | Approved
3353 | 3353-Karak_Hospital_PC_Fiber_TASC | TASC | KRK-53-R | Karak | 914 | 31.1324 | 35.7194 | Karak | Tower | [36 empty] | Approved
1917 | 1917-Jabal_Mughayer_PE_Fiber_TASC | TASC | ZRQ-170-R | Zarqa | 586 | 32.0947 | 36.0828 | Zarqa | Tower | [36 empty] | Approved
883 | 883-Karak_Ruba_Market_PD_Fiber_TASC_O | TASC | KRK-194-R | Karak |  | 31.2671 | 35.7359 | Karak | Tower | [36 empty] | Approved
5814 | 5814-Fifa_PA_Fiber_TASC | TASC | KRK-14-G | Karak | 956 | 30.9384 | 35.4503 | Karak | Tower | [36 empty] | Approved
832 | 832-Sheehan_Village_Karak_PE_Fiber_TASC_O | TASC | KRK-228-R | Karak |  | 31.3643 | 35.7479 | Karak | Pole | [36 empty] | Approved
3315 | 3315-Daba_Desert_Rd_PC_Fiber_TASC | TASC | KRK-131-G | Amman | 959 | 31.5938 | 36.0042 | Amman | Tower | [36 empty] | Approved
1544 | 1544-Rawda_Aghwar_PF_O | TASC | BLQ-151-R | Balqa |  | 31.8274 | 35.6717 | Balqa | Tower | [36 empty] | Approved
3336 | 3336-Iraq_Karak_Ent_PF_TASC | TASC | KRK-36-G | Karak | 883 | 31.1053 | 35.6463 | Karak | Tower | [36 empty] | Approved
1517 | 1517-Sweimeh_JV_PA_Fiber_TASC | TASC | MAD-122-G | Balqa | 932 | 31.8007 | 35.5929 | Balqa | Tower | [36 empty] | Approved
1590 | 1590-South_Shouneh_TL_PD_O | TASC | BLQ-178-R | Balqa |  | 31.8996 | 35.6208 | Balqa | Pole | [36 empty] | Approved
3306 | 3306-Swaqa_PB_Fiber_TASC | TASC | KRK-6-G | Amman | 841 | 31.4056 | 36.1019 | Amman | Tower | [36 empty] | Approved
849 | 849-Ain_Sarah_PE_Fiber_TASC_O | TASC | KRK-49-G | Karak |  | 31.1931 | 35.6923 | Karak | Tower | [36 empty] | Approved
835 | 835-Wadi_Bani_Hammad_PE_TASC | TASC | KRK-35-G | Karak | 891 | 31.2926 | 35.7 | Karak | Tower | [36 empty] | Approved
3382 | 3382-Hussainiah_Karak_PF_EBand_TASC_O | TASC | KRK-178-R | Karak |  | 31.0233 | 35.724 | Karak | Pole | [36 empty] | Approved
842 | 842-Sakka_Karak_PE_Fiber_TASC_O | TASC | KRK-231-R | Karak |  | 31.2048 | 35.6604 | Karak | Pole | [36 empty] | Approved
807 | 807-Samra_Karak_PF_EBand_TASC_O | TASC | KRK-234-R | Karak |  | 31.2003 | 35.657 | Karak | Pole | [36 empty] | Approved
1541 | 1541-Rawda_Ramah_PE_O | TASC | BLQ-144-R | Balqa |  | 31.83 | 35.6591 | Balqa | Pole | [36 empty] | Approved
875 | 875-Zahoom_Karak_PF_TASC_O | TASC | KRK-154-R | Karak |  | 31.1704 | 35.7612 | Karak | Pole | [36 empty] | Approved
804 | 804-Alamro_Village_Karak_PD_EBand_TASC | TASC | KRK-139-G | Karak | 971 | 31.4135 | 35.7757 | Karak | Tower | [36 empty] | Approved
3354 | 3354-Zmaileh_Desert_Rd_PE_TASC_O | TASC | KRK-249-R | Amman |  | 31.5452 | 36.0467 | Amman | Tower | [36 empty] | Approved
3389 | 3389-Manshiet_Mazar_Karak_PF_TASC_O | TASC | KRK-230-R | Karak |  | 31.0458 | 35.6824 | Karak | Pole | [36 empty] | Approved
2836 | 2836-Sukhneh_PC_Fiber_TASC | TASC | ZRQ-27-G | Zarqa | 667 | 32.1269 | 36.0723 | Zarqa | Tower | [36 empty] | Approved
5863 | 5863-South_Fifa_PE_Fiber_TASC | TASC | TAF-12-G | Karak | 910 | 30.8859 | 35.4218 | Karak | Tower | [36 empty] | Approved
1174 | 1174-Zaatari_East_Camp_PE_Zain_TASC_O | TASC | MFQ-110-R | Mafraq | 1824 | 32.2917 | 36.3448 | Mafraq | Tower | [36 empty] | Approved
4767 | 4767-Mafraq_Hay_Husban_PE_Fiber_TASC_O | TASC | MFQ-141-R | Mafraq |  | 32.3469 | 36.1892 | Mafraq | Tower | [36 empty] | Approved
4797 | 4797-Mafraq_Ave_PE_Fiber_Zain_O | TASC | MFQ-109-R | Mafraq |  | 32.3258 | 36.2094 | Mafraq | Tower | [36 empty] | Approved
4205 | 4205-Cinema_Salwa_PE_Fiber_TASC | TASC | ZRQ-35-R | Zarqa | 530 | 32.0648 | 36.0937 | Zarqa | Pole | [36 empty] | Approved
1955 | 1955-Batrawi_Ave_End_PD_O | TASC | ZRQ-268-R | Zarqa |  | 32.1011 | 36.0973 | Zarqa | Pole | [36 empty] | Approved
4783 | 4783-BSC_AlBait_Uni_PA_Fiber_TASC | TASC | MFQ-60-G | Mafraq | 774 | 32.3247 | 36.2284 | Mafraq | Tower | [36 empty] | Approved
1110 | 1110-Sabha_PC_Fiber_TASC | TASC | MFQ-10-G | Mafraq | 675 | 32.2986 | 36.4956 | Mafraq | Tower | [36 empty] | Approved
4217 | 4217-Zarqa_Post_PF_TASC | TASC | ZRQ-139-R | Zarqa | 564 | 32.0578 | 36.0843 | Zarqa | Tower | [36 empty] | Approved
1128 | 1128-Traibeel_PD_Fiber_TASC | TASC | MFQ-28-G | Mafraq |  | 32.686 | 38.9133 | Mafraq | Tower | [36 empty] | Approved
2848 | 2848-Hallabat_Palace_PB_Fiber_TASC | TASC | ZRQ-91-G | Zarqa | 538 | 32.0603 | 36.31 | Zarqa | Tower | [36 empty] | Approved
1141 | 1141-Princess_Bassma_Village_PE_O | TASC | MFQ-97-G | Mafraq |  | 32.2926 | 36.3844 | Mafraq | Tower | [36 empty] | Approved
2817 | 2817-FreeZone_Vehicles_PF_TASC_O | TASC | ZRQ-133-R | Zarqa |  | 32.0955 | 36.2105 | Zarqa | Pole | [36 empty] | Approved
4732 | 4732-Rehab_CTR_PE | TASC | MFQ-90-R | Mafraq | 1807 | 32.3228 | 36.0919 | Mafraq | Tower | [36 empty] | Approved
1123 | 1123-Safawi_PA_Fiber_TASC | TASC | MFQ-23-G | Mafraq | 677 | 32.1929 | 37.1265 | Mafraq | Tower | [36 empty] | Approved
4750 | 4750-Manshiet_Bani_Hassan_2_PD_Fiber_O | TASC | MFQ-143-R | Mafraq |  | 32.3737 | 36.0779 | Mafraq | Tower | [36 empty] | Approved
1908 | 1908-Shola_Hall_Zarqa_PF_TASC | TASC | ZRQ-38-R | Zarqa | 537 | 32.0862 | 36.108 | Zarqa | Pole | [36 empty] | Approved
1116 | 1116-Hamedieh_PA_Fiber_TASC | TASC | MFQ-16-G | Mafraq | 644 | 32.202 | 36.665 | Mafraq | Tower | [36 empty] | Approved
2827 | 2827-FreeZone_Well_Room_PF_TASC_O | TASC | ZRQ-137-R | Zarqa |  | 32.0849 | 36.2281 | Zarqa | Pole | [36 empty] | Approved
4227 | 4227-Zarqa_Camp_PF_TASC | TASC | ZRQ-150-R | Zarqa | 580 | 32.0581 | 36.0896 | Zarqa | Tower | [36 empty] | Approved
1119 | 1119-Rahbet_Rakkad_PE_TASC | TASC | MFQ-87-G | Mafraq | 2123 | 32.2218 | 36.604 | Mafraq | Tower | [36 empty] | Approved
4704 | 4704-Rehab_PE_TASC_O | TASC | MFQ-4-G | Mafraq |  | 32.3099 | 36.0767 | Mafraq | Tower | [36 empty] | Approved
4723 | 4723-Um_Naam_PC_Fiber_TASC | TASC | MFQ-82-G | Mafraq | 2115 | 32.3513 | 36.14 | Mafraq | Tower | [36 empty] | Approved
1921 | 1921-Zarqa_Crafts_City_PF_TASC_O | TASC | ZRQ-274-R | Zarqa |  | 32.0965 | 36.111 | Zarqa | Tower | [36 empty] | Approved
1101 | 1101-Showaier_PC_Fiber_TASC_Solar | TASC | MFQ-1-G | Zarqa | 674 | 31.9797 | 36.4854 | Zarqa | Tower | [36 empty] | Approved
4733 | 4733-Hay_Hussein_Mafraq_PC_Fiber | TASC | MFQ-93-R | Mafraq | 1814 | 32.3532 | 36.2082 | Mafraq | Tower | [36 empty] | Approved
4792 | 4792-Hay_Zohoor_Mafraq_PE_O | TASC | MFQ-142-R | Mafraq |  | 32.3398 | 36.197 | Mafraq | Pole | [36 empty] | Approved
1914 | 1914-Shomar_PE_TASC | TASC | ZRQ-14-R | Zarqa | 558 | 32.0871 | 36.0631 | Zarqa | Tower | [36 empty] | Approved
1147 | 1147-Baej_PC_EBand_TASC | TASC | MFQ-46-G | Mafraq | 640 | 32.3684 | 36.333 | Mafraq | Tower | [36 empty] | Approved
4737 | 4737-Dajanya_PD_TASC | TASC | MFQ-29-R | Mafraq | 2129 | 32.3395 | 36.0255 | Mafraq | Tower | [36 empty] | Approved
1129 | 1129-Deir_Kahf_PE_TASC | TASC | MFQ-80-G | Mafraq | 2106 | 32.2783 | 36.8395 | Mafraq | Tower | [36 empty] | Approved
2803 | 2803-FreeZone_Tafeh_PB_TASC | TASC | ZRQ-70-G | Zarqa | 547 | 32.0495 | 36.2346 | Zarqa | Tower | [36 empty] | Approved
1125 | 1125-Ruwaished_PA_Fiber_TASC | TASC | MFQ-25-G | Mafraq | 661 | 32.5075 | 38.1985 | Mafraq | Tower | [36 empty] | Approved
1112 | 1112-Tal_Asfar_PD_TASC | TASC | MFQ-12-G | Mafraq | 579 | 32.1892 | 36.8913 | Mafraq | Tower | [36 empty] | Approved
4738 | 4738-Sama_Sarhan_PC_EBand_TASC | TASC | MFQ-112-R | Mafraq | 1823 | 32.4657 | 36.2403 | Mafraq | Tower | [36 empty] | Approved
1146 | 1146-Salhya_PC_TASC | TASC | MFQ-45-G | Mafraq | 711 | 32.2359 | 36.5544 | Mafraq | Tower | [36 empty] | Approved
4789 | 4789-AlBait_Uni_Bani_Hashem_PE_Fiber_TASC_O | TASC | MFQ-135-R | Mafraq |  | 32.3294 | 36.2426 | Mafraq | Pole | [36 empty] | Approved
2852 | 2852-Sukhneh_2_PD_O | TASC | JRS-40-R | Zarqa |  | 32.1346 | 36.0729 | Zarqa | Tower | [36 empty] | Approved
4796 | 4796-Hashmi_Mafraq_End_PE_O | TASC | MFQ-137-R | Mafraq |  | 32.3292 | 36.1823 | Mafraq | Tower | [36 empty] | Approved
4786 | 4786-Hashmi_Mafraq_PE_EBand_TASC | TASC | MFQ-89-G | Mafraq | 2125 | 32.3272 | 36.1929 | Mafraq | Tower | [36 empty] | Approved
4734 | 4734-Mafraq_3_PC_Fiber_TASC | TASC | MFQ-101-R | Mafraq | 1820 | 32.348 | 36.2125 | Mafraq | Tower | [36 empty] | Approved
1106 | 1106-Um_Ejjmal_PB_Fiber_TASC | TASC | MFQ-6-G | Mafraq | 620 | 32.3244 | 36.3646 | Mafraq | Tower | [36 empty] | Approved
4728 | 4728-Bwaidah_Ramtha_PD_TASC | TASC | IRB-238-R | Irbid | 2124 | 32.4726 | 36.0602 | Irbid | Tower | [36 empty] | Approved
1105 | 1105-Dafianeh_PE_TASC | TASC | MFQ-5-G | Mafraq | 649 | 32.3102 | 36.5651 | Mafraq | Tower | [36 empty] | Approved
2814 | 2814-Khaw_PE | TASC | ZRQ-79-G | Zarqa | 573 | 32.0927 | 36.1451 | Zarqa | Tower | [36 empty] | Approved
1149 | 1149-Saaedieh_PB_Fiber_TASC | TASC | MFQ-48-G | Mafraq | 723 | 32.27 | 36.4489 | Mafraq | Tower | [36 empty] | Approved
1113 | 1113-Tal_Remah_PF_TASC | TASC | MFQ-62-G | Mafraq | 772 | 32.3106 | 36.8884 | Mafraq | Tower | [36 empty] | Approved
4714 | 4714-Deir_Waraq_PB_Fiber_TASC | TASC | MFQ-52-G | Mafraq | 654 | 32.3682 | 36.0447 | Mafraq | Tower | [36 empty] | Approved
1145 | 1145-Um_Qutain_PE_TASC | TASC | MFQ-44-G | Mafraq | 636 | 32.3065 | 36.6386 | Mafraq | Tower | [36 empty] | Approved
4702 | 4702-Manshiet_Bani_Hassan_PC_Fiber_TASC | TASC | MFQ-50-G | Mafraq | 759 | 32.3708 | 36.0878 | Mafraq | Tower | [36 empty] | Approved
1153 | 1153-Zbedyeh_Mafraq_PF_TASC_O | TASC | MFQ-216-R | Mafraq |  | 32.3794 | 36.2921 | Mafraq | Tower | [36 empty] | Approved
1140 | 1140-Um_Serb_PE_TASC | TASC | MFQ-40-G | Mafraq | 621 | 32.4349 | 36.3139 | Mafraq | Tower | [36 empty] | Approved
1118 | 1118-Zamlet_Amir_Ghazi_PF_TASC_O | TASC | MFQ-203-R | Mafraq |  | 32.2536 | 36.5046 | Mafraq | Tower | [36 empty] | Approved
4716 | 4716-Hamra_Mafraq_PC_TASC | TASC | MFQ-75-R | Mafraq | 795 | 32.4408 | 36.1525 | Mafraq | Tower | [36 empty] | Approved
4740 | 4740-Thagret_Jub_Mafraq_Rd_PF_TASC_Solar_O | TASC | MFQ-115-G | Mafraq |  | 32.2394 | 36.2521 | Mafraq | Tower | [36 empty] | Approved
4761 | 4761-Thagret_Jub_Village_PE | TASC | MFQ-114-G | Mafraq | 1825 | 32.2699 | 36.2289 | Mafraq | Tower | [36 empty] | Approved
1114 | 1114-Nasereya_PA_Fiber | TASC | MFQ-14-G | Mafraq | 720 | 32.3157 | 36.3153 | Mafraq | Tower | [36 empty] | Approved
4712 | 4712-Znyeah_PC_TASC | TASC | AJL-2-G | Mafraq | 656 | 32.2023 | 36.105 | Mafraq | Tower | [36 empty] | Approved
4748 | 4748-Mafraq_West_PC_Fiber_TASC | TASC | MFQ-47-R | Mafraq | 664 | 32.3462 | 36.2011 | Mafraq | Pole | [36 empty] | Approved
1155 | 1155-Koam_Alahmar_Mafraq_PF_TASC | TASC | MFQ-91-G | Mafraq | 2137 | 32.3633 | 36.3946 | Mafraq | Tower | [36 empty] | Approved
4209 | 4209-Hawouz_Back_Zarqa_PE_Fiber_O | TASC | ZRQ-264-R | Zarqa |  | 32.0643 | 36.0878 | Zarqa | Pole | [36 empty] | Approved
1188 | 1188-Um_Qutain_2_PF_O | TASC | MFQ-146-R | Mafraq |  | 32.314 | 36.6307 | Mafraq | Tower | [36 empty] | Approved
4726 | 4726-Rabaa_Serhan_PE_TASC | TASC | MFQ-84-G | Mafraq | 2114 | 32.4219 | 36.2387 | Mafraq | Tower | [36 empty] | Approved
4715 | 4715-Edoon_Bani_Hassan_PE_EBand_TASC_O | TASC | ZRQ-68-G | Mafraq |  | 32.3049 | 36.1712 | Mafraq | Tower | [36 empty] | Approved
1135 | 1135-Karameh_Border_PA_Fiber_TASC | TASC | MFQ-68-G | Mafraq | 778 | 32.7253 | 38.9849 | Mafraq | Tower | [36 empty] | Approved
1127 | 1127-Subhieh_PC_Fiber_TASC | TASC | MFQ-27-G | Mafraq | 710 | 32.34 | 36.4888 | Mafraq | Tower | [36 empty] | Approved
2826 | 2826-FreeZone_Safety_PE_O | TASC | ZRQ-131-R | Zarqa |  | 32.0937 | 36.2175 | Zarqa | Pole | [36 empty] | Approved
4701 | 4701-Hayan_Rowaibed_PF_TASC | TASC | ZRQ-90-G | Mafraq | 572 | 32.265 | 36.1519 | Mafraq | Tower | [36 empty] | Approved
1918 | 1918-Jabal_Mughayer_2_PE_Fiber_TASC | TASC | ZRQ-202-R | Zarqa | 1800 | 32.089 | 36.084 | Zarqa | Pole | [36 empty] | Approved
4711 | 4711-Balaama_PC_O | TASC | MFQ-127-G | Mafraq |  | 32.2571 | 36.0914 | Mafraq | Tower | [36 empty] | Approved
4724 | 4724-Sweilmeh_PD_EBand_TASC_O | TASC | MFQ-73-G | Mafraq |  | 32.4824 | 36.1579 | Mafraq | Tower | [36 empty] | Approved
4225 | 4225-Hay_Nuzha_PF_TASC | TASC | ZRQ-16-R | Zarqa | 513 | 32.0345 | 36.0452 | Zarqa | Pole | [36 empty] | Approved
4727 | 4727-Khanasri_Mafraq_PD_TASC | TASC | MFQ-86-G | Mafraq | 2122 | 32.4092 | 36.0579 | Mafraq | Tower | [36 empty] | Approved
2870 | 2870-Hashmia_Uni_CTR_PF_TASC_O | TASC | ZRQ-272-R | Zarqa |  | 32.1034 | 36.1857 | Zarqa | Pole | [36 empty] | Approved
4703 | 4703-Hosha_PC_TASC | TASC | MFQ-51-G | Mafraq | 647 | 32.4478 | 36.0957 | Mafraq | Tower | [36 empty] | Approved
1011 | 1011-Prince_Rashid_CPLX_Zarqa_PF_O | TASC | ZRQ-284-R | Zarqa |  | 32.0553 | 36.0928 | Zarqa | Tower | [36 empty] | Approved
2894 | 2894-Mafraq_Rd_PD_TASC | TASC | MFQ-49-G | Zarqa | 534 | 32.1631 | 36.219 | Zarqa | Tower | [36 empty] | Approved
3320 | 3320-Merwed_Meddein_PE_TASC | TASC | KRK-144-R | Karak | 979 | 31.1077 | 35.7218 | Karak | Tower | [36 empty] | Approved
4233 | 4233-Ghwereieh_Prince_Mohammed_Msq_PF_TASC_O | TASC | ZRQ-267-R | Zarqa |  | 32.0749 | 36.0919 | Zarqa | Pole | [36 empty] | Approved
4784 | 4784-AlBait_Uni_Quraish_PE_Fiber_TASC_O | TASC | MFQ-136-R | Mafraq |  | 32.3376 | 36.2405 | Mafraq | Pole | [36 empty] | Approved
2811 | 2811-Khaldieh_PB_Fiber_TASC | TASC | ZRQ-78-G | Mafraq | 517 | 32.1819 | 36.32 | Mafraq | Tower | [36 empty] | Approved
1103 | 1103-Refaayat_PE_TASC | TASC | MFQ-3-G | Mafraq | 666 | 32.2626 | 36.7167 | Mafraq | Tower | [36 empty] | Approved
4707 | 4707-Akedar_PE_O | TASC | IRB-95-G | Mafraq |  | 32.5009 | 36.0868 | Mafraq | Tower | [36 empty] | Approved
4763 | 4763-Jaber_Border_PB_Fiber_TASC | TASC | MFQ-66-G | Mafraq | 775 | 32.5105 | 36.1913 | Mafraq | Tower | [36 empty] | Approved
4713 | 4713-Hamamet_Omoush_PF_TASC_O | TASC | MFQ-13-G | Mafraq |  | 32.3191 | 36.0307 | Mafraq | Tower | [36 empty] | Approved
2893 | 2893-Kherbeh_Samra_PF_Zain_TASC_Relo_O | TASC | MFQ-236-R | Mafraq |  | 32.184 | 36.1638 | Mafraq | Tower | [36 empty] | Approved
4334 | 4334-Jabal_Shamali_CTR_PE_Fiber_TASC_O | TASC | ZRQ-290-R | Zarqa |  | 32.0281 | 36.0423 | Zarqa | Pole | [36 empty] | Approved
1164 | 1164-Aqib_Mafraq_PF_TASC_O | TASC | MFQ-226-R | Mafraq |  | 32.2718 | 36.4094 | Mafraq | Pole | [36 empty] | Approved
1160 | 1160-Subhieh_Esyar_Mafraq_PE_Fiber_TASC_O | TASC | MFQ-212-R | Mafraq |  | 32.3409 | 36.4668 | Mafraq | Pole | [36 empty] | Approved
4742 | 4742-Hamra_Mafraq_End_PD_TASC_O | TASC | MFQ-168-R | Mafraq |  | 32.4293 | 36.1455 | Mafraq | Pole | [36 empty] | Approved
1915 | 1915-Jabal_Mughayer_Badi_CRL_PE_Fiber_TASC_O | TASC | ZRQ-302-R | Zarqa |  | 32.0923 | 36.0797 | Zarqa | Tower | [36 empty] | Approved
4744 | 4744-Mansoura_Mafraq_PD_O | TASC | MFQ-153-G | Mafraq |  | 32.4187 | 36.1621 | Mafraq | Tower | [36 empty] | Approved
4766 | 4766-Sama_Sarhan_CTR_PD_TASC_O | TASC | MFQ-165-R | Mafraq |  | 32.4723 | 36.2401 | Mafraq | Tower | [36 empty] | Approved
4309 | 4309-Jundi_Ave_PF_TASC_O | TASC | ZRQ-326-R | Zarqa |  | 32.0266 | 36.0773 | Zarqa | Pole | [36 empty] | Approved
1185 | 1185-Hamra_Eshaim_PF_TASC_O | TASC | MFQ-179-R | Mafraq |  | 32.1721 | 36.7646 | Mafraq | Tower | [36 empty] | Approved
4318 | 4318-AbuSayah_Village_PE_TASC_O | TASC | ZRQ-341-R | Amman |  | 31.9947 | 36.0544 | Amman | Pole | [36 empty] | Approved
4316 | 4316-Souq_Talal_HSG_PF_TASC_O | TASC | ZRQ-327-R | Zarqa |  | 32.0301 | 36.0556 | Zarqa | Pole | [36 empty] | Approved
2867 | 2867-Sukhneh_Zarqa_West_PD_Fiber_TASC_O | TASC | ZRQ-332-R | Zarqa |  | 32.1323 | 36.0667 | Zarqa | Pole | [36 empty] | Approved
4749 | 4749-Mafraq_South_Ave_PE_O | TASC | MFQ-188-R | Mafraq |  | 32.3297 | 36.2069 | Mafraq | Tower | [36 empty] | Approved
4720 | 4720-Mafraq_Rehab_Rd_PE_TASC_O | TASC | MFQ-20-G | Mafraq |  | 32.3285 | 36.1318 | Mafraq | Tower | [36 empty] | Approved
2876 | 2876-Delail_CPLX_PD_Fiber_TASC_O | TASC | ZRQ-321-R | Zarqa |  | 32.1207 | 36.2901 | Zarqa | Pole | [36 empty] | Approved
1184 | 1184-Um_Ejjmal_CTR_PF_TASC_O | TASC | MFQ-167-R | Mafraq |  | 32.3372 | 36.357 | Mafraq | Tower | [36 empty] | Approved
4759 | 4759-Ghadeer_Abiad_Mafraq_PF_TASC_O | TASC | MFQ-120-R | Mafraq |  | 32.3791 | 36.2111 | Mafraq | Pole | [36 empty] | Approved
4722 | 4722-Rehab_Electric_Staion_PE_TASC_O | TASC | MFQ-177-R | Mafraq |  | 32.3299 | 36.047 | Mafraq | Tower | [36 empty] | Approved
1013 | 1013-Wadi_Hajar_Region_2_PE_TASC_O | TASC | ZRQ-282-R | Zarqa |  | 32.0355 | 36.0891 | Zarqa | Pole | [36 empty] | Approved
1179 | 1179-Koam_Erraf_Mafraq_PF_TASC_O | TASC | MFQ-181-R | Mafraq |  | 32.3676 | 36.4588 | Mafraq | Pole | [36 empty] | Approved
1182 | 1182-Mkaifteh_Mafraq_PF_TASC_O | TASC | MFQ-184-R | Mafraq |  | 32.2905 | 36.6508 | Mafraq | Tower | [36 empty] | Approved
4202 | 4202-Hay_Ramzi_6th_Region_PE_Fiber_TASC_O | TASC | ZRQ-287-R | Zarqa |  | 32.0755 | 36.0862 | Zarqa | Pole | [36 empty] | Approved
1167 | 1167-Jobayyah_Mafraq_PF_TASC_O | TASC | MFQ-227-R | Mafraq |  | 32.2956 | 36.7904 | Mafraq | Pole | [36 empty] | Approved
3325 | 3325-Mahay_PD_TASC | TASC | KRK-25-G | Karak | 888 | 30.9929 | 35.8603 | Karak | Tower | [36 empty] | Approved
1177 | 1177-Mishref_Mafraq_PF_TASC_O | TASC | MFQ-171-R | Mafraq |  | 32.3883 | 36.3535 | Mafraq | Tower | [36 empty] | Approved
4765 | 4765-Mughayer_Sarhan_CTR_PE_O | TASC | MFQ-164-R | Mafraq |  | 32.4562 | 36.1869 | Mafraq | Pole | [36 empty] | Approved
1168 | 1168-Sabha_Airplane_CRL_PD_Fiber_TASC_O | TASC | MFQ-155-R | Mafraq |  | 32.3304 | 36.5026 | Mafraq | Tower | [36 empty] | Approved
2858 | 2858-Ghabawi_PE_TASC_O | TASC | AME-137-R | Zarqa |  | 31.9996 | 36.2188 | Zarqa | Tower | [36 empty] | Approved
4739 | 4739-Mafraq_Safwa_Sch_Back_PE_TASC_O | TASC | MFQ-220-R | Mafraq |  | 32.3332 | 36.1926 | Mafraq | Tower | [36 empty] | Approved
4756 | 4756-Mafraq_King_Abdullah_Ave_PD_Fiber_TASC_O | TASC | MFQ-223-R | Mafraq |  | 32.3232 | 36.2196 | Mafraq | Tower | [36 empty] | Approved
1152 | 1152-Khasha_Slaiteen_Mafraq_PF_Zain_TASC | TASC | MFQ-92-G | Mafraq | 2136 | 32.3319 | 36.5958 | Mafraq | Tower | [36 empty] | Approved
2864 | 2864-West_Hallabat_PF_O | TASC | ZRQ-298-R | Zarqa |  | 32.0953 | 36.3312 | Zarqa | Pole | [36 empty] | Approved
1144 | 1144-Khaldieh_Mafraq_Rd_PD_Zain_TASC | TASC | MFQ-96-G | Mafraq | 1809 | 32.2648 | 36.2755 | Mafraq | Tower | [36 empty] | Approved
4770 | 4770-Mafraq_Um_Lulo_PF_O | TASC | MFQ-156-R | Mafraq |  | 32.3928 | 36.0937 | Mafraq | Pole | [36 empty] | Approved
816 | 816-Jdaideh_PE_TASC_O | TASC | KRK-129-R | Karak |  | 31.2535 | 35.8121 | Karak | Tower | [36 empty] | Approved
1169 | 1169-Mafraq_Amra_And_Amiereh_PE_O | TASC | MFQ-160-R | Mafraq |  | 32.3042 | 36.4359 | Mafraq | Tower | [36 empty] | Approved
4745 | 4745-Doqmosseh_Mafraq_PF_TASC_O | TASC | MFQ-174-R | Mafraq |  | 32.3125 | 35.992 | Mafraq | Pole | [36 empty] | Approved
4758 | 4758-Um_Naam_West_PE_Fiber_TASC_O | TASC | MFQ-182-R | Mafraq |  | 32.3595 | 36.1098 | Mafraq | Pole | [36 empty] | Approved
4760 | 4760-Bwaidhe_Elaimat_Mafraq_PF_O | TASC | MFQ-175-R | Mafraq |  | 32.3447 | 36.0638 | Mafraq | Tower | [36 empty] | Approved
814 | 814-Karak_Potash_Rd_PF_TASC_Solar_O | TASC | KRK-128-G | Karak |  | 31.2519 | 35.6191 | Karak | Tower | [36 empty] | Approved
1183 | 1183-Refaayat_Village_PF_TASC_O | TASC | MFQ-178-R | Mafraq |  | 32.2611 | 36.7491 | Mafraq | Pole | [36 empty] | Approved
812 | 812-Rashidieh_Karak_PE_Fiber_TASC_O | TASC | KRK-245-R | Karak |  | 31.1942 | 35.7521 | Karak | Pole | [36 empty] | Approved
808 | 808-Mojeb_Valley_PF_TASC_Solar | TASC | KRK-124-G | Madaba | 839 | 31.4737 | 35.791 | Madaba | Tower | [36 empty] | Approved
4743 | 4743-Hayan_East_Mafraq_PF_TASC_O | TASC | MFQ-186-R | Mafraq |  | 32.2437 | 36.1307 | Mafraq | Pole | [36 empty] | Approved
4746 | 4746-Mafraq_North_Ave_PD_Fiber_TASC_O | TASC | MFQ-187-R | Mafraq |  | 32.3284 | 36.2015 | Mafraq | Pole | [36 empty] | Approved
4717 | 4717-Mshairfe_Ghayyath_PF_TASC_O | TASC | IRB-392-R | Jarash |  | 32.3675 | 35.9704 | Jarash | Pole | [36 empty] | Approved
1909 | 1909-Hararieh_HSG_North_PF_TASC_O | TASC | ZRQ-323-R | Zarqa |  | 32.1051 | 36.0915 | Zarqa | Pole | [36 empty] | Approved
5882 | 5882-Ghor_Safi_Club_PE_Fiber_TASC_O | TASC | KRK-161-R | Karak |  | 31.0325 | 35.4873 | Karak | Pole | [36 empty] | Approved
1015 | 1015-Jabal_Hassan_CTR_PF_TASC_O | TASC | ZRQ-338-R | Zarqa |  | 32.0401 | 36.0737 | Zarqa | Pole | [36 empty] | Approved
1907 | 1907-Jabal_Mughayer_East_PD_Fiber_TASC_O | TASC | ZRQ-328-R | Zarqa |  | 32.0953 | 36.0919 | Zarqa | Tower | [36 empty] | Approved
848 | 848-Smakieh_Hmoud_PF_TASC_O | TASC | KRK-143-G | Karak |  | 31.3022 | 35.7992 | Karak | Tower | [36 empty] | Approved
3340 | 3340-Hammamat_Shammout_PF_Zain_TASC_O | TASC | KRK-140-G | Amman |  | 31.6045 | 36.1204 | Amman | Tower | [36 empty] | Approved
4769 | 4769-Mazeh_Mafraq_PF_TASC_O | TASC | MFQ-198-R | Mafraq |  | 32.3198 | 36.1847 | Mafraq | Pole | [36 empty] | Approved
2851 | 2851-Delail_South_PD_Fiber_TASC_O | TASC | ZRQ-322-R | Zarqa |  | 32.108 | 36.2553 | Zarqa | Pole | [36 empty] | Approved
1906 | 1906-New_Zarqa_Civil_Defence_PF_TASC_O | TASC | ZRQ-289-R | Zarqa |  | 32.0854 | 36.082 | Zarqa | Tower | [36 empty] | Approved
4790 | 4790-Harsh_Mafraq_PE_TASC_O | TASC | MFQ-170-R | Mafraq |  | 32.4366 | 36.0523 | Mafraq | Tower | [36 empty] | Approved
4741 | 4741-Balaama_South_PF_TASC_O | TASC | MFQ-190-R | Mafraq |  | 32.2382 | 36.0918 | Mafraq | Tower | [36 empty] | Approved
1052 | 1052-Sharef_Hussein_Hall_Zarqa_PF_TASC_O | TASC | ZRQ-281-R | Zarqa |  | 32.0542 | 36.0871 | Zarqa | Pole | [36 empty] | Approved
2843 | 2843-Delail_CTR_PE_O | TASC | ZRQ-331-R | Zarqa |  | 32.1228 | 36.2662 | Zarqa | Tower | [36 empty] | Approved
1196 | 1196-Omary_PA_Fiber_TASC | TASC | MFQ-41-G | Zarqa | 688 | 31.5356 | 37.074 | Zarqa | Tower | [36 empty] | Approved
4306 | 4306-Tatweer_Hadari_Zarqa_PF_TASC_O | TASC | ZRQ-325-R | Zarqa |  | 32.0362 | 36.0602 | Zarqa | Pole | [36 empty] | Approved
4754 | 4754-Jnaidiyeh_Jerash_PF_TASC_O | TASC | JRS-61-R | Jarash |  | 32.3558 | 35.9881 | Jarash | Tower | [36 empty] | Approved
1186 | 1186-Bishriyeh_Mafraq_PF_O | TASC | MFQ-169-R | Mafraq |  | 32.157 | 36.8132 | Mafraq | Tower | [36 empty] | Approved
5822 | 5822-Ghor_Safi_PC_Fiber_TASC | TASC | KRK-134-G | Karak | 967 | 31.0385 | 35.4802 | Karak | Tower | [36 empty] | Approved
4768 | 4768-Faa_Mafraq_PE_TASC_O | TASC | MFQ-197-R | Mafraq |  | 32.4211 | 36.0833 | Mafraq | Pole | [36 empty] | Approved
1170 | 1170-Azraq_Market_PD_O | TASC | MFQ-161-R | Zarqa |  | 31.8334 | 36.8147 | Zarqa | Pole | [36 empty] | Approved
3303 | 3303-Qatraneh_PA_Fiber_TASC | TASC | KRK-3-G | Karak | 881 | 31.2436 | 36.0451 | Karak | Tower | [36 empty] | Approved
4721 | 4721-Mansoura_Mafraq_South_PF_TASC_O | TASC | MFQ-172-R | Mafraq |  | 32.4096 | 36.182 | Mafraq | Tower | [36 empty] | Approved
2861 | 2861-West_Hallabat_End_PF_TASC_O | TASC | ZRQ-355-R | Zarqa |  | 32.1052 | 36.3184 | Zarqa | Pole | [36 empty] | Approved
4772 | 4772-Noor_Ave_Mafraq_PE_TASC_O | TASC | MFQ-202-R | Mafraq |  | 32.3267 | 36.1579 | Mafraq | Tower | [36 empty] | Approved
2865 | 2865-East_Hallabat_PE_TASC_O | TASC | ZRQ-293-R | Zarqa |  | 32.0815 | 36.3675 | Zarqa | Tower | [36 empty] | Approved
1187 | 1187-Rawdhet_Bassma_PE_O | TASC | MFQ-173-R | Mafraq |  | 32.2936 | 36.3698 | Mafraq | Pole | [36 empty] | Approved
4771 | 4771-Dandaneh_Mafraq_PF_TASC_O | TASC | MFQ-205-R | Mafraq |  | 32.4639 | 36.1549 | Mafraq | Pole | [36 empty] | Approved
2856 | 2856-Delail_Mabroukeh_East_PF_TASC_O | TASC | ZRQ-352-R | Mafraq |  | 32.1438 | 36.2906 | Mafraq | Pole | [36 empty] | Approved
4777 | 4777-Tumera_Irbid_Mafraq_Rd_PF_TASC_O | TASC | MFQ-196-R | Mafraq |  | 32.3909 | 36.0059 | Mafraq | Pole | [36 empty] | Approved
1138 | 1138-Zaied_PD_TASC | TASC | MFQ-38-G | Zarqa |  | 31.9432 | 36.5754 | Zarqa | Tower | [36 empty] | Approved
1122 | 1122-Ashrafyeh_Mafraq_PF_TASC_O | TASC | MFQ-208-R | Mafraq |  | 32.2133 | 36.6287 | Mafraq | Tower | [36 empty] | Approved
5815 | 5815-Potash_PB_EBand_TASC | TASC | KRK-15-G | Karak | 811 | 31.2667 | 35.4639 | Karak | Tower | [36 empty] | Approved
1104 | 1104-Azraq_Zaied_Rd_PA_Fiber_TASC | TASC | MFQ-56-G | Zarqa | 773 | 31.9126 | 36.6154 | Zarqa | Tower | [36 empty] | Approved
3355 | 3355-Sultani_PD_Fiber_TASC_O | TASC | KRK-34-G | Karak |  | 31.1104 | 36.0099 | Karak | Tower | [36 empty] | Approved
879 | 879-Um_Rasas_Salieh_PF_TASC_O | TASC | KRK-157-R | Amman |  | 31.4482 | 35.905 | Amman | Tower | [36 empty] | Approved
3350 | 3350-Mazar_Maqamat_Sahaba_PE_TASC_O | TASC | KRK-237-R | Karak |  | 31.0659 | 35.6997 | Karak | Pole | [36 empty] | Approved
3321 | 3321-Taibeh_Karak_PF_EBand_TASC_O | TASC | KRK-206-R | Karak |  | 31.052 | 35.6052 | Karak | Pole | [36 empty] | Approved
1962 | 1962-Batrawi_Back_PE_Fiber_TASC_O | TASC | ZRQ-350-R | Zarqa |  | 32.0991 | 36.0922 | Zarqa | Pole | [36 empty] | Approved
4779 | 4779-Mafraq_Nawarah_PE_Fiber_TASC_O | TASC | MFQ-207-R | Mafraq |  | 32.3484 | 36.1968 | Mafraq | Tower | [36 empty] | Approved
2857 | 2857-Khaldieh_End_PD_TASC_O | TASC | ZRQ-354-R | Mafraq |  | 32.1855 | 36.3273 | Mafraq | Pole | [36 empty] | Approved
4310 | 4310-Zarqa_Awajan_North_PF_TASC_O | TASC | ZRQ-345-R | Zarqa |  | 32.0265 | 36.0644 | Zarqa | Pole | [36 empty] | Approved
829 | 829-Karak_Baqee_PF_TASC_O | TASC | KRK-227-R | Karak |  | 31.2216 | 35.6417 | Karak | Pole | [36 empty] | Approved
1581 | 1581-South_Shouneh_City_PC_Fiber_TASC | TASC | MAD-24-G | Balqa | 164 | 31.8946 | 35.6124 | Balqa | Tower | [36 empty] | Approved
4781 | 4781-Bwedet_Hawamdeh_PE_Fiber_TASC_O | TASC | MFQ-224-R | Mafraq |  | 32.3417 | 36.1572 | Mafraq | Pole | [36 empty] | Approved
2869 | 2869-Delail_Cows_Farm_PF_TASC_O | TASC | ZRQ-359-R | Zarqa |  | 32.135 | 36.3129 | Zarqa | Tower | [36 empty] | Approved
4775 | 4775-Moamarya_Balaama_PF_TASC_O | TASC | MFQ-217-R | Mafraq |  | 32.2815 | 36.0994 | Mafraq | Pole | [36 empty] | Approved
5895 | 5895-Ghor_Haditheh_CTR_PE_EBand_TASC_O | TASC | KRK-232-R | Karak |  | 31.2902 | 35.5375 | Karak | Tower | [36 empty] | Approved
4774 | 4774-Mafraq_Tayib_Esim_PF_TASC_O | TASC | MFQ-209-R | Mafraq |  | 32.3618 | 36.1658 | Mafraq | Pole | [36 empty] | Approved
1199 | 1199-Baej_InterX_PE_Fiber_TASC_O | TASC | MFQ-199-R | Mafraq |  | 32.3273 | 36.2838 | Mafraq | Tower | [36 empty] | Approved
890 | 890-Karak_Wassieh_PF_TASC_O | TASC | KRK-193-R | Karak |  | 31.2315 | 35.7244 | Karak | Pole | [24 empty] | Approved |  |  | Approved | [8 empty] | Approved
4778 | 4778-Officers_Ave_Mafraq_PE_Fiber_TASC_O | TASC | MFQ-210-R | Mafraq |  | 32.3459 | 36.2141 | Mafraq | Tower | [36 empty] | Approved
4773 | 4773-Hosha_End_PF_TASC_O | TASC | MFQ-200-R | Mafraq |  | 32.4517 | 36.1092 | Mafraq | Pole | [36 empty] | Approved
3368 | 3368-Mutah_Military_PC_Fiber_TASC | TASC | KRK-66-G | Karak | 898 | 31.0983 | 35.7064 | Karak | Tower | [36 empty] | Approved
3338 | 3338-Faisalieh_Karak_PF_TASC_O | TASC | KRK-38-R | Karak |  | 31.023 | 35.7429 | Karak | Tower | [36 empty] | Approved
3316 | 3316-Jwayer_PD_EBand_TASC | TASC | KRK-16-G | Karak | 821 | 31.0218 | 35.6922 | Karak | Tower | [36 empty] | Approved
1924 | 1924-Zarqa_Snt_Joseph_Church_PE_Fiber_TASC_O | TASC | ZRQ-356-R | Zarqa |  | 32.1012 | 36.1051 | Zarqa | Pole | [36 empty] | Approved
5858 | 5858-Ghor_Safi_Court_PE_Fiber_TASC_O | TASC | KRK-188-R | Karak |  | 31.0397 | 35.4837 | Karak | Pole | [36 empty] | Approved
5859 | 5859-Ghor_Safi_Market_PD_Fiber_TASC_O | TASC | KRK-189-R | Karak |  | 31.0358 | 35.4855 | Karak | Pole | [36 empty] | Approved
876 | 876-Sarfa_Karak_PD_TASC | TASC | KRK-155-R | Karak | 993 | 31.3305 | 35.6538 | Karak | Pole | [36 empty] | Approved
5886 | 5886-Ghor_Safi_3_PD_Fiber_TASC_O | TASC | KRK-168-G | Karak |  | 31.0342 | 35.4953 | Karak | Tower | [36 empty] | Approved
4780 | 4780-Mafraq_Hussein_Club_PF_TASC_O | TASC | MFQ-222-R | Mafraq |  | 32.3616 | 36.2127 | Mafraq | Pole | [36 empty] | Approved
2862 | 2862-Doqarah_Hashmia_PD_Fiber_TASC_O | TASC | ZRQ-360-R | Zarqa |  | 32.1346 | 36.0372 | Zarqa | Pole | [36 empty] | Approved
1158 | 1158-Mfardat_Khaldieh_PF_TASC_O | TASC | MFQ-218-R | Mafraq |  | 32.2338 | 36.2904 | Mafraq | Tower | [36 empty] | Approved
4776 | 4776-Ghadeer_Abiad_Village_PF_TASC_O | TASC | MFQ-213-R | Mafraq |  | 32.3893 | 36.1986 | Mafraq | Pole | [36 empty] | Approved
533 | 533-Mahis_Downtown_CRL_PC_Fiber_TASC_O | TASC | BLQ-180-R | Balqa |  | 31.9849 | 35.7686 | Balqa | Tower | [36 empty] | Approved
537 | 537-Mahis_2_PB_Fiber_Zain_TASC | TASC | BLQ-34-G | Balqa | 242 | 31.9767 | 35.7691 | Balqa | Tower | [36 empty] | Approved
532 | 532-New_Bader_PC_Fiber_TASC | TASC | AMW-417-G | Amman | 430 | 31.9724 | 35.781 | Amman | Tower | [36 empty] | Approved
529 | 529-Bader_2_PD_TASC | TASC | AMW-798-R | Amman | 1735 | 31.9565 | 35.7633 | Amman | Tower | [36 empty] | Approved
520 | 520-Fardous_PB_Fiber_TASC | TASC | AMW-415-G | Balqa | 420 | 31.9828 | 35.7937 | Balqa | Tower | [36 empty] | Approved
531 | 531-Bader_1_PE_TASC_O | TASC | AMW-797-R | Amman |  | 31.967 | 35.771 | Amman | Pole | [36 empty] | Approved
506 | 506-Zabda_PF_TASC_O | TASC | AMW-632-R | Amman |  | 31.9428 | 35.7512 | Amman | Pole | [36 empty] | Approved
2617 | 2617-Sight_And_Sound_PB_TASC | TASC | AME-296-R | Amman | 125 | 31.9725 | 35.8976 | Amman | Pole | [24 empty] | Approved |  |  | Approved |  |  | Approved |  |  | Approved |  |  | Approved
2660 | 2660-HSG_Bank_PA_Fiber_IBS_TASC | TASC | AME-322-R | Amman | 246 | 31.971 | 35.907 | Amman | [21 empty] | IBS | [15 empty] | Approved
1473 | 1473-Kettah_1_PD_Fiber_TASC_O | TASC | JRS-43-R | Jarash |  | 32.2772 | 35.8405 | Jarash | Tower | [36 empty] | Approved
1497 | 1497-Jerash_Camp_CTR_PE_EBand_TASC_O | TASC | JRS-50-R | Jarash |  | 32.2623 | 35.8559 | Jarash | Tower | [36 empty] | Approved
1403 | 1403-Um_Yanabee_PB_TASC | TASC | AJL-1-G | Ajloun | 760 | 32.372 | 35.7653 | Ajloun | Tower | [36 empty] | Approved
4525 | 4525-Baqaa_PC_Fiber_TASC | TASC | AMW-251-G | Balqa | 43 | 32.0688 | 35.8454 | Balqa | Tower | [36 empty] | Approved
4520 | 4520-Safoot_Rising_PE_O | TASC | AMW-822-R | Balqa |  | 32.0511 | 35.8444 | Balqa | Tower | [36 empty] | Approved
1495 | 1495-Rajib_PF_TASC_O | TASC | AJL-25-R | Ajloun |  | 32.2341 | 35.6955 | Ajloun | Pole | [36 empty] | Approved
1433 | 1433-Safenneh_PD | TASC | AJL-11-G | Ajloun | 669 | 32.2531 | 35.7094 | Ajloun | Tower | [36 empty] | Approved
4526 | 4526-Burma_Jerash_PD_Zain_TASC | TASC | JRS-14-G | Jarash | 740 | 32.2152 | 35.8437 | Jarash | Tower | [36 empty] | Approved
1496 | 1496-Souf_Camp_CTR_PE_O | TASC | JRS-49-R | Jarash |  | 32.3086 | 35.8841 | Jarash | Tower | [36 empty] | Approved
1457 | 1457-Irbid_Rd_PE_TASC | TASC | IRB-216-R | Jarash | 726 | 32.2887 | 35.9141 | Jarash | Tower | [36 empty] | Approved
1430 | 1430-Halawa_PB_TASC | TASC | AJL-9-G | Ajloun | 642 | 32.3809 | 35.6714 | Ajloun | Tower | [36 empty] | Approved
4540 | 4540-Zaatari_Salt_PE_O | TASC | BLQ-116-R | Balqa |  | 32.0729 | 35.743 | Balqa | Pole | [36 empty] | Approved
1431 | 1431-Eshtafina_Ain_Jannah_PF_TASC | TASC | AJL-17-G | Ajloun | 738 | 32.3425 | 35.76 | Ajloun | Tower | [36 empty] | Approved
1442 | 1442-Ibeen_Ibleen_PD_EBand_TASC | TASC | AJL-14-G | Ajloun | 712 | 32.3522 | 35.8234 | Ajloun | Tower | [36 empty] | Approved
4524 | 4524-Baqaa_Market_PD_Fiber_TASC | TASC | AMW-388-R | Balqa | 460 | 32.0756 | 35.8431 | Balqa | Pole | [36 empty] | Approved
1424 | 1424-Souf_Camp_PD_Fiber_TASC | TASC | JRS-7-R | Jarash | 779 | 32.3114 | 35.8867 | Jarash | Pole | [36 empty] | Approved
1401 | 1401-BSC_Koam_PA_Fiber_TASC | TASC | JRS-1-G | Jarash | 697 | 32.3278 | 35.9032 | Jarash | Tower | [36 empty] | Approved
1449 | 1449-Ghaza_Camp_PE_TASC | TASC | JRS-28-R | Jarash | 788 | 32.2658 | 35.8619 | Jarash | Pole | [36 empty] | Approved
4512 | 4512-Berin_PA_Fiber_Zain_TASC | TASC | AMW-261-G | Zarqa | 47 | 32.0763 | 35.9391 | Zarqa | Tower | [36 empty] | Approved
4543 | 4543-Sarrout_PE_TASC_O | TASC | ZRQ-162-R | Zarqa |  | 32.1426 | 35.9566 | Zarqa | Pole | [36 empty] | Approved
1482 | 1482-Jabal_Atmat_Jerash_PD_O | TASC | JRS-38-R | Jarash |  | 32.2718 | 35.9 | Jarash | Tower | [36 empty] | Approved
1465 | 1465-Anjarah_CTR_PE_Fiber_TASC_O | TASC | AJL-24-R | Ajloun |  | 32.3049 | 35.7549 | Ajloun | Pole | [36 empty] | Approved
4537 | 4537-Rmamein_PE_Zain_TASC | TASC | AMW-252-G | Balqa | 119 | 32.0857 | 35.7966 | Balqa | Tower | [36 empty] | Approved
4514 | 4514-Jelaad_CTR_PF_TASC_O | TASC | BLQ-174-R | Balqa |  | 32.1195 | 35.7783 | Balqa | Tower | [36 empty] | Approved
4538 | 4538-Jelaad_PE_TASC | TASC | AMW-287-G | Balqa | 419 | 32.1009 | 35.7656 | Balqa | Tower | [36 empty] | Approved
1494 | 1494-Nabi_Hood_Ave_PF_O | TASC | JRS-59-R | Jarash |  | 32.2609 | 35.9084 | Jarash | Pole | [36 empty] | Approved
4506 | 4506-Ain_AlBasha_CTR_PD_Fiber_TASC | TASC | AMW-699-R | Balqa | 100 | 32.0611 | 35.8299 | Balqa | Pole | [36 empty] | Approved
4508 | 4508-Baqaa_Karameh_PC_Fiber_TASC | TASC | AMW-663-R | Balqa | 1591 | 32.076 | 35.853 | Balqa | Tower | [36 empty] | Approved
4522 | 4522-Mashtal_Faisal_PF_TASC_O | TASC | JRS-10-G | Jarash |  | 32.2261 | 35.903 | Jarash | Tower | [36 empty] | Approved
1475 | 1475-Sakhra_East_PF_TASC_O | TASC | AJL-50-R | Ajloun |  | 32.3674 | 35.8497 | Ajloun | Tower | [36 empty] | Approved
4536 | 4536-Jubbah_Jerash_PD_Fiber_TASC_O | TASC | JRS-48-R | Jarash |  | 32.1894 | 35.8825 | Jarash | Tower | [36 empty] | Approved
1466 | 1466-Ibeen_Ajloun_PF_TASC | TASC | AJL-26-R | Ajloun | 2138 | 32.3579 | 35.8054 | Ajloun | Pole | [36 empty] | Approved
4560 | 4560-Rmamein_CTR_PF_O | TASC | JRS-45-R | Balqa |  | 32.1064 | 35.7989 | Balqa | Pole | [36 empty] | Approved
4516 | 4516-Irbid_Rd_1_PD_EBand_TASC_O | TASC | AMW-260-R | Jarash |  | 32.144 | 35.8596 | Jarash | Pole | [36 empty] | Approved
4547 | 4547-Slaihy_West_PF_O | TASC | BLQ-181-R | Balqa |  | 32.1343 | 35.8169 | Balqa | Pole | [36 empty] | Approved
4562 | 4562-Fowwarah_Jerash_PF_TASC_O | TASC | JRS-76-R | Jarash |  | 32.2095 | 35.7653 | Jarash | Pole | [36 empty] | Approved
4505 | 4505-Baqaa_CTR_PD_Fiber_TASC | TASC | AMW-682-R | Balqa | 41 | 32.0709 | 35.8423 | Balqa | Tower | [36 empty] | Approved
4685 | 4685-Kufer_Abeel_PC_EBand_TASC | TASC | IRB-200-R | Irbid | 790 | 32.4181 | 35.6604 | Irbid | Tower | [36 empty] | Approved
4528 | 4528-Salhoub_PC_TASC | TASC | AMW-454-G | Balqa | 473 | 32.1248 | 35.8596 | Balqa | Tower | [36 empty] | Approved
1440 | 1440-Hashmia_Ajloun_Ent_PF_O | TASC | AJL-47-R | Ajloun |  | 32.3647 | 35.6683 | Ajloun | Tower | [36 empty] | Approved
4511 | 4511-Faloujeh_Assoc_Baqaa_PD_Fiber_TASC_O | TASC | BLQ-160-R | Balqa |  | 32.0778 | 35.85 | Balqa | Tower | [36 empty] | Approved
4532 | 4532-Kamsheh_PE_TASC_O | TASC | JRS-35-R | Zarqa |  | 32.1276 | 35.9144 | Zarqa | Tower | [36 empty] | Approved
1421 | 1421-Anjarah_PA_Fiber_Zain_TASC | TASC | AJL-6-G | Ajloun | 689 | 32.2959 | 35.7424 | Ajloun | Tower | [36 empty] | Approved
1446 | 1446-Halawa_CTR_PE_TASC_O | TASC | AJL-42-R | Ajloun |  | 32.3845 | 35.6626 | Ajloun | Tower | [36 empty] | Approved
1408 | 1408-Nadreh_PE_TASC | TASC | JRS-4-G | Mafraq | 706 | 32.3023 | 35.9786 | Mafraq | Tower | [36 empty] | Approved
1459 | 1459-Khshaibeh_Jerash_PF_TASC_O | TASC | JRS-65-R | Jarash |  | 32.2036 | 35.7167 | Jarash | Pole | [36 empty] | Approved
4544 | 4544-Ain_AlBasha_Tatweer_PE_O | TASC | AMW-893-R | Balqa |  | 32.0587 | 35.8114 | Balqa | Pole | [36 empty] | Approved
4513 | 4513-Ain_AlBasha_Foursieh_PF_O | TASC | AMW-879-R | Balqa |  | 32.0692 | 35.8186 | Balqa | Pole | [36 empty] | Approved
4534 | 4534-Alouk_PD_TASC | TASC | ZRQ-30-G | Zarqa | 413 | 32.1672 | 35.9176 | Zarqa | Tower | [36 empty] | Approved
1434 | 1434-Balqaa_Ajloun_College_PF_TASC_O | TASC | AJL-53-R | Ajloun |  | 32.3185 | 35.7515 | Ajloun | Pole | [36 empty] | Approved
4535 | 4535-Ain_AlBasha_2_PB_Fiber_Zain_TASC | TASC | AMW-284-G | Balqa | 348 | 32.058 | 35.8384 | Balqa | Tower | [36 empty] | Approved
4541 | 4541-Baqaa_East_PF_O | TASC | BLQ-159-R | Balqa |  | 32.0731 | 35.8405 | Balqa | Pole | [36 empty] | Approved
1405 | 1405-Ras_Moneef_Ajloun_PF_TASC_O | TASC | AJL-41-R | Ajloun |  | 32.3824 | 35.8024 | Ajloun | Pole | [36 empty] | Approved
4523 | 4523-Baqaa_2_PD_EBand_TASC | TASC | AMW-267-R | Balqa | 44 | 32.0785 | 35.8374 | Balqa | Pole | [36 empty] | Approved
1454 | 1454-Mar_Elias_PF_TASC | TASC | AJL-16-G | Ajloun | 698 | 32.3367 | 35.7046 | Ajloun | Tower | [36 empty] | Approved
4539 | 4539-Salouf_PE_TASC_O | TASC | BLQ-191-R | Balqa |  | 32.0799 | 35.7707 | Balqa | Pole | [36 empty] | Approved
4502 | 4502-Ain_AlBasha_PB_Fiber_TASC | TASC | AMW-250-R | Balqa | 196 | 32.0541 | 35.8302 | Balqa | Tower | [36 empty] | Approved
1460 | 1460-Remon_Nahleh_PA_Fiber_TASC | TASC | JRS-34-R | Jarash | 2104 | 32.2817 | 35.8258 | Jarash | Pole | [36 empty] | Approved
2980 | 2980-Kufer_Khall_East_PE_EBand_TASC | TASC | JRS-19-G | Jarash | 730 | 32.361 | 35.8868 | Jarash | Tower | [36 empty] | Approved
3452 | 3452-Mkhaibeh_Foga_Irbid_PF_TASC_O | TASC | IRB-379-R | Irbid |  | 32.7026 | 35.6845 | Irbid | Pole | [36 empty] | Approved
4501 | 4501-Ain_AlBasha_3_PC_EBand_TASC | TASC | AMW-662-R | Balqa | 1578 | 32.0706 | 35.8376 | Balqa | Tower | [36 empty] | Approved
1441 | 1441-Jerash_Ent_PC_Fiber_TASC | TASC | JRS-12-G | Jarash | 715 | 32.2492 | 35.8832 | Jarash | Tower | [36 empty] | Approved
3493 | 3493-Gigeen_North_PE_TASC_O | TASC | IRB-407-R | Irbid |  | 32.5858 | 35.7692 | Irbid | Tower | [36 empty] | Approved
1432 | 1432-Hashmia_Ajloun_PF_TASC | TASC | AJL-10-R | Ajloun | 729 | 32.3637 | 35.6566 | Ajloun | Tower | [36 empty] | Approved
4509 | 4509-Ain_AlBasha_Safoot_PD_Fiber_O | TASC | AMW-889-R | Balqa |  | 32.0497 | 35.8302 | Balqa | Pole | [36 empty] | Approved
1425 | 1425-Megebleh_Jerash_PE_TASC_O | TASC | JRS-66-R | Jarash |  | 32.3169 | 35.8639 | Jarash | Pole | [36 empty] | Approved
4503 | 4503-Slaihy_PF_TASC_O | TASC | AMW-253-R | Balqa |  | 32.1186 | 35.8295 | Balqa | Tower | [36 empty] | Approved
4510 | 4510-Iskan_Qakeesh_PE_EBand_TASC | TASC | AMW-676-R | Balqa | 1607 | 32.0605 | 35.8153 | Balqa | Pole | [36 empty] | Approved
4518 | 4518-Philadelphia_Uni_PE_Fiber_TASC_O | TASC | AMW-269-R | Balqa |  | 32.1663 | 35.8503 | Balqa | Pole | [36 empty] | Approved
1435 | 1435-Hweshan_Nadreh_PF_TASC_O | TASC | JRS-81-R | Mafraq |  | 32.2996 | 35.9462 | Mafraq | Pole | [36 empty] | Approved
1412 | 1412-Jerash_Ain_Nabi_PF_TASC_O | TASC | JRS-85-R | Jarash |  | 32.2858 | 35.9265 | Jarash | Pole | [36 empty] | Approved
1411 | 1411-Ras_Munif_PA_Fiber_Zain_TASC | TASC | AJL-5-G | Ajloun | 655 | 32.3785 | 35.8126 | Ajloun | Tower | [36 empty] | Approved
3499 | 3499-Um_Qais_Ent_PE_TASC_O | TASC | IRB-381-R | Irbid |  | 32.6501 | 35.6947 | Irbid | Tower | [36 empty] | Approved
4504 | 4504-King_Hussein_Camp_PF_TASC_O | TASC | AMW-266-R | Balqa |  | 32.0632 | 35.8012 | Balqa | Pole | [36 empty] | Approved
4596 | 4596-Rayah_Jerash_PF_TASC_O | TASC | JRS-53-R | Jarash |  | 32.1589 | 35.8781 | Jarash | Pole | [36 empty] | Approved
4530 | 4530-Burma_PE_O | TASC | JRS-29-R | Jarash |  | 32.2095 | 35.7817 | Jarash | Tower | [36 empty] | Approved
1474 | 1474-Ballas_Ajloun_PF_TASC_O | TASC | AJL-38-R | Ajloun |  | 32.26 | 35.6988 | Ajloun | Pole | [36 empty] | Approved
3703 | 3703-Yarqa_1_PD_Fiber_TASC | TASC | BLQ-131-R | Balqa | 1612 | 31.9874 | 35.6997 | Balqa | Pole | [36 empty] | Approved
3738 | 3738-Um_Jozeh_Salt_PF_Zain_O | TASC | BLQ-166-R | Balqa |  | 32.095 | 35.738 | Balqa | Tower | [36 empty] | Approved
3711 | 3711-Balqaa_Applied_Uni_PC_Fiber_TASC | TASC | BLQ-10-G | Balqa | 61 | 32.0199 | 35.7116 | Balqa | Tower | [36 empty] | Approved
3762 | 3762-Ain_Saadah_Salt_PF_TASC_O | TASC | BLQ-184-R | Balqa |  | 32.0891 | 35.7023 | Balqa | Pole | [36 empty] | Approved
3402 | 3402-Qumaim_PC | TASC | IRB-168-G | Irbid | 769 | 32.5733 | 35.7375 | Irbid | Tower | [36 empty] | Approved
3718 | 3718-Yarqa_Batana_PE_Fiber_TASC_O | TASC | BLQ-133-R | Balqa |  | 31.9839 | 35.6963 | Balqa | Pole | [36 empty] | Approved
3418 | 3418-Deir_Abu_Saeed_Ghor_1_PF_Zain_TASC | TASC | IRB-37-G | Irbid | 651 | 32.5014 | 35.629 | Irbid | Tower | [36 empty] | Approved
1498 | 1498-Ebeen_CTR_PE_TASC_O | TASC | AJL-37-R | Ajloun |  | 32.3599 | 35.8128 | Ajloun | Tower | [36 empty] | Approved
3713 | 3713-Salt_Ind_Area_PE_Fiber_TASC_O | TASC | BLQ-163-R | Balqa |  | 32.045 | 35.7228 | Balqa | Pole | [36 empty] | Approved
1447 | 1447-Eshtafina_Mehna_Ajloun_PF_O | TASC | AJL-44-R | Ajloun |  | 32.3602 | 35.7438 | Ajloun | Tower | [36 empty] | Approved
3430 | 3430-Sheikh_Hussein_PB_Fiber_TASC | TASC | BLQ-28-G | Irbid | 165 | 32.5181 | 35.5895 | Irbid | Tower | [36 empty] | Approved
3715 | 3715-Yarqa_Wadi_Shoaib_Ent_PF_O | TASC | BLQ-143-R | Balqa |  | 31.9812 | 35.7018 | Balqa | Pole | [36 empty] | Approved
3761 | 3761-Salt_Teachers_Club_PF_O | TASC | BLQ-183-R | Balqa |  | 32.0334 | 35.7158 | Balqa | Pole | [36 empty] | Approved
1489 | 1489-Sakib_CTR_PD_Fiber_TASC_O | TASC | JRS-58-R | Jarash |  | 32.2848 | 35.8097 | Jarash | Tower | [36 empty] | Approved
3726 | 3726-Salt_Naqb_Dabbour_PE_O | TASC | BLQ-162-R | Balqa |  | 32.0436 | 35.7421 | Balqa | Pole | [36 empty] | Approved
3720 | 3720-Salt_Akrad_Valley_PF_O | TASC | BLQ-161-R | Balqa |  | 32.0456 | 35.7163 | Balqa | Pole | [36 empty] | Approved
3708 | 3708-Safeh_Salt_PF_EBand_TASC | TASC | BLQ-135-R | Balqa | 1650 | 32.0399 | 35.7074 | Balqa | Pole | [36 empty] | Approved
3768 | 3768-Buhaira_Salt_PC_EBand_TASC_O | TASC | BLQ-186-R | Balqa |  | 32.0536 | 35.7355 | Balqa | Tower | [36 empty] | Approved
3701 | 3701-Daam_Ghazalat_PE_Fiber_TASC_O | TASC | BLQ-124-R | Balqa |  | 32.0776 | 35.7196 | Balqa | Tower | [36 empty] | Approved
3425 | 3425-Qarn_Aghwar_PE_Fiber_TASC_O | TASC | BLQ-187-R | Irbid |  | 32.3301 | 35.5975 | Irbid | Pole | [36 empty] | Approved
1417 | 1417-Jazzazeh_Jerash_PF_TASC_O | TASC | JRS-68-R | Jarash |  | 32.2331 | 35.8212 | Jarash | Pole | [36 empty] | Approved
3760 | 3760-Salt_Comprehensive_Sch_PE_Fiber_TASC_O | TASC | BLQ-64-R | Balqa |  | 32.0283 | 35.7172 | Balqa | Pole | [36 empty] | Approved
3781 | 3781-Yazidieh_Salt_PE_TASC | TASC | AMW-777-R | Balqa | 1697 | 32.0605 | 35.7776 | Balqa | Pole | [36 empty] | Approved
3723 | 3723-Salalem_2_PD_Fiber_TASC | TASC | BLQ-21-R | Balqa | 382 | 32.0517 | 35.7248 | Balqa | Tower | [36 empty] | Approved
3769 | 3769-Salt_Rd_1_PF_TASC_O | TASC | BLQ-12-R | Balqa |  | 32.0538 | 35.7616 | Balqa | Pole | [36 empty] | Approved
3771 | 3771-Iskan_Taibeh_PF_TASC_O | TASC | BLQ-113-R | Balqa |  | 32.0514 | 35.7961 | Balqa | Pole | [36 empty] | Approved
4529 | 4529-Marsaa_PF_EBand_TASC_O | TASC | JRS-26-R | Jarash |  | 32.1493 | 35.8793 | Jarash | Pole | [36 empty] | Approved
3721 | 3721-Wadi_Akrad_Salt_PD_Fiber_TASC | TASC | BLQ-103-R | Balqa | 439 | 32.041 | 35.7184 | Balqa | Tower | [36 empty] | Approved
1478 | 1478-Dahal_Mafraq_PF_TASC_O | TASC | MFQ-191-R | Mafraq |  | 32.2693 | 35.9706 | Mafraq | Tower | [36 empty] | Approved
3403 | 3403-Sad_Wadi_AlArab_PF | TASC | IRB-3-G | Irbid | 668 | 32.6134 | 35.6609 | Irbid | Tower | [36 empty] | Approved
3770 | 3770-Salt_Bridge_PE_TASC_O | TASC | BLQ-119-R | Balqa |  | 32.0524 | 35.7463 | Balqa | Pole | [36 empty] | Approved
1484 | 1484-Um_Btaimah_PF_TASC_O | TASC | MFQ-176-R | Mafraq |  | 32.3064 | 35.9623 | Mafraq | Pole | [36 empty] | Approved
3707 | 3707-Nabi_Youshaa_PA_Fiber_TASC | TASC | BLQ-6-G | Balqa | 286 | 32.0562 | 35.6982 | Balqa | Tower | [36 empty] | Approved
3756 | 3756-Salalem_Salt_PD_TASC | TASC | BLQ-53-R | Balqa | 139 | 32.0397 | 35.7312 | Balqa | Pole | [36 empty] | Approved
1461 | 1461-Safsafeh_Huseineyat_PF_EBand_TASC_O | TASC | JRS-33-R | Jarash |  | 32.2561 | 35.7861 | Jarash | Pole | [36 empty] | Approved
3475 | 3475-Waqqas_North_Shouneh_PF_TASC_O | TASC | IRB-387-R | Irbid |  | 32.5389 | 35.6043 | Irbid | Tower | [36 empty] | Approved
4545 | 4545-Um_Dannaneer_PE_EBand_TASC_O | TASC | AMW-839-R | Balqa |  | 32.0832 | 35.8284 | Balqa | Tower | [36 empty] | Approved
3495 | 3495-Zmaleyyeh_North_Shouneh_PE_Fiber_TASC_O | TASC | IRB-396-R | Irbid |  | 32.5036 | 35.6036 | Irbid | Tower | [36 empty] | Approved
1406 | 1406-Shawahed_Jabal_Akhdar_PE_Fiber_TASC_O | TASC | JRS-56-R | Jarash |  | 32.2982 | 35.9069 | Jarash | Tower | [36 empty] | Approved
1491 | 1491-Deir_Alleyat_PE_O | TASC | JRS-54-R | Jarash |  | 32.2936 | 35.8752 | Jarash | Pole | [36 empty] | Approved
1487 | 1487-Souf_East_PD_TASC_O | TASC | JRS-57-R | Jarash |  | 32.3115 | 35.841 | Jarash | Tower | [36 empty] | Approved
3776 | 3776-Um_Qsair_Msq_Salt_Rd_PE_TASC | TASC | AMW-772-R | Balqa | 442 | 32.0578 | 35.7507 | Balqa | Pole | [36 empty] | Approved
3709 | 3709-Era_CTR_PF_TASC_O | TASC | BLQ-142-R | Balqa |  | 31.9931 | 35.6729 | Balqa | Pole | [36 empty] | Approved
3702 | 3702-Era_Aghwar_Rd_PF_O | TASC | BLQ-145-R | Balqa |  | 32 | 35.6642 | Balqa | Tower | [36 empty] | Approved
3725 | 3725-Aziryeh_Msq_Salt_PE_Fiber_O | TASC | BLQ-158-R | Balqa |  | 32.0388 | 35.7234 | Balqa | Pole | [36 empty] | Approved
3717 | 3717-Salalem_3_PE_Fiber_TASC_O | TASC | BLQ-117-R | Balqa |  | 32.0585 | 35.7206 | Balqa | Pole | [36 empty] | Approved
3722 | 3722-Yarqa_Majdalah_PE_Fiber_TASC_O | TASC | BLQ-157-R | Balqa |  | 31.9722 | 35.698 | Balqa | Pole | [36 empty] | Approved
4515 | 4515-Rumman_PB_Fiber_TASC | TASC | AMW-258-G | Balqa | 118 | 32.1695 | 35.8251 | Balqa | Tower | [36 empty] | Approved
3714 | 3714-Salt_2_PA_Fiber_TASC | TASC | BLQ-13-G | Balqa | 141 | 32.0312 | 35.738 | Balqa | Tower | [36 empty] | Approved
3419 | 3419-Zabda_Wasatieh_PE | TASC | IRB-121-G | Irbid | 737 | 32.5734 | 35.6677 | Irbid | Tower | [36 empty] | Approved
4598 | 4598-Rahmanieh_Jerash_PF_TASC_O | TASC | JRS-79-R | Jarash |  | 32.1553 | 35.8639 | Jarash | Pole | [36 empty] | Approved
3450 | 3450-Deir_Abu_Saeed_Ghor_2_PD_Fiber_TASC | TASC | IRB-47-G | Irbid | 653 | 32.5121 | 35.6422 | Irbid | Tower | [36 empty] | Approved
1439 | 1439-Jabal_Akhdar_Ajloun_PF_TASC_O | TASC | AJL-54-R | Ajloun |  | 32.2339 | 35.7287 | Ajloun | Pole | [36 empty] | Approved
3704 | 3704-Maghareeb_Salt_PD_Fiber_TASC_O | TASC | BLQ-121-R | Balqa |  | 32.0393 | 35.6968 | Balqa | Tower | [36 empty] | Approved
3498 | 3498-Adassiyah_CTR_PF_TASC_O | TASC | IRB-385-R | Irbid |  | 32.6688 | 35.6236 | Irbid | Tower | [36 empty] | Approved
1444 | 1444-Osrah_Ajloun_PF_TASC_O | TASC | AJL-46-R | Ajloun |  | 32.3836 | 35.6913 | Ajloun | Tower | [36 empty] | Approved
4667 | 4667-Kufer_Abeel_East_PE_EBand_TASC_O | TASC | IRB-398-R | Irbid |  | 32.4174 | 35.6694 | Irbid | Tower | [36 empty] | Approved
3727 | 3727-Eng_HSG_Salt_PF_TASC_O | TASC | BLQ-167-R | Balqa |  | 32.0507 | 35.7339 | Balqa | Tower | [36 empty] | Approved
3772 | 3772-Salt_Rd_PC_TASC | TASC | BLQ-14-R | Balqa | 184 | 32.0329 | 35.7924 | Balqa | Tower | [36 empty] | Approved
3463 | 3463-Malka_North_PD_TASC_O | TASC | IRB-382-R | Irbid |  | 32.6754 | 35.7484 | Irbid | Tower | [36 empty] | Approved
3716 | 3716-Baqee_Salt_PD_Fiber_TASC_O | TASC | BLQ-179-R | Balqa |  | 32.0368 | 35.713 | Balqa | Tower | [36 empty] | Approved
3456 | 3456-AlHamad_Village_PF_TASC_O | TASC | BLQ-156-R | Balqa |  | 32.1665 | 35.585 | Balqa | Tower | [36 empty] | Approved
3437 | 3437-Saydoor_Irbid_PF_TASC | TASC | IRB-243-R | Irbid | 2130 | 32.6149 | 35.6955 | Irbid | Pole | [36 empty] | Approved
3496 | 3496-Medraj_North_Shouneh_PF_TASC_O | TASC | IRB-388-R | Irbid |  | 32.6312 | 35.6182 | Irbid | Tower | [36 empty] | Approved
4551 | 4551-Karameh_Baqaa_North_PE_TASC_O | TASC | AMW-973-R | Balqa |  | 32.0774 | 35.8623 | Balqa | Pole | [36 empty] | Approved
3409 | 3409-Derar_PC_Fiber_TASC | TASC | BLQ-42-G | Balqa | 949 | 32.2131 | 35.6259 | Balqa | Tower | [36 empty] | Approved
3415 | 3415-Maadde_PC_Fiber_TASC | TASC | BLQ-109-G | Balqa | 28 | 32.1615 | 35.6184 | Balqa | Tower | [36 empty] | Approved
3471 | 3471-Merehba_Irbid_PE_O | TASC | IRB-342-R | Irbid |  | 32.5104 | 35.6749 | Irbid | Tower | [36 empty] | Approved
3470 | 3470-AbuZeeghan_PC_EBand_TASC_O | TASC | BLQ-60-G | Balqa | 351 | 32.2 | 35.6375 | Balqa | Tower | [36 empty] | Approved
3422 | 3422-Mkhaibeh_PF_TASC_O | TASC | IRB-19-G | Irbid |  | 32.6729 | 35.6735 | Irbid | Tower | [36 empty] | Approved
3448 | 3448-Subahi_Salt_PE_Fiber_TASC_O | TASC | BLQ-138-R | Balqa |  | 32.1413 | 35.6876 | Balqa | Pole | [36 empty] | Approved
3485 | 3485-Shouneh_Karameh_PF_O | TASC | BLQ-153-R | Balqa |  | 31.9484 | 35.5802 | Balqa | Pole | [36 empty] | Approved
3444 | 3444-Foara_PD_TASC_O | TASC | IRB-166-G | Irbid | 690 | 32.6174 | 35.7617 | Irbid | Tower | [36 empty] | Approved
3407 | 3407-Kherbet_Alwahadneh_PE_TASC | TASC | BLQ-47-G | Ajloun | 648 | 32.3239 | 35.6433 | Ajloun | Tower | [36 empty] | Approved
3479 | 3479-Foara_East_Irbid_PE_TASC_O | TASC | IRB-415-R | Irbid |  | 32.6148 | 35.7656 | Irbid | Pole | [36 empty] | Approved
3451 | 3451-Tabaqet_Fahel_PD_Fiber_TASC | TASC | BLQ-48-G | Irbid | 182 | 32.4463 | 35.6044 | Irbid | Tower | [36 empty] | Approved
3459 | 3459-Makhraba_Irbid_PF_TASC_O | TASC | IRB-332-R | Irbid |  | 32.5782 | 35.6512 | Irbid | Tower | [36 empty] | Approved
3482 | 3482-Ibdar_Hatem_InterX_PE_Fiber_TASC_O | TASC | IRB-458-R | Irbid |  | 32.6571 | 35.7813 | Irbid | Pole | [36 empty] | Approved
3488 | 3488-Thahret_Ramel_PE_TASC_O | TASC | BLQ-169-R | Balqa |  | 32.0659 | 35.5966 | Balqa | Tower | [36 empty] | Approved
3427 | 3427-Balawneh_Ghor_PC_Fiber_TASC | TASC | BLQ-129-R | Balqa | 320 | 32.24 | 35.6136 | Balqa | Tower | [36 empty] | Approved
3477 | 3477-Houfa_Irbid_PF_O | TASC | IRB-333-R | Irbid |  | 32.5712 | 35.7105 | Irbid | Tower | [36 empty] | Approved
4517 | 4517-Berin_Village_PE_TASC_O | TASC | ZRQ-337-R | Zarqa |  | 32.0979 | 35.9581 | Zarqa | Pole | [36 empty] | Approved
3472 | 3472-Mandah_Irbid_PF_EBand_TASC_O | TASC | IRB-344-R | Irbid |  | 32.5537 | 35.6698 | Irbid | Pole | [36 empty] | Approved
3757 | 3757-Salt_Wadi_Shoaib_St_PF_TASC_O | TASC | BLQ-199-R | Balqa |  | 32.0293 | 35.7247 | Balqa | Pole | [36 empty] | Approved
3435 | 3435-North_Shouneh_PE_Zain_TASC | TASC | BLQ-134-G | Irbid | 1648 | 32.6051 | 35.6124 | Irbid | Tower | [36 empty] | Approved
3405 | 3405-Hatem_PF_TASC_O | TASC | IRB-195-R | Irbid |  | 32.6473 | 35.7788 | Irbid | Pole | [36 empty] | Approved
3449 | 3449-Kufer_Asad_PC_TASC | TASC | IRB-46-G | Irbid | 762 | 32.5977 | 35.7121 | Irbid | Tower | [36 empty] | Approved
3442 | 3442-Fanoush_PC_TASC | TASC | BLQ-39-G | Balqa | 208 | 32.1257 | 35.6029 | Balqa | Tower | [36 empty] | Approved
3458 | 3458-Samma_PE_TASC | TASC | IRB-50-R | Irbid | 678 | 32.57 | 35.6912 | Irbid | Tower | [36 empty] | Approved
3490 | 3490-AbuHabeel_Aghwar_PE_Fiber_TASC_O | TASC | BLQ-192-R | Irbid |  | 32.36 | 35.5806 | Irbid | Pole | [36 empty] | Approved
3461 | 3461-Ghor_Kabed_PB_TASC | TASC | MAD-56-G | Balqa | 328 | 32.0405 | 35.5813 | Balqa | Tower | [36 empty] | Approved
3445 | 3445-Malka_PC_Fiber_TASC | TASC | IRB-24-G | Irbid | 770 | 32.6666 | 35.7492 | Irbid | Tower | [36 empty] | Approved
3466 | 3466-AbuSeedo_North_PE_Fiber_TASC_O | TASC | BLQ-198-R | Irbid |  | 32.3133 | 35.5831 | Irbid | Pole | [36 empty] | Approved
3742 | 3742-Zay_PC_Fiber_TASC | TASC | BLQ-35-G | Balqa | 124 | 32.1052 | 35.7147 | Balqa | Tower | [36 empty] | Approved
3467 | 3467-Kufer_ElMa_PE_EBand_TASC_O | TASC | IRB-341-R | Irbid |  | 32.4872 | 35.6927 | Irbid | Tower | [36 empty] | Approved
3476 | 3476-Juffeen_PF_TASC_O | TASC | IRB-484-R | Irbid |  | 32.4899 | 35.6555 | Irbid | Pole | [36 empty] | Approved
3739 | 3739-Salalem_Salt_East_PF_TASC_O | TASC | BLQ-203-R | Balqa |  | 32.0422 | 35.7338 | Balqa | Pole | [36 empty] | Approved
4683 | 4683-Rasoon_Ajloun_PF_TASC_O | TASC | AJL-49-R | Ajloun |  | 32.4001 | 35.7589 | Ajloun | Pole | [36 empty] | Approved
1499 | 1499-Rashaydeh_Jerash_PF_TASC_O | TASC | JRS-86-R | Jarash |  | 32.2435 | 35.8981 | Jarash | Pole | [36 empty] | Approved
3408 | 3408-Deir_Alla_PB_Fiber_TASC | TASC | BLQ-32-G | Balqa | 109 | 32.1943 | 35.5942 | Balqa | Tower | [36 empty] | Approved
3441 | 3441-North_Adassiyah_PE_TASC | TASC | BLQ-38-G | Irbid | 191 | 32.6486 | 35.6176 | Irbid | Tower | [36 empty] | Approved
3439 | 3439-Karameh_PB_EBand_TASC | TASC | MAD-38-G | Balqa | 356 | 31.9532 | 35.5778 | Balqa | Tower | [36 empty] | Approved
4686 | 4686-Sanaar_Mrajjem_PF_TASC_O | TASC | AJL-51-R | Ajloun |  | 32.4066 | 35.7886 | Ajloun | Pole | [36 empty] | Approved
4592 | 4592-Sarrout_North_PF_TASC_O | TASC | ZRQ-353-R | Zarqa |  | 32.1558 | 35.9836 | Zarqa | Pole | [36 empty] | Approved
4572 | 4572-Baqaa_Ajour_CPLX_PE_Fiber_TASC_O | TASC | BLQ-212-R | Balqa | 2161 | 32.0799 | 35.8459 | Balqa | Pole | [36 empty] | Approved
3421 | 3421-Sawalha_PD_Fiber_TASC_Relo_O | TASC | BLQ-232-R | Balqa |  | 32.1813 | 35.6214 | Balqa | Tower | [36 empty] | Approved
3443 | 3443-Karameh_North_PE_TASC_O | TASC | BLQ-197-R | Balqa |  | 31.9593 | 35.5801 | Balqa | Pole | [36 empty] | Approved
3440 | 3440-Mansoura_PD_Zain_TASC | TASC | IRB-20-G | Irbid | 763 | 32.65 | 35.7277 | Irbid | Tower | [36 empty] | Approved
3423 | 3423-Harrawiyeh_Sheikh_Hussein_Bridge_PD_Fiber_TASC | TASC | BLQ-136-R | Irbid | 1686 | 32.4986 | 35.5807 | Irbid | Pole | [36 empty] | Approved
3426 | 3426-Irbid_Kufer_Rahta_PF_TASC_O | TASC | IRB-347-R | Irbid |  | 32.5822 | 35.7568 | Irbid | Pole | [36 empty] | Approved
3489 | 3489-Khazma_AlAghwar_PD_Fiber_TASC_O | TASC | BLQ-207-R | Balqa |  | 32.2239 | 35.6245 | Balqa | Pole | [36 empty] | Approved
1492 | 1492-Nahleh_CTR_PF_O | TASC | JRS-78-R | Jarash |  | 32.2716 | 35.8285 | Jarash | Pole | [36 empty] | Approved
3436 | 3436-Baqura_PD_TASC | TASC | BLQ-33-G | Irbid | 25 | 32.6196 | 35.5803 | Irbid | Tower | [36 empty] | Approved
3434 | 3434-Uni_Farms_JV_PE_O | TASC | MAD-72-G | Balqa |  | 32.0832 | 35.5917 | Balqa | Tower | [36 empty] | Approved
3416 | 3416-Bayouda_Sbaihi_PC_Fiber_TASC | TASC | BLQ-63-G | Balqa | 428 | 32.1415 | 35.7096 | Balqa | Tower | [36 empty] | Approved
3411 | 3411-Esheh_PF_TASC | TASC | IRB-10-G | Irbid | 733 | 32.7098 | 35.7313 | Irbid | Tower | [36 empty] | Approved
3743 | 3743-Allan_Um_Jozeh_Salt_PE_TASC | TASC | BLQ-132-R | Balqa | 1644 | 32.1073 | 35.7404 | Balqa | Tower | [36 empty] | Approved
3413 | 3413-Um_Qais_PA_TASC | TASC | IRB-12-G | Irbid | 622 | 32.6546 | 35.6885 | Irbid | Tower | [36 empty] | Approved
3429 | 3429-North_Aghwar_PA_Fiber_TASC | TASC | BLQ-125-G | Irbid | 1552 | 32.348 | 35.5871 | Irbid | Tower | [36 empty] | Approved
3474 | 3474-Kharaj_Irbid_PF_TASC_O | TASC | IRB-336-R | Irbid |  | 32.5836 | 35.7063 | Irbid | Tower | [36 empty] | Approved
4591 | 4591-Maqam_Issa_Zarqa_PE_TASC_O | TASC | ZRQ-336-R | Amman |  | 32.0872 | 35.9054 | Amman | Pole | [36 empty] | Approved
3431 | 3431-AbuZeeghan_Aghwar_PE_Fiber_TASC_O | TASC | BLQ-195-R | Balqa |  | 32.1896 | 35.641 | Balqa | Pole | [36 empty] | Approved
3741 | 3741-Zay_Tabbaa_Ave_PF_O | TASC | BLQ-139-R | Balqa |  | 32.095 | 35.7121 | Balqa | Pole | [36 empty] | Approved
4568 | 4568-Jerash_Zarqa_Rd_PE_Fiber_TASC_O | TASC | JRS-80-R | Zarqa |  | 32.2173 | 35.9817 | Zarqa | Pole | [36 empty] | Approved
2948 | 2948-JUST_M_Square_PF_TASC_O | TASC | IRB-366-R | Irbid |  | 32.5003 | 35.9943 | Irbid | Pole | [36 empty] | Approved
2966 | 2966-Ramtha_Mestahi_CRL_PD_Fiber_TASC_O | TASC | IRB-475-R | Irbid |  | 32.5558 | 36.0098 | Irbid | Pole | [36 empty] | Approved
2944 | 2944-Ramtha_West_4_PF_O | TASC | IRB-319-R | Irbid |  | 32.543 | 35.9988 | Irbid | Pole | [36 empty] | Approved
2930 | 2930-Ramtha_South_CRL_PE | TASC | IRB-251-R | Irbid | 2140 | 32.5523 | 36.0106 | Irbid | Tower | [36 empty] | Approved
2913 | 2913-Ramtha_West_2_PC_Fiber_TASC | TASC | IRB-219-R | Irbid | 702 | 32.5629 | 36.0056 | Irbid | Tower | [36 empty] | Approved
2967 | 2967-Ramtha_Market_PE_Fiber_TASC_O | TASC | IRB-477-R | Irbid |  | 32.5611 | 36.0086 | Irbid | Pole | [36 empty] | Approved
2961 | 2961-Ramtha_East_Ind_St_PE_Fiber_TASC_O | TASC | IRB-456-R | Irbid |  | 32.5502 | 36.017 | Irbid | Pole | [36 empty] | Approved
3779 | 3779-Buhaira_Salt_CTR_PE_Fiber_TASC_O | TASC | BLQ-210-R | Balqa |  | 32.0598 | 35.7321 | Balqa | Pole | [36 empty] | Approved
3478 | 3478-Malka_Irbid_InterX_PE_Fiber_TASC_O | TASC | IRB-461-R | Irbid |  | 32.6526 | 35.7436 | Irbid | Pole | [36 empty] | Approved
2960 | 2960-Ramtha_Hay_Iskan_PD_Fiber_TASC_O | TASC | IRB-452-R | Irbid |  | 32.5565 | 36.0053 | Irbid | Pole | [36 empty] | Approved
2918 | 2918-Qafqafa_Gas_Station_PE_Zain_TASC | TASC | IRB-106-G | Irbid | 736 | 32.419 | 35.9672 | Irbid | Tower | [36 empty] | Approved
3777 | 3777-Balqaa_Applied_Uni_Eng_PE_Fiber_TASC_O | TASC | BLQ-204-R | Balqa |  | 32.0225 | 35.7175 | Balqa | Pole | [36 empty] | Approved
2970 | 2970-Qafqafa_Ent_PF_TASC_O | TASC | JRS-51-R | Jarash |  | 32.3572 | 35.9322 | Jarash | Pole | [36 empty] | Approved
2963 | 2963-Ramtha_Megdad_Sch_PE_Fiber_TASC_O | TASC | IRB-470-R | Irbid |  | 32.5594 | 36.0054 | Irbid | Pole | [36 empty] | Approved
4563 | 4563-Um_Dannaneer_North_PE_TASC_O | TASC | AMW-987-R | Balqa |  | 32.092 | 35.8356 | Balqa | Tower | [36 empty] | Approved
2969 | 2969-Ramtha_Dahdah_Ave_PF_TASC_O | TASC | IRB-488-R | Irbid |  | 32.5722 | 36.0072 | Irbid | Pole | [36 empty] | Approved
2916 | 2916-Ramtha_West_3_PC_Fiber_TASC | TASC | IRB-235-R | Irbid | 2116 | 32.5575 | 36.0006 | Irbid | Pole | [36 empty] | Approved
2962 | 2962-Ramtha_Dabbeh_South_PD_Fiber_TASC_O | TASC | IRB-457-R | Irbid |  | 32.5617 | 35.9996 | Irbid | Pole | [36 empty] | Approved
1420 | 1420-Jerash_Jbeirat_Ave_PE_Fiber_TASC_O | TASC | JRS-83-R | Jarash |  | 32.2618 | 35.8858 | Jarash | Pole | [36 empty] | Approved
3778 | 3778-Balqaa_Applied_Uni_Library_PE_Fiber_TASC_O | TASC | BLQ-205-R | Balqa |  | 32.025 | 35.7171 | Balqa | Pole | [36 empty] | Approved
2926 | 2926-Ramtha_Hay_Mustashfa_PE_EBand_TASC | TASC | IRB-262-R | Irbid | 2150 | 32.5664 | 36.0122 | Irbid | Pole | [36 empty] | Approved
3487 | 3487-Arda_Aghwar_Ent_PE_TASC_O | TASC | BLQ-201-R | Balqa |  | 32.1401 | 35.61 | Balqa | Tower | [36 empty] | Approved
2921 | 2921-Ramtha_Deewan_Samarah_PF_O | TASC | IRB-318-R | Irbid |  | 32.5506 | 35.998 | Irbid | Tower | [36 empty] | Approved
3480 | 3480-Deir_Allah_Dbab_PE_TASC_O | TASC | BLQ-208-R | Balqa |  | 32.192 | 35.6307 | Balqa | Tower | [36 empty] | Approved
2972 | 2972-Ramtha_Hay_Zohour_PE_Fiber_TASC_O | TASC | IRB-473-R | Irbid |  | 32.517 | 35.9916 | Irbid | Pole | [36 empty] | Approved
2941 | 2941-Qafqafa_CTR_PE_TASC | TASC | IRB-230-R | Jarash | 2111 | 32.3489 | 35.9392 | Jarash | Pole | [36 empty] | Approved
2968 | 2968-Ramtha_North_Ent_PE_TASC_O | TASC | IRB-478-R | Irbid |  | 32.5726 | 36.0022 | Irbid | Pole | [36 empty] | Approved
2956 | 2956-Hassan_Ind_Classic_PE_Fiber_TASC_O | TASC | IRB-431-R | Irbid |  | 32.5052 | 36.021 | Irbid | Pole | [36 empty] | Approved
2958 | 2958-Ramtha_Hay_Jalameh_PD_O | TASC | IRB-459-R | Irbid |  | 32.5505 | 36.0054 | Irbid | Pole | [36 empty] | Approved
2914 | 2914-Ramtha_Hay_AbuBasal_PF_TASC | TASC | IRB-227-R | Irbid | 2102 | 32.547 | 35.9702 | Irbid | Pole | [36 empty] | Approved
1102 | 1102-Azraq_Middle_Ave_PF_TASC_O | TASC | MFQ-237-R | Mafraq |  | 31.8579 | 36.809 | Mafraq | Tower | [36 empty] | Approved
2911 | 2911-Ramtha_East_PD_Fiber_TASC | TASC | IRB-157-R | Irbid | 728 | 32.5661 | 36.0235 | Irbid | Pole | [36 empty] | Approved
2917 | 2917-Ramtha_South_PD_Fiber_TASC | TASC | IRB-246-R | Irbid | 2134 | 32.5549 | 36.0164 | Irbid | Tower | [36 empty] | Approved
5775 | 5775-Madaba_Court_PE_TASC_O | TASC | MAD-225-R | Madaba |  | 31.7295 | 35.7912 | Madaba | Tower | [36 empty] | Approved
1571 | 1571-Mahabeh_CRL_PE_TASC_O | TASC | MAD-219-R | Madaba |  | 31.7224 | 35.8061 | Madaba | Tower | [36 empty] | Approved
1531 | 1531-Jabal_Nebo_PE_TASC | TASC | MAD-195-R | Madaba | 482 | 31.7638 | 35.7447 | Madaba | Tower | [36 empty] | Approved
5719 | 5719-Madaba_Ent_PD_Fiber_TASC_O | TASC | MAD-200-R | Amman |  | 31.7442 | 35.8783 | Amman | Tower | [36 empty] | Approved
602 | 602-Muwaqqar_Harraneh_Rd_PE_TASC | TASC | AME-501-G | Amman | 480 | 31.7743 | 36.2605 | Amman | Tower | [36 empty] | Approved
5796 | 5796-Madaba_Khataybeh_PF_O | TASC | MAD-227-R | Madaba |  | 31.7431 | 35.7882 | Madaba | Pole | [36 empty] | Approved
3812 | 3812-Airport_Rd_3_PE_TASC | TASC | MAD-183-G | Amman | 1580 | 31.8089 | 35.913 | Amman | Tower | [36 empty] | Approved
636 | 636-Muwaqqar_Ind_WaterTank_PE_TASC_O | TASC | AMS-41-R | Amman |  | 31.7893 | 36.2327 | Amman | Pole | [36 empty] | Approved
622 | 622-Salem_Village_PE_O | TASC | AME-824-R | Amman |  | 31.85 | 35.9727 | Amman | Tower | [36 empty] | Approved
5716 | 5716-Mansoura_Madaba_PD_O | TASC | MAD-207-R | Amman |  | 31.8462 | 35.8265 | Amman | Tower | [36 empty] | Approved
3801 | 3801-Israa_Uni_HSG_PD_Fiber_TASC_O | TASC | AMS-43-R | Amman |  | 31.7901 | 35.9271 | Amman | Pole | [36 empty] | Approved
5776 | 5776-Greneh_Madaba_PF_O | TASC | MAD-228-R | Madaba |  | 31.7716 | 35.7745 | Madaba | Tower | [36 empty] | Approved
5774 | 5774-Gharnata_Madaba_PB_Fiber_TASC | TASC | MAD-66-G | Madaba | 354 | 31.7572 | 35.7837 | Madaba | Tower | [36 empty] | Approved
1597 | 1597-Mansaf_Madaba_PE_TASC_O | TASC | MAD-257-R | Madaba |  | 31.6057 | 35.7607 | Madaba | Tower | [36 empty] | Approved
1504 | 1504-Manshiet_Maeen_PE_Zain_TASC | TASC | MAD-4-G | Madaba | 278 | 31.6849 | 35.7059 | Madaba | Tower | [36 empty] | Approved
1592 | 1592-Madaba_Mleeh_PD_TASC_O | TASC | AMS-28-R | Madaba |  | 31.5873 | 35.8079 | Madaba | Tower | [36 empty] | Approved
1518 | 1518-Madaba_Uni_PE_TASC | TASC | MAD-190-G | Madaba | 1595 | 31.6583 | 35.7794 | Madaba | Tower | [36 empty] | Approved
3832 | 3832-Qastal_Ent_MGS_PE_Fiber_TASC_O | TASC | MAD-222-R | Amman |  | 31.7618 | 35.9401 | Amman | Pole | [36 empty] | Approved
5793 | 5793-Madaba_Coca_Cola_PE_TASC_O | TASC | MAD-252-R | Madaba |  | 31.7368 | 35.8066 | Madaba | Pole | [36 empty] | Approved
649 | 649-Sahab_Cemetry_Rd_PE_Fiber_TASC_O | TASC | AMS-63-R | Amman |  | 31.858 | 36.0218 | Amman | Tower | [36 empty] | Approved
624 | 624-Sahab_Hatemieh_PE_TASC_O | TASC | AME-821-R | Amman |  | 31.7921 | 36.0957 | Amman | Tower | [36 empty] | Approved
620 | 620-Salem_Tajamuat_PA_Fiber_TASC | TASC | AME-92-G | Amman | 392 | 31.8605 | 35.9708 | Amman | Tower | [36 empty] | Approved
642 | 642-Faisalieh_Sahab_PC | TASC | AME-731-R | Amman | 1711 | 31.8528 | 36.056 | Amman | Pole | [36 empty] | Approved
3811 | 3811-Jizah_PA_Fiber_TASC | TASC | MAD-11-G | Amman | 77 | 31.6995 | 35.959 | Amman | Tower | [36 empty] | Approved
3816 | 3816-Qastal_PD_Fiber_TASC | TASC | MAD-16-R | Amman | 213 | 31.7463 | 35.9396 | Amman | Tower | [36 empty] | Approved
5754 | 5754-Madaba_2_PA_Fiber_TASC | TASC | MAD-62-R | Madaba | 234 | 31.7297 | 35.7998 | Madaba | Tower | [36 empty] | Approved
5799 | 5799-Mamounieh_Madaba_PE_O | TASC | MAD-230-R | Madaba |  | 31.7445 | 35.8026 | Madaba | Tower | [36 empty] | Approved
3808 | 3808-Um_Amad_PA_Fiber_TASC | TASC | MAD-8-G | Amman | 21 | 31.8069 | 35.8631 | Amman | Tower | [36 empty] | Approved
652 | 652-Princess_Eman_CTR_PD_Fiber_TASC_O | TASC | AMS-71-R | Amman |  | 31.8517 | 35.9863 | Amman | Tower | [36 empty] | Approved
644 | 644-Mughayer_Muhanna_Back_PF_TASC_O | TASC | AMS-35-R | Amman |  | 31.8369 | 36.1331 | Amman | Pole | [36 empty] | Approved
5712 | 5712-Tal_Husban_PC_Fiber_TASC | TASC | MAD-12-G | Amman | 50 | 31.8056 | 35.8208 | Amman | Tower | [36 empty] | Approved
5711 | 5711-Kings_Academy_PB_Fiber_Zain_TASC | TASC | MAD-153-G | Amman | 1520 | 31.7494 | 35.8473 | Amman | Tower | [36 empty] | Approved
3802 | 3802-Zaytoonah_Uni_2_PF_TASC_O | TASC | MAD-254-R | Amman |  | 31.8325 | 35.8933 | Amman | Pole | [36 empty] | Approved
1569 | 1569-Madaba_PSD_Governate_PF_O | TASC | MAD-218-R | Madaba |  | 31.6898 | 35.7594 | Madaba | Pole | [36 empty] | Approved
5760 | 5760-Yadoudeh_Ramadan_Msq_PD_Fiber_TASC_O | TASC | AMS-85-R | Amman |  | 31.8505 | 35.9195 | Amman | Pole | [36 empty] | Approved
648 | 648-Mughayer_Muhanna_Ent_PE_TASC_O | TASC | AMS-39-R | Amman |  | 31.823 | 36.1065 | Amman | Tower | [36 empty] | Approved
3831 | 3831-Um_Qaseer_Ent_PE_TASC_O | TASC | AMS-78-R | Amman |  | 31.6659 | 35.894 | Amman | Pole | [36 empty] | Approved
5762 | 5762-Mshaqqar_CTR_PE_TASC_O | TASC | AMS-83-R | Amman |  | 31.7949 | 35.7708 | Amman | Pole | [36 empty] | Approved
5322 | 5322-Prince_Ali_Ave_CTR_PF_TASC_O | TASC | AMS-101-R | Amman |  | 31.8653 | 35.9076 | Amman | Pole | [36 empty] | Approved
639 | 639-Sahab_Dabaibeh_Ave_PD_EBand_TASC_O | TASC | AMS-45-R | Amman |  | 31.8864 | 36.0406 | Amman | Tower | [36 empty] | Approved
638 | 638-Jwaideh_MGS_PF_O | TASC | AME-784-R | Amman |  | 31.8767 | 35.9573 | Amman | Tower | [36 empty] | Approved
626 | 626-Tutanji_Hospital_PD_Fiber_TASC | TASC | AME-666-R | Amman | 1589 | 31.8541 | 35.9981 | Amman | Tower | [36 empty] | Approved
3833 | 3833-Um_Basateen_PD_Fiber_TASC_O | TASC | AMS-82-R | Amman |  | 31.8224 | 35.8736 | Amman | Pole | [36 empty] | Approved
5714 | 5714-Green_Land_PE_Zain_TASC_O | TASC | MAD-173-G | Amman |  | 31.8598 | 35.8409 | Amman | Tower | [36 empty] | Approved
5749 | 5749-Wadi_Sheta_PC_Fiber_TASC_O | TASC | MAD-135-R | Amman |  | 31.8675 | 35.7619 | Amman | Tower | [36 empty] | Approved
3838 | 3838-Israa_Uni_PD_Fiber_TASC | TASC | MAD-37-G | Amman | 59 | 31.7718 | 35.9418 | Amman | Tower | [36 empty] | Approved
3805 | 3805-Natel_PF_TASC | TASC | MAD-5-G | Amman | 287 | 31.6502 | 35.8642 | Amman | Tower | [36 empty] | Approved
611 | 611-Sahab_Bridge_PB_Fiber_TASC | TASC | AME-69-R | Amman | 71 | 31.8552 | 36.0061 | Amman | Tower | [36 empty] | Approved
656 | 656-Sahab_Janzeer_St_PD_Fiber_TASC_O | TASC | AMS-92-R | Amman |  | 31.8722 | 36.0074 | Amman | Pole | [36 empty] | Approved
1515 | 1515-Maeen_1_PE_Zain_TASC | TASC | MAD-15-G | Madaba | 244 | 31.6665 | 35.6598 | Madaba | Tower | [36 empty] | Approved
1503 | 1503-Lib_PC_TASC | TASC | MAD-3-G | Madaba | 230 | 31.6179 | 35.7732 | Madaba | Tower | [36 empty] | Approved
5756 | 5756-Rawda_Husban_PF_TASC_O | TASC | AMS-74-R | Amman |  | 31.8282 | 35.7868 | Amman | Pole | [36 empty] | Approved
5763 | 5763-Karmiet_Husban_PE_TASC_O | TASC | AMS-96-R | Amman |  | 31.7994 | 35.8088 | Amman | Tower | [36 empty] | Approved
630 | 630-Dhaibeh_West_PC_Fiber_TASC | TASC | AME-699-R | Amman | 1621 | 31.7994 | 36.0253 | Amman | Tower | [36 empty] | Approved
3804 | 3804-Lubban_PE_TASC_O | TASC | AME-590-R | Amman |  | 31.8223 | 35.9606 | Amman | Tower | [36 empty] | Approved
1595 | 1595-Helaliyeh_Madaba_PF_O | TASC | MAD-258-R | Madaba |  | 31.638 | 35.7688 | Madaba | Tower | [36 empty] | Approved
1598 | 1598-Malih_East_PF_TASC_O | TASC | MAD-260-R | Madaba |  | 31.5904 | 35.8213 | Madaba | Pole | [36 empty] | Approved
3806 | 3806-Jaloul_PE_EBand_TASC | TASC | MAD-179-G | Amman | 280 | 31.718 | 35.8528 | Amman | Tower | [36 empty] | Approved
5717 | 5717-German_Uni_Madaba_PC_Fiber_Zain_TASC | TASC | MAD-194-G | Amman | 1662 | 31.7835 | 35.801 | Amman | Tower | [36 empty] | Approved
5715 | 5715-Cigarette_Company_PC_TASC | TASC | MAD-7-G | Amman | 159 | 31.8539 | 35.8331 | Amman | Tower | [36 empty] | Approved
3826 | 3826-Um_AlBerak_PD_Fiber_O | TASC | AMS-40-R | Amman |  | 31.8122 | 35.8627 | Amman | Tower | [36 empty] | Approved
5710 | 5710-German_Uni_2_PF_TASC_O | TASC | MAD-210-R | Amman |  | 31.7763 | 35.8029 | Amman | Pole | [36 empty] | Approved
3807 | 3807-Pharmacists_HSG_PD_Fiber_O | TASC | AME-814-R | Amman |  | 31.832 | 35.9258 | Amman | Tower | [36 empty] | Approved
3861 | 3861-Zaytoonah_Uni_PA_Fiber_TASC | TASC | MAD-125-G | Amman | 424 | 31.8275 | 35.8802 | Amman | Tower | [36 empty] | Approved
5761 | 5761-Yadoudeh_End_PF_O | TASC | AMS-75-R | Amman |  | 31.8523 | 35.9084 | Amman | Pole | [36 empty] | Approved
3803 | 3803-Yadoudeh_PC_Fiber_Zain_TASC | TASC | AME-380-G | Amman | 323 | 31.8204 | 35.9358 | Amman | Tower | [36 empty] | Approved
633 | 633-Sahab_Rd_PD_Fiber_TASC | TASC | AME-706-R | Amman | 1630 | 31.8647 | 36.0006 | Amman | Tower | [36 empty] | Approved
5720 | 5720-Rawda_Sahab_PF_TASC_O | TASC | MAD-6-R | Amman |  | 31.8341 | 35.8067 | Amman | Pole | [36 empty] | Approved
5798 | 5798-Faisalieh_PC_Fiber_TASC | TASC | MAD-1-R | Madaba | 211 | 31.7486 | 35.7709 | Madaba | Tower | [36 empty] | Approved
5330 | 5330-Customs_Dallah_CRL_PE_Fiber_TASC | TASC | AME-718-R | Amman | 1655 | 31.8963 | 35.9303 | Amman | Pole | [36 empty] | Approved
5727 | 5727-Sail_Husban_PC_EBand_TASC | TASC | MAD-26-G | Amman | 146 | 31.8549 | 35.7784 | Amman | Tower | [36 empty] | Approved
634 | 634-Sahab_East_PD | TASC | AME-719-R | Amman | 1700 | 31.8653 | 36.0159 | Amman | Pole | [36 empty] | Approved
606 | 606-Tarkhees_Sahab_PB_Fiber_TASC | TASC | AME-529-G | Amman | 489 | 31.834 | 36.0526 | Amman | Tower | [36 empty] | Approved
629 | 629-Dhaibeh_East_PE_O | TASC | AME-796-R | Amman |  | 31.8098 | 36.0552 | Amman | Pole | [36 empty] | Approved
607 | 607-Muwaqqar_Um_Botmah_PE_EBand_TASC_O | TASC | AME-797-R | Amman |  | 31.8251 | 36.0725 | Amman | Tower | [36 empty] | Approved
1547 | 1547-Madaba_Police_Directorate_PF_TASC_O | TASC | MAD-259-R | Madaba |  | 31.7221 | 35.7846 | Madaba | Pole | [36 empty] | Approved
618 | 618-Iskan_Rawda_PF_TASC_O | TASC | AME-632-G | Amman |  | 31.8236 | 36.1535 | Amman | Tower | [36 empty] | Approved
1574 | 1574-Madaba_Faislieh_CRL_PE_O | TASC | MAD-226-R | Madaba |  | 31.7383 | 35.77 | Madaba | Pole | [36 empty] | Approved
5314 | 5314-Jwaideh_Khraibet_Souq_PF_EBand_TASC_O | TASC | AMS-90-R | Amman |  | 31.8787 | 35.926 | Amman | Pole | [36 empty] | Approved
1594 | 1594-Madaba_Camp_PE_TASC_O | TASC | MAD-251-R | Madaba |  | 31.7108 | 35.7865 | Madaba | Pole | [36 empty] | Approved
3815 | 3815-Andalusieh_PD_Fiber_Zain_TASC | TASC | MAD-174-G | Amman | 1563 | 31.7615 | 35.8932 | Amman | Tower | [36 empty] | Approved
1566 | 1566-Madaba_3_PE_TASC | TASC | MAD-61-R | Madaba | 235 | 31.7163 | 35.7804 | Madaba | Tower | [36 empty] | Approved
5751 | 5751-Turkey_PF_TASC_O | TASC | MAD-235-R | Amman |  | 31.8449 | 35.7508 | Amman | Pole | [36 empty] | Approved
657 | 657-Faisalieh_Sahab_South_PD_Fiber_TASC_O | TASC | AMS-87-R | Amman |  | 31.846 | 36.0503 | Amman | Pole | [36 empty] | Approved
653 | 653-Nqairah_PE_TASC_O | TASC | AMS-81-R | Amman |  | 31.8314 | 36.0823 | Amman | Pole | [36 empty] | Approved
3823 | 3823-QAIA_Cargo_PE_Fiber_TASC_O | TASC | MAD-212-R | Amman |  | 31.7232 | 35.9973 | Amman | Pole | [36 empty] | Approved
5703 | 5703-Arabic_Horse_Club_PF_TASC_O | TASC | MAD-50-R | Amman |  | 31.8439 | 35.8812 | Amman | Pole | [36 empty] | Approved
5320 | 5320-Jawa_South_PC_EBand_TASC | TASC | AME-512-R | Amman | 438 | 31.8557 | 35.9361 | Amman | Pole | [36 empty] | Approved
3872 | 3872-Madaba_Bridge_PB_Fiber_TASC | TASC | MAD-67-G | Amman | 342 | 31.7858 | 35.9024 | Amman | Tower | [36 empty] | Approved
1513 | 1513-Maeen_CRL_PD_EBand_TASC | TASC | MAD-142-R | Madaba | 492 | 31.6784 | 35.7354 | Madaba | Tower | [36 empty] | Approved
3817 | 3817-Qastal_Ind_PB_Fiber_TASC | TASC | MAD-192-G | Amman | 1592 | 31.7574 | 35.9663 | Amman | Tower | [36 empty] | Approved
3839 | 3839-Jizah_Ind_PC_TASC | TASC | MAD-71-G | Amman | 462 | 31.6772 | 35.9643 | Amman | Tower | [36 empty] | Approved
3814 | 3814-Samek_PE_TASC_O | TASC | AMS-93-R | Amman |  | 31.7956 | 35.8611 | Amman | Pole | [36 empty] | Approved
610 | 610-Haier_Factory_PC_Fiber_TASC | TASC | AME-577-R | Amman | 1532 | 31.8075 | 36.0405 | Amman | Tower | [36 empty] | Approved
615 | 615-Mughayer_Muhanna_PE_EBand_TASC_O | TASC | AME-73-R | Amman |  | 31.8335 | 36.1119 | Amman | Pole | [36 empty] | Approved
3840 | 3840-Backaldrin_Factory_PF_TASC_O | TASC | MAD-201-R | Amman |  | 31.7599 | 35.9912 | Amman | Pole | [36 empty] | Approved
5705 | 5705-King_Hussein_Forest_PF_TASC_O | TASC | MAD-176-R | Amman |  | 31.8589 | 35.8674 | Amman | Pole | [36 empty] | Approved
3860 | 3860-Jizah_Camp_PC_Fiber_TASC | TASC | MAD-204-R | Amman | 1656 | 31.706 | 35.9489 | Amman | Tower | [36 empty] | Approved
5315 | 5315-Bait_AlMaqdes_Sch_PC_EBand_TASC | TASC | AME-700-R | Amman | 1618 | 31.8699 | 35.9104 | Amman | Tower | [36 empty] | Approved
5767 | 5767-Amman_Waves_Rd_PE_TASC_O | TASC | AMS-142-R | Amman |  | 31.8623 | 35.8898 | Amman | Pole | [36 empty] | Approved
614 | 614-Sahab_PA_Fiber_TASC | TASC | AME-72-G | Amman | 128 | 31.8804 | 35.9872 | Amman | Tower | [36 empty] | Approved
613 | 613-Sahab_City_PC | TASC | AME-71-R | Amman | 129 | 31.8707 | 36.0052 | Amman | Pole | [36 empty] | Approved
637 | 637-Souq_Khudra_PC_Fiber_TASC | TASC | AME-84-G | Amman | 142 | 31.8696 | 35.9575 | Amman | Tower | [36 empty] | Approved
5305 | 5305-Jwaideh_Hay_Albayer_PE | TASC | AME-729-R | Amman | 1684 | 31.8869 | 35.9382 | Amman | Pole | [36 empty] | Approved
603 | 603-Mustanada_PD_O | TASC | AME-91-R | Amman |  | 31.9054 | 36.001 | Amman | Pole | [36 empty] | Approved
5306 | 5306-Jwaideh_Taibeh_PD_Fiber | TASC | AME-727-R | Amman | 1698 | 31.8828 | 35.9255 | Amman | Tower | [36 empty] | Approved
609 | 609-Baida_Sahab_PC_Zain | TASC | AME-105-G | Amman | 394 | 31.9062 | 36.0615 | Amman | Tower | [36 empty] | Approved
608 | 608-Halawani_Factory_PF_TASC_O | TASC | AME-99-R | Amman |  | 31.9026 | 36.0159 | Amman | Pole | [36 empty] | Approved
5310 | 5310-Jawa_PC_Fiber | TASC | AME-385-R | Amman | 63 | 31.869 | 35.9281 | Amman | Tower | [36 empty] | Approved
628 | 628-AbuAlanda_2_PC_Fiber_TASC | TASC | AME-81-G | Amman | 3 | 31.8986 | 35.9809 | Amman | Tower | [36 empty] | Approved
5341 | 5341-Khraibet_Alsouq_PC_EBand_TASC | TASC | AME-85-R | Amman | 88 | 31.8791 | 35.9331 | Amman | Tower | [36 empty] | Approved
5355 | 5355-Yadoudeh_2_PD_O | TASC | AME-791-R | Amman |  | 31.8559 | 35.9157 | Amman | Pole | [36 empty] | Approved
658 | 658-Nafe_Village_East_PE_TASC_O | TASC | AMS-115-R | Amman |  | 31.869 | 35.9499 | Amman | Tower | [36 empty] | Approved
619 | 619-Sahab_Ind_2_PE_TASC | TASC | AME-555-R | Amman | 110 | 31.8854 | 35.9684 | Amman | Tower | [36 empty] | Approved
5329 | 5329-Jawa_Alwafa_PC_O | TASC | AME-779-R | Amman |  | 31.8417 | 35.9517 | Amman | Pole | [36 empty] | Approved
5316 | 5316-Jwaideh_West_PC_Fiber_TASC | TASC | AME-425-R | Amman | 436 | 31.8806 | 35.9198 | Amman | Tower | [36 empty] | Approved
632 | 632-Sahab_Airplane_CRL_PD | TASC | AME-738-R | Amman | 1716 | 31.8802 | 36.0014 | Amman | Pole | [36 empty] | Approved
650 | 650-Abdalieh_Sahab_PD_Fiber_TASC_O | TASC | AMS-62-R | Amman |  | 31.8889 | 36.01 | Amman | Pole | [36 empty] | Approved
5317 | 5317-AbuAlanda_Caragat_CTR_PF_TASC_O | TASC | AMS-76-R | Amman |  | 31.8947 | 35.9498 | Amman | Tower | [36 empty] | Approved
5303 | 5303-Mugabalein_Um_Quseir_PF_TASC_O | TASC | AME-672-R | Amman |  | 31.8849 | 35.9141 | Amman | Pole | [36 empty] | Approved
5325 | 5325-Taibeh_Khraibet_Alsouq_PB_Fiber_TASC | TASC | AME-795-R | Amman | 1741 | 31.8684 | 35.9237 | Amman | Tower | [36 empty] | Approved
625 | 625-Sahab_St_PD_Fiber_TASC | TASC | AME-419-R | Amman | 418 | 31.8738 | 35.9975 | Amman | Pole | [36 empty] | Approved
5302 | 5302-Jawa_South_2_PE_TASC | TASC | AME-667-R | Amman | 1593 | 31.8474 | 35.9396 | Amman | Tower | [36 empty] | Approved
5345 | 5345-Customs_2_PE_EBand_TASC | TASC | AME-88-R | Amman | 74 | 31.8916 | 35.9394 | Amman | Tower | [36 empty] | Approved
5333 | 5333-Jwaideh_Iskan_Maleyeh_PD_Fiber_TASC | TASC | AME-722-R | Amman | 1658 | 31.8917 | 35.9265 | Amman | Pole | [36 empty] | Approved
5340 | 5340-Jawa_3_PE_EBand_TASC | TASC | AME-715-R | Amman | 1657 | 31.8661 | 35.9328 | Amman | Tower | [36 empty] | Approved
655 | 655-Sahab_East_2_PD_O | TASC | AMS-80-R | Amman |  | 31.8741 | 36.0184 | Amman | Pole | [36 empty] | Approved
646 | 646-Sahab_West_Mada_PF_Fiber_TASC_O | TASC | AMS-53-R | Amman |  | 31.8766 | 35.997 | Amman | Pole | [36 empty] | Approved
659 | 659-Souq_Khudra_Markazi_PF_TASC_O | TASC | AMS-113-R | Amman |  | 31.8657 | 35.9601 | Amman | Pole | [36 empty] | Approved
635 | 635-Sahab_City_2_PC_Fiber_TASC | TASC | AME-83-R | Amman | 130 | 31.8783 | 36.0098 | Amman | Pole | [36 empty] | Approved
5344 | 5344-Customs_PC_Fiber_TASC | TASC | AME-87-R | Amman | 73 | 31.8969 | 35.9364 | Amman | Tower | [36 empty] | Approved
5312 | 5312-Jawa_Mada_PF_TASC_O | TASC | AMS-64-R | Amman |  | 31.8721 | 35.9304 | Amman | Pole | [36 empty] | Approved
3605 | 3605-Um_Qsair_NEPCO_PE_O | TASC | AME-815-R | Amman |  | 31.8902 | 35.9042 | Amman | Pole | [36 empty] | Approved
647 | 647-Rajeeb_East_PF_TASC_O | TASC | AMS-61-R | Amman |  | 31.8871 | 35.9783 | Amman | Tower | [36 empty] | Approved
5743 | 5743-Naour_Ent_PF_TASC_O | TASC | AMS-20-R | Amman |  | 31.8834 | 35.8336 | Amman | Tower | [36 empty] | Approved
5741 | 5741-Naour_Bahath_PA_Fiber_TASC | TASC | MAD-40-G | Amman | 283 | 31.9151 | 35.782 | Amman | Tower | [36 empty] | Approved
5702 | 5702-Naour_2_PC_O | TASC | AME-753-R | Amman |  | 31.8825 | 35.8258 | Amman | Pole | [36 empty] | Approved
5701 | 5701-Naour_City_PB_Fiber_TASC | TASC | AME-411-G | Amman | 390 | 31.8739 | 35.8172 | Amman | Tower | [36 empty] | Approved
5726 | 5726-AbuAlSous_Greenland_PE_Fiber_TASC_O | TASC | AMS-104-R | Amman |  | 31.9218 | 35.7953 | Amman | Pole | [36 empty] | Approved
5744 | 5744-Naour_Basset_Bridge_Um_PE_Fiber_TASC_O | TASC | AMS-17-R | Amman |  | 31.8676 | 35.8115 | Amman | Tower | [36 empty] | Approved
5764 | 5764-Bassah_CTR_PE_TASC_O | TASC | AMS-89-R | Amman |  | 31.9291 | 35.7823 | Amman | Pole | [36 empty] | Approved
5723 | 5723-Farouq_Ave_PF_TASC_O | TASC | AMS-110-R | Amman |  | 31.8729 | 35.8853 | Amman | Pole | [36 empty] | Approved
5746 | 5746-Iraq_Amir_Rawashdeh_PF_O | TASC | AMS-29-R | Amman |  | 31.9213 | 35.7555 | Amman | Pole | [36 empty] | Approved
5765 | 5765-Maniyeh_Qasabat_PF_TASC_O | TASC | AMS-88-R | Amman |  | 31.9056 | 35.7686 | Amman | Pole | [36 empty] | Approved
5707 | 5707-Airport_Rd_1_PD_EBand_TASC | TASC | AMW-514-G | Amman | 1508 | 31.8813 | 35.8801 | Amman | Tower | [36 empty] | Approved
5740 | 5740-Naour_Middle_PE_Fiber_TASC_O | TASC | AMS-21-R | Amman |  | 31.8754 | 35.8204 | Amman | Tower | [36 empty] | Approved
107 | 107-Park_Plaza_PA_Fiber_IBS_TASC | TASC | AMS-32-R | Amman |  | 31.9587 | 35.8692 | Amman | [21 empty] | IBS | [15 empty] | Approved
5745 | 5745-Naour_Police_Station_PE_Fiber_TASC_O | TASC | AMS-19-R | Amman |  | 31.8733 | 35.8287 | Amman | Pole | [36 empty] | Approved
5724 | 5724-Belaas_PB_Fiber_TASC | TASC | AME-626-R | Amman | 1556 | 31.8721 | 35.8391 | Amman | Pole | [36 empty] | Approved
1549 | 1549-Madaba_Camp_North_PF_TASC_O | TASC | MAD-266-R | Madaba |  | 31.7174 | 35.7871 | Madaba | Pole | [36 empty] | Approved
5358 | 5358-Iskan_Taibeh_Sch_Back_PF_TASC_O | TASC | AMS-137-R | Amman |  | 31.8808 | 35.9146 | Amman | Pole | [36 empty] | Approved
1550 | 1550-Madaba_Camp_South_PE_TASC_O | TASC | MAD-265-R | Madaba |  | 31.7075 | 35.7848 | Madaba | Tower | [36 empty] | Approved
5354 | 5354-Taibeh_Mazharieh_Cross_PF_TASC_O | TASC | AMS-148-R | Amman |  | 31.8731 | 35.9208 | Amman | Pole | [36 empty] | Approved
5359 | 5359-Jawa_4_PD_Fiber_TASC_O | TASC | AMS-160-R | Amman |  | 31.8647 | 35.9271 | Amman | Tower | [36 empty] | Approved
664 | 664-Khashafiet_Dabaibeh_North_PE_TASC_O | TASC | AMS-141-R | Amman |  | 31.8927 | 36.0517 | Amman | Pole | [36 empty] | Approved
672 | 672-Halawani_Factory_Back_PD_TASC_O | TASC | AMS-156-R | Amman |  | 31.8941 | 36.0254 | Amman | Tower | [36 empty] | Approved
1552 | 1552-Madaba_Azazmeh_Ave_PF_TASC_O | TASC | MAD-264-R | Madaba |  | 31.6989 | 35.7784 | Madaba | Tower | [36 empty] | Approved
1551 | 1551-Madaba_South_PE_TASC_O | TASC | MAD-262-R | Madaba |  | 31.7069 | 35.8032 | Madaba | Pole | [36 empty] | Approved
5768 | 5768-Mansoura_Rawda_South_PD_TASC_O | TASC | AMS-135-R | Amman |  | 31.8358 | 35.8297 | Amman | Pole | [36 empty] | Approved
5353 | 5353-Hurrieh_St_Mid_PF_TASC_O | TASC | AMS-153-R | Amman |  | 31.8931 | 35.9195 | Amman | Pole | [36 empty] | Approved
661 | 661-Mustanada_HSG_PD_EBand_TASC_O | TASC | AMS-118-R | Amman |  | 31.9003 | 35.996 | Amman | Tower | [36 empty] | Approved
669 | 669-Abdalieh_South_PD_Fiber_TASC_O | TASC | AMS-152-R | Amman |  | 31.8831 | 36.0196 | Amman | Pole | [36 empty] | Approved
5766 | 5766-Aal_CTR_PD_TASC_O | TASC | AMS-94-R | Amman |  | 31.8145 | 35.8367 | Amman | Pole | [36 empty] | Approved
663 | 663-Sahab_Old_CPLX_PE_Fiber_TASC_O | TASC | AMS-140-R | Amman |  | 31.8755 | 36.0051 | Amman | Pole | [36 empty] | Approved
665 | 665-Sahab_Rujm_Shami_Sch_PD_Fiber_TASC_O | TASC | AMS-121-R | Amman |  | 31.8419 | 36.0024 | Amman | Pole | [36 empty] | Approved
667 | 667-Raqeem_South_PE_TASC_O | TASC | AMS-117-R | Amman |  | 31.8915 | 35.9857 | Amman | Tower | [36 empty] | Approved
3835 | 3835-Qnaitreh_Jizah_PF_TASC_O | TASC | AMS-79-R | Amman |  | 31.6667 | 36.0468 | Amman | Pole | [36 empty] | Approved
1548 | 1548-Madaba_East_PE_TASC_O | TASC | MAD-268-R | Madaba |  | 31.7138 | 35.8067 | Madaba | Pole | [36 empty] | Approved
5357 | 5357-Jawa_Dahieh_Sch_PF_TASC_O | TASC | AMS-157-R | Amman |  | 31.863 | 35.9406 | Amman | Tower | [36 empty] | Approved
3834 | 3834-Arainbeh_PE_TASC | TASC | KRK-72-R | Amman | 970 | 31.6433 | 36.0005 | Amman | Tower | [36 empty] | Approved
5732 | 5732-Madaba_Maamonieh_East_PF_TASC_O | TASC | MAD-267-R | Amman |  | 31.7382 | 35.8378 | Amman | Pole | [36 empty] | Approved
5362 | 5362-Jwaideh_Umzaarorah_PE_EBand_TASC_O | TASC | AMS-165-R | Amman |  | 31.874 | 35.9422 | Amman | Pole | [36 empty] | Approved
1559 | 1559-Madaba_East_2_PE_TASC_O | TASC | MAD-270-R | Madaba |  | 31.7174 | 35.8068 | Madaba | Tower | [36 empty] | Approved
660 | 660-Sahab_Princess_Eman_HSG_PE_TASC_O | TASC | AME-925-R | Amman |  | 31.8409 | 35.9764 | Amman | Pole | [36 empty] | Approved
5351 | 5351-Bayer_Ave_South_PF_TASC_O | TASC | AMS-146-R | Amman |  | 31.8848 | 35.9474 | Amman | Pole | [36 empty] | Approved
1586 | 1586-Rmail_PE_TASC | TASC | KRK-19-G | Amman | 803 | 31.5609 | 35.8778 | Amman | Tower | [36 empty] | Approved
5769 | 5769-Balaas_Salam_Ave_PF_TASC_O | TASC | AMS-161-R | Amman |  | 31.863 | 35.8582 | Amman | Pole | [36 empty] | Approved
668 | 668-Nozhet_Sahab_PE_Fiber_TASC_O | TASC | AMS-144-R | Amman |  | 31.8571 | 35.9798 | Amman | Pole | [36 empty] | Approved
662 | 662-Sahab_Rujm_Shami_South_PD_TASC_O | TASC | AMS-139-R | Amman |  | 31.8315 | 36.0017 | Amman | Pole | [36 empty] | Approved
670 | 670-Lubban_100_St_End_PE_TASC_O | TASC | AMS-125-R | Amman |  | 31.8138 | 35.9805 | Amman | Tower | [36 empty] | Approved
5805 | 5805-Tafilah_Jurf_Daraweish_1_PF_TASC | TASC | TAF-9-G | Tafila | 849 | 30.7433 | 35.7813 | Tafila | Tower | [36 empty] | Approved
5830 | 5830-Tafilah_Ghor_Rd_PE_Fiber_TASC_Solar_O | TASC | TAF-53-G | Tafila |  | 30.8646 | 35.5221 | Tafila | Tower | [36 empty] | Approved
5818 | 5818-Rashadyeh_Desert_Rd_PE_Fiber_TASC_Solar | TASC | MAN-65-G | Tafila | 966 | 30.6294 | 35.6707 | Tafila | Tower | [36 empty] | Approved
5835 | 5835-Salmani_PD_Fiber_TASC | TASC | TAF-2-G | Karak | 840 | 30.8235 | 35.371 | Karak | Tower | [36 empty] | Approved
5880 | 5880-Namaty_Tafilah_PF_TASC_O | TASC | TAF-23-G | Tafila |  | 30.8019 | 35.5521 | Tafila | Pole | [36 empty] | Approved
5823 | 5823-Karak_Tafilah_Rd_PF_TASC_Solar | TASC | KRK-63-G | Tafila | 852 | 30.9234 | 35.7115 | Tafila | Tower | [36 empty] | Approved
5836 | 5836-Qraiqra_PE_Fiber_TASC | TASC | TAF-3-G | Aqaba | 879 | 30.7223 | 35.3122 | Aqaba | Tower | [36 empty] | Approved
621 | 621-Souq_Halal_PE_Zain_TASC_O | TASC | AME-655-G | Amman |  | 31.9098 | 36.1222 | Amman | Tower | [36 empty] | Approved
3719 | 3719-Wadi_Shoaib_PF_Zain_TASC_Solar | TASC | BLQ-17-G | Balqa | 427 | 31.9491 | 35.6748 | Balqa | Tower | [36 empty] | Approved
1458 | 1458-Sakib_Anjarah_Rd_2_PD_Fiber_TASC | TASC | JRS-32-R | Jarash | 2105 | 32.2787 | 35.7983 | Jarash | Pole | [36 empty] | Approved
1916 | 1916-Jabal_Mughayer_3_PF_EBand_TASC_O | TASC | ZRQ-237-R | Zarqa |  | 32.1005 | 36.08 | Zarqa | Pole | [36 empty] | Approved
4507 | 4507-Sukhneh_Qunieh_Rd_1_PE_Fiber_TASC | TASC | JRS-3-G | Zarqa | 685 | 32.1427 | 36.0136 | Zarqa | Tower | [36 empty] | Approved
3410 | 3410-Burma_Sbaihi_PF_TASC | TASC | BLQ-9-G | Balqa | 469 | 32.1704 | 35.6989 | Balqa | Tower | [36 empty] | Approved
1445 | 1445-Sakib_Anjarah_Rd_PE_TASC | TASC | AJL-19-G | Ajloun | 755 | 32.2934 | 35.7852 | Ajloun | Tower | [36 empty] | Approved
1414 | 1414-Sukhneh_Qunieh_Rd_2_PE_TASC | TASC | JRS-5-G | Jarash | 686 | 32.2375 | 35.9704 | Jarash | Tower | [36 empty] | Approved
4531 | 4531-Qunieh_PB_Fiber_TASC | TASC | JRS-2-G | Jarash | 691 | 32.2353 | 35.9547 | Jarash | Tower | [36 empty] | Approved
3417 | 3417-Arda_PF_TASC_O | TASC | BLQ-7-G | Balqa |  | 32.1244 | 35.6867 | Balqa | Tower | [36 empty] | Approved
3432 | 3432-Dogara_Irbid_PF_TASC_O | TASC | IRB-304-R | Irbid |  | 32.5996 | 35.7408 | Irbid | Pole | [36 empty] | Approved
3744 | 3744-Um_AlAmmad_Salt_PF_TASC | TASC | BLQ-130-R | Balqa | 1613 | 32.1082 | 35.7523 | Balqa | Pole | [36 empty] | Approved
3737 | 3737-Maghareeb_PF_TASC_O | TASC | BLQ-114-R | Balqa |  | 32.0199 | 35.6805 | Balqa | Pole | [36 empty] | Approved
3454 | 3454-Arda_3_PF_Zain_TASC | TASC | BLQ-51-G | Balqa | 468 | 32.1387 | 35.6468 | Balqa | Tower | [36 empty] | Approved
3455 | 3455-Hemmeh_PF_TASC_O | TASC | BLQ-127-R | Irbid |  | 32.6113 | 35.6152 | Irbid | Pole | [36 empty] | Approved
3705 | 3705-Yarqa_PB_Fiber_TASC | TASC | BLQ-4-G | Balqa | 324 | 31.9672 | 35.7058 | Balqa | Tower | [36 empty] | Approved
2845 | 2845-AbuZeeghan_Village_PE_TASC_O | TASC | BLQ-137-R | Zarqa |  | 32.1183 | 36.0513 | Zarqa | Pole | [36 empty] | Approved
4719 | 4719-Hayan_Mafraq_PF_TASC | TASC | MFQ-94-R | Mafraq | 1813 | 32.2415 | 36.1214 | Mafraq | Pole | [36 empty] | Approved
1126 | 1126-Shaalan_PE_Fiber_TASC_Solar | TASC | MFQ-26-G | Mafraq | 673 | 32.6233 | 38.6049 | Mafraq | Tower | [36 empty] | Approved
1124 | 1124-Ashqaf_PE_Fiber_TASC_Solar | TASC | MFQ-24-G | Mafraq | 618 | 32.3444 | 37.6208 | Mafraq | Tower | [36 empty] | Approved
1121 | 1121-Hwejeh_Mafraq_PE_TASC_O | TASC | MFQ-99-G | Mafraq | 1718 | 32.3935 | 36.2622 | Mafraq | Tower | [36 empty] | Approved
1197 | 1197-Jafer_6_PD_TASC | TASC | MFQ-15-G | Zarqa | 635 | 31.6444 | 36.8578 | Zarqa | Tower | [36 empty] | Approved
1107 | 1107-Azraq_Safawi_Rd_PE_Fiber_TASC_Solar | TASC | MFQ-7-G | Mafraq | 682 | 31.9848 | 36.9275 | Mafraq | Tower | [36 empty] | Approved
1133 | 1133-Ashqaf_Ruwaished_Rd_PE_Fiber_TASC_Solar | TASC | MFQ-33-G | Mafraq | 683 | 32.4166 | 37.9008 | Mafraq | Tower | [36 empty] | Approved
4736 | 4736-Thaghret_Jub_PF_TASC | TASC | ZRQ-88-G | Mafraq | 504 | 32.245 | 36.244 | Mafraq | Tower | [36 empty] | Approved
1108 | 1108-Harraneh_Palace_PF_TASC_Solar | TASC | MFQ-8-G | Amman | 638 | 31.7368 | 36.5188 | Amman | Tower | [36 empty] | Approved
1142 | 1142-Azraq_Harraneh_Rd_PF_TASC | TASC | MFQ-42-G | Zarqa | 639 | 31.853 | 36.6787 | Zarqa | Tower | [36 empty] | Approved
1117 | 1117-Safawi_Ashqaf_Rd_PE_Fiber_TASC_Solar | TASC | MFQ-55-G | Mafraq | 758 | 32.2689 | 37.3647 | Mafraq | Tower | [36 empty] | Approved
1109 | 1109-Ruwaished_Camp_PE_Fiber_TASC | TASC | MFQ-61-G | Mafraq | 766 | 32.5836 | 38.4627 | Mafraq | Tower | [36 empty] | Approved
3854 | 3854-Traffic_Institute_PC_Zain_TASC | TASC | AME-496-G | Amman | 416 | 31.7547 | 36.0356 | Amman | Tower | [36 empty] | Approved
5728 | 5728-Naour_Edbayyan_MGS_PF_TASC_O | TASC | MAD-223-R | Amman |  | 31.8469 | 35.8484 | Amman | Pole | [36 empty] | Approved
819 | 819-Afraneh_PE_TASC | TASC | KRK-4-G | Karak | 855 | 31.1645 | 35.6638 | Karak | Tower | [36 empty] | Approved
867 | 867-Karak_Bus_CPLX_PE_Fiber_TASC_O | TASC | KRK-65-R | Karak |  | 31.1727 | 35.7035 | Karak | Pole | [36 empty] | Approved
1560 | 1560-Makawer_PE_Zain_TASC | TASC | MAD-124-G | Madaba |  | 31.5877 | 35.6701 | Madaba | Tower | [36 empty] | Approved
1564 | 1564-Oyon_Theb_PF_TASC | TASC | MAD-59-G | Madaba | 332 | 31.6994 | 35.7271 | Madaba | Tower | [36 empty] | Approved
1528 | 1528-Faiha_PC_TASC_Solar | TASC | MAD-27-G | Madaba | 209 | 31.735 | 35.7122 | Madaba | Tower | [36 empty] | Approved
3137 | 3137-Yajouz_Special_Operation_PF_TASC_O | TASC | ZRQ-270-R | Amman |  | 32.0246 | 35.9787 | Amman | Tower | [36 empty] | Approved
4222 | 4222-Hashmia_Hall_Zarqa_PF_O | TASC | ZRQ-297-G | Zarqa |  | 32.0758 | 36.1018 | Zarqa | Tower | [36 empty] | Approved
1035 | 1035-Um_Alfatayer_PF_TASC_O | TASC | ZRQ-214-G | Zarqa |  | 32.0723 | 35.9972 | Zarqa | Pole | [36 empty] | Approved
708 | 708-Eshidiya_Rd_PC_Zain_TASC_Solar | TASC | MAN-8-G | Ma'an | 845 | 29.9939 | 35.9333 | Ma'an | Tower | [36 empty] | Approved
711 | 711-Maan_Jafer_Rd_PE_TASC_O | TASC | MAN-64-G | Ma'an | 850 | 30.1799 | 36.0366 | Ma'an | Tower | [36 empty] | Approved
1455 | 1455-Harth_Ajloun_PE_Fiber_TASC_O | TASC | AJL-21-R | Ajloun |  | 32.2691 | 35.6709 | Ajloun | Pole | [36 empty] | Approved
671 | 671-Baida_100_St_Bridge_PF_TASC_O | TASC | AMS-133-R | Amman |  | 31.9168 | 36.0732 | Amman | Tower | [36 empty] | Approved
3849 | 3849-Jawa_Quba_District_East_PE_Fiber_TASC_O | TASC | AMS-168-R | Amman |  | 31.8364 | 35.9323 | Amman | Pole | [36 empty] | Approved
1131 | 1131-Manara_Mafraq_PF_TASC_O | TASC | MFQ-211-R | Mafraq |  | 32.1886 | 36.7108 | Mafraq | Tower | [36 empty] | Approved
1111 | 1111-Nahdah_Mafraq_PF_TASC_O | TASC | MFQ-206-G | Mafraq |  | 32.3967 | 36.3225 | Mafraq | Tower | [36 empty] | Approved
4573 | 4573-Um_Rummaneh_Zarqa_PE_TASC_O | TASC | ZRQ-365-R | Zarqa |  | 32.0977 | 35.9282 | Zarqa | Pole | [36 empty] | Approved
1056 | 1056-Zarqa_Madina_Monawara_South_PF_TASC_O | TASC | ZRQ-364-R | Zarqa |  | 32.0476 | 36.052 | Zarqa | Pole | [36 empty] | Approved
1438 | 1438-Sakhra_Ajloun_PE_TASC_O | TASC | AJL-55-R | Ajloun |  | 32.3745 | 35.8397 | Ajloun | Tower | [36 empty] | Approved
4708 | 4708-Breqa_Village_PE_TASC_O | TASC | MFQ-230-G | Mafraq |  | 32.4453 | 36.0278 | Mafraq | Tower | [36 empty] | Approved
731 | 731-Petra_Mkhaimer_PF_TASC_O | TASC | MAN-165-R | Ma'an |  | 30.3104 | 35.4707 | Ma'an | Pole | [36 empty] | Approved
4311 | 4311-Zarqa_Qadesieh_CTR_PE_TASC_O | TASC | ZRQ-369-R | Zarqa |  | 32.0382 | 36.0412 | Zarqa | Tower | [36 empty] | Approved
1306 | 1306-Hizam_Rd_PE_Fiber_TASC_O | TASC | AME-1002-R | Amman |  | 31.9572 | 35.99 | Amman | Pole | [36 empty] | Approved
3107 | 3107-Wadi_Alsh_100_St_PF_TASC_O | TASC | ZRQ-371-G | Zarqa |  | 31.948 | 36.0906 | Zarqa | Tower | [36 empty] | Approved
5748 | 5748-Naour_Rujum_Sawaeer_PE_Fiber_TASC_O | TASC | AMS-188-R | Amman |  | 31.8665 | 35.8191 | Amman | Tower | [36 empty] | Approved
1479 | 1479-Anjarah_1_PF_O | TASC | AJL-56-R | Ajloun |  | 32.2772 | 35.7257 | Ajloun | Pole | [36 empty] | Approved
5327 | 5327-Jawa_Qaisieh_Ave_PE_EBand_TASC_O | TASC | AMS-199-R | Amman |  | 31.8767 | 35.9325 | Amman | Tower | [36 empty] | Approved
4557 | 4557-Baqaa_Middle_PD_Fiber_TASC_O | TASC | BLQ-225-R | Balqa |  | 32.075 | 35.8469 | Balqa | Pole | [36 empty] | Approved
4558 | 4558-Baqaa_West_2_PE_Fiber_TASC_O | TASC | BLQ-226-R | Balqa |  | 32.0757 | 35.8401 | Balqa | Pole | [36 empty] | Approved
3122 | 3122-Hitteen_Camp_East_PF_TASC_O | TASC | AME-1016-R | Amman |  | 32.0059 | 36.0212 | Amman | Pole | [36 empty] | Approved
2895 | 2895-Delail_Howeid_Ave_PE_Fiber_TASC_O | TASC | ZRQ-377-R | Zarqa |  | 32.1193 | 36.2841 | Zarqa | Tower | [36 empty] | Approved
5722 | 5722-Kan_Zaman_PB_Fiber_TASC | TASC | AMS-200-R | Amman | 1745 | 31.8428 | 35.911 | Amman | Tower | [36 empty] | Approved
2883 | 2883-Delail_Obiedi_Ave_PD_Fiber_TASC_O | TASC | ZRQ-376-R | Zarqa |  | 32.1164 | 36.2897 | Zarqa | Tower | [36 empty] | Approved
3468 | 3468-Manshiet_Ghor_PC_EBand_TASC_O | TASC | IRB-505-R | Irbid |  | 32.5871 | 35.6034 | Irbid | Tower | [36 empty] | Approved
4574 | 4574-Baqaa_South_West_Ave_PE_O | TASC | BLQ-224-R | Balqa |  | 32.0679 | 35.8399 | Balqa | Tower | [36 empty] | Approved
3462 | 3462-Qam_Irbid_St_PF_TASC_O | TASC | IRB-504-R | Irbid |  | 32.5839 | 35.7239 | Irbid | Tower | [36 empty] | Approved
4668 | 4668-Tubneh_Irbid_Back_PF_TASC_O | TASC | IRB-503-R | Irbid |  | 32.4814 | 35.7236 | Irbid | Pole | [36 empty] | Approved
4552 | 4552-Baqaa_Mid_2_PE_Fiber_TASC_O | TASC | BLQ-227-R | Balqa |  | 32.0727 | 35.8445 | Balqa | Pole | [36 empty] | Approved
666 | 666-Sahab_Abdalieh_North_PE_TASC_O | TASC | AMS-208-R | Amman |  | 31.8946 | 36.0096 | Amman | Tower | [36 empty] | Approved
675 | 675-Sahab_City_Southern_Msq_PE_Fiber_TASC_O | TASC | AMS-209-R | Amman |  | 31.8675 | 36.0053 | Amman | Tower | [36 empty] | Approved
1328 | 1328-Marka_Prince_Faisal_South_PE_Fiber_TASC_O | TASC | AME-1018-R | Amman |  | 31.9637 | 35.9701 | Amman | Tower | [36 empty] | Approved
5747 | 5747-Madaba_Engineering_HSG_PF_TASC_O | TASC | MAD-275-R | Madaba |  | 31.7345 | 35.7846 | Madaba | Tower | [36 empty] | Approved
3101 | 3101-Queen_Nour_Forest_PF_TASC_O | TASC | AME-259-G | Amman | 198 | 32.0218 | 35.9536 | Amman | Tower | [36 empty] | Approved
1934 | 1934-Zarqa_Jawabreh_Hotel_PE_Fiber_TASC_O | TASC | ZRQ-390-R | Zarqa |  | 32.0933 | 36.0876 | Zarqa | Pole | [36 empty] | Approved
4218 | 4218-Zarqa_Hay_Shbeb_PE_TASC_O | TASC | ZRQ-389-R | Zarqa |  | 32.0643 | 36.0827 | Zarqa | Pole | [36 empty] | Approved
3119 | 3119-Marka_Naqab_HSG_PF_TASC_O | TASC | ZRQ-387-R | Zarqa |  | 32.0009 | 36.0251 | Zarqa | Tower | [36 empty] | Approved
3818 | 3818-Um_AlWaleed_PE_TASC_O | TASC | AMS-213-R | Amman |  | 31.6513 | 35.89 | Amman | Tower | [36 empty] | Approved
676 | 676-Sahab_Khashafiet_Shawbkeh_PF_TASC_O | TASC | AMS-217-R | Amman |  | 31.872 | 36.0316 | Amman | Pole | [36 empty] | Approved
756 | 756-Wadi_Moussa_Beqaa_PF_TASC_O | TASC | MAN-183-R | Ma'an |  | 30.3086 | 35.4969 | Ma'an | Tower | [36 empty] | Approved
4322 | 4322-Hay_Shaheed_South_PF_TASC_O | TASC | ZRQ-396-R | Zarqa |  | 32.0245 | 36.0375 | Zarqa | Tower | [36 empty] | Approved
4219 | 4219-Hay_Hussein_Middle_PE_Fiber_TASC_O | TASC | ZRQ-392-R | Zarqa |  | 32.0699 | 36.0854 | Zarqa | Pole | [36 empty] | Approved
4230 | 4230-Hay_Masoum_Cemetary_PF_TASC_O | TASC | ZRQ-402-R | Zarqa |  | 32.0729 | 36.0807 | Zarqa | Pole | [36 empty] | Approved
1911 | 1911-AbuAlfool_CTR_Zarqa_PF_EBand_TASC_O | TASC | ZRQ-401-R | Zarqa |  | 32.0858 | 36.1047 | Zarqa | Pole | [36 empty] | Approved
1352 | 1352-Nasser_Railway_CTR_PF_Fiber_TASC_O | TASC | AME-1028-R | Amman |  | 31.9602 | 35.9633 | Amman | Pole | [36 empty] | Approved
5894 | 5894-Shoubak_Mqareea_PF_TASC_O | TASC | MAN-185-G | Ma'an |  | 30.5502 | 35.565 | Ma'an | Pole | [36 empty] | Approved
4323 | 4323-Zarqa_Awajan_West_PE_TASC_O | TASC | ZRQ-399-R | Zarqa |  | 32.0234 | 36.0506 | Zarqa | Tower | [36 empty] | Approved
4320 | 4320-Zarqa_Tatweer_30_St_PF_TASC_O | TASC | ZRQ-400-R | Zarqa |  | 32.041 | 36.0578 | Zarqa | Tower | [36 empty] | Approved
3140 | 3140-Msherfeh_CTR_PF_EBand_TASC_O | TASC | ZRQ-409-R | Zarqa |  | 32.0135 | 36.0205 | Zarqa | Tower | [36 empty] | Approved
1024 | 1024-AL_Zawahrah_West_PF_TASC_O | TASC | ZRQ-397-R | Zarqa |  | 32.073 | 36.0614 | Zarqa | Tower | [36 empty] | Approved
3139 | 3139-Zarqa_Hay_Fakhorah_PF_Fiber_TASC_O | TASC | ZRQ-398-R | Zarqa |  | 32.005 | 36.034 | Zarqa | Tower | [36 empty] | Approved
3484 | 3484-Salt_Subaihi_Arqob_PE_Fiber_TASC_O | TASC | BLQ-230-R | Balqa |  | 32.151 | 35.6997 | Balqa | Tower | [36 empty] | Approved
4326 | 4326-AbuSayah_Village_North_PF_TASC_O | TASC | ZRQ-407-R | Zarqa |  | 32.0016 | 36.0468 | Zarqa | Tower | [36 empty] | Approved
3731 | 3731-Safeh_Salt_Sch_PF_EBand_TASC_O | TASC | BLQ-237-R | Balqa |  | 32.042 | 35.7117 | Balqa | Pole | [36 empty] | Approved
3790 | 3790-Hekmah_Company_Back_PF_O | TASC | BLQ-236-R | Balqa |  | 32.0532 | 35.7283 | Balqa | Tower | [36 empty] | Approved
3481 | 3481-Salt_Bayouda_West_PE_Fiber_TASC_O | TASC | BLQ-240-R | Balqa |  | 32.1488 | 35.7213 | Balqa | Tower | [36 empty] | Approved
1038 | 1038-Zawahrah_North_PF_TASC_O | TASC | ZRQ-403-R | Zarqa |  | 32.0713 | 36.0455 | Zarqa | Pole | [36 empty] | Approved
3728 | 3728-Salt_Fardous_Msq_PE_Fiber_TASC_O | TASC | BLQ-238-R | Balqa |  | 32.0334 | 35.7069 | Balqa | Pole | [36 empty] | Approved
3412 | 3412-Salt_Bayouda_East_PE_Fiber_TASC_O | TASC | BLQ-233-R | Balqa |  | 32.1299 | 35.7306 | Balqa | Tower | [36 empty] | Approved
3414 | 3414-Salt_Sehan_PF_TASC_O | TASC | BLQ-234-R | Balqa |  | 32.1398 | 35.7544 | Balqa | Tower | [36 empty] | Approved
1208 | 1208-Aqaba-FreeZoqaba-FreeZone-PB-Fiber-TASC | TASC | AQB-15-R | Aqaba | 897 | 29.5493 | 35.0206 | Aqaba | Tower | [36 empty] | Approved
4178 | 4178-Aqaba-Ind-North-PF-TASC-O | TASC | AQB-260-R | Aqaba |  | 29.5955 | 35.0633 | Aqaba | Pole | [36 empty] | Approved
1223 | 1223-Aqaba-Authority-Bldg-PD-Fiber-TASC-O | TASC | AQB-33-R | Aqaba |  | 29.5383 | 35.0139 | Aqaba | Pole | [36 empty] | Approved
1277 | 1277-Aqaba-Kuwait-St-PD-Fiber-TASC-O | TASC | AQB-171-R | Aqaba |  | 29.561 | 35.0094 | Aqaba | Pole | [36 empty] | Approved
1225 | 1225-10th-Ave-PC-Fiber-TASC | TASC | AQB-24-R | Aqaba | 907 | 29.5654 | 35.0062 | Aqaba | Pole | [36 empty] | Approved
1237 | 1237-Rimal-Aimal-Ave-PA-Fiber-TASC | TASC | AQB-51-R | Aqaba | 861 | 29.5566 | 35.0011 | Aqaba | Pole | [36 empty] | Approved
1264 | 1264-8th-Ave-PD-Fiber-TASC | TASC | AQB-156-R | Aqaba | 983 | 29.5574 | 35.0092 | Aqaba | Pole | [36 empty] | Approved
1273 | 1273-8th-Ave-Market-PD-Fiber-TASC-O | TASC | AQB-191-R | Aqaba |  | 29.5587 | 35.0114 | Aqaba | Pole | [36 empty] | Approved
1267 | 1267-6th-Ave-PD-Fiber-TASC | TASC | AQB-164-R | Aqaba | 977 | 29.5504 | 35.0121 | Aqaba | Pole | [36 empty] | Approved
1238 | 1238-Iskan-Mahdoud-PD-Fiber-TASC | TASC | AQB-52-R | Aqaba | 868 | 29.5507 | 35.0017 | Aqaba | Pole | [36 empty] | Approved
1276 | 1276-9th-Ave-Aqaba-2-PE-TASC-O | TASC | AQB-177-R | Aqaba |  | 29.549 | 35.0379 | Aqaba | Pole | [36 empty] | Approved
1201 | 1201-Aqaba-Petra-Hotel-PD-Zain-TASC | TASC | AQB-141-R | Aqaba | 955 | 29.5242 | 35.0105 | Aqaba | Tower | [36 empty] | Approved
1217 | 1217-Khazan-Aqaba-PE-TASC-O | TASC | AQB-127-R | Aqaba |  | 29.525 | 35.0171 | Aqaba | Pole | [36 empty] | Approved
1233 | 1233-Aqaba-Ind-PF-Fiber-TASC | TASC | AQB-123-R | Aqaba | 917 | 29.5556 | 35.0286 | Aqaba | Tower | [36 empty] | Approved
1212 | 1212-Dream-Mall-Aqaba-PC-Fiber-TASC | TASC | AQB-137-R | Aqaba | 945 | 29.5331 | 35.0068 | Aqaba | Pole | [36 empty] | Approved
1206 | 1206-North-Mahdoud-PE-Fiber-TASC-O | TASC | AQB-199-R | Aqaba |  | 29.553 | 35.0039 | Aqaba | Pole | [36 empty] | Approved
1286 | 1286-Aqaba-7th-Ave-PF-EBand-TASC-O | TASC | AQB-195-R | Aqaba |  | 29.5487 | 35.0235 | Aqaba | Pole | [36 empty] | Approved
1290 | 1290-Aqaba-Wihdat-East-PF-TASC-O | TASC | AQB-222-R | Aqaba |  | 29.535 | 35.0029 | Aqaba | Pole | [36 empty] | Approved
1249 | 1249-9th-Ave-South-PE-TASC-O | TASC | AQB-204-R | Aqaba |  | 29.5425 | 35.0267 | Aqaba | Pole | [36 empty] | Approved
1218 | 1218-Aqaba-5th-Ave-PF-TASC-O | TASC | AQB-245-R | Aqaba |  | 29.5409 | 35.0188 | Aqaba | Pole | [36 empty] | Approved
1252 | 1252-5th-Ave-Market-PF-TASC-O | TASC | AQB-212-R | Aqaba |  | 29.5351 | 35.0169 | Aqaba | Pole | [36 empty] | Approved
1250 | 1250-9th-Ave-Jameiat-PE-EBand-TASC-O | TASC | AQB-211-R | Aqaba |  | 29.5461 | 35.0348 | Aqaba | Pole | [36 empty] | Approved
1291 | 1291-3rd-Ave-Captain-PD-Fiber-TASC-O | TASC | AQB-203-R | Aqaba |  | 29.5506 | 35.0183 | Aqaba | Pole | [36 empty] | Approved
1289 | 1289-South-Mahdoud-PD-Fiber-TASC-O | TASC | AQB-200-R | Aqaba |  | 29.5482 | 35.0049 | Aqaba | Pole | [36 empty] | Approved
4135 | 4135-Shakriet-Rum-PC-Fiber-TASC | TASC | MAN-3-G | Aqaba | 835 | 29.6801 | 35.4562 | Aqaba | Tower | [36 empty] | Approved
1288 | 1288-10th-Ave-Market-PD-Fiber-TASC-O | TASC | AQB-197-R | Aqaba |  | 29.5627 | 35.0076 | Aqaba | Pole | [36 empty] | Approved
1259 | 1259-Aqaba-Stores-ADC-PF-TASC-O | TASC | AQB-188-G | Aqaba |  | 29.5514 | 35.0332 | Aqaba | Tower | [36 empty] | Approved
1254 | 1254-7th-Ave-PF-TASC-O | TASC | AQB-219-R | Aqaba |  | 29.5496 | 35.0253 | Aqaba | Tower | [36 empty] | Approved
1292 | 1292-3rd-Ave-CRL-PE-Fiber-TASC-O | TASC | AQB-202-R | Aqaba |  | 29.5476 | 35.0145 | Aqaba | Pole | [36 empty] | Approved
1246 | 1246-Aqaba-Old-Town-PE-EBand-TASC-O | TASC | AQB-207-R | Aqaba |  | 29.5214 | 35.0076 | Aqaba | Pole | [36 empty] | Approved
1216 | 1216-Shwaik-PD-EBand-TASC | TASC | AQB-27-R | Aqaba | 863 | 29.5299 | 35.0045 | Aqaba | Pole | [36 empty] | Approved
1296 | 1296-1st-Ave-North-PF-TASC-O | TASC | AQB-237-R | Aqaba |  | 29.5398 | 35.0002 | Aqaba | Pole | [36 empty] | Approved
1285 | 1285-Aqaba-King-Faisal-St-PE-Fiber-TASC-O | TASC | AQB-196-R | Aqaba |  | 29.5557 | 35.0187 | Aqaba | Pole | [36 empty] | Approved
4140 | 4140-Aqaba-Ent-PC-Fiber-TASC | TASC | AQB-1-G | Aqaba | 869 | 29.7293 | 35.0365 | Aqaba | Tower | [36 empty] | Approved
4148 | 4148-Qabos-City-Aqaba-PA-Fiber-Zain-TASC | TASC | AQB-53-G | Aqaba |  | 29.4335 | 34.9766 | Aqaba | Tower | [36 empty] | Approved
1231 | 1231-3rd-Ave-East-PE-Fiber-TASC-O | TASC | AQB-268-R | Aqaba |  | 29.5528 | 35.0189 | Aqaba | Pole | [36 empty] | Approved
1239 | 1239-9th-Ave-North-Aqaba-PF-TASC-O | TASC | AQB-264-R | Aqaba |  | 29.5537 | 35.0432 | Aqaba | Pole | [36 empty] | Approved
1281 | 1281-Aqaba-Islamic-Hospital-Back-PE-Fiber-TASC-O | TASC | AQB-265-R | Aqaba |  | 29.539 | 35.0059 | Aqaba | Pole | [36 empty] | Approved
1219 | 1219-Aqaba-Rawda-PE-Fiber-TASC-O | TASC | AQB-266-R | Aqaba |  | 29.5454 | 35.0181 | Aqaba | Pole | [36 empty] | Approved
1224 | 1224-10th-Ave-CTR-PE-Fiber-TASC-O | TASC | AQB-263-R | Aqaba |  | 29.5629 | 35.0034 | Aqaba | Pole | [36 empty] | Approved
1221 | 1221-Rimal-Ave-West-PE-Fiber-TASC-O | TASC | AQB-267-R | Aqaba |  | 29.5594 | 35.0006 | Aqaba | Pole | [36 empty] | Approved
1251 | 1251-Mahdoud-Aqsa-Sch-PE-Fiber-TASC-O | TASC | AQB-262-R | Aqaba |  | 29.5532 | 35 | Aqaba | Pole | [36 empty] | Approved
1242 | 1242-Shabieh-South-PE-Fiber-TASC-O | TASC | AQB-261-R | Aqaba |  | 29.5475 | 35.0008 | Aqaba | Pole | [36 empty] | Approved
4121 | 4121-Aqaba-Gate-PB-EBand-TASC | TASC | AQB-31-G | Aqaba | 885 | 29.5761 | 35.0608 | Aqaba | Tower | [36 empty] | Approved
1210 | 1210-Aqaba-Uni-College-PF-TASC-O | TASC | AQB-232-R | Aqaba |  | 29.5671 | 35.0219 | Aqaba | Pole | [36 empty] | Approved
4164 | 4164-Aqaba-Airport-PF-Fiber-TASC-O | TASC | AQB-221-R | Aqaba |  | 29.6089 | 35.0209 | Aqaba | Pole | [36 empty] | Approved
4114 | 4114-Passenger-Port-PE-TASC-O | TASC | AQB-25-R | Aqaba |  | 29.4602 | 34.9767 | Aqaba | Pole | [36 empty] | Approved
1269 | 1269-10th-Ave-East-PD-Fiber-TASC | TASC | AQB-167-R | Aqaba | 986 | 29.5636 | 35.0115 | Aqaba | Pole | [36 empty] | Approved
4137 | 4137-Rum-Rest-PD-Fiber-Zain-TASC | TASC | MAN-14-G | Aqaba | 834 | 29.5734 | 35.4239 | Aqaba | Tower | [36 empty] | Approved
4108 | 4108-Aqaba-Airport-Rd-MGS-PF-TASC-O | TASC | AQB-190-R | Aqaba |  | 29.6003 | 35.028 | Aqaba | Pole | [36 empty] | Approved
1274 | 1274-1st-Ave-Aqaba-PF-TASC-O | TASC | AQB-178-R | Aqaba |  | 29.5357 | 34.9987 | Aqaba | Pole | [36 empty] | Approved
1248 | 1248-10th-Ave-2-PD-Fiber-TASC-O | TASC | AQB-210-R | Aqaba |  | 29.5634 | 35.0137 | Aqaba | Pole | [36 empty] | Approved
4128 | 4128-Dissie-Railway-PC-Fiber-Zain-TASC-O | TASC | MAN-127-G | Aqaba |  | 29.6562 | 35.5129 | Aqaba | Tower | [36 empty] | Approved
4158 | 4158-Twaiseh-Dissie-PF-TASC-O | TASC | AQB-228-G | Aqaba |  | 29.6532 | 35.5451 | Aqaba | Tower | [36 empty] | Approved
4122 | 4122-Container-Port-Rd-PF-Zain-TASC | TASC | AQB-55-G | Aqaba | 960 | 29.4694 | 35.0127 | Aqaba | Tower | [36 empty] | Approved
1275 | 1275-Aqaba-3rd-Ave-PD-Fiber-TASC-O | TASC | AQB-201-R | Aqaba |  | 29.5506 | 35.0157 | Aqaba | Pole | [36 empty] | Approved
4151 | 4151-Salhiet-Rum-PD-Zain-TASC-O | TASC | MAN-89-G | Aqaba |  | 29.701 | 35.3767 | Aqaba | Tower | [36 empty] | Approved
4136 | 4136-Rum-PC-Fiber-TASC | TASC | MAN-6-G | Aqaba | 833 | 29.7182 | 35.2944 | Aqaba | Tower | [36 empty] | Approved
4103 | 4103-Durra-Aqaba-PA-Fiber-TASC | TASC | AQB-158-G | Aqaba |  | 29.3816 | 34.9664 | Aqaba | Tower | [36 empty] | Approved
1278 | 1278-Aqaba-West-Mahdoud-PE-Fiber-TASC-O | TASC | AQB-172-R | Aqaba |  | 29.55 | 34.9987 | Aqaba | Pole | [36 empty] | Approved
4112 | 4112-Police-Patrol-Aqaba-PC-Fiber-TASC | TASC | AQB-23-G | Aqaba | 860 | 29.4482 | 35.03 | Aqaba | Tower | [36 empty] | Approved
1229 | 1229-BSC-Aqaba-PA-Fiber-TASC | TASC | AQB-148-G | Aqaba | 968 | 29.5601 | 35.0317 | Aqaba | Tower | [36 empty] | Approved
1260 | 1260-Rimal-2-PE-Fiber-TASC-O | TASC | AQB-181-R | Aqaba |  | 29.56 | 35.0032 | Aqaba | Pole | [36 empty] | Approved
4138 | 4138-Dissie-PD-Fiber-TASC | TASC | MAN-18-G | Aqaba | 828 | 29.625 | 35.5676 | Aqaba | Tower | [36 empty] | Approved
1287 | 1287-Aqaba-Salah-Addin-PF-TASC-O | TASC | AQB-224-R | Aqaba |  | 29.5182 | 35.0059 | Aqaba | Pole | [36 empty] | Approved
4147 | 4147-Wadi-Youtum-Customs-PE-Zain-TASC | TASC | AQB-8-G | Aqaba | 857 | 29.5758 | 35.1643 | Aqaba | Tower | [36 empty] | Approved
4146 | 4146-Wadi-Youtum-Customs-2-PC-Fiber-TASC | TASC | AQB-7-G | Aqaba | 858 | 29.623 | 35.1922 | Aqaba | Tower | [36 empty] | Approved
4145 | 4145-Aqaba-Trucks-Rd-PF-TASC | TASC | AQB-5-G | Aqaba |  | 29.5019 | 35.0916 | Aqaba | Tower | [36 empty] | Approved
1268 | 1268-10th-Ave-West-PD-Fiber-TASC | TASC | AQB-162-R | Aqaba | 987 | 29.5632 | 34.9989 | Aqaba | Pole | [36 empty] | Approved
4104 | 4104-Wadi-Titn-PF-Zain-TASC-O | TASC | AQB-159-G | Aqaba |  | 29.535 | 35.1293 | Aqaba | Tower | [36 empty] | Approved
4143 | 4143-Trucks-Park-PE-Fiber-TASC | TASC | AQB-2-G | Aqaba | 895 | 29.6677 | 35.2238 | Aqaba | Tower | [36 empty] | Approved
4119 | 4119-Container-Port-PE-TASC | TASC | AQB-29-G | Aqaba | 878 | 29.4715 | 34.9782 | Aqaba | Tower | [36 empty] | Approved
4124 | 4124-Nadi-Ghous-Aqaba-PF-Org-TASC-O | TASC | AQB-273-G | Aqaba |  | 29.4013 | 34.9705 | Aqaba | Tower | [36 empty] | Approved
4179 | 4179-Aqaba-Ind-Yard-1-PF-TASC-O | TASC | AQB-271-G | Aqaba |  | 29.4539 | 35.0359 | Aqaba | Tower | [36 empty] | Approved
4126 | 4126-Aqaba-Port-HSG-PF-TASC-O | TASC | AQB-280-G | Aqaba |  | 29.4034 | 35.0133 | Aqaba | Tower | [36 empty] | Approved
4176 | 4176-Aqaba-New-Port-PF-TASC-O | TASC | AQB-281-G | Aqaba |  | 29.3618 | 34.9735 | Aqaba | Tower | [36 empty] | Approved
501 | 501-Zabda_Al_Kashef_PF_TASC_O | TASC | AMW-1077-R | Amman |  | 31.9537 | 35.757 | Amman | Tower | [36 empty] | Approved
813 | 813-Marj_Top_Karak_PE_Fiber_TASC_O | TASC | KRK-264-R | Karak |  | 31.1676 | 35.7078 | Karak | Pole | [36 empty] | Approved
3367 | 3367-Karak_Omarieh_Ent_PF_TASC_O | TASC | KRK-265-R | Karak |  | 31.0383 | 35.719 | Karak | Tower | [36 empty] | Approved
679 | 679-Sahab_Raqeem_North_PF_EBand_TASC_O | TASC | AMS-231-R | Amman |  | 31.8975 | 35.9888 | Amman | Tower | [36 empty] | Approved
3464 | 3464-Allan_CTR_PF_TASC_O | TASC | BLQ-245-R | Balqa |  | 32.1181 | 35.7444 | Balqa | Tower | [36 empty] | Approved
3332 | 3332-Mutah_Motors_Ave_PE_Fiber_TASC_O | TASC | KRK-266-R | Karak |  | 31.0944 | 35.7011 | Karak | Tower | [36 empty] | Approved
5328 | 5328-jawa_Bir_Waliden_Msq_PF_TASC_O | TASC | AMS-230-R | Amman |  | 31.856 | 35.9427 | Amman | Tower | [36 empty] | Approved
5736 | 5736-Madaba_Middle_PF_TASC_O | TASC | MAD-277-R | Madaba |  | 31.7258 | 35.7976 | Madaba | Tower | [36 empty] | Approved
3733 | 3733-Maghareeb_Salt_South_PF_TASC_O | TASC | BLQ-244-R | Balqa |  | 32.0336 | 35.6986 | Balqa | Tower | [36 empty] | Approved
765 | 765-Jafer_CTR_PF_TASC_O | TASC | MAN-188-R | Ma'an |  | 30.3191 | 36.178 | Ma'an | Tower | [36 empty] | Approved
3111 | 3111-Jabal_Faisal_West_PE_EBand_TASC_O | TASC | ZRQ-408-R | Zarqa |  | 32.0086 | 36.0023 | Zarqa | Tower | [36 empty] | Approved
4206 | 4206-Chechan_Msq_PE_Fiber_TASC_Relo_O | TASC | ZRQ-406-R | Zarqa |  | 32.0623 | 36.0874 | Zarqa | Pole | [36 empty] | Approved
4570 | 4570-Ain_AlBasha_Zahraa_Ave_PF_TASC_Relo_O | TASC | AMW-1088-R | Amman |  | 32.0529 | 35.8232 | Amman | Tower | [36 empty] | Approved
4597 | 4597-Ain_AlBasha_Zahra_North_PF_TASC_O | TASC | AMW-1091-R | Amman |  | 32.0573 | 35.8236 | Amman | Tower | [36 empty] | Approved
1448 | 1448-Jerash_Jabal_Akhdar_PE_Fiber_TASC_O | TASC | JRS-90-R | Jarash |  | 32.2879 | 35.9086 | Jarash | Tower | [36 empty] | Approved
5861 | 5861-Beir_Mazkour_Village_PF_TASC_O | TASC | AQB-285-R | Aqaba |  | 30.4386 | 35.2869 | Aqaba | Pole | [36 empty] | Approved
3837 | 3837-Jizah_Camp_Back_PE_EBand_TASC_O | TASC | AMS-237-R | Amman |  | 31.7132 | 35.9468 | Amman | Tower | [36 empty] | Approved
4331 | 4331-Zarqa_Qadesieh_East_PF_TASC_O | TASC | ZRQ-411-R | Zarqa |  | 32.0414 | 36.037 | Zarqa | Tower | [36 empty] | Approved
3123 | 3123-Jabal_Faisal_East_PF_TASC_O | TASC | ZRQ-419-R | Zarqa |  | 32.0129 | 36.0037 | Zarqa | Tower | [36 empty] | Approved
1042 | 1042-Wadi_Hajar_CTR_PE_TASC_O | TASC | ZRQ-425-R | Zarqa |  | 32.0389 | 36.0868 | Zarqa | Pole | [36 empty] | Approved
4559 | 4559-Ain_AlBasha_West_PF_TASC_O | TASC | BLQ-247-R | Balqa |  | 32.0646 | 35.8249 | Balqa | Tower | [36 empty] | Approved
3328 | 3328-Enjasah_karak_Back_PE_Fiber_TASC_O | TASC | KRK-271-R | Karak |  | 31.0972 | 35.6912 | Karak | Tower | [36 empty] | Approved
3124 | 3124-Hitteen_Camp_Mid_PE_TASC_O | TASC | AME-1043-R | Amman |  | 32.0078 | 36.0186 | Amman | Tower | [36 empty] | Approved
5897 | 5897-Ghor_Safi_North_East_PE_Fiber_TASC_O | TASC | KRK-270-R | Karak |  | 31.0381 | 35.4931 | Karak | Tower | [36 empty] | Approved
4588 | 4588-Talet_Alruz_PF_TASC_O | TASC | JRS-91-R | Jarash |  | 32.172 | 35.8672 | Jarash | Pole | [36 empty] | Approved
4329 | 4329-Jabal_Shamali_Farajeen_PF_TASC_O | TASC | ZRQ-423-R | Zarqa |  | 32.0257 | 36.0463 | Zarqa | Tower | [36 empty] | Approved
3729 | 3729-Salt_Sawada_Olya_PF_TASC_O | TASC | BLQ-249-R | Balqa |  | 32.0466 | 35.7034 | Balqa | Pole | [36 empty] | Approved
1931 | 1931-Saeed_Sch_Zarqa_PF_Fiber_TASC_O | TASC | ZRQ-422-R | Zarqa |  | 32.079 | 36.089 | Zarqa | Tower | [36 empty] | Approved
5332 | 5332-Jawa_Old_Msq_PF_TASC_O | TASC | AMS-249-R | Amman |  | 31.8593 | 35.9357 | Amman | Pole | [36 empty] | Approved
1402 | 1402-Jarash_Engineering_HSG_PE_Fiber_TASC_O | TASC | JRS-94-R | Jarash |  | 32.2995 | 35.8895 | Jarash | Pole | [36 empty] | Approved
5339 | 5339-Jwaideh_Jail_West_PF_TASC_O | TASC | AMS-251-R | Amman |  | 31.8938 | 35.9316 | Amman | Pole | [36 empty] | Approved
1327 | 1327-Megherat_Ave_2_PF_TASC_O | TASC | AME-1045-R | Amman |  | 31.961 | 36.0195 | Amman | Pole | [36 empty] | Approved
1329 | 1329-Harsha_Back_PF_TASC_O | TASC | AME-1046-R | Amman |  | 31.9409 | 35.9752 | Amman | Pole | [36 empty] | Approved
815 | 815-Um_Rasas_CTR_PF_TASC_O | TASC | KRK-274-R | Karak |  | 31.5011 | 35.9166 | Karak | Pole | [36 empty] | Approved
4556 | 4556-Baqaa_East_2_PE_Fiber_TASC_O | TASC | AMW-1051-R | Amman |  | 32.0724 | 35.8477 | Amman | tower | [36 empty] | Approved
1543 | 1543-Buhaira_DeadSea_PF_TASC_Relo_O | TASC | BLQ-248-R | Balqa |  | 31.808 | 35.6268 | Balqa | Tower | [36 empty] | Approved
5334 | 5334-Khraibet_Alsouq_West_PF_Fiber_TASC_O | TASC | AMS-252-R | Amman |  | 31.8689 | 35.9184 | Amman | Pole | [36 empty] | Approved
1426 | 1426-Aseem_Ajloun_PF_TASC_O | TASC | AJL-62-R | Ajloun |  | 32.4049 | 35.8122 | Ajloun | Tower | [36 empty] | Approved
3730 | 3730-Salt_Academy_PF_TASC_O | TASC | BLQ-250-R | Balqa |  | 32.0384 | 35.7378 | Balqa | Pole | [36 empty] | Approved
4641 | 4641-Habaka_End_PF_TASC_O | TASC | IRB-518-R | Irbid |  | 32.4691 | 35.8533 | Irbid | Tower | [36 empty] | Approved
5869 | 5869-Ghor_Mazraah_Hay_Jaish_North_PF_EBand_TASC_O | TASC | KRK-273-R | Karak |  | 31.2698 | 35.535 | Karak | Tower | [36 empty] | Approved
817 | 817-Falcon_Hotel_Karak_Back_PF_TASC_O | TASC | KRK-272-R | Karak |  | 31.1769 | 35.7069 | Karak | Pole | [36 empty] | Approved
3732 | 3732-Salt_Arda_Bridge_PF_EBand_TASC_O | TASC | BLQ-252-R | Balqa |  | 32.0655 | 35.7177 | Balqa | Tower | [36 empty] | Approved
3390 | 3390-Karak_UmGezlan_Top_PF_TASC_O | TASC | KRK-277-R | Karak |  | 31.034 | 35.6588 | Karak | Pole | [36 empty] | Approved
5318 | 5318-Jawa_Iskan_Eshk_PF_TASC_O | TASC | AMS-257-R | Amman |  | 31.8565 | 35.93 | Amman | Pole | [36 empty] | Approved
5713 | 5713-Naour_Arabic_Horse_Club_South_PF_Org_TASC_O | TASC | AMS-258-R | Amman |  | 31.8376 | 35.8577 | Amman | Tower | [36 empty] | Approved
3734 | 3734-Yarqa_North_Ave_PF_TASC_O | TASC | BLQ-254-R | Balqa | 1 | 32.0104 | 35.7091 | Balqa | Tower | [36 empty] | Approved
683 | 683-Sahab_Abdalieh_West_PF_TASC_O | TASC | AMS-266-R | Amman |  | 31.8857 | 35.9939 | Amman | Tower | [36 empty] | Approved
4788 | 4788-Mughayar_Al_Sarhan_PC_Fiber_TASC_Relo | TASC | MFQ-240-G | Mafraq |  | 32.4643 | 36.2001 | Mafraq | Tower | [36 empty] | Approved
1562 | 1562-Areed_PF_TASC_O | TASC | MAD-281-R | Madaba |  | 31.5471 | 35.6343 | Madaba | Pole | [36 empty] | Approved
5319 | 5319-Jwaideh_East_PF_TASC_O | TASC | AMS-267-R | Amman |  | 31.8741 | 35.9266 | Amman | Tower | [36 empty] | Approved
4565 | 4565-Ain_AlBasha_Tatweer_South_PF_TASC_O | TASC | AMW-1115-R | Amman |  | 32.0552 | 35.8169 | Amman | Pole | [36 empty] | Approved
3843 | 3843-Yadoudeh_East_PF_TASC_O | TASC | AMS-268-R | Amman |  | 31.8231 | 35.9462 | Amman | Tower | [36 empty] | Approved
4132 | 4132-Qweirah_CTR_PF_Fiber_TASC_O | TASC | MAN-191-R | Ma'an |  | 29.7999 | 35.31 | Ma'an | Pole | [36 empty] | Approved
4561 | 4561-Salt_Salouf_Middle_PF_TASC_O | TASC | BLQ-256-R | Balqa |  | 32.0731 | 35.7582 | Balqa | Tower | [36 empty] | Approved
5795 | 5795-Mamounieh_Ayla_Factory_North_PF_TASC_O | TASC | MAD-284-R | Madaba |  | 31.7432 | 35.8175 | Madaba | Tower | [36 empty] | Approved
4564 | 4564-Ain_AlBasha_North_PF_TASC_O | TASC | AMW-1104-R | Amman |  | 32.0633 | 35.833 | Amman | Tower | [36 empty] | Approved
861 | 861-Hwiyah_Karak_PF_Fiber_TASC_O | TASC | KRK-278-R | Karak |  | 31.1476 | 35.6988 | Karak | Pole | [36 empty] | Approved
4521 | 4521-Jordan_St_5_PF_TASC_Relo_O | TASC | AMW-1113-R | Amman |  | 32.0874 | 35.8932 | Amman | Tower | [36 empty] | Approved
1933 | 1933-Jabal_Mughayer_West_PE_Fiber_TASC_O | TASC | ZRQ-431-R | Zarqa | 990 | 32.0947 | 36.0765 | Zarqa | Tower | [36 empty] | Approved
5794 | 5794-Mamounieh_CTR_PF_TASC_O | TASC | MAD-283-R | Madaba |  | 31.7406 | 35.7998 | Madaba | Tower | [36 empty] | Approved
1427 | 1427-Sakib_South_Ave_PB_Fiber_TASC_O | TASC | JRS-96-R | Jarash |  | 32.2615 | 35.8143 | Jarash | Tower | [36 empty] | Approved
1471 | 1471-Sakib_Main_Ent_PE_TASC_O | TASC | JRS-97-R | Jarash |  | 32.263 | 35.8086 | Jarash | Tower | [36 empty] | Approved
862 | 862-Sarfa_Middle_Karak_Rd_PF_TASC_O | TASC | KRK-279-R | Karak |  | 31.3418 | 35.6669 | Karak | Pole | [36 empty] | Approved
833 | 833-Mughayer_Karak_PF_TASC_O | TASC | KRK-281-R | Karak |  | 31.406 | 35.7709 | Karak | Tower | [36 empty] | Approved
2818 | 2818-Delail_Mabroukeh_West_PE_TASC_O | TASC | ZRQ-433-R | Zarqa |  | 32.1611 | 36.2756 | Zarqa | Tower | [36 empty] | Approved
3424 | 3424-Allan_West_Salt_PF_TASC_O | TASC | BLQ-258-R | Balqa |  | 32.1175 | 35.7331 | Balqa | Pole | [36 empty] | Approved
1452 | 1452-Khadra_Jarash_PF_EBand_TASC_O | TASC | JRS-100-R | Jarash |  | 32.2724 | 35.9063 | Jarash | Pole | [36 empty] | Approved
4691 | 4691-Beit_Idis_Top_PF_EBand_TASC_O | TASC | IRB-535-R | Irbid |  | 32.436 | 35.698 | Irbid | Tower | [36 empty] | Approved
2806 | 2806-Delail_Tawhid_Msq_PF_EBand_TASC_O | TASC | ZRQ-437-R | Zarqa |  | 32.1361 | 36.2615 | Zarqa | Pole | [36 empty] | Approved
3438 | 3438-Aghwar_AbuZeeghan_Top_PF_EBand_TASC_O | TASC | BLQ-260-R | Balqa |  | 32.2076 | 35.6444 | Balqa | Tower | [36 empty] | Approved
1488 | 1488-Kettah_Jarash_PF_EBand_TASC_O | TASC | JRS-101-R | Jarash |  | 32.2727 | 35.8525 | Jarash | Tower | [36 empty] | Approved
1537 | 1537-Madaba_South_Ent_PF_EBand_TASC_O | TASC | MAD-286-R | Madaba |  | 31.7016 | 35.793 | Madaba | Tower | [36 empty] | Approved
3825 | 3825-Madaba_Dleilet_AlHamaideh_PF_TASC_O | TASC | MAD-288-R | Madaba |  | 31.6408 | 35.829 | Madaba | Tower | [36 empty] | Approved
2903 | 2903-Sareeh_Howara_East_PF_TASC_O | TASC | IRB-538-R | Irbid |  | 32.5135 | 35.905 | Irbid | Tower | [36 empty] | Approved
706 | 706-Jafer_North_PF_EBand_TASC_O | TASC | MAN-208-R | Ma'an |  | 30.32 | 36.1702 | Ma'an | Tower | [36 empty] | Approved
5734 | 5734-Naour_Rujum_Sawaeer_West_PF_EBand_TASC_O | TASC | AMS-282-R | Amman |  | 31.8661 | 35.8 | Amman | Pole | [36 empty] | Approved
3304 | 3304-That_Ras_East_Karak_PF_TASC_O | TASC | KRK-286-R | Karak |  | 30.9917 | 35.7773 | Karak | Tower | [36 empty] | Approved
684 | 684-AbuAlanda_Mustanada_PE_EBand_TASC_O | TASC | AME-1073-R | Amman |  | 31.907 | 35.9894 | Amman | Tower | [36 empty] | Approved
1428 | 1428-Jabal_Sheikh_Musleh_Jarash_PF_TASC_O | TASC | JRS-99-R | Jarash |  | 32.2822 | 35.9068 | Jarash | Tower | [36 empty] | Approved
4693 | 4693-Samad_End_PF_TASC_O | TASC | IRB-548-R | Irbid |  | 32.4603 | 35.8332 | Irbid | Pole | [36 empty] | Approved
4578 | 4578-Ain_Al_Basha_Agriculture_Ave_PF_EBand_TASC_O | TASC | AMW-1121-R | Amman |  | 32.0753 | 35.8308 | Amman | Tower | [36 empty] | Approved
2982 | 2982-Ramtha_Rd_Saeed_Mall_PF_Fiber_TASC_O | TASC | IRB-546-R | Irbid |  | 32.5256 | 35.9996 | Irbid | Pole | [36 empty] | Approved
1462 | 1462-Talet_Jarash_PF_TASC_O | TASC | JRS-102-R | Jarash |  | 32.2409 | 35.8796 | Jarash | Pole | [36 empty] | Approved
1409 | 1409-Kufranjeh_PE_EBand_TASC_O | TASC | AJL-63-R | Ajloun |  | 32.2911 | 35.6902 | Ajloun | Tower | [36 empty] | Approved
5739 | 5739-Madaba_Grena_West_PE_Fiber_TASC_O | TASC | MAD-287-R | Madaba |  | 31.7601 | 35.7951 | Madaba | Pole | [36 empty] | Approved
5834 | 5834-Ghor_Safi_South_PF_EBand_TASC_O | TASC | KRK-282-R | Karak |  | 31.0333 | 35.4817 | Karak | Pole | [36 empty] | Approved
735 | 735-Taybeh_Maan_South_PF_EBand_TASC_O | TASC | MAN-203-R | Ma'an |  | 30.2416 | 35.4684 | Ma'an | Pole | [36 empty] | Approved
5347 | 5347-Jawa_Alwafa_Ave_PF_TASC_O | TASC | AMS-288-R | Amman |  | 31.8491 | 35.9464 | Amman | Tower | [36 empty] | Approved
5797 | 5797-Madaba_Rawda_West_Ave_PE_TASC_O | TASC | MAD-290-R | Madaba |  | 31.8423 | 35.8179 | Madaba | Pole | [36 empty] | Approved
727 | 727-Maan_Uni_RD_PF_TASC_O | TASC | MAN-207-R | Ma'an |  | 30.2203 | 35.7135 | Ma'an | Tower | [36 empty] | Approved
766 | 766-Wadi_Moussa_North_PF_Fiber_TASC_O | TASC | MAN-205-R | Ma'an |  | 30.3301 | 35.4812 | Ma'an | Tower | [36 empty] | Approved
1163 | 1163-Salhya_Mafraq_Top_PF_TASC_O | TASC | MFQ-251-R | Mafraq |  | 32.2573 | 36.4792 | Mafraq | Tower | [36 empty] | Approved
4735 | 4735-Manshiet_Bani_Hassan_South_PF_EBand_TASC_O | TASC | MFQ-253-R | Mafraq |  | 32.3659 | 36.1939 | Mafraq | Tower | [36 empty] | Approved
3108 | 3108-Yajouz_Rasheed_Ave_Noura_Msq_PF_Fiber_TASC_O | TASC | ZRQ-441-R | Zarqa |  | 32.0196 | 36.0088 | Zarqa | Tower | [36 empty] | Approved
4793 | 4793-Mafraq_King_Abdullah_Ave_South_PF_EBand_TASC_O | TASC | MFQ-252-R | Mafraq |  | 32.3118 | 36.2106 | Mafraq | Tower | [36 empty] | Approved
688 | 688-Sahab_Princess_Eman_PF_TASC_O | TASC | AMS-289-R | Amman |  | 31.8413 | 35.9846 | Amman | Pole | [36 empty] | Approved
1342 | 1342-Marka_Hizam_Ibn_Zaydoon_Sch_PF_EBand_TASC_O | TASC | AME-1078-R | Amman |  | 31.9665 | 35.9861 | Amman | Tower | [36 empty] | Approved
685 | 685-Dhaibeh_Eastern_Mid_PF_TASC_O | TASC | AMS-292-R | Amman |  | 31.8067 | 36.0503 | Amman | Tower | [36 empty] | Approved
4582 | 4582-Berin_Khelleh_PF_TASC_O | TASC | ZRQ-443-R | Zarqa |  | 32.1261 | 35.9872 | Zarqa | Tower | [36 empty] | Approved
687 | 687-Um_Botmah_West_PF_EBand_TASC_O | TASC | AMS-291-R | Amman |  | 31.8211 | 36.066 | Amman | Tower | [36 empty] | Approved
1464 | 1464-Hameed_Jarash_PF_TASC_O | TASC | JRS-104-R | Jarash |  | 32.2579 | 36.0034 | Jarash | Pole | [36 empty] | Approved
4698 | 4698-Mazar_Shamali_Dier_Yousef_PF_EBand_TASC_O | TASC | IRB-553-R | Irbid |  | 32.4863 | 35.8068 | Irbid | Pole | [36 empty] | Approved
1593 | 1593-Fayhaa_Madaba_North_PF_TASC_O | TASC | MAD-291-R | Madaba |  | 31.7183 | 35.7421 | Madaba | Tower | [36 empty] | Approved
790 | 790-Ohaida_Maan_PF_TASC_O | TASC | MAN-213-R | Ma'an |  | 30.1399 | 35.5716 | Ma'an | Pole | [36 empty] | Approved
4576 | 4576-Sarrout_South_PF_TASC_O | TASC | ZRQ-444-R | Zarqa |  | 32.1342 | 35.9454 | Zarqa | Pole | [36 empty] | Approved
834 | 834-Fagoue_Zahra_Karak_PF_TASC_Relo_O | TASC | KRK-287-R | Karak |  | 31.3622 | 35.6824 | Karak | Tower | [36 empty] | Approved
4699 | 4699-Kufer_Rakeb_North_PF_TASC_O | TASC | IRB-552-R | Irbid |  | 32.4589 | 35.6816 | Irbid | Tower | [36 empty] | Approved
4187 | 4187-10th-Ave-North-PF-EBand-TASC-O | TASC | AQB-294-R | Aqaba |  | 29.5654 | 35.0017 | Aqaba | Pole | [36 empty] | Approved
4159 | 4159-9th-Ave-East-PF-EBand-TASC-O | TASC | AQB-292-R | Aqaba |  | 29.5462 | 35.0394 | Aqaba | Pole | [36 empty] | Approved
4180 | 4180-9th-Ave-Middle-PF-EBand-TASC-O | TASC | AQB-293-R | Aqaba |  | 29.5483 | 35.0349 | Aqaba | Pole | [36 empty] | Approved
1469 | 1469-Ajloun_Wadi_Rajeb_PF_TASC_O | TASC | AJL-64-R | Ajloun |  | 32.2486 | 35.6691 | Ajloun | Tower | [36 empty] | Approved
4199 | 4199-Aqaba-9th-Ave-Ahali-PF-EBand-TASC-O | TASC | AQB-300-R | Aqaba |  | 29.5433 | 35.0316 | Aqaba | Pole | [36 empty] | Approved
4710 | 4710-Mafraq_Tayeb_Esim_West_PF_EBand_TASC_O | TASC | MFQ-254-R | Mafraq |  | 32.3626 | 36.1493 | Mafraq | Pole | [36 empty] | Approved
4185 | 4185-5th-Ave-CTR-PF-Fiber-TASC-O | TASC | AQB-296-R | Aqaba |  | 29.5308 | 35.0122 | Aqaba | Pole | [36 empty] | Approved
4169 | 4169-6th-Ave-West-PF-Fiber-TASC-O | TASC | AQB-298-R | Aqaba |  | 29.5512 | 35.0098 | Aqaba | Pole | [36 empty] | Approved
1018 | 1018-Princess_Haya_Ave_West_PF_TASC_O | TASC | ZRQ-440-R | Zarqa |  | 32.0722 | 36.032 | Zarqa | Tower | [36 empty] | Approved
4189 | 4189-3rd-Ave-North-PF-Fiber-TASC-O | TASC | AQB-301-R | Aqaba |  | 29.5533 | 35.0163 | Aqaba | Pole | [36 empty] | Approved
4188 | 4188-10th-Ave-Farouq-PF-Fiber-TASC-O | TASC | AQB-297-R | Aqaba |  | 29.5657 | 35.0104 | Aqaba | Pole | [36 empty] | Approved
4186 | 4186-8th-Ave-CTR-PF-Fiber-TASC-O | TASC | AQB-299-R | Aqaba |  | 29.5564 | 35.0125 | Aqaba | Pole | [36 empty] | Approved
5759 | 5759-Naour_Farouq_Msq_PF_TASC_O | TASC | AMS-294-R | Amman |  | 31.8526 | 35.8123 | Amman | Tower | [36 empty] | Approved
728 | 728-Hussainiah_CTR_PE_Fiber_TASC_O | TASC | MAN-210-G | Ma'an |  | 30.5936 | 35.7985 | Ma'an | Tower | [36 empty] | Approved
3447 | 3447-Deir_Alla_Om_Hammad_Ave_PF_TASC_O | TASC | BLQ-262-R | Balqa |  | 32.139 | 35.5744 | Balqa | Tower | [36 empty] | Approved
3132 | 3132-Jreiba_Shafa_Badran_PF_TASC_O | TASC | ZRQ-445-R | Zarqa |  | 32.0567 | 35.9695 | Zarqa | Tower | [36 empty] | Approved
850 | 850-Mseitbeh_South_PF_TASC_O | TASC | AMS-295-R | Amman |  | 31.4872 | 35.9768 | Amman | Tower | [36 empty] | Approved
4569 | 4569-Kamsheh_West_PF_TASC_O | TASC | AMW-1137-R | Amman |  | 32.1238 | 35.8843 | Amman | Pole | [36 empty] | Approved
3773 | 3773-Amman_Ahlieh_Uni_Gate_PA_Fiber_TASC_Relo | TASC | AMW-1131-R | Amman |  | 32.0432 | 35.7782 | Amman | Pole | [36 empty] | Approved
3852 | 3852-Najdieh_Muwaqqar_PF_TASC_O | TASC | AMS-293-G | Amman |  | 31.735079 | 36.0742 | Amman | Tower | [36 empty] | Approved
729 | 729-Maan_Desert_Rd_PF_TASC_O | TASC | MAN-206-G | Ma'an |  | 30.2272 | 35.7386 | Ma'an | Tower | [36 empty] | Approved
691 | 691-Muwaqqar_East_Dabobi_Msq_PF_TASC_O | TASC | AMS-296-R | Amman |  | 31.8067 | 36.1184 | Amman | Tower | [36 empty] | Approved
4177 | 4177-Aqaba-Techno-Uni-PF-EBand-TASC-O | TASC | AQB-288-R | Aqaba |  | 29.438 | 35.0124 | Aqaba | Pole | [36 empty] | Approved
4196 | 4196-Dissie-CTR-PF-EBand-TASC-O | TASC | MAN-212-R | Ma'an |  | 29.6521 | 35.5116 | Ma'an | Pole | [36 empty] | Approved
2928 | 2928-Ramtha_Dabbeh_Nemer_PE_TASC | TASC | IRB-561-R | Irbid |  | 32.5662 | 36.0008 | Irbid | Tower | [36 empty] | Approved
3863 | 3863-Rabiet_Mohareb_O | TASC | AME-1080-G | Amman |  | 31.6765 | 36.2125 | Amman | Tower | [36 empty] | Approved
4725 | 4725-Balaama_CTR_PE_TASC_O | TASC | MFQ-81-R | Mafraq |  | 32.2366 | 36.0828 | Mafraq | Tower | [36 empty] | Approved
4599 | 4599-Halawa_2_PB | TASC | AJL-23-R | Ajloun |  | 32.3874 | 35.6519 | Ajloun | Tower | [36 empty] | Approved
3299 | 3299-King_hussein_Mosque_WMX | TASC | AMW-557-R | Amman | 1522 | 31.9911 | 35.8168 | Amman | Pole | [36 empty] | Approved
1099 | 1099-BSC_Dwaik_MADA_PD | TASC | ZRQ-320-G | Zarqa |  | 32.0399 | 36.0665 | Zarqa | Tower | [36 empty] | Approved
4499 | 4499-BSC_Mada_Abu_Ali_PD | TASC | IRB-496-R | Irbid |  | 32.5559 | 35.8507 | Irbid | Tower | [36 empty] | Approved
1271 | 1271-8th-Ave-East-PE-Org-BTS-O | TASC | AQB-173-R | Aqaba |  | 29.557 | 35.015 | Aqaba | Pole | [36 empty] | Approved
2823 | 2823-AbuZeeghan_South_Zarqa_PF_BTS_O | TASC | ZRQ-442-R | Zarqa |  | 32.108 | 36.0564 | Zarqa | Tower | [36 empty] | Approved
4583 | 4583-Baqaa_South_East_Ave_PF_EBand_BTS_O | TASC | BLQ-265-R | Balqa |  | 32.065601 | 35.8439 | Balqa | Tower | [36 empty] | Approved
768 | 768-Maan_Agriculture_Back_PF_BTS_O | TASC | MAN-217-R | Ma'an |  | 30.1875 | 35.7097 | Ma'an | Tower | [36 empty] | Approved
3791 | 3791-Dogara_East_PF_BTS_O | TASC | IRB-558-R | Irbid |  | 32.5953 | 35.7531 | Irbid | Tower | [36 empty] | Approved
4696 | 4696-Kufer_Awan_North_PF_EBand_BTS_O | TASC | IRB-551-R | Irbid |  | 32.4343 | 35.682 | Irbid | Tower | [36 empty] | Approved
1343 | 1343-Marka_Hizam_Rd_Tile_Ind_PF_EBand_BTS_O | TASC | AME-1084-R | Amman |  | 31.9651 | 35.9923 | Amman | Tower | [36 empty] | Approved
692 | 692-Sakan_Kareem_Hizam_East_PF_BTS_O | TASC | AME-1088-R | Amman |  | 31.9212 | 36.0155 | Amman | Tower | [36 empty] | Approved
3880 | 3880-Howara_Madaba_PF_BTS_O | TASC | MAD-292-R | Madaba |  | 31.6929 | 35.8466 | Madaba | Tower | [36 empty] | Approved
3311 | 3311-Amreyeh_Village_PF_BTS_O | TASC | KRK-289-G | Karak |  | 31.6217 | 36.0429 | Karak | Tower | [36 empty] | Approved
690 | 690-Dhaibeh_North_PF_BTS_O | TASC | AMS-300-R | Amman |  | 31.8031 | 36.0208 | Amman | Tower | [36 empty] | Approved
5709 | 5709-Naour_Um_Asaker_PF_BTS_O | TASC | AMS-299-R | Amman |  | 31.8446 | 35.8645 | Amman | Tower | [36 empty] | Approved
3148 | 3148-Hitteen_Camp_Zaid_Bin_Haritha_Msq_PF_BTS_O | TASC | AME-1086-R | Amman |  | 32.0089 | 36.0147 | Amman | Tower | [36 empty] | Approved
767 | 767-Wadi_Moussa_West_PE_O | TASC | MAN-216-R | Ma'an |  | 30.3175 | 35.4739 | Ma'an | Tower | [36 empty] | Approved
5899 | 5899-Ain_Albaida_CTR_PE_O | TASC | TAF-57-R | Tafila |  | 30.7857 | 35.5973 | Tafila | Tower | [36 empty] | Approved
3883 | 3883-Arainbeh_CTR_O | TASC | MAD-296-R | Madaba |  | 31.6442 | 35.9376 | Madaba | Tower | [36 empty] | Approved
2897 | 2897-Mafraq_Sara_Hospital_PE_O | TASC | MFQ-259-R | Mafraq |  | 32.3514 | 36.181 | Mafraq | Tower | [36 empty] | Approved
3865 | 3865-Andalusieh_West_PE | TASC | MAD-298-R | Madaba |  | 31.7621 | 35.8792 | Madaba | Tower | [36 empty] | Approved
2892 | 2892-Ain_Balama_Re_PF_O | TASC | MFQ-258-R | Mafraq |  | 32.2719 | 36.0552 | Mafraq | Tower | [36 empty] | Approved
1346 | 1346-Salhiet_Abed_Iskan_Fardous_PF_O | TASC | AME-1103-R | Amman |  | 31.9489 | 36.0052 | Amman | Tower | [36 empty] | Approved
6032 | 6032-Mafraq_Jundi_Ave_PF_O | TASC | MFQ-262-R | Mafraq |  | 32.3623 | 36.1976 | Mafraq | Tower | [36 empty] | Approved
4585 | 4585-Abu_Algeen_Irbid_PF_O | TASC | IRB-565-R | Irbid |  | 32.4761 | 35.6721 | Irbid | Tower | [36 empty] | Approved
6204 | 6204-Tafilah_Mjadel_PF_O | TASC | TAF-59-R | Tafila |  | 30.863 | 35.6551 | Tafila | Tower | [36 empty] | Approved
617 | 617-Sahab_Rujm_Shami_East_PF_O | TASC | AMS-320-R | Amman |  | 31.8341 | 36.0111 | Amman | Tower | [36 empty] | Approved
4586 | 4586-Kamsheh_South_PF_O | TASC | AMW-1156-R | Amman |  | 32.1056 | 35.9126 | Amman | Pole | [36 empty] | Approved
6103 | 6103-Salt_Qaseem_Jreish_PF_O | TASC | BLQ-268-R | Balqa |  | 32.1638 | 35.7536 | Balqa | Tower | [36 empty] | Approved
3149 | 3149-Marka_Mugherat_Ave_PF_O | TASC | AME-1099-R | Amman |  | 31.9707 | 36.0215 | Amman | Tower | [36 empty] | Approved
6002 | 6002-Jerash_Jabal_Akhdar_North_PF_O | TASC | JRS-106-R | Jarash |  | 32.2936 | 35.9086 | Jarash | Tower | [36 empty] | Approved
1340 | 1340-Mugherat_Ave_West_PF_O | TASC | AME-1100-R | Amman |  | 31.9571 | 36.013 | Amman | Tower | [36 empty] | Approved
2825 | 2825-Dogara_Hashmieh_South_PF_O | TASC | ZRQ-448-R | Zarqa |  | 32.1294 | 36.0501 | Zarqa | Tower | [36 empty] | Approved
1348 | 1348-Hizam_Orouba_District_PE_O | TASC | AME-1114-R | Amman |  | 31.9252 | 35.9793 | Amman | Tower | [36 empty] | Approved
1577 | 1577-Madaba_Faisalieh_PF_O | TASC | MAD-300-R | Madaba |  | 31.7383 | 35.77 | Madaba | Tower | [36 empty] | Approved
695 | 695-Baida_Sahab_Big_Msq_PF_O | TASC | AMS-319-R | Amman |  | 31.9156 | 36.053 | Amman | Tower | [36 empty] | Approved
6073 | 6073-Mafraq_Mkaifteh_West_PF_O | TASC | MFQ-263-R | Mafraq |  | 32.2866 | 36.6571 | Mafraq | Tower | [36 empty] | Approved
6031 | 6031-Hamra_Mafraq_West_PF_O | TASC | MFQ-261-R | Mafraq |  | 32.4408 | 36.1608 | Mafraq | Tower | [36 empty] | Approved
1520 | 1520-New_Shouneh_North_PF_O | TASC | BLQ-270-R | Balqa |  | 31.9149 | 35.6174 | Balqa | Tower | [36 empty] | Approved
6001 | 6001-Alwahadneh_Junction_PF_O | TASC | AJL-66-R | Ajloun |  | 32.3293 | 35.6815 | Ajloun | Tower | [36 empty] | Approved
6102 | 6102-Wadi_AlYabes_North_PF_O | TASC | IRB-568-R | Irbid |  | 32.4096 | 35.5919 | Irbid | Tower | [36 empty] | Approved
6045 | 6045-Berin_Rujm_Shook_PF_O | TASC | ZRQ-447-R | Zarqa |  | 32.0769 | 35.9547 | Zarqa | Tower | [36 empty] | Approved
2898 | 2898-Znayya_South_PF_O | TASC | ZRQ-450-R | Zarqa |  | 32.1924 | 36.1109 | Zarqa | Tower | [36 empty] | Approved
5363 | 5363-Bayer_Ave_PF_O | TASC | AMS-316-R | Amman |  | 31.8804 | 35.9437 | Amman | Tower | [36 empty] | Approved
599 | 599-Bassah_Zabda_Bader_PF_O | TASC | AMW-1159-R | Amman |  | 31.9432 | 35.7709 | Amman | Tower | [36 empty] | Approved
6202 | 6202-Tafilah_Sweimeh_PF_O | TASC | TAF-60-R | Tafila |  | 30.8362 | 35.6566 | Tafila | Tower | [36 empty] | Approved
696 | 696-Afeef_Kataneh_Sahab_PF_O | TASC | AME-1107-R | Amman |  | 31.8427 | 36.0648 | Amman | Tower | [36 empty] | Approved
3142 | 3142-Marka_Kitar_Valley_PF | TASC | AME-1111-R | Amman |  | 31.9751 | 36.0368 | Amman | Pole | [36 empty] | Approved
5367 | 5367-Jwaideh_Abu_Bakr_Msq_PE_O | TASC | AMS-321-R | Amman |  | 31.8826 | 35.9182 | Amman | Tower | [36 empty] | Approved
1349 | 1349-Um_Nowarah_Aden_Circle_PF_O | TASC | AME-1096-R | Amman |  | 31.9392 | 35.9771 | Amman | Tower | [36 empty] | Approved
3794 | 3794-Um_Jozeh_South_PF_O | TASC | BLQ-271-R | Balqa |  | 32.0909 | 35.747 | Balqa | Tower | [36 empty] | Approved
697 | 697-Sahab_Khawla_Bint_Azwar_Sch_PE_O | TASC | AMS-322-R | Amman |  | 31.8715 | 36.0122 | Amman | Pole | [36 empty] | Approved
1193 | 1193-Salhieh_Zamlet_Amir_Ghazi_PF_O | TASC | MFQ-266-R | Mafraq |  | 32.242 | 36.5269 | Mafraq | Tower | [36 empty] | Approved
4328 | 4328-Zarqa_Jabal_Shamali_North_O | TASC | ZRQ-449-R | Zarqa |  | 32.0338 | 36.0413 | Zarqa | Tower | [36 empty] | Approved
6033 | 6033-AlAlBait_Ave_PF_O | TASC | MFQ-264-R | Mafraq |  | 32.3194 | 36.2367 | Mafraq | Tower | [36 empty] | Approved
6034 | 6034-Rabaa_Sarhan_North_PF_O | TASC | MFQ-265-G | Mafraq |  | 32.4378 | 36.2239 | Mafraq | Tower | [36 empty] | Approved
3326 | 3326-Karak_Mazar_South_Entrance_PF_O | TASC | KRK-291-R | Karak |  | 31.0562 | 35.7013 | Karak | Tower | [36 empty] | Approved
2986 | 2986-Ramtha_Stadium_Back_PF_O | TASC | IRB-562-R | Irbid |  | 32.5424 | 36.0093 | Irbid | Tower | [36 empty] | Approved
6082 | 6082-Jawasereh_East_PF_O | TASC | MAD-303-R | Madaba |  | 31.866 | 35.6473 | Madaba | Tower | [36 empty] | Approved
4584 | 4584-Baqaa_Mid_PE_O | TASC | BLQ-272-R | Balqa |  | 32.0756 | 35.8495 | Balqa | Tower | [36 empty] | Approved
4577 | 4577-Burma_Jarash_CTR_PF_O | TASC | JRS-107-R | Jarash |  | 32.2184 | 35.7809 | Jarash | Pole | [36 empty] | Approved
698 | 698-Sahab_Mercedes_Bridge_PF_O | TASC | AMS-326-R | Amman |  | 31.8942 | 35.9728 | Amman | Tower | [36 empty] | Approved
4336 | 4336-Zarqa_Tatweer_O | TASC | ZRQ-451-R | Zarqa |  | 32.0399 | 36.0493 | Zarqa | Tower | [36 empty] | Approved
1039 | 1039-Falah_Av_Zarqa_PF_O | TASC | ZRQ-452-R | Zarqa |  | 31.9347 | 35.9183 | Zarqa | Pole | [36 empty] | Approved
6077 | 6077-Mafraq_Um_Quttein_West_PF_O | TASC | MFQ-271-R | Mafraq |  | 32.3154 | 36.6235 | Mafraq | Tower | [36 empty] | Approved
694 | 694-Dheibeh_Housing_PF_O | TASC | AMS-325-R | Amman |  | 31.8099 | 36.0447 | Amman | Pole | [36 empty] | Approved
6078 | 6078-Saaedieh_West_O | TASC | MFQ-272-R | Mafraq |  | 32.2736 | 36.4373 | Mafraq | Tower | [36 empty] | Approved
4587 | 4587-Wassieh_North_Salt_O | TASC | BLQ-269-R | Balqa |  | 32.0976 | 35.7832 | Balqa | Tower | [36 empty] | Approved
5369 | 5369-Jawa_Yadoudeh_O | TASC | AMS-328-R | Amman |  | 31.8472 | 35.9332 | Amman | Tower | [36 empty] | Approved
2987 | 2987-Sareeh_Nazzal_District_O | TASC | IRB-575-R | Irbid |  | 32.5104 | 35.8908 | Irbid | Tower | [36 empty] | Approved
6084 | 6084-Madaba_Camp_West_O | TASC | MAD-308-R | Madaba |  | 31.7108 | 35.7776 | Madaba | Tower | [36 empty] | Approved
6100 | 6100-Madaba_Sakan_Kareem_South_O | TASC | MAD-309-R | Madaba |  | 31.7148 | 35.7712 | Madaba | Tower | [36 empty] | Approved
6080 | 6080-Samou_West_O | TASC | IRB-574-R | Irbid |  | 32.5175 | 35.7304 | Irbid | Tower | [36 empty] | Approved
3324 | 3324-Mutah_Mazar_Karak_O | TASC | KRK-293-R | Karak |  | 31.0845 | 35.6928 | Karak | Tower | [36 empty] | Approved
3314 | 3314-Mutah_Uni_Med_Faculty_O | TASC | KRK-290-R | Karak |  | 31.0915 | 35.7149 | Karak | Pole | [36 empty] | Approved
4764 | 4764-Mafraq_Irbid_Rd_O | TASC | MFQ-274-R | Mafraq |  | 32.4206 | 36.1264 | Mafraq | Tower | [36 empty] | Approved
6040 | 6040-Mafraq_Housing_Avenue_O | TASC | MFQ-275-R | Mafraq |  | 32.3295 | 36.1747 | Mafraq | Tower | [36 empty] | Approved
3141 | 3141-Jabal_Faisal_Ammar_Mosque_O | TASC | ZRQ-454-R | Zarqa |  | 32.0069 | 36.0051 | Zarqa | Tower | [36 empty] | Approved
6038 | 6038-Bwaidah_Ramtha_South_O | TASC | IRB-576-R | Irbid |  | 32.4674 | 36.0568 | Irbid | Tower | [36 empty] | Approved
3795 | 3795-Salt_Um_Zaytooneh_O | TASC | BLQ-274-R | Balqa |  | 32.0269 | 35.6949 | Balqa | Tower | [36 empty] | Approved
843 | 843-Karak_Wasieh_O | TASC | KRK-294-R | Karak |  | 31.2197 | 35.7333 | Karak | Pole | [36 empty] | Approved
6039 | 6039-Znayya_Zaytooneh_East_O | TASC | ZRQ-456-R | Zarqa |  | 32.2031 | 36.1188 | Zarqa | Tower | [36 empty] | Approved
6101 | 6101-Wadi_Al_Hedan_Madaba_O | TASC | MAD-307-G | Madaba |  | 31.524 | 35.6708 | Madaba | Tower | [36 empty] | Approved
6181 | 6181-Modawara_South_O | TASC | MAN-224-G | Ma'an |  | 29.2679 | 36.0364 | Ma'an | Tower | [36 empty] | Approved
847 | 847-Brza_Madaba_O | TASC | MAD-310-G | Madaba |  | 31.523 | 35.7472 | Madaba | Tower | [36 empty] | Approved
3847 | 3847-Tnaib_Madaba_O | TASC | MAD-311-R | Madaba |  | 31.8001 | 35.9266 | Madaba | Pole | [36 empty] | Approved
699 | 699-Sahab_Moe_O | TASC | AMS-331-R | Amman |  | 31.8687 | 35.9917 | Amman | Pole | [36 empty] | Approved
1556 | 1556-Grena_East_O | TASC | MAD-306-R | Madaba |  | 31.7592 | 35.8046 | Madaba | Tower | [36 empty] | Approved
3392 | 3392-Mahmoudeh_Top_Karak_PF_TASC_RELO_O | TASC | KRK-296-R | Karak |  | 31.1179 | 35.7025 | Karak | Tower | [36 empty] | Approved
1272 | 1272-5th_Ave_South_Relo_O | TASC | AQB-315-R | Aqaba |  | 29.5287 | 35.0138 | Aqaba | Pole | [36 empty] | Approved
5338 | 5338-Abu_Alanda_Caragat_Stores_O | TASC | AMS-338-R | Amman |  | 31.8938 | 35.9553 | Amman | Tower | [36 empty] | Approved
1539 | 1539-Sweimeh_City_Relo_PE | TASC | AMS-337-G | Amman |  | 31.7703 | 35.602 | Amman | Tower | [36 empty] | Approved
856 | 856-Wasieh_Rakeen_Scl_Karak_O | TASC | KRK-301-R | Karak |  | 31.2243 | 35.7179 | Karak | Tower | [36 empty] | Approved
3618 | 3618-Mugabalein_Big_Msq_Back_O | TASC | AMS-339-R | Amman |  | 31.905 | 35.9066 | Amman | Tower | [36 empty] | Approved
3631 | 3631-Um_Heran_Christian_Cemetary_O | TASC | AME-1134-R | Amman |  | 31.9119 | 35.9434 | Amman | Tower | [36 empty] | Approved
6142 | 6142-Kettah_South_Jerash_O | TASC | JRS-113-R | Jarash |  | 32.2122 | 35.9296 | Jarash | Tower | [36 empty] | Approved
3748 | 3748-Salt_Kufr_Hoda_O | TASC | BLQ-278-R | Balqa |  | 32.0663 | 35.7003 | Balqa | Pole | [36 empty] | Approved
857 | 857-Ethhebeh_Gharbieh_O | TASC | MAD-319-R | Madaba |  | 31.5061 | 35.7605 | Madaba | Tower | [36 empty] | Approved
6030 | 6030-Mafraq_King_Abdullah_Ave_Mid_O | TASC | MFQ-281-R | Mafraq |  | 32.3174 | 36.2175 | Mafraq | Tower | [36 empty] | Approved
6251 | 6251-Salt_Wadi_Hour_O | TASC | BLQ-276-R | Balqa |  | 32.086 | 35.7745 | Balqa | Tower | [36 empty] | Approved
6088 | 6088-Taybeh_Market_O | TASC | IRB-586-R | Irbid |  | 32.5442 | 35.7243 | Irbid | Tower | [36 empty] | Approved
6007 | 6007-Jerash_Zegreet_O | TASC | JRS-112-R | Jarash |  | 32.2915 | 35.6628 | Jarash | Tower | [36 empty] | Approved
6012 | 6012-Baoon_Ajloun_West_O | TASC | AJL-68-R | Ajloun |  | 32.3865 | 35.7338 | Ajloun | Tower | [36 empty] | Approved
686 | 686-Sahab_Urban_Development_O | TASC | AME-1118-R | Amman |  | 31.8596 | 35.991 | Amman | Pole | [36 empty] | Approved
6037 | 6037-Hosha_Faa_Intersection_O | TASC | MFQ-284-R | Mafraq |  | 32.4319 | 36.0933 | Mafraq | Tower | [36 empty] | Approved
6083 | 6083-Jumha_Center_O | TASC | IRB-591-R | Irbid |  | 32.5546 | 35.7774 | Irbid | Tower | [36 empty] | Approved
6042 | 6042-Nimreh_Balaama_O | TASC | MFQ-283-R | Mafraq |  | 32.2218 | 36.1582 | Mafraq | Tower | [36 empty] | Approved
5721 | 5721-Madaba_Manja_O | TASC | MAD-313-R | Madaba |  | 31.7444 | 35.8539 | Madaba | Tower | [36 empty] | Approved
6011 | 6011-Jerash_Jamla_O | TASC | JRS-111-R | Jarash |  | 32.2551 | 35.8441 | Jarash | Tower | [36 empty] | Approved
1575 | 1575-Madaba_Khansaa_School_O | TASC | MAD-320-R | Madaba |  | 31.7021 | 35.7849 | Madaba | Tower | [36 empty] | Approved
6092 | 6092-Deir_Esseneh_South_o | TASC | IRB-596-R | Irbid |  | 32.5259 | 35.7497 | Irbid | Tower | [36 empty] | Approved
6105 | 6105-Ghour_Sheikh_Hussien_O | TASC | IRB-603-R | Irbid |  | 32.5286 | 35.6027 | Irbid | Tower | [36 empty] | Approved
6094 | 6094-Taiybeh_Aisha_Sch_O | TASC | IRB-598-R | Irbid |  | 32.5528 | 35.7082 | Irbid | Tower | [36 empty] | Approved
858 | 858-Fagou_Thnebat_Avenue_O | TASC | KRK-303-R | Karak |  | 31.3375 | 35.7048 | Karak | Tower | [36 empty] | Approved
2838 | 2838-Delail_South_2 | TASC | ZRQ-459-R | Zarqa |  | 32.1125 | 36.267 | Zarqa | Tower | [36 empty] | Approved
3334 | 3334-Karak_Qasabah_O | TASC | KRK-302-R | Karak |  | 31.1064 | 35.71 | Karak | Tower | [36 empty] | Approved
1507 | 1507-Madaba_Industrial_Area_O | TASC | MAD-302-R | Madaba |  | 31.7201 | 35.8151 | Madaba | Tower | [36 empty] | Approved
906 | 906-Jandaweel_KHBP_Back_O | TASC | AMW-1183-R | Amman |  | 31.9689 | 35.8378 | Amman | Tower | [10 empty] | SMP-WO-1339682 | [25 empty] | Approved
5126 | 5126-Wihdat_Camp_Shops_Street_O | TASC | AME-1137-R | Amman |  | 31.9305 | 35.9383 | Amman | Tower | [36 empty] | Approved
6093 | 6093-Rabieh_Koorah_O | TASC | IRB-594-R | Irbid |  | 32.5126 | 35.7474 | Irbid | Tower | [36 empty] | Approved
6104 | 6104-Mansourah_West_O | TASC | IRB-597-R | Irbid |  | 32.649 | 35.7105 | Irbid | Tower | [36 empty] | Approved
853 | 853-Um_Rasas_Yahoon | TASC | KRK-300-R | Karak |  | 31.4634 | 35.8548 | Karak | Tower | [36 empty] | Approved
2438 | 2438-Irbid_CC_North_O | TASC | IRB-590-R | Irbid |  | 32.5374 | 35.8647 | Irbid | Tower | [36 empty] | Approved
2992 | 2992-Ramtha_West_Top_O | TASC | IRB-613-R | Irbid |  | 32.5789 | 35.9868 | Irbid | Tower | [36 empty] | Approved
6250 | 6250-Zobya_North_AV | TASC | IRB-579-G | Irbid |  | 32.4352 | 35.7665 | Irbid | Tower | [36 empty] | Approved
6115 | 6115-Qumaim_Wasatieh_Mid | TASC | IRB-604-R | Irbid |  | 32.567 | 35.7395 | Irbid | Tower | [36 empty] | Approved
6013 | 6013-Jerash_Camp_South_O | TASC | JRS-115-R | Jarash |  | 32.26 | 35.8619 | Jarash | Tower | [36 empty] | Approved
3846 | 3846-Madaba_AlGhubaya_Alkhadra_O | TASC | MAD-312-R | Madaba |  | 31.8014 | 35.882 | Madaba | Pole | [36 empty] | Approved
6004 | 6004-Ajloun_Uni_Back | TASC | AJL-67-G | Ajloun |  | 32.3923 | 35.824 | Ajloun | Tower | [36 empty] | Approved
1602 | 1602-Rasheed_Back_2_O | TASC | AMW-1173-R | Amman |  | 32.0059 | 35.8893 | Amman | Pole | [10 empty] | SMP-WO-1339685 | [25 empty] | Approved
3855 | 3855-Jiza_Baselieh_O | TASC | MAD-316-G | Madaba |  | 31.6227 | 35.9666 | Madaba | Tower | [36 empty] | Approved
3750 | 3750-Era_Karameh_Road | TASC | BLQ-280-R | Balqa |  | 31.9954 | 35.6637 | Balqa | Tower | [36 empty] | Approved
6111 | 6111-Dogarah_East_Entrance | TASC | IRB-615-G | Irbid |  | 32.5924 | 35.7639 | Irbid | Tower | [36 empty] | Approved
6144 | 6144-AlRawda_Sch_Aghwar | TASC | BLQ-281-R | Balqa |  | 31.8308 | 35.6689 | Balqa | Tower | [36 empty] | Approved
5311 | 5311-Abu_Alanda_Atheer_School | TASC | AMS-347-R | Amman |  | 31.9099 | 35.9731 | Amman | Tower | [36 empty] | Approved
3747 | 3747-Salt_Um_Jozeh_O | TASC | BLQ-277-G | Balqa |  | 32.1061 | 35.7266 | Balqa | Tower | [36 empty] | Approved
6098 | 6098-Kufur_Asad_West_O | TASC | IRB-626-R | Irbid |  | 32.6069 | 35.6987 | Irbid | Tower | [36 empty] | Approved
1572 | 1572-Jofeh_End_Aghwar_O | TASC | BLQ-279-R | Balqa |  | 31.8631 | 35.6336 | Balqa | Pole | [36 empty] | Approved
3853 | 3853-Jiza_Camp_West_O | TASC | MAD-315-R | Madaba |  | 31.7035 | 35.9426 | Madaba | Tower | [36 empty] | Approved
6048 | 6048-Balama_West_Av_O | TASC | MFQ-295-R | Mafraq |  | 32.2206 | 36.0742 | Mafraq | Tower | [36 empty] | Approved
2995 | 2995-Ramtha_Asher_North_O | TASC | IRB-635-R | Irbid |  | 32.582 | 36.0189 | Irbid | Tower | [36 empty] | Approved
6016 | 6016-Ekhsheibeh_Ajloun_O | TASC | AJL-73-R | Ajloun |  | 32.2276 | 35.725 | Ajloun | Tower | [36 empty] | Approved
6018 | 6018-Sarieh_Tareq_Bin_Ziad_Msq | TASC | IRB-631-R | Irbid |  | 32.4951 | 35.8925 | Irbid | Tower | [36 empty] | Approved
6017 | 6017-Baoon_Sakan_Kareem_O | TASC | AJL-72-R | Ajloun |  | 32.38 | 35.7228 | Ajloun | Tower | [36 empty] | Approved
1553 | 1553-Ramah_Mid_O | TASC | BLQ-282-R | Balqa |  | 31.4841 | 35.3927 | Balqa | Tower | [36 empty] | Approved
6206 | 6206-Ghor_Mazraah_Center_O | TASC | KRK-310-R | Karak |  | 31.2648 | 35.5268 | Karak | Tower | [36 empty] | Approved
6014 | 6014-Ghour_Derar_End_O | TASC | BLQ-295-R | Balqa |  | 32.2104 | 35.6343 | Balqa | Tower | [36 empty] | Approved
3632 | 3632-Benayat_Hasad_North_O | TASC | AMS-354-R | Amman |  | 31.8949 | 35.8935 | Amman | Tower | [10 empty] | SMP-WO-1391178 | [25 empty] | Approved
3751 | 3751-Salt_Industrial_O | TASC | BLQ-302-G | Balqa |  | 31.9853 | 35.715 | Balqa | Tower | [36 empty] | Approved
6531 | 6531-Mansoura_Big_Msq_O | TASC | MFQ-297-R | Mafraq |  | 32.4162 | 36.1724 | Mafraq | Tower | [36 empty] | Approved
863 | 863-Al_Subhiat_Karak_O | TASC | KRK-311-R | Karak |  | 31.1754 | 35.7265 | Karak | Tower | [36 empty] | Approved
6114 | 6114-Maadde_East_TASC_O | TASC | BLQ-286-R | Balqa |  | 32.1631 | 35.6279 | Balqa | Pole | [36 empty] | Approved
6282 | 6282-Maan_Shediah_Village | TASC | MAN-237-G | Ma'an |  | 29.847 | 35.9332 | Ma'an | Tower | [36 empty] | Approved
2996 | 2996-Ramtha_PrinceHashim_Stadium_Back_TASC_O | TASC | IRB-649-R | Irbid |  | 32.543 | 36.0277 | Irbid | Tower | [36 empty] | Approved
6020 | 6020-Sarieh_Khansaa_Sch_TASC_O | TASC | IRB-648-R | Irbid |  | 32.5085 | 35.9 | Irbid | Tower | [36 empty] | Approved
737 | 737-Nabateen_Hotel_PF_CIBS_Manage | ZAIN/M | MAN-25-R | Ma'an | 874 | 30.2882 | 35.4566 | Ma'an | Pole | [20 empty] | C | [15 empty] | Approved
745 | 745-Movenpick_Petra_PF_EBand_AIBS_Manage_O | ZAIN/M | MAN-74-R | Ma'an |  | 30.3254 | 35.4693 | Ma'an | [21 empty] | A | [15 empty] | Approved
759 | 759-JIFCO_Eshidiya_PE_Manage_O | ZAIN/M | MAN-106-G | Ma'an |  | 29.8947 | 36.1351 | Ma'an | Tower | [36 empty] | Approved
5810 | 5810-Hasa_PC_Zain_Manage | ZAIN/M | KRK-10-G | Tafila | 822 | 30.8404 | 36.0177 | Tafila | Tower | [36 empty] | Approved
4672 | 4672-Barqash_PF_Manage_O | ZAIN/M | AJL-20-G | Irbid |  | 32.439 | 35.7278 | Irbid | Pole | [36 empty] | Approved
720 | 720-Eshidiya_Mines_PB_Manage | ZAIN/M | MAN-17-G | Ma'an | 844 | 29.9358 | 36.1375 | Ma'an | Tower | [36 empty] | Approved
704 | 704-Eshidiya_Mines_PF_Manage_O | ZAIN/M | MAN-11-R | Ma'an |  | 29.8841 | 36.2035 | Ma'an | Pole | [36 empty] | Approved
5874 | 5874-Prince_Zaid_Hospital_Tafilah_PD_Fiber_Manage_O | ZAIN/M | TAF-25-R | Tafila |  | 30.8255 | 35.5883 | Tafila | Pole | [36 empty] | Approved
5842 | 5842-Qadesieh_Lafarj_PE_Fiber_Manage_O | ZAIN/M | TAF-44-R | Tafila |  | 30.6865 | 35.6342 | Tafila | Pole | [36 empty] | Approved
4173 | 4173-Modawara_Customs_PSD_PE_Fiber_Manage | ZAIN/M | MAN-72-G | Ma'an | 962 | 29.1932 | 36.0738 | Ma'an | Tower | [36 empty] | Approved
5825 | 5825-Shobak_Sama_Factory_PF_Manage | ZAIN/M | MAN-96-R | Ma'an | 976 | 30.4563 | 35.5909 | Ma'an | Tower | [36 empty] | Approved
4174 | 4174-Daoom_Modawara_PF_Manage_O | ZAIN/M | MAN-119-R | Ma'an |  | 29.5561 | 35.9283 | Ma'an | Pole | [36 empty] | Approved
783 | 783-Phosphate_Eshidiya_PF_Manage_O | ZAIN/M | MAN-131-R | Ma'an |  | 29.8639 | 36.2604 | Ma'an | Pole | [36 empty] | Approved
5839 | 5839-Hasa_City_Market_PF_Manage_O | ZAIN/M | TAF-45-G | Tafila |  | 30.8562 | 35.9751 | Tafila | Pole | [36 empty] | Approved
2907 | 2907-King_Abdullah_2_Gardens_PF_Manage_O | ZAIN/M | IRB-383-R | Irbid |  | 32.5296 | 35.8828 | Irbid | Pole | [36 empty] | Approved
4157 | 4157-Bayer_Police_Station_PSD_PE_Manage_O | ZAIN/M | MAN-149-G | Ma'an |  | 30.7845 | 36.516 | Ma'an | Tower | [36 empty] | Approved
3113 | 3113-Wadi_ElEsh_PF_Manage_O | ZAIN/M | ZRQ-177-G | Amman |  | 31.9851 | 36.0731 | Amman | Tower | [36 empty] | Approved
3307 | 3307-Qatraneh_Phosphate_PF_Manage_O | ZAIN/M | KRK-175-R | Ma'an |  | 31.2222 | 36.1815 | Ma'an | Pole | [36 empty] | Approved
1506 | 1506-Kempinski_JV_Main_PF_DIBS_Manage | ZAIN/M | MAD-156-R | Madaba |  | 31.716 | 35.5875 | Madaba | Pole | [20 empty] | D | [15 empty] | Approved
1536 | 1536-Maghtas_Ticketing_Ent_PF_Manage_O | ZAIN/M | BLQ-200-R | Balqa |  | 31.8447 | 35.578 | Balqa | Pole | [36 empty] | Approved
1554 | 1554-Movenpick_DeadSea_Beach_PF_Manage | ZAIN/M | MAD-161-R | Balqa |  | 31.7178 | 35.5839 | Balqa | [37 empty] | Approved
1555 | 1555-Movenpick_DeadSea_Spa_PF_IBS_Manage | ZAIN/M | MAD-53-R | Balqa |  | 31.7177 | 35.5858 | Balqa | [21 empty] | IBS | [15 empty] | Approved
1545 | 1545-Movenpick_DeadSea_Main_PF_DIBS_Manage | ZAIN/M | MAD-44-R | Balqa |  | 31.7177 | 35.5883 | Balqa | Pole | [20 empty] | D | [15 empty] | Approved
1510 | 1510-Zara_1_PE_Fiber_Manage | ZAIN/M | MAD-149-G | Madaba | 944 | 31.6247 | 35.5708 | Madaba | [37 empty] | Approved
6162 | 6162-Prince_Hamza_Wells_O | ZAIN/M | MFQ-239-R | Mafraq |  | 31.7181 | 37.1126 | Mafraq | Tower | [36 empty] | Approved
1525 | 1525-Russian_Church_Monopole_PF_Manage_O | ZAIN/M | MAD-202-G | Balqa |  | 31.8314 | 35.549 | Balqa | Pole | [36 empty] | Approved
3301 | 3301-Manaseer_Swaqa_PF_Manage_O | ZAIN/M | KRK-132-G | Amman |  | 31.3278 | 36.1264 | Amman | Pole | [36 empty] | Approved
5884 | 5884-Phosphate_Hasa_PF_O | ZAIN/M | MAN-115-R | Tafila |  | 30.7417 | 36.0249 | Tafila | Pole | [36 empty] | Approved
5885 | 5885-Potash_City_DeadSea_PF_Manage_O | ZAIN/M | KRK-176-R | Karak |  | 31.2448 | 35.5354 | Karak | Pole | [36 empty] | Approved
828 | 828-Omari_Msq_Karak_PE_Fiber_UMN_Manage_O | ZAIN/M | KRK-223-R | Karak |  | 31.1848 | 35.7057 | Karak | Tower | [36 empty] | Approved
5871 | 5871-Potash_Factory_DeadSea_PF_UMN_Manage_O | ZAIN/M | KRK-218-R | Karak |  | 31.0888 | 35.5138 | Karak | Tower | [36 empty] | Approved
3343 | 3343-Karak_Governorate_Hospital_PE_Fiber_Manage_O | ZAIN/M | KRK-212-R | Karak |  | 31.1472 | 35.7253 | Karak | Pole | [36 empty] | Approved
1529 | 1529-Hilton_DeadSea_1_PE_Fiber_BDIBS_Manage | ZAIN/M | MAD-243-R | Balqa |  | 31.7221 | 35.5877 | Balqa | [21 empty] | BD | [15 empty] | Approved
1511 | 1511-Holiday_Inn_DeadSea_PF_DIBS_Manage | ZAIN/M | MAD-171-R | Balqa | 1546 | 31.7518 | 35.5909 | Balqa | Pole | [20 empty] | D | [15 empty] | Approved
5843 | 5843-Potash_Kharazeh_TL | ZAIN/M | KRK-299-G | Karak |  | 31.2504 | 35.5193 | Karak | Tower | [36 empty] | Approved
3356 | 3356-Phosphate_Abiad_PF_Manage_O | ZAIN/M | KRK-164-R | Karak |  | 31.0719 | 36.1468 | Karak | Tower | [36 empty] | Approved
3369 | 3369-Qatraneh_Cement_Factory_PF_Manage_O | ZAIN/M | KRK-138-R | Karak |  | 31.1844 | 36.074 | Karak | Pole | [36 empty] | Approved
5824 | 5824-Bromeen_Factory_PD_Manage | ZAIN/M | KRK-24-G | Karak | 809 | 31.1338 | 35.5251 | Karak | Tower | [36 empty] | Approved
2832 | 2832-Tafeh_PE_Manage_O | ZAIN/M | ZRQ-186-R | Zarqa |  | 32.0434 | 36.2458 | Zarqa | Pole | [36 empty] | Approved
2802 | 2802-Hashmia_Uni_Rd_PE_Manage | ZAIN/M | ZRQ-190-G | Zarqa | 595 | 32.1128 | 36.1844 | Zarqa | Tower | [36 empty] | Approved
1190 | 1190-Mafraq_Development_PF_UMN_Manage_O | ZAIN/M | MFQ-151-R | Mafraq |  | 32.3818 | 36.254 | Mafraq | Tower | [36 empty] | Approved
4709 | 4709-Mshairfe_Mafraq_PF_Manage_O | ZAIN/M | MFQ-76-R | Mafraq |  | 32.3431 | 35.9894 | Mafraq | Pole | [36 empty] | Approved
2815 | 2815-Hashmia_Uni_2_PF_Manage | ZAIN/M | ZRQ-118-G | Zarqa | 566 | 32.1061 | 36.1903 | Zarqa | Tower | [36 empty] | Approved
2849 | 2849-Delail_Sama_AlUrdon_PE_Manage_O | ZAIN/M | MFQ-150-R | Zarqa |  | 32.0669 | 36.4186 | Zarqa | Pole | [36 empty] | Approved
4731 | 4731-Mafraq_SCC_PF_Manage_O | ZAIN/M | MFQ-145-G | Mafraq |  | 32.3431 | 36.2125 | Mafraq | Tower | [36 empty] | Approved
1159 | 1159-Etihad_Farms_Mafraq_PF_Manage_O | ZAIN/M | MFQ-134-G | Mafraq |  | 32.233 | 36.392 | Mafraq | Tower | [36 empty] | Approved
1139 | 1139-Azraq_PA_Fiber_Manage_O | ZAIN/M | MFQ-39-G | Zarqa |  | 31.8324 | 36.8075 | Zarqa | Tower | [36 empty] | Approved
1173 | 1173-Azraq_Camp_Police_Station_PE_Manage_Gen_O | ZAIN/M | MFQ-129-R | Zarqa |  | 31.902 | 36.5718 | Zarqa | Tower | [36 empty] | Approved
2854 | 2854-Hallabat_Farms_PF_Manage_O | ZAIN/M | MFQ-149-R | Zarqa |  | 32.1319 | 36.4101 | Zarqa | Pole | [36 empty] | Approved
2847 | 2847-Hashmia_Uni_South_PF_Manage_O | ZAIN/M | ZRQ-273-R | Zarqa |  | 32.1005 | 36.1942 | Zarqa | Tower | [36 empty] | Approved
1171 | 1171-Azraq_Camp_CTR_PE_Manage_Gen_O | ZAIN/M | MFQ-130-R | Zarqa |  | 31.8883 | 36.5903 | Zarqa | Tower | [36 empty] | Approved
4753 | 4753-UN_Mafraq_HSG_PF_Manage_O | ZAIN/M | MFQ-132-R | Mafraq |  | 32.3354 | 36.2201 | Mafraq | Pole | [36 empty] | Approved
2830 | 2830-Amayreh_PF_Manage_O | ZAIN/M | ZRQ-85-R | Zarqa |  | 32.0437 | 36.2226 | Zarqa | Pole | [36 empty] | Approved
1172 | 1172-Azraq_Camp_End_PB_Fiber_Manage_O | ZAIN/M | MFQ-131-R | Zarqa |  | 31.9103 | 36.5999 | Zarqa | Tower | [36 empty] | Approved
1194 | 1194-Risheh_Traibeel_PF_Org_Manage_O | ZAIN/M | MFQ-193-G | Mafraq |  | 32.5748 | 39.0138 | Mafraq | Tower | [36 empty] | Approved
1148 | 1148-Jazeera_Farms_Safawi_Rd_PD_Manage_O | ZAIN/M | MFQ-113-G | Mafraq |  | 32.1706 | 36.961 | Mafraq | Tower | [36 empty] | Approved
2881 | 2881-Delail_Mabroukeh_Ave_PE_EBand_UMN_Manage_O | ZAIN/M | ZRQ-303-R | Mafraq |  | 32.1566 | 36.2841 | Mafraq | Tower | [36 empty] | Approved
1156 | 1156-Mafraq_Plastic_Factory_PF_Manage_O | ZAIN/M | MFQ-95-R | Mafraq |  | 32.2572 | 36.3146 | Mafraq | Pole | [36 empty] | Approved
2880 | 2880-Delail_Musherfeh_PF_Manage_O | ZAIN/M | ZRQ-304-R | Mafraq |  | 32.1366 | 36.2868 | Mafraq | Tower | [36 empty] | Approved
4305 | 4305-Russayfah_Awajan_PE_Org_Manage_O | ZAIN/M | ZRQ-329-R | Zarqa |  | 32.0213 | 36.056 | Zarqa | Tower | [36 empty] | Approved
1192 | 1192-Brigade_Desert_Azraq_PSD_PE_Fiber_Manage_O | ZAIN/M | MFQ-221-R | Zarqa |  | 31.8739 | 36.761 | Zarqa | Pole | [36 empty] | Approved
1189 | 1189-Azraq_Barakeh_Farms_PF_Manage_O | ZAIN/M | MFQ-158-G | Zarqa |  | 31.8371 | 36.922 | Zarqa | Tower | [36 empty] | Approved
1561 | 1561-Conference_Palace_PF_CIBS_Manage | ZAIN/M | MAD-144-R | Balqa |  | 31.7214 | 35.5894 | Balqa | [21 empty] | C | [15 empty] | Approved
4757 | 4757-Jaber_Border_SCC_PF_EBand_Manage_O | ZAIN/M | MFQ-152-R | Mafraq |  | 32.5187 | 36.1925 | Mafraq | Tower | [36 empty] | Approved
3358 | 3358-Sultani_Karak_PE_Org_Manage_O | ZAIN/M | KRK-224-G | Karak |  | 31.0812 | 36.0062 | Karak | Tower | [36 empty] | Approved
1120 | 1120-Jazeera_Farm_Mshanshal_PF_Manage_O | ZAIN/M | MFQ-128-R | Mafraq |  | 32.2058 | 36.5007 | Mafraq | Pole | [36 empty] | Approved
1514 | 1514-Crown_Plaza_DeadSea_PF_DIBS_Manage | ZAIN/M | MAD-178-R | Madaba | 1559 | 31.708 | 35.5853 | Madaba | Pole | [20 empty] | D | [15 empty] | Approved
5896 | 5896-Mojeb_Valley_Bridge_PF_Manage_O | ZAIN/M | KRK-235-G | Madaba |  | 31.4685 | 35.5721 | Madaba | Tower | [36 empty] | Approved
1599 | 1599-Zara_2_PE_Fiber_Manage | ZAIN/M | KRK-39-G | Madaba | 838 | 31.5182 | 35.5567 | Madaba | Tower | [36 empty] | Approved
3319 | 3319-Karak_UmGezlan_PF_EBand_Org_Manage_O | ZAIN/M | KRK-199-G | Karak |  | 31.0285 | 35.6814 | Karak | Tower | [36 empty] | Approved
1578 | 1578-Bani_Hamida_PF_Org_Manage_O | ZAIN/M | MAD-242-G | Madaba |  | 31.5529 | 35.6567 | Madaba | Tower | [36 empty] | Approved
3341 | 3341-Iraq_Karak_PF_EBand_Org_Manage_O | ZAIN/M | KRK-225-G | Karak |  | 31.0917 | 35.644 | Karak | Tower | [36 empty] | Approved
3504 | 3504-Sheraton_Bldg_PF_IBS_Manage | ZAIN/M | AMW-66-R | Amman |  | 31.9601 | 35.8795 | Amman | [21 empty] | IBS | [15 empty] | Approved
211 | 211-Kempinski_Hotel_PF_IBS_Manage | ZAIN/M | AMW-389-R | Amman | 407 | 31.9683 | 35.897 | Amman | [21 empty] | IBS | [15 empty] | Approved
3473 | 3473-Wadi_AlYabes_PE_Fiber_Org_Manage_O | ZAIN/M | IRB-375-G | Irbid |  | 32.3965 | 35.5834 | Irbid | Tower | [36 empty] | Approved
1472 | 1472-Um_Qontarah_PF_Org_Manage_O | ZAIN/M | JRS-69-R | Jarash |  | 32.2649 | 35.9389 | Jarash | Tower | [36 empty] | Approved
3710 | 3710-Zay_Bridge_PD_Fiber_Manage_O | ZAIN/M | BLQ-61-G | Balqa |  | 32.0652 | 35.7251 | Balqa | Tower | [36 empty] | Approved
2981 | 2981-Kufer_Khall_West_PE_EBand_Org_Manage_O | ZAIN/M | JRS-71-R | Jarash |  | 32.358 | 35.88 | Jarash | Tower | [36 empty] | Approved
3433 | 3433-Qaawar_Farm_PE_Manage_O | ZAIN/M | MAD-68-R | Balqa |  | 32.0046 | 35.5842 | Balqa | Pole | [36 empty] | Approved
2908 | 2908-JUST_2_PE_Fiber_Manage | ZAIN/M | IRB-183-R | Irbid | 780 | 32.4924 | 35.9886 | Irbid | Pole | [36 empty] | Approved
2957 | 2957-Quds_College_Irbid_PF_IBS_Manage_O | ZAIN/M | IRB-442-R | Irbid |  | 32.489 | 35.9766 | Irbid | [21 empty] | IBS | [15 empty] | Approved
2902 | 2902-King_Abdullah_Hospital_PE_Fiber_IBS_Zain_Manage | ZAIN/M | IRB-179-R | Irbid |  | 32.5005 | 35.9935 | Irbid | [21 empty] | IBS | [15 empty] | Approved
631 | 631-Muwaqqar_PSD_Training_PE_Manage | ZAIN/M | AME-751-R | Amman | 1680 | 31.7904 | 36.2089 | Amman | Tower | [36 empty] | Approved
616 | 616-Muwaqqar_PA_Fiber_Manage | ZAIN/M | AME-74-G | Amman | 1574 | 31.8064 | 36.1 | Amman | Tower | [36 empty] | Approved
3828 | 3828-Jizah_Manara_ATCCO_PF_Manage_O | ZAIN/M | MAD-214-G | Amman |  | 31.6931 | 35.9144 | Amman | Tower | [36 empty] | Approved
3813 | 3813-Joramco_PF_Manage_O | ZAIN/M | MAD-175-R | Amman |  | 31.724 | 36.0059 | Amman | Pole | [36 empty] | Approved
1557 | 1557-Fayhaa_Madaba_PF_Org_Manage_O | ZAIN/M | MAD-269-R | Madaba |  | 31.7106 | 35.737 | Madaba | Tower | [36 empty] | Approved
601 | 601-North_Jordan_Cement_Factory_PF_Manage_O | ZAIN/M | AME-616-G | Amman | 1541 | 31.7522 | 36.1908 | Amman | Pole | [36 empty] | Approved
1151 | 1151-Jazeera_Thuraya_Farms_PF_Manage_O | ZAIN/M | MFQ-117-R | Mafraq |  | 32.28 | 36.28 | Mafraq | Pole | [36 empty] | Approved
4762 | 4762-UCIC_Factory_Mafraq_Rd_PF_Manage_O | ZAIN/M | MFQ-138-R | Mafraq |  | 32.2045 | 36.2399 | Mafraq | Pole | [36 empty] | Approved
4718 | 4718-Rajhi_Factory_Mafraq_PF_Manage_O | ZAIN/M | MFQ-78-R | Mafraq |  | 32.2168 | 36.2044 | Mafraq | Pole | [36 empty] | Approved
3380 | 3380-Karak_Ent_PF_UMN_Manage_O | ZAIN/M | KRK-179-R | Karak |  | 31.1852 | 35.7879 | Karak | Tower | [36 empty] | Approved
2934 | 2934-Naaimeh_Bridge_PF_UMN_Manage_O | ZAIN/M | IRB-294-G | Irbid |  | 32.4333 | 35.9516 | Irbid | Tower | [36 empty] | Approved
1502 | 1502-Kempinski_JV_Ashtar_PF_IBS_Manage | ZAIN/M | MAD-157-R | Madaba |  | 31.7162 | 35.585 | Madaba | [21 empty] | IBS | [15 empty] | Approved
1589 | 1589-Madaba_American_Uni_PF_Manage_O | ZAIN/M | MAD-272-R | Madaba |  | 31.6607 | 35.8003 | Madaba | Pole | [36 empty] | Approved
4156 | 4156-Toba_Rest_PSD_PF_Manage_O | ZAIN/M | MAN-151-G | Ma'an |  | 31.286 | 36.6844 | Ma'an | Tower | [36 empty] | Approved
4170 | 4170-Dissie_Project_PF_Manage_Mcar | ZAIN/M | MAN-98-R | Ma'an |  | 29.423 | 35.817 | Ma'an | Pole | [36 empty] | Approved
4155 | 4155-Jafer_Police_Station_PSD_PD_Manage_O | ZAIN/M | MAN-150-G | Ma'an |  | 30.524 | 36.2434 | Ma'an | Tower | [36 empty] | Approved
3521 | 3521-Saint_Regis_Branded_PF_Fiber_IBS_Manage | ZAIN/M | AMW-1005-R | Amman |  | 31.9579 | 35.8768 | Amman | [21 empty] | IBS | [15 empty] | Approved
2888 | 2888-Dairy_Alyoum_PF_IBS_Manage_O | ZAIN/M | ZRQ-370-R | Zarqa |  | 32.068 | 36.4075 | Zarqa | [21 empty] | IBS | [15 empty] | Approved
1585 | 1585-Waleh_Dam_Project_PF_Manage_O | ZAIN/M | MAD-273-R | Madaba |  | 31.5651 | 35.7957 | Madaba | Pole | [36 empty] | Approved
739 | 739-IJC_Eshidiya_PF_Manage_O | ZAIN/M | MAN-169-R | Ma'an |  | 29.9134 | 36.1416 | Ma'an | Pole | [36 empty] | Approved
2466 | 2466-Irbid_Speciality_Hospital_PE_Fiber_IBS_Manage_O | ZAIN/M | IRB-498-R | Irbid |  | 32.5336 | 35.8625 | Irbid | [21 empty] | IBS | [15 empty] | Approved
1591 | 1591-O_Beach_DeadSea_PE_UMN_Manage_O | ZAIN/M | MAD-274-G | Madaba |  | 31.6802 | 35.577 | Madaba | Tower | [36 empty] | Approved
732 | 732-AlJazeera_Eshidiya_PF_Manage_O | ZAIN/M | MAN-157-G | Ma'an |  | 29.8462 | 36.1575 | Ma'an | Pole | [36 empty] | Approved
3327 | 3327-JoPetrol_Attarat_PF_Manage_O | ZAIN/M | MAN-166-R | Amman |  | 31.2737 | 36.4464 | Amman | Tower | [36 empty] | Approved
3323 | 3323-Phosphate_Abiad_Alown_PF_Manage_O | ZAIN/M | KRK-258-R | Karak |  | 31.0544 | 36.1314 | Karak | Pole | [36 empty] | Approved
3535 | 3535-Saint_Regis_Hotel_PF_IBS_Zain_Manage | ZAIN/M | AMW-1004-R | Amman |  | 31.9575 | 35.8779 | Amman | [21 empty] | IBS | [15 empty] | Approved
1150 | 1150-UEC_Shomari_Azraq_PF_Manage_O | ZAIN/M | ZRQ-381-R | Zarqa |  | 31.7806 | 36.7874 | Zarqa | Pole | [36 empty] | Approved
4687 | 4687-Prince_Rashid_Hospital_PF_IBS_Manage_O | ZAIN/M | IRB-499-R | Irbid |  | 32.5037 | 35.8647 | Irbid | [21 empty] | IBS | [15 empty] | Approved
1490 | 1490-Eshtafina_Ajloun_Ent_PF_Org_Manage_O | ZAIN/M | AJL-59-G | Ajloun |  | 32.3603 | 35.784 | Ajloun | Tower | [36 empty] | Approved
1534 | 1534-Prince_Hussein_Park_DeadSea_PF_Manage_O | ZAIN/M | BLQ-235-R | Balqa |  | 31.783 | 35.5744 | Balqa | Pole | [36 empty] | Approved
1215 | 1215-Movenpick-Aqaba-PD-EBand-EIBS-Manage | ZAIN/M | AQB-26-R | Aqaba | 950 | 29.5328 | 35.0005 | Aqaba | Pole | [20 empty] | E | [15 empty] | Approved
4142 | 4142-Sheikh-Zayed-PF-Manage-O | ZAIN/M | MAN-92-G | Aqaba |  | 29.5464 | 35.6635 | Aqaba | Tower | [36 empty] | Approved
1205 | 1205-Kempinski-Aqaba-PF-IBS-Zain-Manage | ZAIN/M | AQB-147-R | Aqaba |  | 29.5321 | 34.9977 | Aqaba | Pole | [20 empty] | IBS | [15 empty] | Approved
1204 | 1204-Intercontinental-Aqaba-PF-CDIBS-Manage | ZAIN/M | AQB-140-R | Aqaba | 943 | 29.5342 | 34.9958 | Aqaba | Pole | [20 empty] | IBS | [15 empty] | Approved
4139 | 4139-Dissie-2-PD-Fiber-Zain-Manage | ZAIN/M | MAN-73-G | Aqaba | 937 | 29.5415 | 35.721 | Aqaba | Tower | [36 empty] | Approved
4110 | 4110-Shmeisani-Aqaba-PF-Manage | ZAIN/M | AQB-257-R | Aqaba |  | 29.4995 | 35.0983 | Aqaba | Pole | [36 empty] | Approved
1240 | 1240-Sidney_Shamieh_PF_Manage_Mcar | ZAIN/M | AQB-251-R | Aqaba |  | 29.5938 | 35.0659 | Aqaba | Pole | [36 empty] | Approved
1596 | 1596-Porto_DeadSea_PF_Manage_O | ZAIN/M | BLQ-243-R | Balqa |  | 31.684 | 35.5757 | Balqa | Pole | [36 empty] | Approved
5972 | 5972-Sweifieh_Village_PF_Fiber_IBS_Manage | ZAIN/M | AMS-228-R | Amman |  | 31.9478 | 35.8649 | Amman | [21 empty] | IBS | [15 empty] | Approved
1535 | 1535-Panorama_DeadSea_SCC_PF_Manage_O | ZAIN/M | MAD-279-G | Madaba |  | 31.6313 | 35.5848 | Madaba | Tower | [36 empty] | Approved
4787 | 4787-King_Hussein_College_Mafraq_PF_Manage_O | ZAIN/M | MFQ-241-R | Mafraq |  | 32.3516 | 36.2464 | Mafraq | Tower | [36 empty] | Approved
3330 | 3330-Wataneih_Poultry_Karak_PF_IBS_Manage_O | ZAIN/M | KRK-276-R | Karak |  | 31.2157 | 36.0224 | Karak | [21 empty] | IBS | [15 empty] | Approved
3366 | 3366-Adnanieh_PF_UMN_Manage_Relo_O | ZAIN/M | KRK-275-R | Karak |  | 31.1332 | 35.6965 | Karak | Tower | [36 empty] | Approved
758 | 758-Eshidiya_Contractors_PF_Manage_O | ZAIN/M | MAN-194-G | Ma'an |  | 29.8859 | 36.2508 | Ma'an | Pole | [36 empty] | Approved
1161 | 1161-Emirates_Camp_PE_Manage_O | ZAIN/M | ZRQ-414-G | Zarqa |  | 32.0325 | 36.4456 | Zarqa | Tower | [36 empty] | Approved
2979 | 2979-CMJ_Hassan_Ind_PF_EBand_IBS_Manage_O | ZAIN/M | IRB-544-R | Irbid |  | 32.5001 | 36.0274 | Irbid | [21 empty] | IBS | [15 empty] | Approved
893 | 893-Shuqaiq_Madaba_PF_Org_Manage_O | ZAIN/M | MAD-294-R | Madaba |  | 31.5015 | 35.7376 | Madaba | Tower | [36 empty] | Approved
1211 | 1211-Ayla-North-West-Offices-PE-Fiber-Zain-Manage | ZAIN/M | AQB-238-G | Aqaba |  | 29.5643 | 34.9794 | Aqaba | Tower | [36 empty] | Approved
REP | REP-Qatraneh_AF_Zayed_62_Rep | ZAIN/M | MAN-172-G | Ma'an |  | 31.2763 | 36.2865 | Ma'an | Tower | [36 empty] | Approved
951 | 951-LampSite_PF_IBS | ZAIN | AMW-121-R | Amman |  | 31.9636 | 35.8447 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
923 | 923-Zain_Bunker_PF_IBS | ZAIN | AMS-220-R | Amman |  | 31.9717 | 35.8341 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
2850 | 2850-Delail_Twal_Farms_PF_Manage_O | ZAIN | ZRQ-279-R | Zarqa |  | 32.0957 | 36.2697 | Zarqa | Pole | [36 empty] | Approved
2807 | 2807-Jordan_Steel_PF_Manage_O | ZAIN | ZRQ-147-R | Zarqa |  | 32.1129 | 36.1409 | Zarqa | Pole | [36 empty] | Approved
1521 | 1521-Manaseer_Ramah_PF_Manage_O | ZAIN | BLQ-193-R | Balqa |  | 31.8094 | 35.6715 | Balqa | Pole | [36 empty] | Approved
1463 | 1463-Asfoor_Jerash_PF_Org_Manage_O | ZAIN | JRS-75-R | Jarash |  | 32.3228 | 35.8814 | Jarash | Tower | [36 empty] | Approved
4589 | 4589-Berin_PE_UMN_Manage_O | ZAIN | ZRQ-294-R | Zarqa |  | 32.0974 | 35.969 | Zarqa | Tower | [36 empty] | Approved
5758 | 5758-Dunes_Club_PF_DIBS_Manage_O | ZAIN | AME-403-R | Amman |  | 31.8515 | 35.8995 | Amman | Pole | [20 empty] | D | [15 empty] | Approved
641 | 641-Ghabawi_Landfill_PF_Manage_O | ZAIN | AME-735-R | Amman |  | 31.9287 | 36.1807 | Amman | Pole | [36 empty] | Approved
2322 | 2322-Marka_Training_CTR_PF_O | ZAIN | AME-900-R | Amman |  | 31.9765 | 35.9805 | Amman | Pole | [36 empty] | Approved
2321 | 2321-Marka_Officers_Club_PF_O | ZAIN | AME-899-R | Amman |  | 31.9704 | 35.9738 | Amman | Pole | [36 empty] | Approved
3357 | 3357-JAFCCO_Wadi_Abiad_PF_O | ZAIN | KRK-148-R | Karak |  | 30.9999 | 36.0625 | Karak | Pole | [36 empty] | Approved
3829 | 3829-Traffic_Institute_PSD_PF_Org_Manage_O | ZAIN | AME-781-G | Amman |  | 31.708 | 36.1241 | Amman | Tower | [36 empty] | Approved
3745 | 3745-Salt_New_Hospital_PF_Org_O | ZAIN | BLQ-246-R | Balqa |  | 32.0617 | 35.7075 | Balqa | [37 empty] | Approved
5507 | 5507-Crown_Plaza_Hotel_PF_IBS_O | ZAIN | AMW-46-R | Amman |  | 31.9621 | 35.8701 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
651 | 651-Nabeel_Factory_PF_CIBS_O | ZAIN | AMS-73-R | Amman |  | 31.857 | 36.0103 | Amman | [21 empty] | C | [15 empty] | Approved
627 | 627-United_Pharmaceuticals_PF_O | ZAIN | AMS-24-R | Amman |  | 31.8838 | 35.984 | Amman | Pole | [36 empty] | Approved
2877 | 2877-Zarqa_Joint_Training_South_PF_O | ZAIN | ZRQ-379-G | Zarqa |  | 32.0206 | 36.1302 | Zarqa | Tower | [36 empty] | Approved
3842 | 3842-GID_Airport_Bldg_PF_Org_O | ZAIN | AMS-253-R | Amman |  | 31.7084 | 35.979 | Amman | Tower | [36 empty] | Approved
1749 | 1749-Parliament_Council_PF_IBS_O | ZAIN | AME-995-R | Amman |  | 31.9638 | 35.9123 | Amman | [21 empty] | IBS | [15 empty] | Approved
370 | 370-Royal_Hotel_PF_IBS_O | ZAIN | AME-42-R | Amman |  | 31.9533 | 35.9087 | Amman | [21 empty] | IBS | [15 empty] | Approved
335 | 335-Intercontinental_PF_IBS_M | ZAIN | AME-33-R | Amman |  | 31.9532 | 35.9135 | Amman | [21 empty] | IBS | [15 empty] | Approved
317 | 317-Hayatt_Hotel_PF_IBS_O | ZAIN | AME-15-R | Amman |  | 31.9559 | 35.9098 | Amman | [21 empty] | IBS | [15 empty] | Approved
738 | 738-Railway_Maan_PF_O | ZAIN | MAN-80-R | Ma'an |  | 30.1775 | 35.7737 | Ma'an | Pole | [36 empty] | Approved
724 | 724-Maan_Enezeh_PF_SCC_M | ZAIN | MAN-140-G | Ma'an |  | 30.4948 | 35.7947 | Ma'an | Tower | [36 empty] | Approved
2950 | 2950-JRTR_Irbid_PF_O | ZAIN | IRB-281-G | Mafraq |  | 32.4638 | 35.9719 | Mafraq | Pole | [36 empty] | Approved
3333 | 3333-Attarat_Chimney_PF_O | ZAIN | MAN-198-R | Ma'an |  | 31.2684 | 36.4493 | Ma'an | Wall-Mount | [36 empty] | Approved
1721 | 1721-Abdali_Suhaib_Ibin_Senan_St_PF_M | ZAIN | AME-19-R | Amman |  | 31.967 | 35.9061 | Amman | Pole | [36 empty] | Approved
305 | 305-Cinema_Century_PF_IBS_M | ZAIN | AME-511-R | Amman |  | 31.9565 | 35.9108 | Amman | [21 empty] | IBS | [15 empty] | Approved
1584 | 1584-South_Shouneh_Hospital_PD_Org_O | ZAIN | BLQ-168-R | Balqa |  | 31.902 | 35.6269 | Balqa | Tower | [36 empty] | Approved
4566 | 4566-Hamta_Jerash_PF_Org_O | ZAIN | JRS-70-R | Jarash |  | 32.2164 | 35.8159 | Jarash | Tower | [36 empty] | Approved
4567 | 4567-Kfair_Jerash_PF_Org_O | ZAIN | JRS-77-G | Jarash |  | 32.2166 | 35.9314 | Jarash | Tower | [36 empty] | Approved
324 | 324-House_Hotel_PF_IBS_Org | ZAIN | AME-996-R | Amman |  | 31.951 | 35.9183 | Amman | [21 empty] | IBS | [15 empty] | Approved
1337 | 1337-P_Taqwa_Hizam_PF | ZAIN | AME-768-P | Amman |  | 31.9602 | 35.9989 | Amman | Pole | [36 empty] | Approved
4152 | 4152-Qweirah_PE_Org_O | ZAIN | MAN-139-R | Aqaba |  | 29.7926 | 35.3077 | Aqaba | Tower | [36 empty] | Approved
1737 | 1737-Parliament_PF_IBS_O | ZAIN | AME-805-R | Amman |  | 31.9624 | 35.912 | Amman | [21 empty] | IBS | [15 empty] | Approved
329 | 329-Intercontinental_Garage_PF_IBS_M | ZAIN | AME-27-R | Amman |  | 31.9532 | 35.9135 | Amman | [21 empty] | IBS | [15 empty] | Approved
318 | 318-Landmark_Hotel_PF_IBS_M | ZAIN | AME-614-R | Amman |  | 31.9604 | 35.9039 | Amman | [21 empty] | IBS | [15 empty] | Approved
4624 | 4624-Yarmouk_Uni_HSG_2_PF_M | ZAIN | IRB-254-R | Irbid |  | 32.4558 | 35.9113 | Irbid | Pole | [36 empty] | Approved
4609 | 4609-Yarmouk_Uni_HSG_PF_M | ZAIN | IRB-207-R | Irbid |  | 32.458 | 35.9078 | Irbid | Pole | [36 empty] | Approved
369 | 369-Zahran_Palace_PE_GPON_M | ZAIN | AME-769-R | Amman |  | 31.9564 | 35.9037 | Amman | Pole | [36 empty] | Approved
340 | 340-Middle_East_Insurance_PE_GPON_IBS_M | ZAIN | AME-866-R | Amman |  | 31.9544 | 35.9074 | Amman | [21 empty] | IBS | [15 empty] | Approved
1756 | 1756-Public_Security_PF_IBS_M | ZAIN | AME-49-R | Amman |  | 31.9605 | 35.9096 | Amman | [21 empty] | IBS | [15 empty] | Approved
4154 | 4154-Hmaimeh_PE_UMN_O | ZAIN | MAN-141-R | Aqaba |  | 29.9027 | 35.4074 | Aqaba | Tower | [36 empty] | Approved
799 | 799-Maan_Contract_PF_M | ZAIN | MAN-140-R | Ma'an |  | 29.9311 | 36.166 | Ma'an | Pole | [36 empty] | Approved
785 | 785-Petra_Visitors_Hall_PF_M | ZAIN | MAN-132-R | Ma'an |  | 30.3246 | 35.4675 | Ma'an | Pole | [36 empty] | Approved
4129 | 4129-BeitAli_Camp_PF_M | ZAIN | MAN-156-R | Aqaba |  | 29.6862 | 35.4279 | Aqaba | Pole | [36 empty] | Approved
2740 | 2740-Jabal_Qusor_Rd_PF_Fiber_M | ZAIN | AME-356-R | Amman |  | 31.9597 | 35.9423 | Amman | Tower | [36 empty] | Approved
2323 | 2323-Marka_Air_Force_PF_M | ZAIN | AME-270-R | Amman |  | 31.9754 | 35.9771 | Amman | Pole | [36 empty] | Approved
3104 | 3104-Yajouz_KASOTC_PF_Org_O | ZAIN | ZRQ-300-R | Amman |  | 32.0324 | 35.9712 | Amman | Tower | [36 empty] | Approved
3105 | 3105-Yajouz_Rd_PF_UMN_O | ZAIN | ZRQ-317-R | Zarqa |  | 32.0248 | 35.9907 | Zarqa | Tower | [36 empty] | Approved
2353 | 2353-P_ACI_Marka_PF | ZAIN | AME-992-P | Amman |  | 31.989 | 36.0056 | Amman | Pole | [36 empty] | Approved
3133 | 3133-Pepsi_Company_PF_M | ZAIN | ZRQ-348-R | Zarqa |  | 31.9963 | 36.0195 | Zarqa | Pole | [36 empty] | Approved
2301 | 2301-P_Tarkhees_Marka_South_PF | ZAIN | AME-997-P | Amman |  | 31.9898 | 35.997 | Amman | Pole | [36 empty] | Approved
3344 | 3344-Karak_Governorate_Hospital_PF_IBS_M | ZAIN | KRK-213-R | Karak |  | 31.1472 | 35.7253 | Karak | [21 empty] | IBS | [15 empty] | Approved
3371 | 3371-Daba_Desert_Rd_PF_P | ZAIN | KRK-250-P | Amman |  | 31.582 | 36.0002 | Amman | Pole | [36 empty] | Approved
1568 | 1568-Evason_Maeen_PF_IBS_Zain_M | ZAIN | MAD-63-R | Madaba |  | 31.6084 | 35.6103 | Madaba | Pole | [20 empty] | IBS | [15 empty] | Approved
3376 | 3376-Manaseer_Swaqa_2_PF_M | ZAIN | KRK-169-R | Amman |  | 31.3404 | 36.1252 | Amman | Pole | [36 empty] | Approved
1530 | 1530-Samara_DeadSea_PF_O | ZAIN | MAD-197-R | Balqa |  | 31.7204 | 35.5855 | Balqa | Pole | [36 empty] | Approved
4705 | 4705-Khirat_Farm_PF_M | ZAIN | MFQ-144-R | Mafraq |  | 32.3613 | 36.0888 | Mafraq | Pole | [36 empty] | Approved
1115 | 1115-Gulf_Cables_Mafraq_PF_FiberNode_M | ZAIN | MFQ-106-R | Mafraq |  | 32.3038 | 36.2628 | Mafraq | Pole | [36 empty] | Approved
4730 | 4730-Kibar_Factory_PF_M | ZAIN | MFQ-98-P | Mafraq |  | 32.2176 | 36.2409 | Mafraq | Pole | [36 empty] | Approved
1050 | 1050-P_Zarqa_Madina_Monawara_PF | ZAIN | ZRQ-296-P | Zarqa |  | 32.0562 | 36.0351 | Zarqa | Pole | [36 empty] | Approved
1165 | 1165-Showaier_Force_PF_M | ZAIN | MFQ-195-R | Zarqa |  | 32.0224 | 36.4084 | Zarqa | Pole | [36 empty] | Approved
2812 | 2812-Hallabat_Manaseer_PF_M | ZAIN | ZRQ-193-R | Zarqa |  | 32.0975 | 36.4383 | Zarqa | Pole | [36 empty] | Approved
2842 | 2842-Tarawneh_Asphalt_Factory_PF_M | ZAIN | ZRQ-330-R | Zarqa |  | 32.0852 | 36.3006 | Zarqa | Pole | [36 empty] | Approved
1016 | 1016-Zarqa_Madina_Ave_End_PE_UMN_O | ZAIN | ZRQ-340-R | Zarqa |  | 32.0567 | 36.0489 | Zarqa | Pole | [36 empty] | Approved
2874 | 2874-Ghabawi_HSG_PF_M | ZAIN | ZRQ-309-P | Zarqa |  | 32.0075 | 36.2067 | Zarqa | Tower | [36 empty] | Approved
1014 | 1014-P_Falah_Ave_PF | ZAIN | ZRQ-334-P | Zarqa |  | 32.0589 | 36.0653 | Zarqa | Pole | [36 empty] | Approved
1198 | 1198-Khairat_Shamal_Farm_PF_M | ZAIN | MFQ-201-R | Mafraq |  | 32.4033 | 36.2998 | Mafraq | Pole | [36 empty] | Approved
1579 | 1579-Kempinski_Staff_Dorm_PF_M | ZAIN | MAD-241-R | Balqa |  | 31.784 | 35.5873 | Balqa | Pole | [36 empty] | Approved
1533 | 1533-Grand_East_PF_IBS_M | ZAIN | MAD-249-R | Balqa |  | 31.7461 | 35.5938 | Balqa | [21 empty] | IBS | [15 empty] | Approved
3322 | 3322-Jordanian_Melt_Factory_PF_M | ZAIN | KRK-201-R | Amman |  | 31.4738 | 36.1612 | Amman | Pole | [36 empty] | Approved
522 | 522-P_Fardous_B_Zyara_Back_PF | ZAIN | AMW-728-P | Amman |  | 31.9797 | 35.7994 | Amman | Pole | [36 empty] | Approved
3774 | 3774-Amman_Ahlieh_Uni_Back_PD_EBand | ZAIN | AMW-710-R | Balqa | 1616 | 32.0482 | 35.7847 | Balqa | Tower | [36 empty] | Approved
3256 | 3256-Crises_Management_CTR_PF_IBS | ZAIN | AMW-968-R | Amman |  | 31.9855 | 35.8237 | Amman | [21 empty] | IBS | [15 empty] | Approved
5602 | 5602-Jordan_Palace_Office_PF_IBS_Org_O | ZAIN | AMW-489-R | Amman |  | 32.0211 | 35.8281 | Amman | [21 empty] | IBS | [15 empty] | Approved
3247 | 3247-Manaseer_House_Dabouq_PE_Fiber_IBS | ZAIN | AMW-929-R | Amman |  | 31.9956 | 35.8162 | Amman | [21 empty] | IBS | [15 empty] | Approved
550 | 550-P_Zabda_Batayneh_PF | ZAIN | AMW-937-P | Balqa |  | 31.9471 | 35.7341 | Balqa | Pole | [36 empty] | Approved
577 | 577-Refaai_Zabda_PF_Zain_M | ZAIN | AMW-942-R | Amman |  | 31.9413 | 35.7493 | Amman | Pole | [36 empty] | Approved
594 | 594-Princess_Alia_Palace_PF_Zain_M | ZAIN | AMW-925-R | Amman |  | 32.0158 | 35.8173 | Amman | Pole | [36 empty] | Approved
535 | 535-Bader_Hussein_PF_M | ZAIN | AMW-988-R | Amman |  | 31.966 | 35.7646 | Amman | Pole | [36 empty] | Approved
516 | 516-Rehan_Palace_New_Bader_PF_M | ZAIN | AMW-674-R | Amman |  | 31.9805 | 35.7831 | Amman | Pole | [36 empty] | Approved
5620 | 5620-Hummar_Palace_Alkhasa_Garage_PF_M | ZAIN | AMW-895-R | Amman |  | 32.0161 | 35.8192 | Amman | Pole | [36 empty] | Approved
5621 | 5621-Israa_Hospital_PF_IBS | ZAIN | AMW-412-R | Amman |  | 32.0169 | 35.8659 | Amman | [21 empty] | IBS | [15 empty] | Approved
3249 | 3249-Queen_Rania_Hospital_PF_IBS_Zain_O | ZAIN | AMW-910-R | Amman |  | 31.98 | 35.8328 | Amman | [21 empty] | IBS | [15 empty] | Approved
574 | 574-P_Bader_Elite_Villas_PF | ZAIN | AMW-923-P | Amman |  | 31.9763 | 35.7894 | Amman | Pole | [36 empty] | Approved
3206 | 3206-Amman_Academy_Sch_PE_GPON_IBS | ZAIN | AMW-476-R | Amman |  | 32.004 | 35.8425 | Amman | [21 empty] | IBS | [15 empty] | Approved
1642 | 1642-KHCC_Tower_PF_Fiber_IBS_Zain_O | ZAIN | AMW-1006-R | Amman |  | 32.0048 | 35.8766 | Amman | [21 empty] | IBS | [15 empty] | Approved
1638 | 1638-KHCC_Hospital_PF_Fiber_IBS_O | ZAIN | AMW-541-R | Amman |  | 32.0046 | 35.8751 | Amman | [21 empty] | IBS | [15 empty] | Approved
4013 | 4013-Takhasosi_Hospital_PF_IBS_M | ZAIN | AMW-581-R | Amman |  | 31.9786 | 35.9006 | Amman | [21 empty] | IBS | [15 empty] | Approved
1639 | 1639-Uni_Hospital_PF_IBS_O | ZAIN | AMW-582-R | Amman |  | 32.0072 | 35.8742 | Amman | [21 empty] | IBS | [15 empty] | Approved
578 | 578-P_Fardous_CTR_PF | ZAIN | AMW-1035-P | Amman |  | 31.9731 | 35.7949 | Amman | Pole | [36 empty] | Approved
5506 | 5506-Hijaz_Towers_PF_IBS_O | ZAIN | AMW-592-R | Amman |  | 31.9761 | 35.8608 | Amman | [21 empty] | IBS | [15 empty] | Approved
2020 | 2020-Amman_Mall_PF_IBS_O | ZAIN | AMW-155-R | Amman |  | 31.9891 | 35.8666 | Amman | [21 empty] | IBS | [15 empty] | Approved
5535 | 5535-AJIB_Bank_HQ_PE_GPON_IBS_Org | ZAIN | AMW-944-R | Amman |  | 31.9609 | 35.8729 | Amman | [21 empty] | IBS | [15 empty] | Approved
5544 | 5544-Emaar_Towers_PE_GPON_IBS_O | ZAIN | AMW-825-R | Amman |  | 31.961 | 35.8738 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
2616 | 2616-JEA_KPMG_PF_IBS_M | ZAIN | AMW-912-R | Amman |  | 31.97 | 35.8967 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
5511 | 5511-Days_Inn_Hotel_PF_IBS_M | ZAIN | AMW-704-R | Amman |  | 31.9765 | 35.887 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
5513 | 5513-Naouri_Group_PE_GPON_IBS_M | ZAIN | AMW-821-R | Amman |  | 31.9668 | 35.8777 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
212 | 212-Jordan_Investment_Bank_PF_IBS_M | ZAIN | AMW-708-R | Amman |  | 31.9717 | 35.8963 | Amman | [21 empty] | IBS | [15 empty] | Approved
3523 | 3523-Fairmont_Hotel_PE_Fiber_IBS_Org_O | ZAIN | AMW-1007-R | Amman |  | 31.9601 | 35.8815 | Amman | [21 empty] | IBS | [15 empty] | Approved
3514 | 3514-Abdoun_Aqari_PF_IBS_M | ZAIN | AMW-712-R | Amman |  | 31.9561 | 35.883 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
2656 | 2656-Meridian_PF_IBS_O | ZAIN | AME-321-R | Amman |  | 31.9699 | 35.905 | Amman | [21 empty] | IBS | [15 empty] | Approved
3515 | 3515-AMC_Hospital_PF_IBS_M | ZAIN | AMW-845-R | Amman |  | 31.9596 | 35.8785 | Amman | [21 empty] | IBS | [15 empty] | Approved
216 | 216-Ahli_Bank_PF_IBS_Org | ZAIN | AMW-805-R | Amman |  | 31.9616 | 35.8982 | Amman | [21 empty] | IBS | [15 empty] | Approved
214 | 214-Jordan_Islamic_Bank_PF_IBS_M | ZAIN | AMW-648-R | Amman |  | 31.9681 | 35.8994 | Amman | [21 empty] | IBS | [15 empty] | Approved
2605 | 2605-Regency_Hotel_PF_IBS_O | ZAIN | AMW-646-R | Amman |  | 31.976 | 35.9065 | Amman | [21 empty] | IBS | [15 empty] | Approved
2612 | 2612-Marriott_Hotel_PF_IBS_O | ZAIN | AME-291-R | Amman |  | 31.9739 | 35.9065 | Amman | [21 empty] | IBS | [15 empty] | Approved
3501 | 3501-RJ_HQ_Bldg_PF_Fiber_IBS_M | ZAIN | AMW-950-R | Amman |  | 31.9568 | 35.8776 | Amman | [21 empty] | IBS | [15 empty] | Approved
219 | 219-Millenium_Hotel_PF_IBS_M | ZAIN | AMW-680-R | Amman |  | 31.9667 | 35.8989 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
233 | 233-Arab_Bank_Shmeisani_PF_EBand_IBS_O | ZAIN | AMW-88-R | Amman |  | 31.9654 | 35.8982 | Amman | [21 empty] | IBS | [15 empty] | Approved
585 | 585-P_Rabahieh_West_PF | ZAIN | AMW-1030-P | Balqa |  | 31.9724 | 35.8012 | Balqa | Pole | [36 empty] | Approved
213 | 213-Esteshary_Hospital_PF_IBS_M | ZAIN | AMW-527-R | Amman |  | 31.965 | 35.8859 | Amman | [21 empty] | IBS | [15 empty] | Approved
2049 | 2049-Mahmodieh_Motor_Bldg_PE_GPON_IBS_Org | ZAIN | AMW-1023-R | Amman |  | 31.987 | 35.8661 | Amman | [21 empty] | IBS | [15 empty] | Approved
3505 | 3505-Fine_PF_IBS_M | ZAIN | AMW-531-R | Amman |  | 31.9497 | 35.8928 | Amman | [21 empty] | IBS | [15 empty] | Approved
224 | 224-Jordan_Bank_Shmeisani_PF_IBS_M | ZAIN | AMW-85-R | Amman |  | 31.9679 | 35.8957 | Amman | [21 empty] | IBS | [15 empty] | Approved
1419 | 1419-Kufranjeh_Dam_PF_M | ZAIN | AJL-30-R | Ajloun |  | 32.2664 | 35.6441 | Ajloun | Pole | [36 empty] | Approved
1453 | 1453-Souf_Reserve_PF_M | ZAIN | JRS-72-R | Jarash |  | 32.2987 | 35.8246 | Jarash | Pole | [36 empty] | Approved
4548 | 4548-Salhoub_Forest_PSD_PF_M | ZAIN | AMW-933-R | Balqa |  | 32.1289 | 35.8522 | Balqa | Pole | [36 empty] | Approved
3712 | 3712-P_Salt_Amrieh_PF | ZAIN | BLQ-185-R | Balqa |  | 32.0487 | 35.7499 | Balqa | Pole | [36 empty] | Approved
3780 | 3780-P_Iskan_Taibeh_Back_PF | ZAIN | BLQ-182-P | Balqa |  | 32.0541 | 35.8011 | Balqa | Pole | [36 empty] | Approved
3775 | 3775-Tarkhees_Salt_PF_M | ZAIN | BLQ-111-R | Balqa |  | 32.0492 | 35.7598 | Balqa | Pole | [36 empty] | Approved
1483 | 1483-Souf_Reserve_2_PF_M | ZAIN | JRS-73-R | Jarash |  | 32.3023 | 35.8302 | Jarash | Pole | [36 empty] | Approved
3453 | 3453-Sayad_PF_M | ZAIN | BLQ-50-R | Balqa |  | 32.1088 | 35.6032 | Balqa | Pole | [36 empty] | Approved
3460 | 3460-Tarazeen_PF_M | ZAIN | BLQ-62-R | Balqa |  | 32.0336 | 35.679 | Balqa | Pole | [36 empty] | Approved
4555 | 4555-P_Um_Njasah_PF | ZAIN | BLQ-202-P | Balqa |  | 32.0912 | 35.8174 | Balqa | Pole | [36 empty] | Approved
5704 | 5704-Basset_Naour_PE_EBand_Org_O | ZAIN | AMS-2-G | Amman |  | 31.8569 | 35.7935 | Amman | Tower | [36 empty] | Approved
3810 | 3810-Qastal_Store_PF_O | ZAIN | AMS-111-R | Amman |  | 31.7511 | 35.9874 | Amman | Pole | [36 empty] | Approved
3869 | 3869-QAIA_Hotel_PE_BIBS_O | ZAIN | MAD-64-R | Amman |  | 31.7198 | 35.9649 | Amman | [21 empty] | B | [15 empty] | Approved
623 | 623-Petra_Muwaqqar_PF_M | ZAIN | AME-670-R | Amman |  | 31.7978 | 36.0889 | Amman | Pole | [36 empty] | Approved
3848 | 3848-Teeba_Yadoudeh_PF_M | ZAIN | AMS-4-R | Amman |  | 31.809 | 35.9003 | Amman | Pole | [36 empty] | Approved
5753 | 5753-Naour_Rawda_TL_PE_Org_O | ZAIN | AMS-49-G | Amman |  | 31.8203 | 35.825 | Amman | Tower | [36 empty] | Approved
3862 | 3862-IKEA_PF_IBS_Zain_O | ZAIN | MAD-229-R | Amman |  | 31.8248 | 35.9017 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
159 | 159-Opera_House_PF_IBS | ZAIN | AMW-949-R | Amman |  | 31.9563 | 35.8592 | Amman | [21 empty] | IBS | [15 empty] | Approved
3819 | 3819-P_Madaba_Edwan_PF | ZAIN | AMS-25-P | Amman |  | 31.7847 | 35.8584 | Amman | Pole | [36 empty] | Approved
5742 | 5742-P_Naour_DeadSea_PF | ZAIN | MAD-234-P | Amman |  | 31.8776 | 35.7787 | Amman | Pole | [36 empty] | Approved
5750 | 5750-Choueifat_Sch_PF_M | ZAIN | AMS-1-R | Amman |  | 31.8544 | 35.8814 | Amman | Pole | [36 empty] | Approved
3824 | 3824-QAIA_Parking_PSD_PF_O | ZAIN | MAD-213-G | Amman |  | 31.7223 | 35.9814 | Amman | Tower | [36 empty] | Approved
643 | 643-Sahab_Hatemieh_2_PF_UMN_M | ZAIN | AMS-11-G | Amman |  | 31.803 | 36.0919 | Amman | Tower | [36 empty] | Approved
3830 | 3830-JATS_PF_M | ZAIN | MAD-211-R | Amman |  | 31.7112 | 35.9848 | Amman | Pole | [36 empty] | Approved
5729 | 5729-Madaba_Hamarneh_Farm_PF_M | ZAIN | MAD-248-R | Madaba |  | 31.7677 | 35.8317 | Madaba | Tower | [36 empty] | Approved
5706 | 5706-Maani_PF_M | ZAIN | MAD-164-R | Amman |  | 31.8292 | 35.9117 | Amman | Pole | [36 empty] | Approved
654 | 654-P_Souq_Khudra_TL_PF | ZAIN | AMS-107-P | Amman |  | 31.8771 | 35.9506 | Amman | Pole | [36 empty] | Approved
5313 | 5313-Yadoudeh_Iskan_Karml_PE_UMN_O | ZAIN | AMS-67-R | Amman |  | 31.8518 | 35.9296 | Amman | Tower | [36 empty] | Approved
604 | 604-AbuAlanda_Interbrands_PF_IBS_M | ZAIN | AME-786-R | Amman |  | 31.8948 | 35.9731 | Amman | [21 empty] | IBS | [15 empty] | Approved
5708 | 5708-P_Tawaheen_Bahath_PF | ZAIN | AMS-36-P | Amman |  | 31.9056 | 35.8026 | Amman | Pole | [36 empty] | Approved
5755 | 5755-P_Hamidieh_PF | ZAIN | AMS-69-P | Amman |  | 31.9085 | 35.7344 | Amman | Pole | [36 empty] | Approved
5914 | 5914-Saudi_Embassy_PE_IBS_UMN_O | ZAIN | AMW-908-R | Amman |  | 31.9389 | 35.89 | Amman | [21 empty] | IBS | [15 empty] | Approved
5752 | 5752-AVECO_Factory_Naour_PF_FiberNode_M | ZAIN | AME-714-R | Amman |  | 31.8692 | 35.8235 | Amman | Pole | [36 empty] | Approved
5941 | 5941-Olive_Tree_Hotel_PF_IBS_M | ZAIN | AMW-922-R | Amman |  | 31.9426 | 35.8584 | Amman | [21 empty] | IBS | [15 empty] | Approved
5950 | 5950-Arab_Bank_Airport_Rd_PF_IBS_M | ZAIN | AMW-547-R | Amman |  | 31.9285 | 35.8561 | Amman | [21 empty] | IBS | [15 empty] | Approved
5902 | 5902-Foreign_Ministry_PF_AIBS_M | ZAIN | AMW-585-R | Amman |  | 31.923 | 35.8583 | Amman | Pole | [5 empty] | PO.2 |  |  |  |  | SMP-WO-1544664 | Lewan | Al-Lewan | [7 empty] | A | [15 empty] | Approved | [8 empty] | 1 | Waiting Access Letter
950 | 950-ZINC_PF_IBS_M | ZAIN | AMW-972-R | Amman |  | 31.971 | 35.8327 | Amman | [11 empty] | SMP-WO-1328191 | [9 empty] | IBS | [15 empty] | Approved
908 | 908-Shaab_St_Carage_PF_IBS_M | ZAIN | AMW-117-R | Amman |  | 31.9714 | 35.8247 | Amman | [21 empty] | IBS | [15 empty] | Approved
5770 | 5770-P_Bassah_Back_PF | ZAIN | AMS-120-P | Amman |  | 31.9228 | 35.7838 | Amman | Pole | [36 empty] | Approved
2029 | 2029-IBIS_Hotel_PF_IBS_M | ZAIN | AMW-622-R | Amman |  | 31.99 | 35.8649 | Amman | [21 empty] | IBS | [15 empty] | Approved
1703 | 1703-C_Town_Jabal_Hussein_PF_Fiber_IBS_M | ZAIN | AME-126-R | Amman |  | 31.9661 | 35.9169 | Amman | [21 empty] | IBS | [15 empty] | Approved
2705 | 2705-Fhais_CPLX_PF_M | ZAIN | AME-377-R | Amman |  | 31.9543 | 35.9316 | Amman | Pole | [36 empty] | Approved
2634 | 2634-Borsa_PF_IBS_M | ZAIN | AME-312-R | Amman |  | 31.9777 | 35.909 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
5844 | 5844-Bromeen_Factory_2_PF_M | ZAIN | KRK-136-G | Karak |  | 31.1457 | 35.5262 | Karak | Tower | [36 empty] | Approved
1709 | 1709-Islamic_Hospital_PF_IBS_M | ZAIN | AME-644-R | Amman |  | 31.9669 | 35.9077 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
4603 | 4603-Kasarat_Samad_PF_M | ZAIN | IRB-38-R | Irbid |  | 32.4642 | 35.8486 | Irbid | Pole | [36 empty] | Approved
640 | 640-Sahab_Image_PF_M | ZAIN | AME-734-R | Amman |  | 31.8159 | 36.0846 | Amman | Pole | [36 empty] | Approved
5887 | 5887-Tafilah_ATCCO_Wind_Project_PF_M | ZAIN | TAF-36-G | Tafila |  | 30.7094 | 35.6855 | Tafila | Tower | [36 empty] | Approved
4706 | 4706-Um_Lolo_Prison_PSD_PF_M | ZAIN | MFQ-231-R | Mafraq |  | 32.4033 | 36.1213 | Mafraq | Pole | [36 empty] | Approved
3420 | 3420-P_Arda_PF | ZAIN | BLQ-37-P | Balqa |  | 32.1219 | 35.6811 | Balqa | Pole | [36 empty] | Approved
1470 | 1470-Deir_Alleyat_PF_M | ZAIN | JRS-44-R | Jarash |  | 32.289 | 35.8706 | Jarash | Pole | [36 empty] | Approved
4533 | 4533-Zarqa_River_PF_M | ZAIN | ZRQ-29-R | Zarqa |  | 32.2091 | 35.9894 | Zarqa | Pole | [36 empty] | Approved
2875 | 2875-Rajhi_Factory_West_PF_M | ZAIN | MFQ-77-G | Mafraq |  | 32.2168 | 36.1909 | Mafraq | Pole | [36 empty] | Approved
4549 | 4549-Berin_Sukhneh_Rd_1_PF_M | ZAIN | JRS-25-R | Zarqa |  | 32.1117 | 35.9822 | Zarqa | Pole | [36 empty] | Approved
3736 | 3736-P_Saltous_Hotel_PF | ZAIN | BLQ-141-P | Balqa |  | 32.0407 | 35.7448 | Balqa | Pole | [36 empty] | Approved
3724 | 3724-P_Arda_2_PF | ZAIN | BLQ-128-P | Balqa |  | 32.0796 | 35.7087 | Balqa | Pole | [36 empty] | Approved
4613 | 4613-Shatana_PF_M | ZAIN | IRB-102-R | Irbid |  | 32.4315 | 35.8661 | Irbid | Pole | [36 empty] | Approved
5931 | 5931-Abdoun_Gym_PE_GPON_IBS_M | ZAIN | AMW-498-R | Amman |  | 31.9417 | 35.8844 | Amman | [21 empty] | IBS | [15 empty] | Approved
3915 | 3915-Hikma_Factory_PF_M | ZAIN | AMW-32-R | Amman |  | 31.9431 | 35.8468 | Amman | Pole | [10 empty] | SMP-WO-1414538 | [25 empty] | Approved
1508 | 1508-Marriott_DeadSea_PF_Fiber_IBS_O | ZAIN | MAD-54-R | Balqa |  | 31.7199 | 35.5852 | Balqa | Pole | [20 empty] | IBS | [15 empty] | Approved
1583 | 1583-Wadi_Shoaib_PF_M | ZAIN | MAD-49-R | Balqa |  | 31.9088 | 35.643 | Balqa | Pole | [36 empty] | Approved
1524 | 1524-Ramad_Hotel_DeadSea_PF_IBS_M | ZAIN | MAD-206-R | Balqa |  | 31.7666 | 35.5775 | Balqa | [21 empty] | IBS | [15 empty] | Approved
1526 | 1526-Baptism_Site_PF_M | ZAIN | MAD-237-R | Balqa |  | 31.8368 | 35.5472 | Balqa | Pole | [36 empty] | Approved
1523 | 1523-P_Kasarat_Madaba_PF | ZAIN | MAD-22-P | Madaba |  | 31.6593 | 35.7135 | Madaba | Pole | [36 empty] | Approved
778 | 778-Ras_Naqab_PF_SCC_O | ZAIN | MAN-128-G | Ma'an |  | 29.9946 | 35.5122 | Ma'an | Tower | [36 empty] | Approved
780 | 780-Tasan_PF_M | ZAIN | MAN-121-R | Ma'an |  | 30.0543 | 35.4675 | Ma'an | Pole | [36 empty] | Approved
753 | 753-Petra_Marriott_PF_IBS_M | ZAIN | MAN-76-R | Ma'an |  | 30.3047 | 35.4633 | Ma'an | [21 empty] | IBS | [15 empty] | Approved
709 | 709-Maan_Roof_PF_O | ZAIN | MAN-9-G | Ma'an |  | 30.2571 | 35.8164 | Ma'an | Tower | [36 empty] | Approved
129 | 129-Smartbuy_New_Bldg_PE_GPON_IBS_O | ZAIN | AMS-180-R | Amman |  | 31.9519 | 35.8555 | Amman | [21 empty] | IBS | [15 empty] | Approved
2872 | 2872-Amayreh_Farm_PF_M | ZAIN | ZRQ-998-R | Zarqa |  | 32.0551 | 36.1986 | Zarqa | Pole | [36 empty] | Approved
4579 | 4579-P_Ain_AlBasha_Iraq_Ave_PF | ZAIN | BLQ-215-P | Balqa |  | 32.068 | 35.8071 | Balqa | Pole | [36 empty] | Approved
586 | 586-P_Fardous_CPLX_PF | ZAIN | AMW-1031-P | Balqa |  | 31.978 | 35.8025 | Balqa | Pole | [36 empty] | Approved
2813 | 2813-Zarqa_ACWA_PF_FiberNode_M | ZAIN | ZRQ-368-R | Zarqa |  | 32.1141 | 36.1261 | Zarqa | Pole | [36 empty] | Approved
580 | 580-P_Mahis_Medah_PF | ZAIN | BLQ-217-P | Balqa |  | 31.9716 | 35.7617 | Balqa | Pole | [36 empty] | Approved
3388 | 3388-Swaqa_Jail_PF_O | ZAIN | KRK-253-R | Amman |  | 31.3792 | 36.0744 | Amman | Pole | [36 empty] | Approved
5337 | 5337-Jordan_Post_PF_IBS_M | ZAIN | AMS-186-R | Amman |  | 31.9031 | 35.9291 | Amman | [21 empty] | IBS | [15 empty] | Approved
5066 | 5066-Farah_New_Hospital_PE_Fiber_IBS_Zain_O | ZAIN | AMW-1026-R | Amman |  | 31.9515 | 35.9055 | Amman | [21 empty] | IBS | [15 empty] | Approved
5730 | 5730-P_Adassiyah_2_PF | ZAIN | BLQ-220-P | Madaba |  | 31.8697 | 35.7324 | Madaba | Pole | [36 empty] | Approved
325 | 325-Zara_Towers_PF_Fiber_IBS_O | ZAIN | AME-1004-R | Amman |  | 31.9569 | 35.9093 | Amman | [21 empty] | IBS | [15 empty] | Approved
5971 | 5971-TRC_New_Bldg_PE_GPON_IBS_Zain_O | ZAIN | AMS-197-R | Amman |  | 31.9401 | 35.856 | Amman | [11 empty] | SMP-WO-1509335 | [9 empty] | IBS | [15 empty] | Approved
1181 | 1181-Azraq_Safawi_TSK_PF_M | ZAIN | MFQ-235-R | Mafraq |  | 32.0901 | 37.0225 | Mafraq | Pole | [36 empty] | Approved
277 | 277-Housing_Bank_HQ_New_PF_Fiber_IBS_Org | ZAIN | AMW-1038-R | Amman |  | 31.966 | 35.8932 | Amman | [11 empty] | SMP-WO-1507045 | [9 empty] | IBS | [15 empty] | Approved
1443 | 1443-Haya_Hospital_PF_IBS_Org_O | ZAIN | AJL-58-R | Ajloun |  | 32.344 | 35.8193 | Ajloun | [21 empty] | IBS | [15 empty] | Approved
576 | 576-Hashimeye_Palace_Telecom_Office_PF_O | ZAIN | BLQ-224-G | Balqa |  | 31.9863 | 35.7833 | Balqa | Tower | [36 empty] | Approved
673 | 673-P_Tarkhees_Sahab_100_St_PF_FiberNode | ZAIN | AMS-204-P | Amman |  | 31.852 | 36.0444 | Amman | Pole | [36 empty] | Approved
674 | 674-P_Faisalieh_Baida_100_St_PF | ZAIN | AMS-205-P | Amman |  | 31.8672 | 36.0722 | Amman | Pole | [36 empty] | Approved
1023 | 1023-P_Zarqa_Qadesieh_30_St_PF | ZAIN | ZRQ-378-P | Zarqa |  | 32.0419 | 36.0469 | Zarqa | Pole | [36 empty] | Approved
4755 | 4755-King_Talal_Hospital_PF_IBS_Org_O | ZAIN | MFQ-234-R | Mafraq |  | 32.331 | 36.225 | Mafraq | [21 empty] | IBS | [15 empty] | Approved
645 | 645-Ghabawi_Arabian_Lebanon_PF_M | ZAIN | AMS-214-R | Amman |  | 31.8678 | 36.2009 | Amman | Pole | [36 empty] | Approved
5644 | 5644-Queen_Rania_Academy_PF_Fiber_IBS_O | ZAIN | AMW-1057-R | Amman |  | 32.0218 | 35.8731 | Amman | [21 empty] | IBS | [15 empty] | Approved
3627 | 3627-Hurrieh_Mall_PF_IBS_Org | ZAIN | AMS-206-R | Amman |  | 31.904 | 35.8875 | Amman | [21 empty] | IBS | [15 empty] | Approved
1750 | 1750-Parliament_CO_PF_IBS_Zain_O | ZAIN | AME-1027-R | Amman |  | 31.9624 | 35.9119 | Amman | [21 empty] | IBS | [15 empty] | Approved
1486 | 1486-Souf_PF_M | ZAIN | JRS-89-R | Jarash |  | 32.3036 | 35.8253 | Jarash | Pole | [36 empty] | Approved
712 | 712-Maan_West_PSD_PF_M | ZAIN | MAN-179-R | Ma'an |  | 30.3677 | 35.5073 | Ma'an | Pole | [36 empty] | Approved
3836 | 3836-QAIA_FreeZone_PF_O | ZAIN | AMS-212-R | Amman |  | 31.7158 | 36.0215 | Amman | Pole | [36 empty] | Approved
3138 | 3138-P_Khalid_Bin_Waleed_Village_PF | ZAIN | ZRQ-388-P | Zarqa |  | 31.9778 | 36.0269 | Zarqa | Pole | [36 empty] | Approved
581 | 581-P_Fardous_Fawaeer_Msq_PF | ZAIN | AMW-1068-P | Amman |  | 31.9805 | 35.8038 | Amman | Pole | [36 empty] | Approved
546 | 546-P_Zabda_Um_Njasah_PE | ZAIN | AMW-1062-P | Amman |  | 31.9321 | 35.736 | Amman | Pole | [36 empty] | Approved
4190 | 4190-Wadi_Rum_Camps_Hotel_PF_M | ZAIN | MAN-184-G | Ma'an |  | 29.721 | 35.4844 | Ma'an | Pole | [36 empty] | Approved
4550 | 4550-Anabtawi_Sweetsoobes_PF_M | ZAIN | BLQ-229-R | Balqa |  | 32.1028 | 35.862 | Balqa | Pole | [36 empty] | Approved
3483 | 3483-P_Arda_Cliff_PF | ZAIN | BLQ-239-P | Balqa |  | 32.1386 | 35.6641 | Balqa | Pole | [36 empty] | Approved
3841 | 3841-Jizza_Snokrot_PF_M | ZAIN | AMS-222-R | Amman |  | 31.6586 | 35.9862 | Amman | Pole | [36 empty] | Approved
2030 | 2030-Holiday_Inn_Amman_PF_IBS_O | ZAIN | AMW-1066-R | Amman |  | 31.9861 | 35.8652 | Amman | [21 empty] | IBS | [15 empty] | Approved
5811 | 5811-Potash_Bauer_Company_PF_M | ZAIN | KRK-262-G | Karak |  | 31.3264 | 35.4633 | Karak | Pole | [36 empty] | Approved
3850 | 3850-Nader_Logistic_Storage_PF_IBS_M | ZAIN | AMS-227-R | Amman |  | 31.7429 | 35.989 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
677 | 677-Ghabawi_AES_PF_M | ZAIN | AMS-225-R | Amman |  | 31.8963 | 36.0797 | Amman | Pole | [36 empty] | Approved
733 | 733-Eshidiya_Alhadeel_PF_M | ZAIN | MAN-187-G | Ma'an |  | 30.0525 | 36.1395 | Ma'an | Pole | [36 empty] | Approved
2855 | 2855-Kasarat_Doqarah_PF_Relo | ZAIN | ZRQ-416-R | Zarqa |  | 32.1259 | 36.0326 | Zarqa | Pole | [36 empty] | Approved
2824 | 2824-P_Kasarat_Doqarah_PF | ZAIN | ZRQ-415-P | Zarqa |  | 32.1256 | 36.0258 | Zarqa | Pole | [36 empty] | Approved
4105 | 4105-Maan_PSD_PF_O | ZAIN | MAN-202-G | Ma'an |  | 30.298 | 35.7549 | Ma'an | Pole | [36 empty] | Approved
1203 | 1203-Ayla_Golf_Residences_PF_IBS_M | ZAIN | AQB-999-G | Aqaba |  | 29.5607 | 34.9876 | Aqaba | Wall-Mount | [20 empty] | IBS | [15 empty] | Approved
1235 | 1235-Ayla-Navy-Tower-PF-Fiber-Zain-O | ZAIN | AQB-239-R | Aqaba |  | 29.546 | 34.9817 | Aqaba | Tower | [36 empty] | Approved
1227 | 1227-Royal-Palace-Aqaba-PF-Org-IBS-O | ZAIN | AQB-168-G | Aqaba |  | 29.5432 | 34.9909 | Aqaba | Tower | [20 empty] | IBS | [15 empty] | Approved
1266 | 1266-ASEZA-PF-EBand-IBS-O | ZAIN | AQB-170-R | Aqaba |  | 29.5587 | 35.02 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
4149 | 4149-Hillawei-Camp-PF-M | ZAIN | MAN-145-R | Aqaba |  | 29.64 | 35.5066 | Aqaba | Pole | [36 empty] | Approved
1284 | 1284-Aqaba-Water-Ayla-PF-O | ZAIN | AQB-193-R | Aqaba |  | 29.5689 | 34.9903 | Aqaba | Pole | [36 empty] | Approved
1263 | 1263-Aqaba-New-Shop-PF-Fiber-BIBS-O | ZAIN | AQB-192-R | Aqaba |  | 29.5316 | 35.0026 | Aqaba | Pole | [20 empty] | B | [15 empty] | Approved
1214 | 1214-Ayla-PE-Fiber-EIBS-Zain-O | ZAIN | AQB-240-R | Aqaba |  | 29.5506 | 34.9937 | Aqaba | Pole | [20 empty] | E | [15 empty] | Approved
1299 | 1299-Royal-Palace-Aqaba-2-PF-Zain-O | ZAIN | AQB-206-R | Aqaba |  | 29.5429 | 34.9911 | Aqaba | Pole | [36 empty] | Approved
4101 | 4101-Aqaba-Military-PF-M | ZAIN | AQB-165-G | Aqaba |  | 29.3602 | 35.0391 | Aqaba | Pole | [36 empty] | Approved
4130 | 4130-Phosphate_Aqaba_PF_M | ZAIN | AQB-146-G | Aqaba |  | 29.3697 | 34.9967 | Aqaba | Pole | [36 empty] | Approved
4141 | 4141-Rum-Railway-PF-M | ZAIN | MAN-83-R | Aqaba |  | 29.6993 | 35.4043 | Aqaba | Pole | [36 empty] | Approved
4123 | 4123-Rum-Visitor-CTR-PF-M | ZAIN | AQB-241-R | Aqaba |  | 29.639 | 35.4347 | Aqaba | Pole | [36 empty] | Approved
1226 | 1226-Ayla-Hyatt-Regency-Hotel-PF-IBS-Zain-O | ZAIN | AQB-247-R | Aqaba |  | 29.5451 | 34.9865 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
1230 | 1230-Luxury-Collection-Hotel-PF-IBS-Org-O | ZAIN | AQB-248-R | Aqaba |  | 29.5359 | 34.9934 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
1232 | 1232-Hayatt-Regency-Hotel-PF-IBS-Zain | ZAIN | AQB-255-R | Aqaba |  | 29.5451 | 34.9865 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
6124 | 6124-Hayatt-Regency-Hotel-PF-IBS-Zain | ZAIN | AQB-255-RR | Aqaba |  | 29.5451 | 34.9865 | Aqaba | [15 empty] | Done | [5 empty] | IBS | [15 empty] | Approved | [5 empty] | Approved
4167 | 4167-Raha-Village-PF-IBS-Org-O | ZAIN | AQB-250-R | Aqaba |  | 29.4968 | 35.0025 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
1298 | 1298-Aqaba-South-Custom-PF-SCC-O | ZAIN | AQB-225-R | Aqaba |  | 29.5769 | 34.9826 | Aqaba | Tower | [36 empty] | Approved
1258 | 1258-Prince-Hashem-Hospital-PF-CIBS-Org-O | ZAIN | AQB-189-R | Aqaba |  | 29.5717 | 35.0178 | Aqaba | Pole | [20 empty] | D | [15 empty] | Approved
1261 | 1261-5th-Ave-PSD-PF-O | ZAIN | AQB-183-R | Aqaba |  | 29.5351 | 35.0106 | Aqaba | Tower | [36 empty] | Approved
1283 | 1283-5th-Ave-PF-Org-O | ZAIN | AQB-187-R | Aqaba |  | 29.5378 | 35.0185 | Aqaba | Pole | [36 empty] | Approved
1282 | 1282-ASEZA-2-PE-FiberNode-O | ZAIN | AQB-231-R | Aqaba |  | 29.5587 | 35.02 | Aqaba | Pole | [36 empty] | Approved
4106 | 4106-Rice-Factory-Aqaba-PF-M | ZAIN | AQB-62-P | Aqaba |  | 29.4743 | 34.9783 | Aqaba | Pole | [36 empty] | Approved
4116 | 4116-Movenpick-TalaBay-Aqaba-PE-Fiber-DIBS-O | ZAIN | AQB-254-R | Aqaba |  | 29.4058 | 34.9787 | Aqaba | Pole | [20 empty] | D | [15 empty] | Approved
4184 | 4184-Assas-Cement-Factory-PF-O | ZAIN | AQB-253-R | Aqaba |  | 29.6019 | 35.0584 | Aqaba | Pole | [36 empty] | Approved
4115 | 4115-Ayla-Aqaba-Airport-PF-M | ZAIN | AQB-185-R | Aqaba |  | 29.6047 | 35.0193 | Aqaba | Pole | [36 empty] | Approved
4111 | 4111-KMAPCO-PF-M | ZAIN | AQB-230-R | Aqaba |  | 29.3656 | 34.9654 | Aqaba | Pole | [36 empty] | Approved
1279 | 1279-Oryx-Hotel-PF-IBS-O | ZAIN | AQB-198-R | Aqaba |  | 29.5402 | 34.9993 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
4117 | 4117-Aqaba-Airport-ALC-PF-M | ZAIN | AQB-205-R | Aqaba |  | 29.6205 | 35.0256 | Aqaba | Pole | [36 empty] | Approved
4125 | 4125-Aqaba-Logestic-Village-PF-M | ZAIN | AQB-246-G | Aqaba |  | 29.4531 | 34.989 | Aqaba | Pole | [36 empty] | Approved
4120 | 4120-Wadi-Youtom-Rep-4-PF-M | ZAIN | AQB-67-G | Aqaba |  | 29.5619 | 35.1079 | Aqaba | Tower | [36 empty] | Approved
4113 | 4113-Aqaba-SlaughterHouse-PF-Org-O | ZAIN | AQB-249-G | Aqaba |  | 29.5736 | 35.0769 | Aqaba | Tower | [36 empty] | Approved
4118 | 4118-Wadi-Youtom-Rep-2-PF-M | ZAIN | AQB-66-G | Aqaba |  | 29.563 | 35.0811 | Aqaba | Tower | [36 empty] | Approved
1293 | 1293-Hilton-Aqaba-PF-IBS | ZAIN | AQB-220-R | Aqaba |  | 29.5301 | 35.0033 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
4107 | 4107-Aqaba-Manaseer-Kasarat-PF-O | ZAIN | AQB-227-G | Aqaba |  | 29.5054 | 35.1462 | Aqaba | Pole | [36 empty] | Approved
4163 | 4163-Durra-PSD-PF-O | ZAIN | AQB-182-R | Aqaba |  | 29.3576 | 34.9633 | Aqaba | Tower | [36 empty] | Approved
1220 | 1220-Manaseer-Shamieh-PF-M | ZAIN | AQB-229-R | Aqaba |  | 29.6021 | 35.0577 | Aqaba | Pole | [36 empty] | Approved
1280 | 1280-Aqaba-Police-Station-PF-M | ZAIN | AQB-184-G | Aqaba |  | 29.5656 | 35.0488 | Aqaba | Pole | [36 empty] | Approved
4166 | 4166-Titen-Village-PF-SCC-M | ZAIN | AQB-272-G | Aqaba |  | 29.3735 | 35.1871 | Aqaba | Tower | [36 empty] | Approved
1243 | 1243-Aqaba-Jordan-Uni-PF-O | ZAIN | AQB-276-R | Aqaba |  | 29.5872 | 35.0234 | Aqaba | Pole | [36 empty] | Approved
1262 | 1262-Wadi-Araba-Customs-Office-PF-O | ZAIN | AQB-284-R | Aqaba |  | 29.6713 | 35.0299 | Aqaba | Pole | [36 empty] | Approved
1234 | 1234-Aqaba-5th-PE-FiberNode-O | ZAIN | AQB-275-R | Aqaba |  | 29.5436 | 35.0211 | Aqaba | Pole | [36 empty] | Approved
3379 | 3379-Btoush_Mall_Karak_PF_Fiber_IBS | ZAIN | KRK-268-R | Karak |  | 31.1136 | 35.6994 | Karak | [21 empty] | IBS | [15 empty] | Approved
1929 | 1929-P_Zarqa_Khaw_TL_PF | ZAIN | ZRQ-417-P | Zarqa |  | 32.0885 | 36.1194 | Zarqa | Pole | [36 empty] | Approved
5733 | 5733-Prince_Mohammad_Palace_PF_Zain_M | ZAIN | AMS-239-R | Amman |  | 31.9032 | 35.8119 | Amman | Pole | [36 empty] | Approved
4590 | 4590-Kamsheh_Barakat_Farms_PF_M | ZAIN | ZRQ-421-R | Zarqa |  | 32.1105 | 35.8974 | Zarqa | Pole | [36 empty] | Approved
584 | 584-New_Bader_Bilal_PE_Org_O | ZAIN | AMW-1093-G | Amman |  | 31.9621 | 35.7878 | Amman | Tower | [36 empty] | Approved
680 | 680-Sakan_Kareem_Hizam_PE_UMN_O | ZAIN | AME-1035-G | Amman |  | 31.916 | 36.0114 | Amman | Tower | [36 empty] | Approved
2225 | 2225-Mecca_Mall_New_Ext_PF_Fiber_IBS_Zain_O | ZAIN | AMW-1087-R | Amman |  | 31.9785 | 35.8439 | Amman | [6 empty] | PO.2 |  |  |  |  | SMP-WO-1537006 | Lewan | Al-Lewan | [7 empty] | IBS | [15 empty] | Approved | [8 empty] | 1 | Waiting Access Letter
2618 | 2618-Jordan_Finland_Hospital_PF_IBS_M | ZAIN | AME-1044-R | Amman |  | 31.975 | 35.9086 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
3767 | 3767-Salt_New_Hospital_PF_Fiber_IBS_Org_O | ZAIN | BLQ-251-R | Balqa |  | 32.0617 | 35.7075 | Balqa | [21 empty] | IBS | [15 empty] | Approved
5718 | 5718-Opal_Hotel_PF_IBS_O | ZAIN | AMS-242-R | Amman |  | 31.8606 | 35.8954 | Amman | [21 empty] | IBS | [15 empty] | Approved
5923 | 5923-Judicial_Institute_PE_GPON_IBS_O | ZAIN | AMS-254-R | Amman |  | 31.948 | 35.8548 | Amman | [21 empty] | IBS | [15 empty] | Approved
1256 | 1256-Aqaba_Royal_Villas_PF_M | ZAIN | AQB-289-R | Aqaba |  | 29.5413 | 34.9831 | Aqaba | Pole | [36 empty] | Approved
3740 | 3740-Hikma_Factory_Salt_PE_Fiber_IBS | ZAIN | BLQ-253-R | Balqa |  | 32.0634 | 35.7251 | Balqa | [21 empty] | IBS | [15 empty] | Approved
682 | 682-Dairy_AlYoum_Warehouse_PF_IBS_M | ZAIN | AMS-262-R | Amman |  | 31.9016 | 36.0744 | Amman | [21 empty] | IBS | [15 empty] | Approved
1450 | 1450-Souf_Sahlat_Ave_PF_M | ZAIN | JRS-95-R | Jarash |  | 32.3284 | 35.8511 | Jarash | Pole | [36 empty] | Approved
3851 | 3851-Layan_Warehouse_PF_IBS | ZAIN | AMS-273-R | Amman |  | 31.7111 | 36.0275 | Amman | [21 empty] | IBS | [15 empty] | Approved
5233 | 5233-Queen_Alia_Hospital_PF_IBS_O | ZAIN | AME-1040-R | Amman |  | 32.0005 | 35.9194 | Amman | [21 empty] | IBS | [15 empty] | Approved
1332 | 1332-P_Sakan_Kareem_Hizam_Back_PF | ZAIN | AME-1062-P | Amman |  | 31.9262 | 36.0048 | Amman | Pole | [36 empty] | Approved
5725 | 5725-P_Marj_Um_Al_Summaq_End_PF | ZAIN | AMS-260-P | Amman |  | 31.8735 | 35.8683 | Amman | Pole | [36 empty] | Approved
5757 | 5757-P_Husban_Nutridar_Back_PF | ZAIN | AMS-271-P | Amman |  | 31.8518 | 35.7844 | Amman | Pole | [36 empty] | Approved
3130 | 3130-Kareem_Hypermarket_HQ_PF_IBS_O | ZAIN | ZRQ-430-R | Zarqa |  | 31.9982 | 36.0112 | Zarqa | [21 empty] | IBS | [15 empty] | Approved
5731 | 5731-P_Prince_Ali_Bin_Nayef_Palace_PF | ZAIN | MAD-282-P | Madaba |  | 31.8283 | 35.803 | Madaba | Pole | [36 empty] | Approved
2863 | 2863-AlBaha_Manuf_Zarqa_PF_M | ZAIN | ZRQ-429-R | Zarqa |  | 32.0744 | 36.253 | Zarqa | Pole | [36 empty] | Approved
4150 | 4150-Rum_Railway_PF_Relo_M | ZAIN | MAN-195-G | Ma'an |  | 29.6911 | 35.4188 | Ma'an | Pole | [36 empty] | Approved
1265 | 1265-Aqaba_Islamic_Hospital_PE_Fiber_IBS_O | ZAIN | AQB-291-R | Aqaba |  | 29.533 | 35.0086 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
776 | 776-Qaisi_Eshidiya_Corp_PF_M | ZAIN | MAN-196-G | Ma'an |  | 29.8926 | 36.3066 | Ma'an | Pole | [36 empty] | Approved
4160 | 4160-Sheikh_Zayed_North_PF_M | ZAIN | MAN-193-G | Ma'an |  | 29.5654 | 35.6524 | Ma'an | Pole | [36 empty] | Approved
3857 | 3857-BabyLife_Factory_PF_IBS_O | ZAIN | AMS-275-R | Amman |  | 31.7423 | 35.9755 | Amman | [21 empty] | IBS | [15 empty] | Approved
959 | 959-ATCCO_HQ_Building_PF_Fiber_IBS_O | ZAIN | AMS-272-R | Amman |  | 31.9607 | 35.8447 | Amman | [21 empty] | IBS | [15 empty] | Approved
4814 | 4814-MOH_Main_Building_PF_IBS_O | ZAIN | AME-1067-R | Amman |  | 31.9837 | 35.9409 | Amman | [21 empty] | IBS | [15 empty] | Approved
507 | 507-P_Sukhtian_Farm_M_PF | ZAIN | AMW-1116-P | Amman |  | 31.953 | 35.7609 | Amman | Pole | [36 empty] | Approved
2340 | 2340-JAC_Military_Marka_PF_M | ZAIN | AME-1070-R | Amman |  | 31.9741 | 35.9826 | Amman | Pole | [36 empty] | Approved
3844 | 3844-Spartan_Factory_PF_EBand_IBS | ZAIN | AMS-281-R | Amman |  | 31.7629 | 35.952 | Amman | [21 empty] | IBS | [15 empty] | Approved
508 | 508-P_Um_Al_Osood_Mashhour_Jazi_PF | ZAIN | AMW-1120-P | Amman |  | 31.9793 | 35.7768 | Amman | Pole | [36 empty] | Approved
3253 | 3253-Sara_Saudi_Hospital_PE_GPON_IBS | ZAIN | AMW-1118-R | Amman |  | 31.9977 | 35.8534 | Amman | [21 empty] | IBS | [15 empty] | Approved
2563 | 2563-Jordan_Atomic_Energy_Commission_PF_IBS | ZAIN | AMW-1125-R | Amman |  | 32.035 | 35.9492 | Amman | [21 empty] | IBS | [15 empty] | Approved
5735 | 5735-P_Bikers_Village_PF | ZAIN | AMS-287-P | Amman |  | 31.8446 | 35.8837 | Amman | Pole | [36 empty] | Approved
3428 | 3428-Naouri_Farms_Ghour_PF_O | ZAIN | BLQ-259-R | Balqa |  | 31.9231 | 35.556 | Balqa | Pole | [36 empty] | Approved
1162 | 1162-Delmonte_Mafraq_Farm_PF_M | ZAIN | MFQ-250-G | Mafraq |  | 32.2814 | 36.4639 | Mafraq | Pole | [36 empty] | Approved
4235 | 4235-Zarqa_City_Gate_Mall_PF_IBS_O | ZAIN | ZRQ-432-R | Zarqa |  | 32.0713 | 36.1007 | Zarqa | [21 empty] | IBS | [15 empty] | Approved
4794 | 4794-Rehab_Farms_PF_M | ZAIN | ZRQ-434-R | Zarqa |  | 32.3135 | 36.1042 | Zarqa | Wall-Mount | [36 empty] | Approved
4581 | 4581-P_Jalaad_Faouri_Farm_PF | ZAIN | AMW-1128-P | Amman |  | 32.1409 | 35.7905 | Amman | Pole | [36 empty] | Approved
4697 | 4697-Huson_Mar_John_Church_PF_M | ZAIN | IRB-550-R | Irbid |  | 32.477 | 35.8758 | Irbid | Pole | [36 empty] | Approved
3933 | 3933-TOYOTA_Service_CTR_PF_IBS | ZAIN | AMW-1127-R | Amman |  | 31.9381 | 35.8457 | Amman | [21 empty] | IBS | [15 empty] | Approved
1587 | 1587-Zara_Rd_Sheikh_Resort_PF_M | ZAIN | MAD-289-R | Madaba |  | 31.5972 | 35.5647 | Madaba | Pole | [36 empty] | Approved
5889 | 5889-Hasa_Mines_PE_M | ZAIN | TAF-56-R | Tafila |  | 30.796 | 36.1308 | Tafila | Pole | [36 empty] | Approved
2720 | 2720-Central_Bank_Jordan_PF_IBS | ZAIN | AME-1081-R | Amman |  | 31.9572 | 35.9308 | Amman | [21 empty] | IBS | [15 empty] | Approved
2630 | 2630-ABC_Bank_HQ_building_PF_Fiber_IBS | ZAIN | AMW-1124-R | Amman |  | 31.9688 | 35.9039 | Amman | [21 empty] | IBS | [15 empty] | Approved
4182 | 4182-Qweirah_Baraka_Farm_PF_M | ZAIN | MAN-215-R | Ma'an |  | 29.7416 | 35.3341 | Ma'an | Pole | [36 empty] | Approved
4542 | 4542-Amman_Arab_Uni_PF_O | ZAIN | AMW-1119-R | Amman |  | 32.1164 | 35.8814 | Amman | Pole | [36 empty] | Approved
3881 | 3881-Sheikh_Talal_Sobah_Palace_PF_M | ZAIN | MAD-293-R | Madaba |  | 31.7817 | 35.9144 | Madaba | Pole | [36 empty] | Approved
5254 | 5254-Ministry_of_Agriculture_PF_IBS | ZAIN | AME-1085-R | Amman |  | 32.005 | 35.9186 | Amman | [21 empty] | IBS | [15 empty] | Approved
4168 | 4168-Aqaba-JoPetrol-PF-M | ZAIN | AQB-302-R | Aqaba |  | 29.3823 | 34.9832 | Aqaba | Pole | [36 empty] | Approved
3882 | 3882-Pharmatic_Factory_PF_IBS | ZAIN | AMS-302-R | Amman |  | 31.7595 | 35.9849 | Amman | [21 empty] | IBS | [15 empty] | Approved
1512 | 1512-Sweimeh_Kasarat_PF_Manage_O | ZAIN | AMS-26-R | Balqa |  | 31.7849 | 35.6257 | Balqa | Pole | [36 empty] | Approved
555 | 555-Zabda_Hikmat_Yaseen_PF_Manage_O | ZAIN | AMW-886-R | Amman |  | 31.9495 | 35.7443 | Amman | Pole | [36 empty] | Approved
1522 | 1522-Madaba_Camp_PF_Org_Manage_O | ZAIN | MAD-276-G | Madaba |  | 31.7097 | 35.7907 | Madaba | Tower | [36 empty] | Approved
4127 | 4127-SunSet-Camp-Rum-PE-Manage-O | ZAIN | MAN-133-R | Aqaba |  | 29.6569 | 35.4796 | Aqaba | Pole | [36 empty] | Approved
4194 | 4194-Luxury-Collection-Hotel-2-PF-IBS-Org-O | ZAIN | AQB-304-R | Aqaba |  | 29.5357 | 34.9933 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
4197 | 4197-Aqaba-Royal-Palace-PF-IBS-O | ZAIN | AQB-305-G | Aqaba |  | 29.5389 | 34.9871 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
3531 | 3531-Ritz_Carlton_Hotel_PF_IBS_Org | ZAIN | AMW-1147-R | Amman |  | 31.961 | 35.8821 | Amman | [21 empty] | IBS | [15 empty] | Approved
4198 | 4198-Talabay-Resort-PF-O | ZAIN | AQB-303-R | Aqaba |  | 29.41 | 34.9808 | Aqaba | Pole | [36 empty] | Approved
2632 | 2632-Ministry_Of_Finance_PF_IBS | ZAIN | AMW-1143-R | Amman |  | 31.9666 | 35.9014 | Amman | [21 empty] | IBS | [15 empty] | Approved
3261 | 3261-Dabouq_District_Mall_IBS | ZAIN | AMW-1144-R | Amman |  | 31.9956 | 35.8336 | Amman | [21 empty] | IBS | [15 empty] | Approved
1501 | 1501-Madaba_City_Mall_IBS | ZAIN | MAD-295-R | Madaba |  | 31.7217 | 35.7929 | Madaba | [21 empty] | IBS | [15 empty] | Approved
2896 | 2896-Tahoneh_Farm_Mafraq_PF_M | ZAIN | MFQ-257-G | Mafraq |  | 32.0566 | 36.4011 | Mafraq | Pole | [36 empty] | Approved
773 | 773-Eshidiya_Tarawneh_PF_M | ZAIN | MAN-190-G | Ma'an |  | 29.9289 | 36.2028 | Ma'an | Pole | [36 empty] | Approved
3793 | 3793-Salt_Ind_Mcar | ZAIN | BLQ-266-G | Balqa |  | 31.9852 | 35.7163 | Balqa | [37 empty] | Approved
796 | 796-Al_Hussein_Bin_Talal_Uni_Accommodation_IBS | ZAIN | MAN-221-R | Ma'an |  | 30.2611 | 35.6769 | Ma'an | [21 empty] | IBS | [15 empty] | Approved
3884 | 3884-Loyalty_Support_Services_IBS | ZAIN | AMS-307-R | Amman |  | 31.7558 | 35.9796 | Amman | [21 empty] | IBS | [15 empty] | Approved
3735 | 3735-P_Salt_Batna_M | ZAIN | BLQ-267-P | Balqa |  | 32.0045 | 35.6942 | Balqa | Pole | [36 empty] | Approved
5771 | 5771-P_AbuSous_End_M | ZAIN | AMS-310-P | Amman |  | 31.9115 | 35.7855 | Amman | Pole | [36 empty] | Approved
2324 | 2324-Marka_Airport_college_M | ZAIN | AME-1077-R | Amman |  | 31.9671 | 35.9711 | Amman | Wall-Mount | [36 empty] | Approved
515 | 515-Fuhais_Compound_M | ZAIN | AMW-1150-R | Amman |  | 31.9854 | 35.7781 | Amman | Wall-Mount | [36 empty] | Approved
3885 | 3885-Sinokrot_Qastal_Farms_PF_IBS | ZAIN | MAD-297-R | Madaba |  | 31.7461 | 35.9619 | Madaba | [21 empty] | IBS | [15 empty] | Approved
4165 | 4165-Sidney-Shamieh-HQ-Mcar | ZAIN | AQB-310-R | Aqaba |  | 29.5948 | 35.0651 | Aqaba | [37 empty] | Approved
3886 | 3886-Madaba_K9_Training_Center_M | ZAIN | MAD-299-R | Madaba |  | 31.774 | 35.8503 | Madaba | Pole | [36 empty] | Approved
6010 | 6010-Eman_Ajloun_Hospital_IBS_PF_O | ZAIN | AJL-65-R | Ajloun |  | 32.3215 | 35.755 | Ajloun | [21 empty] | IBS | [15 empty] | Approved
3924 | 3924-Ministry_Of_Public_Works_PE_IBS | ZAIN | AMS-311-R | Amman |  | 31.9532 | 35.8474 | Amman | [21 empty] | IBS | [15 empty] | Approved
1195 | 1195-Ittihad_Farms_Azraq_M | ZAIN | ZRQ-446-R | Zarqa |  | 31.8735 | 36.894 | Zarqa | Pole | [36 empty] | Approved
5738 | 5738-P_Green_Land_M | ZAIN | AMS-312-P | Amman |  | 31.8547 | 35.8423 | Amman | Pole | [36 empty] | Approved
5515 | 5515-Golden_Gate_Mall_PF_IBS | ZAIN | AMW-1160-R | Amman |  | 31.9678 | 35.8759 | Amman | [6 empty] | PO.2 |  |  |  |  | SMP-WO-1544485 | Lewan | Al-Lewan | [7 empty] | IBS | [15 empty] | Approved | [8 empty] | 1 | Waiting Access Letter
3651 | 3651-Nabilsi_Medicine_Stores_PF_IBS | ZAIN | AMS-285-R | Amman |  | 31.9196 | 35.9099 | Amman | [21 empty] | IBS | [15 empty] | Approved
3856 | 3856-Jizza_Gas_Factory_M | ZAIN | MAD-301-R | Madaba |  | 31.6819 | 35.9477 | Madaba | Pole | [36 empty] | Approved
6203 | 6203-Tafilah_Governmental_Hospital_Org_IBS | ZAIN | TAF-58-R | Tafila |  | 30.8455 | 35.6495 | Tafila | [21 empty] | IBS | [15 empty] | Approved
1641 | 1641-National_Center_Diabetes_IBS | ZAIN | AMW-1149-R | Amman |  | 32.008 | 35.8729 | Amman | [21 empty] | IBS | [15 empty] | Approved
6036 | 6036-Aloula_Rehab_Farm_M | ZAIN | MFQ-276-R | Mafraq |  | 32.2982 | 36.0914 | Mafraq | Pole | [36 empty] | Approved
3792 | 3792-Balqa_Uni_Medicine_Faculty_IBS | ZAIN | BLQ-273-R | Balqa |  | 32.0619 | 35.7087 | Balqa | [21 empty] | IBS | [15 empty] | Approved
530 | 530-P_Rabahieh_Complex | ZAIN | AMW-1168-P | Amman |  | 31.9699 | 35.803 | Amman | Pole | [36 empty] | Approved
3845 | 3845-Middle_East_University_IBS_O | ZAIN | AMS-327-R | Amman |  | 31.8099 | 35.9201 | Amman | Pole | [20 empty] | IBS | [15 empty] | Approved
6025 | 6025-Shaab-Mall-Aqaba-IBS-M | ZAIN | AQB-312-R | Aqaba |  | 29.5705 | 35.0164 | Aqaba | [21 empty] | IBS | [15 empty] | Approved
2597 | P_AbuNusair_DiwanZaman_Rest_Back |  | AMW-1231-P | Amman | [15 empty] | SMP-WO-1544662 | Lewan | [24 empty] | Approved
3262 | P_Dabouq_PrinceGhazi__Ave | ZAIN | [11 empty] | Full Swap | Swap Only | [5 empty] | Lewan |  |  | Done | [21 empty] | Approved | [5 empty] | Approved | 2025-05-21 |  |  | The Site is inside Prince Ghazy Palace
Formulas:
Week number = "W"&WEEKNUM([TSSR status Date])
Action Age = TODAY()-[TSSR status Date]